## Completed
RURAL INFRASTRUCTURE DEVELOPMENT FUND
SIKKIM REGIONAL OFFICE
DETAILS OF COMPLETED PROJECTS (Tranche XII-XXV)
POSITION AS ON : 31 MARCH 2024
(Rs. Lakh)
Sr. No. | Sector | District | Village/Taluka/ Block | Tranche | PIC No. | Project Name & Details | Implementing Department | RIDF Loan | Date of Sanction | Amount Drawn
1 | MIC | South Sikkim | South Sikkim | 12 | R121400001 | Ext/Mod. Ranguthang at Ranguthang | Irrigation & Flood Control | 1.9 | 2006-08-08 | 1.9
2 | MIC/Flood Control | South Sikkim | South Sikkim | 12 | R121400002 | Ext/Mod.Chisophani MIC at Jorethan | Irrigation & Flood Control | 1.42 | 2006-08-08 | 1.42
3 | MIC | South Sikkim | South Sikkim | 12 | R121400003 | Extension/Modernisationn of Farasay | Irrigation & Flood Control | 1.42 | 2006-08-08 | 1.42
4 | MIC | South Sikkim | South Sikkim | 12 | R121400004 | Ext/Mod.Salghari MIC at Lower Tark | Irrigation & Flood Control | 1.42 | 2006-08-08 | 1.42
5 | MIC | South Sikkim | South Sikkim | 12 | R121400005 | Ext/Mod.Okhorbotey MIC Rangang Yan | Irrigation & Flood Control | 1.9 | 2006-08-08 | 1.9
6 | MIC | South Sikkim | South Sikkim | 12 | R121400006 | Ext/Mod. of Sajbotey MIC Ramaram, R | Irrigation & Flood Control | 1.42 | 2006-08-08 | 1.42
7 | MIC | South Sikkim | South Sikkim | 12 | R121400007 | Ext/Mod.Butel MIC at Kirtipur Ward | Irrigation & Flood Control | 1.42 | 2006-08-08 | 1.42
8 | MIC | South Sikkim | South Sikkim | 12 | R121400008 | Ext/Mod.Simchumthang MIC (Ph-II), | Irrigation & Flood Control | 1.42 | 2006-08-08 | 1.42
9 | MIC | West Sikkim | West Sikkim | 12 | R121400009 | Con&Ext. Mem Khola Dhakal kulo MIC | Irrigation & Flood Control | 2.85 | 2006-08-08 | 2.85
10 | MIC | North Sikkim | North Sikkim | 12 | R121400010 | Cons.MIC at Sumlek Paddy Field at T | Irrigation & Flood Control | 1.9 | 2006-08-08 | 1.9
11 | MIC | North Sikkim | North Sikkim | 12 | R121400011 | Cons.MIC at Dik kyong to Penzo at N | Irrigation & Flood Control | 1.9 | 2006-08-08 | 1.9
12 | MIC | East Sikkim | East Sikkim | 12 | R121400012 | Con. MIC at Badri khet Bardang West | Irrigation & Flood Control | 1.43 | 2006-08-08 | 1.43
13 | MIC | East Sikkim | East Sikkim | 12 | R121400013 | Con. MIC at Sarderey khet at West P | Irrigation & Flood Control | 1.42 | 2006-08-08 | 1.42
14 | MIC | East Sikkim | East Sikkim | 12 | R121400014 | Con. MIC at Linkhu Ralep KHAMDONG | Irrigation & Flood Control | 1.43 | 2006-08-08 | 1.43
15 | MIC | East Sikkim | East Sikkim | 12 | R121400015 | Con.MIC at Moterey Khet under Singb | Irrigation & Flood Control | 1.43 | 2006-08-08 | 1.43
16 | MIC | East Sikkim | East Sikkim | 12 | R121400016 | Con.MIC from Seem khulcha to Surki | Irrigation & Flood Control | 2.85 | 2006-08-08 | 2.85
17 | MIC | East Sikkim | East Sikkim | 12 | R121400017 | Con.Devisten Khola MIC at Nazitam | Irrigation & Flood Control | 1.43 | 2006-08-08 | 1.43
18 | MIC | East Sikkim | East Sikkim | 12 | R121400018 | Con.Singchey Dara Khet at Upper Sya | Irrigation & Flood Control | 1.43 | 2006-08-08 | 1.43
19 | MIC | East Sikkim | East Sikkim | 12 | R121400019 | Con.MIC at Bhutey Khola to Lower Lu | Irrigation & Flood Control | 1.9 | 2006-08-08 | 1.9
20 | MIC | East Sikkim | East Sikkim | 12 | R121400020 | Con.Uprati Khola to Kazi Khet MIC a | Irrigation & Flood Control | 1.43 | 2006-08-08 | 1.43
21 | MIC | East Sikkim | East Sikkim | 12 | R121400021 | Con.Tulshi Nepal Jhora MIC at Neopa | Irrigation & Flood Control | 1.43 | 2006-08-08 | 1.43
22 | MIC | East Sikkim | East Sikkim | 12 | R121400022 | Ext. Lasho khola MIC at Zingla Sang | Irrigation & Flood Control | 1.42 | 2006-08-08 | 1.42
23 | MIC | East Sikkim | East Sikkim | 12 | R121400023 | Con. Devithan source MIC at Middle | Irrigation & Flood Control | 1.33 | 2006-08-08 | 1.33
24 | MIC | East Sikkim | East Sikkim | 12 | R121400024 | Con. MIC from Ramitey khola to Neop | Irrigation & Flood Control | 2.85 | 2006-08-08 | 2.85
25 | MIC | East Sikkim | East Sikkim | 12 | R121400025 | Ext/Mod.MIC at Paper Factory unde | Irrigation & Flood Control | 1.14 | 2006-08-08 | 1.14
26 | MIC | East Sikkim | East Sikkim | 12 | R121400026 | Con.MIC at Cacha Jhora Tempo Tarkhe | Irrigation & Flood Control | 1.9 | 2006-08-08 | 1.9
27 | MIC | East Sikkim | East Sikkim | 12 | R121400027 | Con.Pairini kulo MIC at Sowrani, un | Irrigation & Flood Control | 1.43 | 2006-08-08 | 1.43
28 | MIC | East Sikkim | East Sikkim | 12 | R121400028 | Ext/Mod.MIC from Buthang Khola at P | Irrigation & Flood Control | 1.42 | 2006-08-08 | 1.42
29 | MIC | East Sikkim | East Sikkim | 12 | R121400029 | Con.MIC at Palung Naitam, under GPU | Irrigation & Flood Control | 1.43 | 2006-08-08 | 1.43
30 | MIC | East Sikkim | East Sikkim | 12 | R121400030 | Con.MIC at Chitwa khola to Aroo bot | Irrigation & Flood Control | 1.95 | 2006-08-08 | 1.95
31 | MIC | East Sikkim | East Sikkim | 12 | R121400031 | Construction of Gurung khola to Bhu | Irrigation & Flood Control | 1.95 | 2006-08-08 | 1.95
32 | MIC | East Sikkim | East Sikkim | 12 | R121400032 | Con.MIC at Dalapechand near Kipoo L | Irrigation & Flood Control | 2.85 | 2006-08-08 | 2.85
33 | MIC | East Sikkim | East Sikkim | 12 | R121400033 | Con. MIC at Sherrey Khola to Ganchu | Irrigation & Flood Control | 2.85 | 2006-08-08 | 2.85
34 | MIC | East Sikkim | East Sikkim | 12 | R121400034 | Con.MIC at Ningtham (second phase) | Irrigation & Flood Control | 1.43 | 2006-08-08 | 1.43
35 | MIC | South Sikkim | South Sikkim | 12 | R121400035 | Con.Guay Khola to Upper Tarku MIC w | Irrigation & Flood Control | 13.85 | 2006-08-08 | 13.85
36 | Toilet | South Sikkim | South Sikkim | 12 | R121400036 | KAZITAR CHILDREN PARK | Urban Development & Housing Dept. | 23.64 | 2006-11-24 | 23.64
37 | Toilet | South Sikkim | South Sikkim | 12 | R121400037 | NAMCHI CENTRE AREA | Urban Development & Housing Dept. | 18.94 | 2006-11-24 | 18.94
38 | Toilet | South Sikkim | South Sikkim | 12 | R121400038 | JORETHANG | Urban Development & Housing Dept. | 22.03 | 2006-11-24 | 22.03
39 | Toilet | West Sikkim | West Sikkim | 12 | R121400039 | GAYLSHING | Urban Development & Housing Dept. | 18.92 | 2006-11-24 | 18.92
40 | Toilet | South Sikkim | South Sikkim | 12 | R121400040 | CHO-ZO LAKE RAVANGLA | Urban Development & Housing Dept. | 18.94 | 2006-11-24 | 18.94
41 | Toilet | South Sikkim | South Sikkim | 12 | R121400041 | RAVANGLA | Urban Development & Housing Dept. | 18.94 | 2006-11-24 | 18.94
42 | Toilet | South Sikkim | South Sikkim | 12 | R121400042 | MANEE LAGHANG, RAVANGLA | Urban Development & Housing Dept. | 18.94 | 2006-11-24 | 18.94
43 | Market/Haat | South Sikkim | South Sikkim | 12 | R121400043 | Const. Haat- Namchi | Urban Development & Housing Dept. | 265.32 | 2006-11-24 | 265.32
44 | RDWS | South Sikkim | South Sikkim | 12 | R121400044 | Aug. WSS at Temi Bazaar | WS & Public Health & Engineering Department | 103.44 | 2006-11-24 | 103.44
45 | RDWS | South Sikkim | South Sikkim | 12 | R121400045 | Mod. of Namthang Water SS | WS & Public Health & Engineering Department | 34.04 | 2006-11-24 | 34.04
46 | MIC/Flood Control | East Sikkim | East Sikkim | 12 | R121400046 | JTW SAI MANDIR BALUWAKHAN | Irrigation & Flood Control | 10.92 | 2007-01-31 | 10.92
47 | RDWS | West Sikkim | West Sikkim | 12 | R121400047 | RDWS - SANGADORJEE | Rural Management Development Department | 128.04 | 2007-01-31 | 128.04
48 | School | East Sikkim | East Sikkim | 12 | R121400048 | A/w Singtam SS School | Human Resource Development Department | 23.9 | 2007-03-20 | 23.9
49 | School | East Sikkim | East Sikkim | 12 | R121400049 | A/w Kaiyathang Primary Sc | Human Resource Development Department | 18.81 | 2007-03-20 | 18.81
50 | School | West Sikkim | West Sikkim | 12 | R121400050 | A/w Daramdin Sec School | Human Resource Development Department | 28.13 | 2007-03-20 | 28.13
51 | School | West Sikkim | West Sikkim | 12 | R121400051 | A/w Tashiding SS School | Human Resource Development Department | 59.83 | 2007-03-20 | 59.83
52 | School | North Sikkim | North Sikkim | 12 | R121400052 | A/w GoR Secondary School | Human Resource Development Department | 28.74 | 2007-03-20 | 28.74
53 | School | North Sikkim | North Sikkim | 12 | R121400053 | A/w Ramom Pr.Sch U/Dzongu | Human Resource Development Department | 11.5 | 2007-03-20 | 11.5
54 | School | South Sikkim | South Sikkim | 12 | R121400054 | A/w Phamtam Junior Hi.Sch | Human Resource Development Department | 24.67 | 2007-03-20 | 24.67
55 | School | South Sikkim | South Sikkim | 12 | R121400055 | A/w Pabong Darring JHScho | Human Resource Development Department | 4.75 | 2007-03-20 | 4.75
56 | RDWS | West Sikkim | West Sikkim | 12 | R121400056 | Aug.Tashidin Bazar WSS | WS & Public Health & Engineering Department | 222.03 | 2007-03-20 | 222.03
57 | RDWS | West Sikkim | West Sikkim | 12 | R121400057 | Aug.Bermiok Bazar WSS | WS & Public Health & Engineering Department | 86.69 | 2007-03-20 | 86.69
58 | RDWS | West Sikkim | West Sikkim | 12 | R121400058 | Mod.Kaluk Rinchinpong WSS | WS & Public Health & Engineering Department | 67.86 | 2007-03-20 | 67.86
59 | RDWS | West Sikkim | West Sikkim | 12 | R121400059 | Cons.Sedi.Tand Naya Bazar | WS & Public Health & Engineering Department | 19.48 | 2007-03-20 | 19.48
60 | RDWS | East Sikkim | East Sikkim | 12 | R121400060 | Cons.Alt.RWM to Gangtok | WS & Public Health & Engineering Department | 149.4 | 2007-03-20 | 149.4
61 | Road | East Sikkim | East Sikkim | 12 | R121400061 | Link Road Sakyong-Beyong(0-2k | Roads & Bridges Department | 79.51 | 2007-03-20 | 79.51
62 | Road | East Sikkim | East Sikkim | 12 | R121400062 | Link Road GRS to Tatopani Rum | Roads & Bridges Department | 40.19 | 2007-03-20 | 40.19
63 | School | East District | East District | 13 | R131400001 | Upper Tathangchen Syari Modern scho | Human Resource Development Department | 102 | 2007-09-24 | 102
64 | School | East District | East District | 13 | R131400002 | Nazitam PS | Human Resource Development Department | 19.38 | 2007-09-24 | 19.38
65 | School | East District | East District | 13 | R131400003 | Amba JHS | Human Resource Development Department | 20.29 | 2007-09-24 | 20.29
66 | School | East District | East District | 13 | R131400004 | Kamarey PS | Human Resource Development Department | 20.03 | 2007-09-24 | 20.03
67 | School | East District | East District | 13 | R131400005 | Samsing Suntaley LPS | Human Resource Development Department | 17.3 | 2007-09-24 | 17.3
68 | School | East District | East District | 13 | R131400006 | Pachey Khani Sanskrit Patshala | Human Resource Development Department | 7.99 | 2007-09-24 | 7.99
69 | School | East District | East District | 13 | R131400007 | Agrigaon LPS | Human Resource Development Department | 21.33 | 2007-09-24 | 21.33
70 | School | North District | North District | 13 | R131400008 | Chungthang SS | Human Resource Development Department | 24.8 | 2007-09-24 | 24.8
71 | School | North District | North District | 13 | R131400009 | Tingvong SS | Human Resource Development Department | 25.65 | 2007-09-24 | 25.65
72 | School | North District | North District | 13 | R131400010 | Naga PS | Human Resource Development Department | 18.73 | 2007-09-24 | 18.73
73 | School | North District | North District | 13 | R131400011 | Loom (Lum) PS | Human Resource Development Department | 22.36 | 2007-09-24 | 22.36
74 | School | West District | West District | 13 | R131400012 | Sakyong SS | Human Resource Development Department | 16.82 | 2007-09-24 | 16.82
75 | School | West District | West District | 13 | R131400013 | Upper Chuchen LPS | Human Resource Development Department | 21.41 | 2007-09-24 | 21.41
76 | School | West District | West District | 13 | R131400014 | Khecheoperi SS | Human Resource Development Department | 24.87 | 2007-09-24 | 24.87
77 | School | West District | West District | 13 | R131400015 | Yangsum SS | Human Resource Development Department | 24.82 | 2007-09-24 | 24.82
78 | School | West District | West District | 13 | R131400016 | Gerethang SS | Human Resource Development Department | 26.95 | 2007-09-24 | 26.95
79 | School | South District | South District | 13 | R131400017 | Lower Chalamthang PS | Human Resource Development Department | 19.22 | 2007-09-24 | 19.22
80 | School | South District | South District | 13 | R131400018 | Basbotay LPS | Human Resource Development Department | 19.75 | 2007-09-24 | 19.75
81 | School | South District | South District | 13 | R131400019 | Mungram LPS | Human Resource Development Department | 17.13 | 2007-09-24 | 17.13
82 | School | South District | South District | 13 | R131400020 | Chuba JHS | Human Resource Development Department | 24.35 | 2007-09-24 | 24.35
83 | School | South District | South District | 13 | R131400021 | Phong JHS | Human Resource Development Department | 26.9 | 2007-09-24 | 26.9
84 | School | South District | South District | 13 | R131400022 | Kewzing SS | Human Resource Development Department | 23.41 | 2007-09-24 | 23.41
85 | School | South District | South District | 13 | R131400023 | Lungchok JHS | Human Resource Development Department | 27.4 | 2007-09-24 | 27.4
86 | MIC | East District | East District | 13 | R131400024 | Const. Sajbotey MIC at Badang under Kh | Irrigation & Flood Control | 1.9 | 2007-09-24 | 1.9
87 | MIC | East District | East District | 13 | R131400025 | Modernization of MIC at Rabong Bharangh khet at | Irrigation & Flood Control | 1.9 | 2007-09-24 | 1.9
88 | MIC | East District | East District | 13 | R131400026 | Const. Thami Dara to Resithang MIC at | Irrigation & Flood Control | 1.9 | 2007-09-24 | 1.9
89 | MIC | East District | East District | 13 | R131400027 | Const. Ralep MIC to Pithangbessey at K | Irrigation & Flood Control | 2.85 | 2007-09-24 | 2.85
90 | MIC | East District | East District | 13 | R131400028 | Const. Karma Khet MIC from Khatley Kho | Irrigation & Flood Control | 1.9 | 2007-09-24 | 1.9
91 | MIC | East District | East District | 13 | R131400029 | Const. MIC at Gairi gaon Neopany Gaon | Irrigation & Flood Control | 1.48 | 2007-09-24 | 1.48
92 | MIC | East District | East District | 13 | R131400030 | Const. Lepcha khet Thulo Kholsa Souren | Irrigation & Flood Control | 1.43 | 2007-09-24 | 1.43
93 | MIC | East District | East District | 13 | R131400031 | Extension of Chuthanga MIC at Lower Tathangc | Irrigation & Flood Control | 2.85 | 2007-09-24 | 2.85
94 | MIC | East District | East District | 13 | R131400032 | Const. Lakhamthang Press Jhora MIC at | Irrigation & Flood Control | 1.9 | 2007-09-24 | 1.9
95 | MIC | East District | East District | 13 | R131400033 | Const. L N Tamang Khet MIC at Lower Sy | Irrigation & Flood Control | 1.9 | 2007-09-24 | 1.9
96 | MIC | East District | East District | 13 | R131400034 | Const. Reshi khet to Dhakal kholsa MIC | Irrigation & Flood Control | 1.43 | 2007-09-24 | 1.43
97 | MIC | North District | North District | 13 | R131400035 | Extension of Guay Khola to Dechu Khet MIC at | Irrigation & Flood Control | 1.43 | 2007-09-24 | 1.43
98 | MIC | South District | South District | 13 | R131400036 | Const. MIC at L/Polok thato Pani Paddy | Irrigation & Flood Control | 1.9 | 2007-09-24 | 1.9
99 | MIC | South District | South District | 13 | R131400037 | Extension MIC from Chil Khola to Pa | Irrigation & Flood Control | 1.9 | 2007-09-24 | 1.9
100 | MIC | South District | South District | 13 | R131400038 | Extension of MIC from Choka to Dungsa U/Naml | Irrigation & Flood Control | 1.9 | 2007-09-24 | 1.9
101 | MIC | South District | South District | 13 | R131400039 | Const. MIC Chochum Khok Doling Gumpa t | Irrigation & Flood Control | 2.37 | 2007-09-24 | 2.37
102 | MIC | South District | South District | 13 | R131400040 | Const. MIC Chuta Khola to Gairi Khate | Irrigation & Flood Control | 2.37 | 2007-09-24 | 2.37
103 | MIC | South District | South District | 13 | R131400041 | Const. Guay Khola MIC at Middle Tarku | Irrigation & Flood Control | 2.37 | 2007-09-24 | 2.37
104 | MIC | West District | West District | 13 | R131400042 | Modernization of Takey Tar MIC at Saladang under | Irrigation & Flood Control | 5.34 | 2007-09-24 | 5.34
105 | MIC | West District | West District | 13 | R131400043 | Const. MIC at Dharagaon at Central Zoo | Irrigation & Flood Control | 4.27 | 2007-09-24 | 4.27
106 | MIC | West District | West District | 13 | R131400044 | Extension of MIC from Rangshang Khola to Run | Irrigation & Flood Control | 3.56 | 2007-09-24 | 3.56
107 | MIC | West District | West District | 13 | R131400045 | Const. Dhamai Khola MIC at Yangten | Irrigation & Flood Control | 2.58 | 2007-09-24 | 2.58
108 | MIC | West District | West District | 13 | R131400046 | Const. Dhamai Khola MIC at Yangten | Irrigation & Flood Control | 1.9 | 2007-09-24 | 1.9
109 | MIC/Flood Control | East District | East District | 13 | R131400047 | AEW below house of Yeshel Bhutia at | Irrigation & Flood Control | 1.9 | 2007-09-24 | 1.9
110 | MIC/Flood Control | East District | East District | 13 | R131400048 | AEW at Upper Sichey above Siva M&ir | Irrigation & Flood Control | 1.9 | 2007-09-24 | 1.9
111 | MIC/Flood Control | East District | East District | 13 | R131400049 | AEW & C.W.D. at Sadhu Gaon at Ray K | Irrigation & Flood Control | 1.86 | 2007-09-24 | 1.86
112 | MIC/Flood Control | East District | East District | 13 | R131400050 | AEW nr Housing Colony at Arithang | Irrigation & Flood Control | 1.73 | 2007-09-24 | 1.73
113 | MIC/Flood Control | South District | South District | 13 | R131400051 | AEW at Linzoo under kewzing-Bhakhim | Irrigation & Flood Control | 2.37 | 2007-09-24 | 2.37
114 | MIC/Flood Control | South District | South District | 13 | R131400052 | AEW at Dara Kharka, Jaubari, Damtha | Irrigation & Flood Control | 1.43 | 2007-09-24 | 1.43
115 | MIC/Flood Control | South District | South District | 13 | R131400053 | AEW nr Rabong Khola at Pamphok, Rat | Irrigation & Flood Control | 1.59 | 2007-09-24 | 1.59
116 | MIC/Flood Control | South District | South District | 13 | R131400054 | AEW below the house of Chumdem Bhut | Irrigation & Flood Control | 1.9 | 2007-09-24 | 1.9
117 | MIC/Flood Control | South District | South District | 13 | R131400055 | AEW/JTW in the holding of Shri S. R | Irrigation & Flood Control | 1.9 | 2007-09-24 | 1.9
118 | MIC/Flood Control | South District | South District | 13 | R131400056 | AEW at CWD nr Devithan at Debrung S | Irrigation & Flood Control | 3.32 | 2007-09-24 | 3.32
119 | MIC/Flood Control | South District | South District | 13 | R131400057 | AEW at Agautey Dara at Kitam Michko | Irrigation & Flood Control | 2.49 | 2007-09-24 | 2.49
120 | MIC/Flood Control | South District | South District | 13 | R131400058 | AEW at Bara Dhara Tea Garden Temi- | Irrigation & Flood Control | 1.81 | 2007-09-24 | 1.81
121 | MIC/Flood Control | West District | West District | 13 | R131400059 | AEW nr Maney below Gyalshing Bazar | Irrigation & Flood Control | 2.37 | 2007-09-24 | 2.37
122 | MIC/Flood Control | West District | West District | 13 | R131400060 | AEW along Kang Khola nr Sai M&ir at | Irrigation & Flood Control | 3.32 | 2007-09-24 | 3.32
123 | MIC/Flood Control | West District | West District | 13 | R131400061 | AEW at U/Pelling at Karki Jhora | Irrigation & Flood Control | 1.9 | 2007-09-24 | 1.9
124 | MIC/Flood Control | East District | East District | 13 | R131400062 | CWD & Protection Work at Dhupi Dara at Burtuk u | Irrigation & Flood Control | 1.9 | 2007-09-24 | 1.9
125 | MIC/Flood Control | North District | North District | 13 | R131400063 | CWD & Protection Workork below Penlong Bazar un | Irrigation & Flood Control | 1.43 | 2007-09-24 | 1.43
126 | MIC/Flood Control | North District | North District | 13 | R131400064 | Const. CWD from Hospital Road to Govt | Irrigation & Flood Control | 2.85 | 2007-09-24 | 2.85
127 | MIC/Flood Control | East District | East District | 13 | R131400065 | JTW at VIP Complex below Bungalow N | Irrigation & Flood Control | 1.9 | 2007-09-24 | 1.9
128 | MIC/Flood Control | East District | East District | 13 | R131400066 | JTW at Tulshi Jhora Rawtey-Rumtek | Irrigation & Flood Control | 2.37 | 2007-09-24 | 2.37
129 | MIC/Flood Control | East District | East District | 13 | R131400067 | JTW at nr the house of R Bhutia at | Irrigation & Flood Control | 1.43 | 2007-09-24 | 1.43
130 | MIC/Flood Control | East District | East District | 13 | R131400068 | JTW along Thula Kholsa at N&ok Bust | Irrigation & Flood Control | 2.85 | 2007-09-24 | 2.85
131 | MIC/Flood Control | East District | East District | 13 | R131400069 | JTW at Basnet Jhora Namcheybong | Irrigation & Flood Control | 1.9 | 2007-09-24 | 1.9
132 | MIC/Flood Control | East District | East District | 13 | R131400070 | JTW at Phipraj Jhora at Tathangchen | Irrigation & Flood Control | 2.42 | 2007-09-24 | 2.42
133 | MIC/Flood Control | East District | East District | 13 | R131400071 | JTW at Burtuk under Burtuk-Ch&mari | Irrigation & Flood Control | 2.85 | 2007-09-24 | 2.85
134 | MIC/Flood Control | East District | East District | 13 | R131400072 | JTW nr the house of Kewal Das Chett | Irrigation & Flood Control | 1.9 | 2007-09-24 | 1.9
135 | MIC/Flood Control | East District | East District | 13 | R131400073 | Jhora Training at Neopaney jhora at | Irrigation & Flood Control | 1.43 | 2007-09-24 | 1.43
136 | MIC/Flood Control | East District | East District | 13 | R131400074 | JTW at SSB Head Quarter below Minto | Irrigation & Flood Control | 2.37 | 2007-09-24 | 2.37
137 | MIC/Flood Control | North District | North District | 13 | R131400075 | JTW along Dorung Golai Jhora at Lin | Irrigation & Flood Control | 2.85 | 2007-09-24 | 2.85
138 | MIC/Flood Control | North District | North District | 13 | R131400076 | JTW along Khimchung Jhora at Sivik | Irrigation & Flood Control | 2.85 | 2007-09-24 | 2.85
139 | MIC/Flood Control | North District | North District | 13 | R131400077 | JTW at Pagla Jhora at Lingdok 8th m | Irrigation & Flood Control | 2.85 | 2007-09-24 | 2.85
140 | MIC/Flood Control | North District | North District | 13 | R131400078 | JTW along Guway Jhora at Lower Samd | Irrigation & Flood Control | 2.85 | 2007-09-24 | 2.85
141 | MIC/Flood Control | North District | North District | 13 | R131400079 | JTW along Sawney jhora at Upper Tin | Irrigation & Flood Control | 2.37 | 2007-09-24 | 2.37
142 | MIC/Flood Control | North District | North District | 13 | R131400080 | JTW & AEW at Tingvong | Irrigation & Flood Control | 1.9 | 2007-09-24 | 1.9
143 | MIC/Flood Control | North District | North District | 13 | R131400081 | JTW at Passingdong, Dzongu | Irrigation & Flood Control | 1.9 | 2007-09-24 | 1.9
144 | MIC/Flood Control | South District | South District | 13 | R131400082 | JTW above Piggery Farm at KholaGari | Irrigation & Flood Control | 2.37 | 2007-09-24 | 2.37
145 | MIC/Flood Control | South District | South District | 13 | R131400083 | JTW below the house of Lading Choda | Irrigation & Flood Control | 2.37 | 2007-09-24 | 2.37
146 | MIC/Flood Control | West District | West District | 13 | R131400084 | JTW at kyongsa Geyzing | Irrigation & Flood Control | 2.37 | 2007-09-24 | 2.37
147 | MIC/Flood Control | West District | West District | 13 | R131400085 | JTW at Tooni Kharga at Labdang unde | Irrigation & Flood Control | 2.85 | 2007-09-24 | 2.85
148 | MIC/Flood Control | East District | East District | 13 | R131400086 | Protection Work at Beychu Jhora under Tathangch | Irrigation & Flood Control | 1.43 | 2007-09-24 | 1.43
149 | MIC/Flood Control | North District | North District | 13 | R131400087 | Protection Work at Shyari Genzal Block Phensong | Irrigation & Flood Control | 1.43 | 2007-09-24 | 1.43
150 | MIC/Flood Control | North District | North District | 13 | R131400088 | Protection Work at Genzal nr the house of Khime | Irrigation & Flood Control | 1.89 | 2007-09-24 | 1.89
151 | RDWS | East District | East District | 13 | R131400089 | Aug Singtam WSS by PHED | WS & Public Health & Engineering Department | 390.68 | 2007-09-24 | 390.68
152 | RDWS | West District | West District | 13 | R131400090 | Aug WSS Mangalbaria PHED | WS & Public Health & Engineering Department | 220.13 | 2007-09-24 | 220.13
153 | RDWS | South District | South District | 13 | R131400091 | DWDS M/P Ri Rangit-Namchi | Rural Management Development Department | 424.41 | 2007-09-24 | 424.41
154 | Road | East District | East District | 13 | R131400092 | Tintek-Dikchu Road 4/0-6/0 | Roads & Bridges Department | 224.66 | 2007-09-24 | 224.66
155 | Road | South District | South District | 13 | R131400093 | Satyamuni Project | Roads & Bridges Department | 360.91 | 2007-09-24 | 360.91
156 | Road | South District | South District | 13 | R131400094 | Melli Bazaar Project | Roads & Bridges Department | 34.06 | 2007-09-24 | 34.06
157 | Road | East District | East District | 13 | R131400095 | Takchi Palace-Upper Luing | Roads & Bridges Department | 289.93 | 2008-01-08 | 289.93
158 | Road | South District | South District | 13 | R131400096 | Tiffin Dara-L/Tingrithang | Roads & Bridges Department | 254.37 | 2008-01-08 | 254.37
159 | Road | West District | West District | 13 | R131400097 | LR Alpine CF-Kaluk Den Km19 | Roads & Bridges Department | 96.77 | 2008-02-06 | 96.77
160 | Market/Haat | East District | East District | 13 | R131400098 | Rural Haats at Sang Bazaar | Urban Development & Housing Dept. | 11.04 | 2008-03-18 | 11.04
161 | Market | North District | North District | 13 | R131400099 | Rural Market at Dikch | Urban Development & Housing Dept. | 11.93 | 2008-03-18 | 11.93
162 | Market | North District | North District | 13 | R131400100 | Rural Market at Phodong | Urban Development & Housing Dept. | 13.31 | 2008-03-18 | 13.31
163 | Market | North District | North District | 13 | R131400101 | Rural Market at Phensong | Urban Development & Housing Dept. | 12.62 | 2008-03-18 | 12.62
164 | Market/Haat | South District | South District | 13 | R131400102 | Rural Haats etc. at Kitam | Urban Development & Housing Dept. | 24.88 | 2008-03-18 | 24.88
165 | Market/Haat | South District | South District | 13 | R131400103 | Rural Haats etc. at Rabong | Urban Development & Housing Dept. | 40.39 | 2008-03-18 | 40.39
166 | Market/Haat | South District | South District | 13 | R131400104 | Rural Haats etc. at Mazitar | Urban Development & Housing Dept. | 22.36 | 2008-03-18 | 22.36
167 | Market/Haat | South District | South District | 13 | R131400105 | Rural Haats etc. at Temi | Urban Development & Housing Dept. | 124.2 | 2008-03-18 | 124.2
168 | Market | South District | South District | 13 | R131400106 | Rural Markets at Ghurpisey | Urban Development & Housing Dept. | 90 | 2008-03-18 | 90
169 | Toilet | South District | South District | 13 | R131400107 | Pay & Use Toilets at Singhithang | Urban Development & Housing Dept. | 18.68 | 2008-03-18 | 18.68
170 | Market | West District | West District | 13 | R131400108 | Rural Markets at Reshi | Urban Development & Housing Dept. | 89.12 | 2008-03-18 | 89.12
171 | Market | West District | West District | 13 | R131400110 | Rural Market at Kaluk | Urban Development & Housing Dept. | 41.99 | 2008-03-18 | 41.99
172 | Market | West District | West District | 13 | R131400111 | Rural markets at Hee | Urban Development & Housing Dept. | 25.79 | 2008-03-18 | 25.79
173 | Market | West District | West District | 13 | R131400112 | Rural markets at Sombaria | Urban Development & Housing Dept. | 29.8 | 2008-03-18 | 29.8
174 | Market | West District | West District | 13 | R131400113 | Rural markets at Daramdin | Urban Development & Housing Dept. | 22.82 | 2008-03-18 | 22.82
175 | Market | West District | West District | 13 | R131400114 | Rural markets at Dentam | Urban Development & Housing Dept. | 20.99 | 2008-03-18 | 20.99
176 | Market | West District | West District | 13 | R131400115 | Rural markets at Bermiok | Urban Development & Housing Dept. | 22.37 | 2008-03-18 | 22.37
177 | RDWS | East District | East District | 13 | R131400116 | Rorathang RDWSS | WS & Public Health & Engineering Department | 468.32 | 2008-03-18 | 468.32
178 | RDWS | East District | East District | 13 | R131400117 | Infr Water Supply Saramsa | WS & Public Health & Engineering Department | 64.82 | 2008-03-18 | 64.82
179 | Road | West Sikkim | West Sikkim | 14 | R141400001 | S&C of Soreng Kaluk Road | Roads & Bridges Department | 999.9 | 2008-05-12 | 999.9
180 | RDWS | West Sikkim | West Sikkim | 14 | R141400002 | Darap Water Supply Scheme | WS & Public Health & Engineering Department | 221.94 | 2008-07-07 | 221.94
181 | RDWS | West Sikkim | West Sikkim | 14 | R141400003 | Reshi Bazaar Water Supply | WS & Public Health & Engineering Department | 238.48 | 2008-07-07 | 238.48
182 | RDWS | South Sikkim | South Sikkim | 14 | R141400004 | WS Debrung,Dambudara&Kamr | WS & Public Health & Engineering Department | 198.67 | 2008-07-07 | 198.67
183 | RDWS | South Sikkim | South Sikkim | 14 | R141400005 | Aug WSS at Jorethang | WS & Public Health & Engineering Department | 48.22 | 2008-07-07 | 48.22
184 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400006 | AEW at Gairi goan, Pachey, Damthang | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
185 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400007 | AEW at Ayurbedic Hospital at Kopche | Irrigation & Flood Control | 1.76 | 2008-09-26 | 1.76
186 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400008 | AE& Protection Work at Upper Salleybong Pakhrin | Irrigation & Flood Control | 2.85 | 2008-09-26 | 2.85
187 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400009 | AEW & JTW along Ghateney Jhora at L | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
188 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400010 | JTW & CWD below Kewzing School, Rav | Irrigation & Flood Control | 3.13 | 2008-09-26 | 3.13
189 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400011 | Const. JTW at Baradhura Tea Garden at | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
190 | MIC/Flood Control | North Sikkim | North Sikkim | 14 | R141400012 | Const. JTW along Tumin Khola at Lower | Irrigation & Flood Control | 2.18 | 2008-09-26 | 2.18
191 | MIC/Flood Control | North Sikkim | North Sikkim | 14 | R141400013 | Const. JTW at Tintek Khola at Tintek, | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
192 | MIC/Flood Control | North Sikkim | North Sikkim | 14 | R141400014 | Const. JTW at Chamey Khola at Tintek, | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
193 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400015 | JTW below IBP Road adjacent to the la | Irrigation & Flood Control | 4.75 | 2008-09-26 | 4.75
194 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400016 | Const. Pharasey MIC at Salghari, Jo | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
195 | MIC | South Sikkim | South Sikkim | 14 | R141400017 | Const. Dong Khola to Simbalbotey MIC, | Irrigation & Flood Control | 4.75 | 2008-09-26 | 4.75
196 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400018 | Const. Barbotey MIC at Nandu Goan, Jor | Irrigation & Flood Control | 3.8 | 2008-09-26 | 3.8
197 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400019 | Const. Bhaley Khola MIC at Lower Ranga | Irrigation & Flood Control | 1.42 | 2008-09-26 | 1.42
198 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400020 | Const. Sumain MIC at Upper Tingmoo, Wo | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
199 | MIC | South Sikkim | South Sikkim | 14 | R141400021 | Const. Doring MIC at Bermiok, Temi Tar | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
200 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400022 | Const. Lower Brom MiC in South Sikkim, | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
201 | MIC | South Sikkim | South Sikkim | 14 | R141400023 | Const. Tangsang MIC at Lower Boomtar, | Irrigation & Flood Control | 1.66 | 2008-09-26 | 1.66
202 | MIC | South Sikkim | South Sikkim | 14 | R141400024 | Const. MIC from Tanam Khola to Karabar | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
203 | MIC | South Sikkim | South Sikkim | 14 | R141400025 | Const. MIC from Khongsa Khola to Kyong | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
204 | MIC | South Sikkim | South Sikkim | 14 | R141400026 | Extn/Ren. of Nangdang MIC at Lower | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
205 | MIC | South Sikkim | South Sikkim | 14 | R141400027 | Const. Tangsang MIC at Lower Boomtar, | Irrigation & Flood Control | 3.32 | 2008-09-26 | 3.32
206 | MIC | East Sikkim | East Sikkim | 14 | R141400028 | Const. MIC from Dhong Dongay Khola to | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
207 | MIC | East Sikkim | East Sikkim | 14 | R141400029 | AEW Mr. P.T. Bhutia at Chandmari, | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
208 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400030 | AEW at Thangsing Kinchu Doma, Berm | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
209 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400031 | AEW at Devithan Jhora at Chuwatar, | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
210 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400032 | AEW Jasoda Sharma at Dumra, Temi T | Irrigation & Flood Control | 2.85 | 2008-09-26 | 2.85
211 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400033 | AEW Nir Maya Giri at Samdur, Rumte | Irrigation & Flood Control | 2.85 | 2008-09-26 | 2.85
212 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400034 | AEW Shri Karma Sonam Bhutia & oth | Irrigation & Flood Control | 3.59 | 2008-09-26 | 3.59
213 | MIC/Flood Control | North Sikkim | North Sikkim | 14 | R141400035 | AEW P. B. Rongpa Sakyong at Kabi | Irrigation & Flood Control | 3.32 | 2008-09-26 | 3.32
214 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400036 | AEW at Black Cat jhora nr IBP road | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
215 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400037 | AEW below the house of C.Lepcha at | Irrigation & Flood Control | 1.42 | 2008-09-26 | 1.42
216 | MIC/Flood Control | North Sikkim | North Sikkim | 14 | R141400038 | AEW at Beng Thangsing, Khamdong, R | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
217 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400039 | AEW at Dugalakha nr the holding of | Irrigation & Flood Control | 3.32 | 2008-09-26 | 3.32
218 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400040 | AEW at Changeylakha under Rongli Ch | Irrigation & Flood Control | 2.85 | 2008-09-26 | 2.85
219 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400041 | AEW at Middle Bhasmey West Pendam, | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
220 | MIC/Flood Control | West Sikkim | West Sikkim | 14 | R141400042 | AEW at Gelling Dham, Chakung Const | Irrigation & Flood Control | 1.42 | 2008-09-26 | 1.42
221 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400043 | AEW below Paljor Stadium at Upper L | Irrigation & Flood Control | 1.42 | 2008-09-26 | 1.42
222 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400044 | AEW at Tharey Khola at L/Borong, Ra | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
223 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400045 | AEW at Lungchok nr RB Rai's house, | Irrigation & Flood Control | 2.85 | 2008-09-26 | 2.85
224 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400046 | AEW at left bank of L.D. Kazi jhor | Irrigation & Flood Control | 1.47 | 2008-09-26 | 1.47
225 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400047 | AEW at Nindi under Amba, Pathing Co | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
226 | MIC/Flood Control | North Sikkim | North Sikkim | 14 | R141400048 | AEW at Khimsa Tingda, Kabi Tingda | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
227 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400049 | AEW at Beng Thangsing nr Public Pl | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
228 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400050 | AEW Kardong Jhora at Karthok busty | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
229 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400051 | AEW at Peptang nr the holding of T | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
230 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400052 | AEW W.T. Bhutia underTathangchen-S | Irrigation & Flood Control | 2.18 | 2008-09-26 | 2.18
231 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400053 | AEW at Ayurbedic Hospital at Kopch | Irrigation & Flood Control | 2.85 | 2008-09-26 | 2.85
232 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400054 | AEW at Ciwribotey Suman Pradhan, C | Irrigation & Flood Control | 1.42 | 2008-09-26 | 1.42
233 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400055 | AEW at IBM, Rangpo, C.Pendam Consti | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
234 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400056 | AEW along Griling jhora Mr Kami L | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
235 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400057 | AEW at Simana Jhora nr the holding | Irrigation & Flood Control | 2.28 | 2008-09-26 | 2.28
236 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400058 | AEW Smt. Dorjee Bhutia L/Tathangc | Irrigation & Flood Control | 2.85 | 2008-09-26 | 2.85
237 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400059 | AEW at Maney Khola at Golitar Bust | Irrigation & Flood Control | 2.85 | 2008-09-26 | 2.85
238 | MIC/Flood Control | West Sikkim | West Sikkim | 14 | R141400060 | AEW at U/Karthok nr the holding of | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
239 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400061 | AEW at Upper Sichey below Lachungp | Irrigation & Flood Control | 1.42 | 2008-09-26 | 1.42
240 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400062 | AEW at Kirtipur Turing Mamring GPU, | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
241 | MIC/Flood Control | West Sikkim | West Sikkim | 14 | R141400063 | AEW & Jhora Trg. Work along Dhar Kh | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
242 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400064 | AEW & Catch Water Dr MK Rasaily at | Irrigation & Flood Control | 2.14 | 2008-09-26 | 2.14
243 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400065 | AEW / Jhora Trg. Work at V.I.P Com | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
244 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400066 | AEW & Jhora Trg. Work at Rani Khola | Irrigation & Flood Control | 2.19 | 2008-09-26 | 2.19
245 | MIC/Flood Control | West Sikkim | West Sikkim | 14 | R141400067 | AEW & Jhora Trg. Work Sashi Limbo, | Irrigation & Flood Control | 2.61 | 2008-09-26 | 2.61
246 | MIC/Flood Control | West Sikkim | West Sikkim | 14 | R141400068 | Anti-Erosion & Jhora Trg. work alon | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
247 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400069 | AEW & Jhora Trg. Work along Hospit | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
248 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400070 | AEW & Jhora Trg. Work PS Tamang, | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
249 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400071 | AEW & Jhora Trg. Work at Peku Raja | Irrigation & Flood Control | 3.32 | 2008-09-26 | 3.32
250 | MIC/Flood Control | West Sikkim | West Sikkim | 14 | R141400072 | AEW & Jhora Trg. Work at Lower Tikj | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
251 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400073 | AEW & Jhora Trg. Work at Naspatey | Irrigation & Flood Control | 2.85 | 2008-09-26 | 2.85
252 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400074 | AE & Protection Workork Mr. Ongyal Bhutia unde | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
253 | MIC/Flood Control | West Sikkim | West Sikkim | 14 | R141400075 | AEW and Jhora Trg. Work at Guruthan | Irrigation & Flood Control | 1.42 | 2008-09-26 | 1.42
254 | MIC/Flood Control | West Sikkim | West Sikkim | 14 | R141400076 | AEW & Jhora Trg. Work at Gyaba Jhor | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
255 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400077 | Const. Catch Water Dr nr the Lassithan | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
256 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400078 | Const. Catch Water Dr at Upper Syari n | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
257 | MIC/Flood Control | West Sikkim | West Sikkim | 14 | R141400079 | Const. Catch Water Dr below Soreng Ba | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
258 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400080 | Const. Catch Water Dr opposite Sec Sc | Irrigation & Flood Control | 1.42 | 2008-09-26 | 1.42
259 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400081 | Catch Water Dr at Sellemthang Yanga | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
260 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400082 | Const. Catch Water Dr at Debrung Busty | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
261 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400083 | Reno/Consn. of Catch Water Dr nr Ju | Irrigation & Flood Control | 2.29 | 2008-09-26 | 2.29
262 | MIC/Flood Control | North Sikkim | North Sikkim | 14 | R141400084 | Const. Catch Water Dr & AEW along Sim | Irrigation & Flood Control | 4.75 | 2008-09-26 | 4.75
263 | MIC/Flood Control | North Sikkim | North Sikkim | 14 | R141400085 | Const. Catch Water Dr & AEW at Gaddi, | Irrigation & Flood Control | 3.8 | 2008-09-26 | 3.8
264 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400086 | Const. Catch Water Dr & AEW at Nor Gum | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
265 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400087 | Const. Catch Water Dr & AEW at LaMICha | Irrigation & Flood Control | 2.85 | 2008-09-26 | 2.85
266 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400088 | Catch Water Dr/Jhora Trg. Work abov | Irrigation & Flood Control | 3.32 | 2008-09-26 | 3.32
267 | MIC/Flood Control | North Sikkim | North Sikkim | 14 | R141400089 | Jhora Trg. Work at Uddauney Khola | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
268 | MIC/Flood Control | North Sikkim | North Sikkim | 14 | R141400090 | Jhora Trg. Work along Tintek Khola | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
269 | MIC/Flood Control | North Sikkim | North Sikkim | 14 | R141400091 | Jhora Trg. Work at Devithan jhora a | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
270 | MIC/Flood Control | North Sikkim | North Sikkim | 14 | R141400092 | Jhora Trg. Work at Lichu Khola, Nin | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
271 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400093 | Jhora Trg. Work at Jali Power House | Irrigation & Flood Control | 2.4 | 2008-09-26 | 2.4
272 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400094 | Jhora Trg. Work at Sirwani Bazaar | Irrigation & Flood Control | 2.85 | 2008-09-26 | 2.85
273 | MIC/Flood Control | West Sikkim | West Sikkim | 14 | R141400095 | Jhora Trg. Work at Rani Khola unde | Irrigation & Flood Control | 2.23 | 2008-09-26 | 2.23
274 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400096 | Jhora Trg. Work nr TNHS School Teac | Irrigation & Flood Control | 2.85 | 2008-09-26 | 2.85
275 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400097 | Jhora Trg. Work along below TNHS S | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
276 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400098 | Jhora Trg. Work along Majuwa Khola | Irrigation & Flood Control | 2.85 | 2008-09-26 | 2.85
277 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400099 | Devithan jhora / Subidar jhora at M | Irrigation & Flood Control | 1.94 | 2008-09-26 | 1.94
278 | MIC/Flood Control | West Sikkim | West Sikkim | 14 | R141400100 | Jhora Trg. Work nr Hee Bazar at KN | Irrigation & Flood Control | 1.14 | 2008-09-26 | 1.14
279 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400101 | Repair & restoration of Kamalnath j | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
280 | MIC/Flood Control | North Sikkim | North Sikkim | 14 | R141400102 | Jhora Trg. Work at Manual Khandu kh | Irrigation & Flood Control | 2.04 | 2008-09-26 | 2.04
281 | MIC/Flood Control | North Sikkim | North Sikkim | 14 | R141400103 | Jhora Trg. Work along Rong Rong Kh | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
282 | MIC/Flood Control | West Sikkim | West Sikkim | 14 | R141400104 | Jhora Trg. Work along Geyzing Malba | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
283 | MIC/Flood Control | West Sikkim | West Sikkim | 14 | R141400105 | Jhora Trg. Work along Trijunction | Irrigation & Flood Control | 2.85 | 2008-09-26 | 2.85
284 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400106 | Const. Chewa Pani Jhora at Lower Path | Irrigation & Flood Control | 2.18 | 2008-09-26 | 2.18
285 | MIC/Flood Control | West Sikkim | West Sikkim | 14 | R141400107 | Jhora Trg. Work along Kyongsa Jhora | Irrigation & Flood Control | 2.09 | 2008-09-26 | 2.09
286 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400108 | Jhora Trg. Work nr the land of Taj | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
287 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400109 | Const. Chewa Pani Jhora at Lower Patha | Irrigation & Flood Control | 2.75 | 2008-09-26 | 2.75
288 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400110 | Jhora Trg. Work nr the hpouse o | Irrigation & Flood Control | 0.95 | 2008-09-26 | 0.95
289 | MIC/Flood Control | West Sikkim | West Sikkim | 14 | R141400111 | Jhora Trg. work at Singlap khola un | Irrigation & Flood Control | 2.75 | 2008-09-26 | 2.75
290 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400112 | Const. Jhora Trg. Work at Sitco jhora | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
291 | MIC/Flood Control | North Sikkim | North Sikkim | 14 | R141400113 | Jhora Trg. Work along Nindek jhora | Irrigation & Flood Control | 2.75 | 2008-09-26 | 2.75
292 | MIC/Flood Control | West Sikkim | West Sikkim | 14 | R141400114 | Jhora Trg. Work at Arjun Kholsa at | Irrigation & Flood Control | 2.75 | 2008-09-26 | 2.75
293 | MIC/Flood Control | North Sikkim | North Sikkim | 14 | R141400115 | Jhora Trg. Work at Seeling Khol | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
294 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400116 | Jhora Trg. Work along Bojeny Jhora | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
295 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400117 | Jhora Trg. Work to Lama jhora a | Irrigation & Flood Control | 2.85 | 2008-09-26 | 2.85
296 | MIC/Flood Control | West Sikkim | West Sikkim | 14 | R141400118 | Jhora Trg. Work along Gairi Kho | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
297 | MIC/Flood Control | West Sikkim | West Sikkim | 14 | R141400119 | Jhora Trg. Work along Sumbuk Dovan | Irrigation & Flood Control | 2.85 | 2008-09-26 | 2.85
298 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400120 | Jhora Trg. Work at Arkya jhora | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
299 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400121 | Construction and Restoration of Saw | Irrigation & Flood Control | 1.57 | 2008-09-26 | 1.57
300 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400122 | Jhora Trg. Work along Sukhapul | Irrigation & Flood Control | 8.07 | 2008-09-26 | 8.07
301 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400123 | Jhora Trg. Work at Sai Mandir J | Irrigation & Flood Control | 2.85 | 2008-09-26 | 2.85
302 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400124 | Jhora Trg. Work at 14th Mile, Kewzi | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
303 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400125 | Jhora Trg. Work at Thuchung khola a | Irrigation & Flood Control | 1.42 | 2008-09-26 | 1.42
304 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400126 | Jhora Trg. Work nr Royal Cottag | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
305 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400127 | Constructin of Jhora Trg. Work at S | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
306 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400128 | Jhora Trg. Work at Jewel Jhora | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
307 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400129 | Jhora Trg. Work at Kewzing road, Ra | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
308 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400130 | Jhora Trg. Work at Hospital Jhora b | Irrigation & Flood Control | 1.42 | 2008-09-26 | 1.42
309 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400131 | Jhora Trg. Work at Ganesh Tok a | Irrigation & Flood Control | 2.85 | 2008-09-26 | 2.85
310 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400132 | Jhora Trg. Work at Jhora nr Swastic | Irrigation & Flood Control | 2.85 | 2008-09-26 | 2.85
311 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400133 | Jhora Trg. Work along Kaluk kholsa, | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
312 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400134 | Const. Bongdu Jhora at L/Kolthang, Kha | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
313 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400135 | Jhora Trg. Work at Phibraj Jhor | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
314 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400136 | Jhora Trg. Work in Jogi Dhara jhora | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
315 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400137 | Jhora Trg. Work along Makhan Jh | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
316 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400138 | Jhora Trg. Work nr Kajla Petrol | Irrigation & Flood Control | 2.09 | 2008-09-26 | 2.09
317 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400139 | Jhora Trg. Work at Ganesh Tok a | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
318 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400140 | Jhora Trg. Work along Army Camp | Irrigation & Flood Control | 2.09 | 2008-09-26 | 2.09
319 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400141 | Jhora Trg. Work at Signal jhor | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
320 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400142 | Jhora Trg. Work at Basnet Jhora La | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
321 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400143 | Jhora Trg. Work at Jali Jhora a | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
322 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400144 | Jhora Trg. Work at Lepcha jhora at | Irrigation & Flood Control | 3.04 | 2008-09-26 | 3.04
323 | MIC/Flood Control | North Sikkim | North Sikkim | 14 | R141400145 | Jhora Trg. Work a Ape Khola at | Irrigation & Flood Control | 2.85 | 2008-09-26 | 2.85
324 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400146 | Jhora Trg. Work at Bagaley dara | Irrigation & Flood Control | 1.71 | 2008-09-26 | 1.71
325 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400147 | Jhora Trg. Work at Rhenock Baza | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
326 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400148 | Jhora Trg. Work B. Tshering at | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
327 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400149 | Jhora Trg. Work at Devithane Jh | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
328 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400150 | Jhora Trg. Work at Dorjee jhora | Irrigation & Flood Control | 2.5 | 2008-09-26 | 2.5
329 | MIC/Flood Control | North Sikkim | North Sikkim | 14 | R141400151 | Jhora Trg. Work at Phaderi khola at | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
330 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400152 | Jhora Trg. Work at Chiptu Khola | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
331 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400153 | Jhora Trg. Work at Chippsu Village | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
332 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400154 | Jhora Trg. Work at Chuba Senti unde | Irrigation & Flood Control | 3.32 | 2008-09-26 | 3.32
333 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400155 | Jhora Trg. Work along Phigu jho | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
334 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400156 | Jhora trg. Work at Tsholamthang | Irrigation & Flood Control | 2.85 | 2008-09-26 | 2.85
335 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400157 | Jhora Trg. Work nr Kajla Petrol | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
336 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400158 | Jhora Trg. Work at Pakha Gaon, Dhya | Irrigation & Flood Control | 2.71 | 2008-09-26 | 2.71
337 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400159 | Jhora Trg. Work at Tamang Jhora, Ar | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
338 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400160 | Jhora Trg. Work at Khanew jhora up | Irrigation & Flood Control | 3.8 | 2008-09-26 | 3.8
339 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400161 | Jhora Trg. Work at Lower Bermio | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
340 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400162 | Jhora Trg. Work at Samsing Tamang | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
341 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400163 | Jhora Trg. Work along Thongsing Ari | Irrigation & Flood Control | 1.8 | 2008-09-26 | 1.8
342 | MIC/Flood Control | North Sikkim | North Sikkim | 14 | R141400164 | Jhora Trg. Work along Changthong Kh | Irrigation & Flood Control | 2.66 | 2008-09-26 | 2.66
343 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400165 | Jhora Trg. Work & AEW along Bhatti | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
344 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400166 | Jhora Trg. Work & AEW along Devitha | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
345 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400167 | Construction/restoration of Jhora T | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
346 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400168 | Jhora Trg. Work &AEW along Sanchi K | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
347 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400169 | Jhora Trg. Work & Catch Water D | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
348 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400170 | Jhora Trg. Work & Catch Water D | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
349 | MIC/Flood Control | West Sikkim | West Sikkim | 14 | R141400171 | Jhora Trg. Work & Catch Water Dr at | Irrigation & Flood Control | 3.32 | 2008-09-26 | 3.32
350 | MIC/Flood Control | West Sikkim | West Sikkim | 14 | R141400172 | Jhora Trg. Work & Catch Water Dr at | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
351 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400173 | Jhora Trg. Work and Protection Work Rinzing Ch | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
352 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400174 | Jhora Trg. Work/AEW at Kazi Dar | Irrigation & Flood Control | 2.09 | 2008-09-26 | 2.09
353 | MIC/Flood Control | West Sikkim | West Sikkim | 14 | R141400175 | Jhora Trg. Work / AEW at Samthang u | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
354 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400176 | Protection Work Dr. Sheela at Sichey East Sikki | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
355 | MIC/Flood Control | North Sikkim | North Sikkim | 14 | R141400177 | Protection Work at Kabi Tatangkha S. Bhutia, K | Irrigation & Flood Control | 2.47 | 2008-09-26 | 2.47
356 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400178 | River Trg. works along Bhotey Khola | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
357 | MIC/Flood Control | North Sikkim | North Sikkim | 14 | R141400179 | River Trg. works along river Teesta bel | Irrigation & Flood Control | 2.85 | 2008-09-26 | 2.85
358 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400180 | Ext. MIC at Babarchi Khet at lower | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
359 | MIC | South Sikkim | South Sikkim | 14 | R141400181 | Const. Kharey Khola MIC | Irrigation & Flood Control | 2.85 | 2008-09-26 | 2.85
360 | MIC | North Sikkim | North Sikkim | 14 | R141400182 | Const. MIC at Tokman khola (Taryang) | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
361 | MIC | South Sikkim | South Sikkim | 14 | R141400183 | Const. MIC from Bojey Khola to Anethan | Irrigation & Flood Control | 2.85 | 2008-09-26 | 2.85
362 | MIC | East Sikkim | East Sikkim | 14 | R141400184 | Const. MIC from Sangey Dhara Souces to | Irrigation & Flood Control | 1.42 | 2008-09-26 | 1.42
363 | MIC | South Sikkim | South Sikkim | 14 | R141400185 | Const. MIC from Kyongsa khola to Kyong | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
364 | MIC | South Sikkim | South Sikkim | 14 | R141400186 | Const. MIC from Tanam Khola to Kerabar | Irrigation & Flood Control | 2.56 | 2008-09-26 | 2.56
365 | MIC | South Sikkim | South Sikkim | 14 | R141400187 | Construciton MIC at Rabitar Syangre | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
366 | MIC | South Sikkim | South Sikkim | 14 | R141400188 | Const. MIC from Lower Tokal to Kungee | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
367 | MIC | East Sikkim | East Sikkim | 14 | R141400189 | Const. MIC at Raja Kulo below Neopaney | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
368 | MIC | South Sikkim | South Sikkim | 14 | R141400190 | Const. MIC from Tanam Khola to Kerabar | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
369 | MIC | South Sikkim | South Sikkim | 14 | R141400191 | Const. Gairi Khet to Khairbotey, Ratey | Irrigation & Flood Control | 2.85 | 2008-09-26 | 2.85
370 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400192 | Const. MIC at Kharka Khet at Nazitam, | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
371 | MIC | East Sikkim | East Sikkim | 14 | R141400193 | Const. MIC from Devithan to Manger khe | Irrigation & Flood Control | 3.8 | 2008-09-26 | 3.8
372 | MIC | West Sikkim | West Sikkim | 14 | R141400194 | Const. MIC at Sumthang Devithan at Sak | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
373 | MIC | South Sikkim | South Sikkim | 14 | R141400195 | Const. MIC from Sawney Jhora to Kamare | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
374 | MIC | South Sikkim | South Sikkim | 14 | R141400196 | Const. MIC at Bermiok below the Phongl | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
375 | MIC | East Sikkim | East Sikkim | 14 | R141400197 | MIC at Devithan source, Eun Tar, Na | Irrigation & Flood Control | 3.3 | 2008-09-26 | 3.3
376 | MIC | East Sikkim | East Sikkim | 14 | R141400198 | Const. MIC at L/Biring, ML Bastola, Rh | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
377 | MIC | East Sikkim | East Sikkim | 14 | R141400199 | Const. MIC at Chakadi Khanda Shivalaya | Irrigation & Flood Control | 3.8 | 2008-09-26 | 3.8
378 | MIC | East Sikkim | East Sikkim | 14 | R141400200 | Const. Kyongsa MIC, Rhenok Tarpin, Rhe | Irrigation & Flood Control | 3.32 | 2008-09-26 | 3.32
379 | MIC | East Sikkim | East Sikkim | 14 | R141400201 | Const. Sajbotey MIC at upper Bering, M | Irrigation & Flood Control | 2.66 | 2008-09-26 | 2.66
380 | MIC | East Sikkim | East Sikkim | 14 | R141400202 | Const. MIC from Luksom Jhora Tsalamtha | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
381 | MIC | East Sikkim | East Sikkim | 14 | R141400203 | MIC at Upper Devithan at Talkharka, | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
382 | MIC | West Sikkim | West Sikkim | 14 | R141400204 | Consn & Extn of MIC at Martalung U | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
383 | MIC | West Sikkim | West Sikkim | 14 | R141400205 | Const. MIC from Alay kholsa to Dara kh | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
384 | MIC | West Sikkim | West Sikkim | 14 | R141400206 | Const. MIC at Andhery Gairi Khet at Sa | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
385 | MIC | East Sikkim | East Sikkim | 14 | R141400207 | Const. MIC from Kardung Khola to Kardu | Irrigation & Flood Control | 2.85 | 2008-09-26 | 2.85
386 | MIC | East Sikkim | East Sikkim | 14 | R141400208 | MIC at Lower Devithan at Talkharka, | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
387 | MIC | East Sikkim | East Sikkim | 14 | R141400209 | Const. MIC at Mulukey, Rhenok Constitu | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
388 | MIC | South Sikkim | South Sikkim | 14 | R141400210 | Const. 6th Mile to Bhutaytar MIC Dew D | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
389 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400211 | Const. Duba Khorey to Lower Tumlabong | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
390 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400212 | Extn of MIC from Sajbotey to Kurley | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
391 | MIC | East Sikkim | East Sikkim | 14 | R141400213 | Const. Sangmo Busty MIC at lower Timpe | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
392 | MIC | East Sikkim | East Sikkim | 14 | R141400214 | Const. MIC at Gairi Khet at Sakyong, S | Irrigation & Flood Control | 1.76 | 2008-09-26 | 1.76
393 | MIC | East Sikkim | East Sikkim | 14 | R141400215 | Const. MIC at Padhery Khet at Zingla, | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
394 | MIC | East Sikkim | East Sikkim | 14 | R141400216 | Const. Chuba Khola to Rakdong Gumpa kh | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
395 | MIC/Flood Control | East Sikkim | East Sikkim | 14 | R141400217 | Const. MIC at Nirola Gaon, Upper Tarey | Irrigation & Flood Control | 2.85 | 2008-09-26 | 2.85
396 | MIC | East Sikkim | East Sikkim | 14 | R141400218 | Const. MIC from Changey Jhora to Bista | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
397 | MIC | East Sikkim | East Sikkim | 14 | R141400219 | Extn of MIC at Bhotey Khola to Nasp | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
398 | MIC | East Sikkim | East Sikkim | 14 | R141400220 | Const. MIC at Kaputhang, Taza, Rhenok | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
399 | MIC | West Sikkim | West Sikkim | 14 | R141400221 | Const. MIC from Sajbotey Dhara to Kazi | Irrigation & Flood Control | 2.85 | 2008-09-26 | 2.85
400 | MIC | West Sikkim | West Sikkim | 14 | R141400222 | Reno. MIC at Sarki Dara village und | Irrigation & Flood Control | 2.85 | 2008-09-26 | 2.85
401 | MIC | West Sikkim | West Sikkim | 14 | R141400223 | Const. Lepcha goan MIC (Phase-II) at M | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
402 | MIC | North Sikkim | North Sikkim | 14 | R141400224 | Extn. of Yechu khola MIC below Penl | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
403 | MIC | North Sikkim | North Sikkim | 14 | R141400225 | Consn MIC from Khongpu Khola to Lin | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
404 | MIC | North Sikkim | North Sikkim | 14 | R141400226 | Conn of MIC from Kopu to Lingtam, | Irrigation & Flood Control | 2.56 | 2008-09-26 | 2.56
405 | MIC | North Sikkim | North Sikkim | 14 | R141400227 | MIC at Sapkota Dhara to Ghimirey Kh | Irrigation & Flood Control | 2.2 | 2008-09-26 | 2.2
406 | MIC/Flood Control | South Sikkim | South Sikkim | 14 | R141400228 | Const. MIC at Ratey Khola at Passi, Ra | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
407 | MIC | North Sikkim | North Sikkim | 14 | R141400229 | Const. Phodock MIC at Lower Rongong un | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
408 | MIC | East Sikkim | East Sikkim | 14 | R141400230 | Const. MIC at Tensong Arithang Khola a | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
409 | MIC | South Sikkim | South Sikkim | 14 | R141400231 | Const. MIC for Cardmom Field from Udau | Irrigation & Flood Control | 2.85 | 2008-09-26 | 2.85
410 | MIC | South Sikkim | South Sikkim | 14 | R141400232 | Ext/Ren. of Nangdang MIC at Lower | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
411 | MIC | South Sikkim | South Sikkim | 14 | R141400233 | Const. MIC from Rateypani to Lepcha Kh | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
412 | MIC | North Sikkim | North Sikkim | 14 | R141400234 | Resto. MIC from Sagong to Thogoma a | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
413 | MIC | West Sikkim | West Sikkim | 14 | R141400235 | Const. Dantey kulo MIC at Kabirthang, | Irrigation & Flood Control | 2.85 | 2008-09-26 | 2.85
414 | MIC | West Sikkim | West Sikkim | 14 | R141400236 | Reno/ Extn of Guea Khola to Majgao | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
415 | MIC/Flood Control | West Sikkim | West Sikkim | 14 | R141400237 | Const. Kagaythang kulo MIC at Kagaytha | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
416 | MIC | West Sikkim | West Sikkim | 14 | R141400238 | Reno/ Extn of Lingbung khola MIC at | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
417 | MIC | West Sikkim | West Sikkim | 14 | R141400239 | Const. MIC at Lower Budang under Chaku | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
418 | MIC | West Sikkim | West Sikkim | 14 | R141400240 | Const. MIC at Bhutey Khola Tadong, Rin | Irrigation & Flood Control | 4.75 | 2008-09-26 | 4.75
419 | MIC | West Sikkim | West Sikkim | 14 | R141400241 | Reno/ Extn of Sadewa khola MIC at Y | Irrigation & Flood Control | 1.9 | 2008-09-26 | 1.9
420 | MIC | West Sikkim | West Sikkim | 14 | R141400242 | Consn/Extn of Rhenock khola to Tibu | Irrigation & Flood Control | 2.36 | 2008-09-26 | 2.36
421 | MIC/Flood Control | West Sikkim | West Sikkim | 14 | R141400243 | Const. MIC Kharey khola source to Lowe | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
422 | MIC | West Sikkim | West Sikkim | 14 | R141400244 | Consn & Extn of MIC from Laley kho | Irrigation & Flood Control | 2.37 | 2008-09-26 | 2.37
423 | MIC | West Sikkim | West Sikkim | 14 | R141400245 | Reno/Extn of Tinziring MIC under Ta | Irrigation & Flood Control | 4.75 | 2008-09-26 | 4.75
424 | RDWS | West Sikkim | West Sikkim | 14 | R141400247 | Aug RWS Rinchenpong-Chaku | Rural Management Development Department | 679.51 | 2008-09-26 | 679.51
425 | RDWS | South Sikkim | South Sikkim | 14 | R141400248 | Aug RWS Darop Salghari | Rural Management Development Department | 131.16 | 2008-09-26 | 131.16
426 | RDWS | East Sikkim | East Sikkim | 14 | R141400249 | Aug RWS Chalampong & Chal | Rural Management Development Department | 99.49 | 2008-09-26 | 99.49
427 | RDWS | East Sikkim | East Sikkim | 14 | R141400250 | Aug RWS Ralop Rangtu Sing | Rural Management Development Department | 117.4 | 2008-09-26 | 117.4
428 | RDWS | East Sikkim | East Sikkim | 14 | R141400251 | Aug RWS Kadamtam | Rural Management Development Department | 54.51 | 2008-09-26 | 52.2
429 | RDWS | North Sikkim | North Sikkim | 14 | R141400252 | Aug RWS U&M Tryang&Sudong | Rural Management Development Department | 92.5 | 2008-09-26 | 88.19
430 | School | East Sikkim | East Sikkim | 14 | R141400253 | Govt Degree College Rundung in Rhe | Human Resource Development Department | 1435.46 | 2008-12-02 | 1078.31
431 | School | West Sikkim | West Sikkim | 14 | R141400254 | 5 room primary school Singpeng | Human Resource Development Department | 30.51 | 2008-12-02 | 28.84
432 | School | West Sikkim | West Sikkim | 14 | R141400255 | 5 room primary school Rangit | Human Resource Development Department | 29.9 | 2008-12-02 | 29.9
433 | School | West Sikkim | West Sikkim | 14 | R141400256 | 5 room primary school Salley | Human Resource Development Department | 30.58 | 2008-12-02 | 29.91
434 | School | West Sikkim | West Sikkim | 14 | R141400257 | 5 room primary school Tikjya | Human Resource Development Department | 30.8 | 2008-12-02 | 30.14
435 | School | West Sikkim | West Sikkim | 14 | R141400258 | 5 room primary school Gitang | Human Resource Development Department | 32.89 | 2008-12-02 | 32
436 | School | West Sikkim | West Sikkim | 14 | R141400259 | 5 room primary school Mendogaon | Human Resource Development Department | 33.24 | 2008-12-02 | 33.24
437 | School | West Sikkim | West Sikkim | 14 | R141400260 | 5 room primary school Salangdang | Human Resource Development Department | 31.04 | 2008-12-02 | 29.31
438 | School | West Sikkim | West Sikkim | 14 | R141400261 | 5 room primary school Lower Okrey | Human Resource Development Department | 31.04 | 2008-12-02 | 29.32
439 | School | West Sikkim | West Sikkim | 14 | R141400262 | 5 room Junior High school Rimbhi | Human Resource Development Department | 41.7 | 2008-12-02 | 39.43
440 | School | West Sikkim | West Sikkim | 14 | R141400263 | 5 room Junior High school Labdang | Human Resource Development Department | 31.82 | 2008-12-02 | 30.93
441 | School | West Sikkim | West Sikkim | 14 | R141400264 | 7 room Junior High school Central M | Human Resource Development Department | 42.57 | 2008-12-02 | 25.46
442 | School | West Sikkim | West Sikkim | 14 | R141400265 | 7 room Junior High school Hushingth | Human Resource Development Department | 42.61 | 2008-12-02 | 41.38
443 | School | West Sikkim | West Sikkim | 14 | R141400266 | 7 room Junior High school Mabong | Human Resource Development Department | 42 | 2008-12-02 | 39.2
444 | School | West Sikkim | West Sikkim | 14 | R141400267 | 7 room Sr secondary school Buriakho | Human Resource Development Department | 37.61 | 2008-12-02 | 35.11
445 | Road | West Sikkim | West Sikkim | 14 | R141400268 | Pelling Chumbung Road | Roads & Bridges Department | 194.87 | 2008-12-02 | 194.87
446 | Road | East Sikkim | East Sikkim | 14 | R141400269 | San Dipudara Road KM 3rd Ch | Roads & Bridges Department | 151.61 | 2008-12-02 | 151.61
447 | Road | East Sikkim | East Sikkim | 14 | R141400270 | SSS School-Kokoley PSchoo | Roads & Bridges Department | 330.07 | 2008-12-02 | 330.07
448 | Road | South Sikkim | South Sikkim | 14 | R141400271 | App Road Belling Vill Turuk | Roads & Bridges Department | 115.76 | 2008-12-02 | 115.76
449 | Road | West Sikkim | West Sikkim | 14 | R141400272 | Heepool to Hee School | Roads & Bridges Department | 59.12 | 2008-12-02 | 59.12
450 | Road | South Sikkim | South Sikkim | 14 | R141400273 | Ben Thalabari to Mangley | Roads & Bridges Department | 348.89 | 2008-12-02 | 348.88
451 | Road | East Sikkim | East Sikkim | 14 | R141400274 | Raley Kambel-Samdong Road | Roads & Bridges Department | 634.27 | 2008-12-02 | 634.27
452 | Road | East Sikkim | East Sikkim | 14 | R141400275 | Syari Coop.Middle Syari S | Roads & Bridges Department | 237.92 | 2008-12-02 | 237.92
453 | Road | East Sikkim | East Sikkim | 14 | R141400276 | SPWD Road Samik Linzey-Dang | Rural Management Development Department | 162.86 | 2008-12-02 | 162.86
454 | Road | South Sikkim | South Sikkim | 14 | R141400277 | Kamrang Coll-Kitchu-Dumra | Rural Management Development Department | 90.85 | 2008-12-02 | 90.85
455 | Toilet | East Sikkim | East Sikkim | 14 | R141400278 | Const. Pay & Use Toilet at Rangpo Baza | Urban Development & Housing Dept. | 16.52 | 2009-01-28 | 16.52
456 | Market | South Sikkim | South Sikkim | 14 | R141400280 | Const. Rural Market-cum-Haat Yard including | Urban Development & Housing Dept. | 67.39 | 2009-01-28 | 67.39
457 | Market/Haat | South Sikkim | South Sikkim | 14 | R141400281 | Const. Rural Haat Shed at Kewzing Bazaar | Urban Development & Housing Dept. | 9.41 | 2009-01-28 | 9.41
458 | Market/Haat | South Sikkim | South Sikkim | 14 | R141400282 | Const. Rural Haat Shed at Yangang | Urban Development & Housing Dept. | 8.62 | 2009-01-28 | 8.62
459 | Market/Haat | West Sikkim | West Sikkim | 14 | R141400283 | Const. Rural Marketing Centre at Gyalzing | Urban Development & Housing Dept. | 43.67 | 2009-01-28 | 43.67
460 | Infra / Social | East Sikkim | East Sikkim | 14 | R141400284 | Infra work related to sanitation in Rangpo bazaar | Urban Development & Housing Dept. | 241.31 | 2009-01-28 | 241.31
461 | Infra / Social | East Sikkim | East Sikkim | 14 | R141400285 | Infra work related to sanitation inRhenock Bazaar | Urban Development & Housing Dept. | 30.65 | 2009-01-28 | 30.65
462 | Infra / Social | South Sikkim | South Sikkim | 14 | R141400286 | Infra work related to sanitation inNaya Bazaar & Reshi Baz | Urban Development & Housing Dept. | 19.27 | 2009-01-28 | 19.27
463 | Infra / Social | South Sikkim | South Sikkim | 14 | R141400287 | Infra work related to sanitation inMelli Bazaar | Urban Development & Housing Dept. | 100.94 | 2009-01-28 | 100.94
464 | Infra / Social | West Sikkim | West Sikkim | 14 | R141400288 | Infra work related to sanitation inGyalzing Bazaar | Urban Development & Housing Dept. | 144.4 | 2009-01-28 | 144.4
465 | RDWS | South Sikkim | South Sikkim | 14 | R141400289 | DWS Rehab centre at Berfung | Urban Development & Housing Dept. | 55.31 | 2009-01-28 | 55.31
466 | School | South Sikkim | South Sikkim | 14 | R141400290 | Const. Vill Trg Centre Bakhim/Kewzing | Urban Development & Housing Dept. | 93.69 | 2009-01-28 | 93.69
467 | Market/Haat | West Sikkim | West Sikkim | 14 | R141400291 | Infra wks Reclamation of Water Logged area at Sipchu | Urban Development & Housing Dept. | 165.35 | 2009-01-28 | 165.35
468 | Road | South Sikkim | South Sikkim | 14 | R141400292 | Sangmoo Link Road | Roads & Bridges Department | 378.29 | 2009-01-28 | 378.29
469 | Road | West Sikkim | West Sikkim | 14 | R141400293 | Chakung-Gelling Km1-7.24k road | Roads & Bridges Department | 471.77 | 2009-01-28 | 471.77
470 | RDWS | East Sikkim | East Sikkim | 14 | R141400294 | Aug.RDWS Middle Camp Baza | WS & Public Health & Engineering Department | 279.01 | 2009-01-28 | 279.01
471 | RDWS | East Sikkim | East Sikkim | 14 | R141400295 | Aug. RDWS Shekwa Bazaar & | WS & Public Health & Engineering Department | 64.69 | 2009-01-28 | 64.69
472 | Road | South Sikkim | South Sikkim | 15 | R151400001 | Const. Phongla Mamring-Basbo | Roads & Bridges Department | 276.82 | 2009-05-11 | 276.81
473 | Road | East Sikkim | East Sikkim | 15 | R151400002 | ICAR Gate-NHPC(1.11km)5th | Roads & Bridges Department | 136.42 | 2009-07-28 | 136.42
474 | RDWS | East Sikkim | East Sikkim | 15 | R151400003 | Const. WSS Lingdok Bazaar | WS & Public Health & Engineering Department | 213.69 | 2009-11-25 | 213.69
475 | Road | East Sikkim | East Sikkim | 15 | R151400004 | Dung Dung Pattey to Sonamati Sr. Se | Roads & Bridges Department | 325.66 | 2010-01-04 | 325.66
476 | Road | East Sikkim | East Sikkim | 15 | R151400005 | Const. Road Beyong Lepcha Gumpa to Tha | Roads & Bridges Department | 140.45 | 2010-01-04 | 140.45
477 | Road | East Sikkim | East Sikkim | 15 | R151400006 | Const. Road Purano Hospital Shanti Naga | Roads & Bridges Department | 217.49 | 2010-01-04 | 217.48
478 | Road | East Sikkim | East Sikkim | 15 | R151400007 | Const. New app Road Syaplay to Pathang | Roads & Bridges Department | 548.3 | 2010-01-04 | 548.29
479 | Road | East Sikkim | East Sikkim | 15 | R151400008 | Upgd & extexsion of Road Rongli to | Roads & Bridges Department | 277.41 | 2010-01-04 | 277.4
480 | Road | North Sikkim | North Sikkim | 15 | R151400009 | Const. 2 km app Road Gor to Taryong | Roads & Bridges Department | 146.31 | 2010-01-04 | 146.31
481 | Road | North Sikkim | North Sikkim | 15 | R151400010 | Const. app Road to Lhevan Village Lingt | Roads & Bridges Department | 99.69 | 2010-01-04 | 99.69
482 | Road | North Sikkim | North Sikkim | 15 | R151400011 | Const. 2 km link Road NSH to Upper Paks | Roads & Bridges Department | 156.46 | 2010-01-04 | 156.46
483 | Road | West Sikkim | West Sikkim | 15 | R151400012 | New app Road Gyalshing Sakyong SPWD | Roads & Bridges Department | 369.86 | 2010-01-04 | 369.86
484 | Road | West Sikkim | West Sikkim | 15 | R151400013 | Const. app Road to Arubotey Road Chakung | Roads & Bridges Department | 410.42 | 2010-01-04 | 410.42
485 | Road | West Sikkim | West Sikkim | 15 | R151400014 | Const. Road Zhap - Zhapey to Pakki Goan | Roads & Bridges Department | 393.84 | 2010-01-04 | 393.84
486 | Road | West Sikkim | West Sikkim | 15 | R151400015 | Const. Link Road Pakki Goan to Budang C | Roads & Bridges Department | 262.19 | 2010-01-04 | 262.19
487 | Road | West Sikkim | West Sikkim | 15 | R151400016 | Const. Link Road Hilley RIBDI Road to Kho | Roads & Bridges Department | 301.1 | 2010-01-04 | 301.1
488 | Road | East Sikkim | East Sikkim | 15 | R151400017 | Pachak rd.-Extension, back cutting, | Roads & Bridges Department | 259.19 | 2010-01-04 | 259.19
489 | Road | East Sikkim | East Sikkim | 15 | R151400018 | Upgr Kingstone Simana Khola rd | Roads & Bridges Department | 263.7 | 2010-01-04 | 263.7
490 | Road | East Sikkim | East Sikkim | 15 | R151400019 | Carpetting of Aritar Hattichere | Roads & Bridges Department | 126.14 | 2010-01-04 | 126.14
491 | Road | East Sikkim | East Sikkim | 15 | R151400020 | Upgr app Road to Saurany village Lin | Roads & Bridges Department | 99.33 | 2010-01-04 | 99.33
492 | Road | East Sikkim | East Sikkim | 15 | R151400021 | Const. link Road Andhari to Gakcha Bu | Roads & Bridges Department | 137.35 | 2010-01-04 | 137.35
493 | Road | West Sikkim | West Sikkim | 15 | R151400023 | Gyaba Golai to Tikjek Road 4 Km under | Roads & Bridges Department | 350.95 | 2010-01-04 | 350.95
494 | Road | West Sikkim | West Sikkim | 15 | R151400024 | Carpetting of existing Soreng to | Roads & Bridges Department | 194.86 | 2010-01-04 | 189.47
495 | School | South Sikkim | South Sikkim | 15 | R151400025 | Lingee Secondary School (9 Cl.Room | Human Resource Development Department | 45.05 | 2010-01-04 | 45.05
496 | School | South Sikkim | South Sikkim | 15 | R151400026 | Melli Secondary School (9 Cl.Rooms | Human Resource Development Department | 43.12 | 2010-01-04 | 43.12
497 | School | South Sikkim | South Sikkim | 15 | R151400027 | Jarrong Secondary School (9 Cl.Roo | Human Resource Development Department | 43.83 | 2010-01-04 | 4.73
498 | School | South Sikkim | South Sikkim | 15 | R151400028 | Ben Junior High School (7 Cl.Rooms) | Human Resource Development Department | 37.57 | 2010-01-04 | 37.57
499 | School | South Sikkim | South Sikkim | 15 | R151400029 | Allaydara Junior High School (7 Cl | Human Resource Development Department | 41.59 | 2010-01-04 | 41.59
500 | School | South Sikkim | South Sikkim | 15 | R151400030 | Lingzo Primary. School (7 Cl.Rooms | Human Resource Development Department | 39.54 | 2010-01-04 | 9.34
501 | School | South Sikkim | South Sikkim | 15 | R151400031 | Mangzing Primary School (7 Cl.Room | Human Resource Development Department | 35.9 | 2010-01-04 | 35.9
502 | School | South Sikkim | South Sikkim | 15 | R151400032 | Ruchung Primary School (5 Cl.Rooms | Human Resource Development Department | 34.51 | 2010-01-04 | 34.51
503 | School | South Sikkim | South Sikkim | 15 | R151400033 | Kitchu Dumbra Primary School (5 Cl | Human Resource Development Department | 33.11 | 2010-01-04 | 33.11
504 | School | South Sikkim | South Sikkim | 15 | R151400034 | Gurung gaon Primary School (5 Cl.R | Human Resource Development Department | 33.82 | 2010-01-04 | 33.82
505 | School | East Sikkim | East Sikkim | 15 | R151400035 | Tumin Secondary School (6 Cl.Rooms | Human Resource Development Department | 45.63 | 2010-01-04 | 45.63
506 | School | East Sikkim | East Sikkim | 15 | R151400036 | Simick Lingzey Junior High School | Human Resource Development Department | 38.5 | 2010-01-04 | 38.49
507 | School | East Sikkim | East Sikkim | 15 | R151400037 | Martam Yangtang Junior High School | Human Resource Development Department | 45.09 | 2010-01-04 | 45.09
508 | School | East Sikkim | East Sikkim | 15 | R151400038 | Sapley Secondary School (6 Cl.Roo | Human Resource Development Department | 39.64 | 2010-01-04 | 39.64
509 | School | East Sikkim | East Sikkim | 15 | R151400039 | Pachak Junior High School (6 Cl.Roo | Human Resource Development Department | 40.04 | 2010-01-04 | 40.04
510 | School | East Sikkim | East Sikkim | 15 | R151400040 | Mazitar Junior High School School ( | Human Resource Development Department | 32.88 | 2010-01-04 | 32.88
511 | School | North Sikkim | North Sikkim | 15 | R151400041 | Shotak Lower Primary School (4 Cl.R | Human Resource Development Department | 27.8 | 2010-01-04 | 27.8
512 | School | East Sikkim | East Sikkim | 15 | R151400042 | Patuk Kokolay Primary School (4 Cl | Human Resource Development Department | 29.65 | 2010-01-04 | 29.65
513 | School | East Sikkim | East Sikkim | 15 | R151400043 | Pachey Primary School (4 Cl.Rooms) | Human Resource Development Department | 26.74 | 2010-01-04 | 26.74
514 | School | East Sikkim | East Sikkim | 15 | R151400044 | N-Regu Junior High School (4 Cl.Roo | Human Resource Development Department | 31.42 | 2010-01-04 | 31.42
515 | School | East Sikkim | East Sikkim | 15 | R151400045 | Rongyek Junior High School (4 Cl.R | Human Resource Development Department | 24.79 | 2010-01-04 | 24.79
516 | School | North Sikkim | North Sikkim | 15 | R151400046 | Ralak Primary School (4 Cl.Rooms) | Human Resource Development Department | 27.24 | 2010-01-04 | 27.24
517 | School | North Sikkim | North Sikkim | 15 | R151400047 | Upper Mangshila Primary High School | Human Resource Development Department | 34.95 | 2010-01-04 | 34.95
518 | School | North Sikkim | North Sikkim | 15 | R151400048 | Rarik Primary School (4 Cl.Rooms) | Human Resource Development Department | 26.53 | 2010-01-04 | 26.53
519 | School | East Sikkim | East Sikkim | 15 | R151400049 | Upper Syari Junior High School (9 Cl.R | Human Resource Development Department | 50.73 | 2010-01-04 | 50.73
520 | School | East Sikkim | East Sikkim | 15 | R151400050 | Light Structure School at Namchey | Human Resource Development Department | 26.46 | 2010-01-04 | 26.46
521 | RDWS | East Sikkim | East Sikkim | 15 | R151400051 | Aug RWSS,Upper Samdong | Rural Management Development Department | 46.47 | 2010-01-04 | 46.47
522 | RDWS | South Sikkim | South Sikkim | 15 | R151400053 | Const. RWSS Tingley Village | Rural Management Development Department | 158.62 | 2010-01-04 | 158.61
523 | RDWS | South Sikkim | South Sikkim | 15 | R151400054 | Const. RWSS Thangsing Villag | Rural Management Development Department | 167.76 | 2010-01-04 | 167.76
524 | RDWS | South Sikkim | South Sikkim | 15 | R151400055 | RWSS Sumbuk Kartikey and | Rural Management Development Department | 592.03 | 2010-01-04 | 592.03
525 | Road | South Sikkim | South Sikkim | 15 | R151400059 | Const. new Road Janta Bazar to Upper Lingmoo | Roads & Bridges Department | 176.81 | 2010-01-28 | 176.81
526 | Road | South Sikkim | South Sikkim | 15 | R151400060 | Const. Truckable Road Old Vetenary compound to Tharpu (Kopchey) | Roads & Bridges Department | 161.6 | 2010-01-28 | 161.6
527 | Road | South Sikkim | South Sikkim | 15 | R151400061 | Const. Truckable Road Susuleydara (Tingl | Roads & Bridges Department | 244.38 | 2010-01-28 | 244.38
528 | Road | South Sikkim | South Sikkim | 15 | R151400062 | Const. new Road Upper Lingmoo to Shiva M | Roads & Bridges Department | 48.05 | 2010-01-28 | 48.05
529 | Road | South Sikkim | South Sikkim | 15 | R151400063 | Const. new Road Pepthang ward to Pepthan | Roads & Bridges Department | 38.62 | 2010-01-28 | 38.62
530 | Road | South Sikkim | South Sikkim | 15 | R151400064 | Const. PMGSY Dong Denchung Road to Be | Roads & Bridges Department | 134.19 | 2010-01-28 | 134.19
531 | Road | South Sikkim | South Sikkim | 15 | R151400065 | Const. new Road GLVC Road to Namprik Busty | Roads & Bridges Department | 90 | 2010-01-28 | 90
532 | Road | South Sikkim | South Sikkim | 15 | R151400066 | Const. Link Road Satam Samrook to Gangla | Roads & Bridges Department | 1618.89 | 2010-01-28 | 1618.89
533 | Road | South Sikkim | South Sikkim | 15 | R151400067 | Const. new Road Nandugaon to water pumpi | Roads & Bridges Department | 453.89 | 2010-01-28 | 444.81
534 | Road | South Sikkim | South Sikkim | 15 | R151400068 | Const. Link Road Damthang to Due Village | Roads & Bridges Department | 178.53 | 2010-01-28 | 178.53
535 | Road | South Sikkim | South Sikkim | 15 | R151400069 | Const. Link Road Lower Goam to Bhandikho | Roads & Bridges Department | 773.48 | 2010-01-28 | 696.13
536 | Road | South Sikkim | South Sikkim | 15 | R151400070 | Const. Truckable Road Solophok PMGSY Rd | Roads & Bridges Department | 89.96 | 2010-01-28 | 50.4
537 | Road | South Sikkim | South Sikkim | 15 | R151400071 | Const. new Road Dong Ambotay School to H | Roads & Bridges Department | 601.49 | 2010-01-28 | 559.39
538 | Road | West Sikkim | West Sikkim | 15 | R151400072 | Upgr Rimbi Khecheperi Road to 14th mi | Roads & Bridges Department | 498.42 | 2010-01-28 | 498.42
539 | Road | West Sikkim | West Sikkim | 15 | R151400073 | Const. App Road Rothak to Segyang School | Roads & Bridges Department | 984.41 | 2010-01-28 | 954.87
540 | Road | South Sikkim | South Sikkim | 15 | R151400074 | Const. New Road Farashay Via Timburey Go | Roads & Bridges Department | 266.63 | 2010-01-28 | 266.63
541 | Road | South Sikkim | South Sikkim | 15 | R151400075 | Const. Road Salghari PHSC to Farasay Gao | Roads & Bridges Department | 257.21 | 2010-01-28 | 227.21
542 | Road | South Sikkim | South Sikkim | 15 | R151400076 | Const. Truckable Road Chemchey via Lachi | Roads & Bridges Department | 677.39 | 2010-01-28 | 677.39
543 | Road | South Sikkim | South Sikkim | 15 | R151400077 | Const. Truckable Road Palum to Shyamdas | Roads & Bridges Department | 240.71 | 2010-01-28 | 240.71
544 | Road | South Sikkim | South Sikkim | 15 | R151400078 | Const. new Road Dhargoan Primary school | Roads & Bridges Department | 328.71 | 2010-01-28 | 328.71
545 | Road | South Sikkim | South Sikkim | 15 | R151400079 | Upgr app Road to Sadam Senior Seconda | Roads & Bridges Department | 128.86 | 2010-01-28 | 128.86
546 | Road | South Sikkim | South Sikkim | 15 | R151400080 | Upgr 9th Mile Sumbuk to Lungchok Rd | Roads & Bridges Department | 205.33 | 2010-01-28 | 205.33
547 | Road | South Sikkim | South Sikkim | 15 | R151400081 | Upgr Road Salghari Bhaisal Gaon to Lo | Roads & Bridges Department | 186.46 | 2010-01-28 | 186.46
548 | Road | South Sikkim | South Sikkim | 15 | R151400082 | Assangthang Dhar Gaon Zero Point Rd | Roads & Bridges Department | 366.73 | 2010-01-28 | 316.33
549 | Road | South Sikkim | South Sikkim | 15 | R151400083 | Upgr Road CCCT to Dorop Salghari | Roads & Bridges Department | 190.8 | 2010-01-28 | 190.8
550 | Road | South Sikkim | South Sikkim | 15 | R151400084 | Upgr Road Namchi Damthang Road to Debru | Roads & Bridges Department | 82.43 | 2010-01-28 | 82.43
551 | Road | West Sikkim | West Sikkim | 15 | R151400085 | Widg/Carpetting of Melli-Tathang R | Roads & Bridges Department | 172.33 | 2010-01-28 | 172.33
552 | Road | South Sikkim | South Sikkim | 15 | R151400086 | Upgr Denchung Dong Road (Upto Primary | Roads & Bridges Department | 208.9 | 2010-01-28 | 198.46
553 | MIC/Flood Control | West Sikkim | West Sikkim | 16 | R161400001 | Jhora Trg, Anti Erosion & Ext of MIC Channel at Rani Khola Omchung, Gyalshing | Irrigation & Flood Control | 188.39 | 2010-06-24 | 188.39
554 | MIC/Flood Control | West Sikkim | West Sikkim | 16 | R161400002 | Flood control & River Training Works along Ranikhola at Ban Jhakri Falls, Ranka | Irrigation & Flood Control | 250.03 | 2010-06-24 | 250.03
555 | MIC/Flood Control | West Sikkim | West Sikkim | 16 | R161400003 | Flood control & River Training Works along Ranikhola & Teesta khola below Singtam Bazaar | Irrigation & Flood Control | 449.48 | 2010-06-24 | 449.47
556 | Road | West Sikkim | West Sikkim | 16 | R161400004 | Roadfrom Rongdu School to Rangsang | Roads & Bridges Department | 182.41 | 2010-06-24 | 164.18
557 | Road | West Sikkim | West Sikkim | 16 | R161400005 | Road from Kaluk-Rinchen,pong Road | Roads & Bridges Department | 232.67 | 2010-06-24 | 197.77
558 | Road | West Sikkim | West Sikkim | 16 | R161400006 | New approach Road from Melli School | Roads & Bridges Department | 252.05 | 2010-06-24 | 226.84
559 | Road | West Sikkim | West Sikkim | 16 | R161400007 | Link road from Khanihserbong-Kamling | Roads & Bridges Department | 385.83 | 2010-06-24 | 247.25
560 | Road | West Sikkim | West Sikkim | 16 | R161400008 | Approach roads to Upper Sreebadam Gu | Roads & Bridges Department | 405.22 | 2010-06-24 | 325.12
561 | Road | South Sikkim | South Sikkim | 16 | R161400011 | Truckable Road from Kewzing to Dalep | Roads & Bridges Department | 290.57 | 2010-06-24 | 290.57
562 | Road | West Sikkim | West Sikkim | 16 | R161400013 | Approach Road from Tikjuk Mechanical | Roads & Bridges Department | 337.8 | 2010-06-24 | 297.27
563 | Road | West Sikkim | West Sikkim | 16 | R161400014 | Road from Sardung towards Lunjik Sch | Roads & Bridges Department | 184.36 | 2010-06-24 | 169.62
564 | Road | West Sikkim | West Sikkim | 16 | R161400015 | Road from Dathongto-Simboley School | Roads & Bridges Department | 142.67 | 2010-06-24 | 136.97
565 | Road | South Sikkim | South Sikkim | 16 | R161400016 | 4Km new Road from Passi School to Pa | Roads & Bridges Department | 129.21 | 2010-06-24 | 129.21
566 | Road | South Sikkim | South Sikkim | 16 | R161400017 | const / ext of Truckable Road from Bo | Roads & Bridges Department | 257.7 | 2010-06-24 | 257.7
567 | Road | South Sikkim | South Sikkim | 16 | R161400018 | 3Km Road from Kolthang Manay Dara to | Roads & Bridges Department | 106.04 | 2010-06-24 | 97.57
568 | Road | South Sikkim | South Sikkim | 16 | R161400020 | Link Road from Gagyong Maney Dara to | Roads & Bridges Department | 121.34 | 2010-06-24 | 121.34
569 | Road | South Sikkim | South Sikkim | 16 | R161400021 | Emergency Pre-mix carpeting along G | Roads & Bridges Department | 316.72 | 2010-06-24 | 316.72
570 | Road | South Sikkim | South Sikkim | 16 | R161400022 | Road from Tingmoo village to Sagbari | Roads & Bridges Department | 619.23 | 2010-06-24 | 588.27
571 | Road | South Sikkim | South Sikkim | 16 | R161400029 | Construction of Road from Cultural Park to Dhappar Dara, Yangyang | Roads & Bridges Department | 128.78 | 2010-06-24 | 128.78
572 | Road | East Sikkim | East Sikkim | 16 | R161400030 | Construction of road from Mechanical Workshop to Lumsey | Urban Development & Housing Dept. | 157.98 | 2010-06-24 | 151.19
573 | Market/Haat | West Sikkim | West Sikkim | 16 | R161400031 | Rural Haat at LEGSHIP Bazaar | Urban Development & Housing Dept. | 23.78 | 2010-06-24 | 22.54
574 | MIC | East Sikkim | East Sikkim | 16 | R161400032 | Infrastructure facilites at Pakyong Bazar | Urban Development & Housing Dept. | 79.82 | 2010-06-24 | 79.82
575 | MIC/Flood Control | East Sikkim | East Sikkim | 16 | R161400033 | Flood control & protective work at Rongli Bazar | Urban Development & Housing Dept. | 48.16 | 2010-06-24 | 48.16
576 | MIC/Flood Control | North Sikkim | North Sikkim | 16 | R161400034 | Flood control & protective work at Kama Jhora-Namchi Bazar | Urban Development & Housing Dept. | 51.4 | 2010-06-24 | 48.7
577 | Market Centers | East Sikkim | East Sikkim | 16 | R161400035 | Market AT RANGPO | Urban Development & Housing Dept. | 95.66 | 2010-08-30 | 95.66
578 | Road | East Sikkim | East Sikkim | 16 | R161400036 | Const of link road from Nazitam 20th km GRS (Gangtok, Rumtek, Sang) Road to Gangjithang | Rural Management Development Department | 152.83 | 2010-08-30 | 143.9
579 | MIC/Flood Control | East Sikkim | East Sikkim | 16 | R161400037 | AEW below Mintokgang at Tathangchen | Irrigation & Flood Control | 10.12 | 2010-11-08 | 10.12
580 | MIC/Flood Control | North Sikkim | North Sikkim | 16 | R161400038 | Providing Drainiange system and Ant | Irrigation & Flood Control | 15.12 | 2010-11-08 | 15.12
581 | MIC/Flood Control | South Sikkim | South Sikkim | 16 | R161400039 | AEW at Gurpisey Devithan Jhora | Irrigation & Flood Control | 11.78 | 2010-11-08 | 11.78
582 | MIC/Flood Control | South Sikkim | South Sikkim | 16 | R161400040 | AEW at Kewzing Gumpa | Irrigation & Flood Control | 11.4 | 2010-11-08 | 11.4
583 | MIC/Flood Control | South Sikkim | South Sikkim | 16 | R161400041 | AEW at Debrung Slide | Irrigation & Flood Control | 9.89 | 2010-11-08 | 9.89
584 | MIC/Flood Control | West Sikkim | West Sikkim | 16 | R161400042 | AEW/JTW along Pandey Jhora at Irrig | Irrigation & Flood Control | 11.78 | 2010-11-08 | 11.78
585 | MIC/Flood Control | West Sikkim | West Sikkim | 16 | R161400043 | AEW above the house of Tara Kumar Subba | Irrigation & Flood Control | 10.65 | 2010-11-08 | 10.65
586 | MIC/Flood Control | East Sikkim | East Sikkim | 16 | R161400044 | Construction of CWD at Samsing Gair | Irrigation & Flood Control | 10.4 | 2010-11-08 | 10.4
587 | MIC/Flood Control | North Sikkim | North Sikkim | 16 | R161400045 | CWD near Vetnary Complex Kopchey Ro | Irrigation & Flood Control | 24.6 | 2010-11-08 | 24.6
588 | MIC/Flood Control | West Sikkim | West Sikkim | 16 | R161400046 | CWD/JTW below Pelling Ground, West | Irrigation & Flood Control | 24.11 | 2010-11-08 | 24.09
589 | MIC/Flood Control | East Sikkim | East Sikkim | 16 | R161400047 | JTW at Chongey jhora in East Sikkim | Irrigation & Flood Control | 9.55 | 2010-11-08 | 9.55
590 | MIC/Flood Control | East Sikkim | East Sikkim | 16 | R161400048 | JTW at Thapa Golai at Middle Sichey | Irrigation & Flood Control | 11.68 | 2010-11-08 | 11.68
591 | MIC/Flood Control | East Sikkim | East Sikkim | 16 | R161400049 | JTW at School jhora at Upper Sichey | Irrigation & Flood Control | 10.54 | 2010-11-08 | 10.54
592 | MIC/Flood Control | East Sikkim | East Sikkim | 16 | R161400050 | JTW in the holding of Tshering Uden | Irrigation & Flood Control | 14.46 | 2010-11-08 | 14.46
593 | MIC/Flood Control | East Sikkim | East Sikkim | 16 | R161400051 | JTW at Bardang jhora in the holding of Ramesh Bishnu Maya Chettri W.Pendam | Irrigation & Flood Control | 4.14 | 2010-11-08 | 4.14
594 | MIC/Flood Control | East Sikkim | East Sikkim | 16 | R161400052 | JTW below Hotel Royal Plaza near th | Irrigation & Flood Control | 11.12 | 2010-11-08 | 11.12
595 | MIC/Flood Control | East Sikkim | East Sikkim | 16 | R161400053 | JTW at Thapa Golai at Middle Sichey below RCC bridge, Phase-II | Irrigation & Flood Control | 17.43 | 2010-11-08 | 17.41
596 | MIC/Flood Control | East Sikkim | East Sikkim | 16 | R161400054 | Construction of the JTW at Bardang | Irrigation & Flood Control | 9.66 | 2010-11-08 | 9.66
597 | MIC/Flood Control | East Sikkim | East Sikkim | 16 | R161400055 | JTW near the house of D.K.Nepal jho | Irrigation & Flood Control | 3.72 | 2010-11-08 | 3.72
598 | MIC/Flood Control | East Sikkim | East Sikkim | 16 | R161400056 | JTW at Rumtek School jhora | Irrigation & Flood Control | 11.01 | 2010-11-08 | 11.01
599 | MIC/Flood Control | East Sikkim | East Sikkim | 16 | R161400057 | Construction of JTW & CWD at Sajong | Irrigation & Flood Control | 10.86 | 2010-11-08 | 10.86
600 | MIC/Flood Control | East Sikkim | East Sikkim | 16 | R161400058 | JTW near Sarya Prasad Adhikari hous | Irrigation & Flood Control | 2.45 | 2010-11-08 | 2.45
601 | MIC/Flood Control | East Sikkim | East Sikkim | 16 | R161400059 | JTW along Zeeten Jhora at Chandmari | Irrigation & Flood Control | 9.92 | 2010-11-08 | 9.92
602 | MIC/Flood Control | East Sikkim | East Sikkim | 16 | R161400060 | Jhora Training Work, Protective Work and Cross Water Drain near Siddhi Vinayak Mandir at Rhenock | Irrigation & Flood Control | 12.09 | 2010-11-08 | 12.07
603 | MIC/Flood Control | East Sikkim | East Sikkim | 16 | R161400061 | JTW at Decheling GREF jhora | Irrigation & Flood Control | 9.55 | 2010-11-08 | 9.55
604 | MIC/Flood Control | East Sikkim | East Sikkim | 16 | R161400062 | JTW at Denzong Nursery | Irrigation & Flood Control | 11.82 | 2010-11-08 | 11.82
605 | MIC/Flood Control | East Sikkim | East Sikkim | 16 | R161400063 | Construction of JTW below State Jai | Irrigation & Flood Control | 14.32 | 2010-11-08 | 14.32
606 | MIC/Flood Control | East Sikkim | East Sikkim | 16 | R161400064 | Construction of JTW at Kazi jhora K | Irrigation & Flood Control | 11.16 | 2010-11-08 | 11.16
607 | MIC/Flood Control | East Sikkim | East Sikkim | 16 | R161400065 | Cosntruction of JTW/Protective Wall | Irrigation & Flood Control | 17.56 | 2010-11-08 | 17.54
608 | MIC/Flood Control | East Sikkim | East Sikkim | 16 | R161400066 | JTW & Restoration work on PNG Schoo | Irrigation & Flood Control | 6.15 | 2010-11-08 | 6.15
609 | MIC/Flood Control | East Sikkim | East Sikkim | 16 | R161400067 | JTW & AEW at Lumsey | Irrigation & Flood Control | 10.95 | 2010-11-08 | 10.95
610 | MIC/Flood Control | East Sikkim | East Sikkim | 16 | R161400068 | JTW below Hobby Centre, below NH-31 | Irrigation & Flood Control | 10.47 | 2010-11-08 | 10.47
611 | MIC/Flood Control | North Sikkim | North Sikkim | 16 | R161400069 | JTW at Lichu Khola Pakhilakha Shota | Irrigation & Flood Control | 10.43 | 2010-11-08 | 10.43
612 | MIC/Flood Control | South Sikkim | South Sikkim | 16 | R161400070 | JTW at Phong Khola Jhora Rateypani | Irrigation & Flood Control | 13.12 | 2010-11-08 | 13.12
613 | MIC/Flood Control | South Sikkim | South Sikkim | 16 | R161400071 | JTW at Chemkeng Kyong at Salalay un | Irrigation & Flood Control | 9.73 | 2010-11-08 | 9.73
614 | MIC/Flood Control | West Sikkim | West Sikkim | 16 | R161400072 | JTW along Samdong jhora at Budang P | Irrigation & Flood Control | 12.72 | 2010-11-08 | 12.72
615 | MIC/Flood Control | West Sikkim | West Sikkim | 16 | R161400073 | JTW along Chuchuey Dhunga, Sajbotey | Irrigation & Flood Control | 12.64 | 2010-11-08 | 12.64
616 | MIC/Flood Control | East Sikkim | East Sikkim | 16 | R161400074 | Construction of PW near the house of Sangchu jhora Tshlamthang | Irrigation & Flood Control | 9.61 | 2010-11-08 | 9.61
617 | MIC/Flood Control | East Sikkim | East Sikkim | 16 | R161400075 | Construction of Protection wall near the Sangboo's House along Sangboo jhora at Chalamthang Lossing Pacheykhani | Irrigation & Flood Control | 10.1 | 2010-11-08 | 10.1
618 | MIC/Flood Control | West Sikkim | West Sikkim | 16 | R161400076 | Providing Protective Work at Bhanapala | Irrigation & Flood Control | 9.96 | 2010-11-08 | 9.96
619 | MIC/Flood Control | East Sikkim | East Sikkim | 16 | R161400077 | Repair & Resto of Doksing khola at | Irrigation & Flood Control | 10.06 | 2010-11-08 | 10.06
620 | MIC/Flood Control | East Sikkim | East Sikkim | 16 | R161400078 | Construction of MIC at Andheri Chamkam Upper Martam | Irrigation & Flood Control | 9.82 | 2010-11-08 | 9.82
621 | MIC | North Sikkim | North Sikkim | 16 | R161400079 | Construction of MIC from Samar Khol | Irrigation & Flood Control | 11.12 | 2010-11-08 | 11.12
622 | MIC | South Sikkim | South Sikkim | 16 | R161400080 | Renovation of MIC from Dong Khola t | Irrigation & Flood Control | 16.36 | 2010-11-08 | 16.36
623 | RDWS | South Sikkim | South Sikkim | 20 | R201400014 | Providing Water Supply to Gumpa dara and Sorrounding areas at Ravangla | WS & Public Health & Engineering Department | 144.68 | 2015-02-20 | 144.68
624 | RDWS | West Sikkim | West Sikkim | 20 | R201400015 | Upgradation & Improvement of existing water supply at Kaluk- Richenpong | WS & Public Health & Engineering Department | 158.41 | 2015-03-13 | 158.41
625 | Road | East Sikkim | East Sikkim | 20 | R201400017 | Construction of Rural Road from Lingdok to Pega Busty via Nechu, East Sikkim | Rural Management Development Department | 218.45 | 2015-03-13 | 193.95
626 | Road | East Sikkim | East Sikkim | 20 | R201400018 | New Connectivity Road from L/Lingzey to U/Lingzey Subithang, East Sikkim | Rural Management Development Department | 411.66 | 2015-03-13 | 396.86
627 | Road | East Sikkim | East Sikkim | 20 | R201400019 | Stage II (Carpeting) of SPWD Road Ganesh mandir to Dangeythang | Rural Management Development Department | 261.12 | 2015-03-13 | 261.12
628 | Road | North Sikkim | North Sikkim | 20 | R201400001 | Construction of Link Road from Phidang to Singtok village at Lower Dzongu, North Sikkim, Km 1 to Km 3 Bazar to Upper Lingmoo | Roads & Bridges Department Department | 422.66 | 30/09/2014 | 422.66
629 | Road | South Sikkim | South Sikkim | 20 | R201400002 | Construction of Truckable Road from Lower Namdong to Mainabotey via Lower Tirikhola in South Sikkim Km 1st to Km 4th | Roads & Bridges Department Department | 403.35 | 30/09/2014 | 403.35
630 | Road | South Sikkim | South Sikkim | 20 | R201400003 | Construction of Link Road from Amlisay( Sumsi) to Sokpay ( Upper Maidang) in South Sikkim | Roads & Bridges Department Department | 407.89 | 30/09/2014 | 407.89
631 | Road | South Sikkim | South Sikkim | 20 | R201400004 | Construction of Road from LANCO road Samrdong to Burul km 1st to 4th in South Sikkim | Roads & Bridges Department Department | 328.42 | 30/09/2014 | 328.42
632 | Road | East Sikkim | East Sikkim | 20 | R201400005 | Construction of Link Road from Nandok School to Rizey Km 1st to 3rd in East Sikkim | Roads & Bridges Department Department | 239.04 | 30/09/2014 | 239.04
633 | Road | South Sikkim | South Sikkim | 20 | R201400006 | Construction of New Road from Debrong to Chamgaon Km 1st to Km 3rd in South Sikkim | Roads & Bridges Department Department | 315.68 | 30/09/2014 | 315.68
634 | Road | South Sikkim | South Sikkim | 20 | R201400007 | Construction of Truckable Road from phungdara( Namchi Phong road) to Upper Phalidara in South Sikkim Km 1st to 3rd | Roads & Bridges Department Department | 262.17 | 30/09/2014 | 262.17
635 | Road | South Sikkim | South Sikkim | 20 | R201400008 | Construction of Road from Lower Tingrithang School to Namchi work road km 1st to km 5th in South sikkim | Roads & Bridges Department Department | 484.58 | 30/09/2014 | 484.58
636 | Road | South Sikkim | South Sikkim | 20 | R201400009 | Construction of Link Road from Upper Pathing PMGSY Road to Paradling Spot via Gurung Gumpha under Yangyang Sub division,( Upper Yangyang to Gurung Gumpha) in South Sikkim | Roads & Bridges Department Department | 505.13 | 30/09/2014 | 505.13
637 | Road | South Sikkim | South Sikkim | 20 | R201400010 | Construction of Road from Namphok Sirsire Dara ( Kalung Dara to Niya via Lower Baram under Yangang Sub division in South Sikkim with 40m Span bridge | Roads & Bridges Department Department | 759.36 | 30/09/2014 | 759.36
638 | Road | East Sikkim | East Sikkim | 20 | R201400011 | Construction of Road from Bhusuk to Shotaklakha in East Sikkim | Roads & Bridges Department Department | 257.15 | 30/09/2014 | 132.1
639 | Road | South Sikkim | South Sikkim | 20 | R201400012 | Construction of 2.15 km Link Road from Yangang-Makha road to Yangang- Rangang under Yangang Sub-division in South Sikkim. | Roads & Bridges Department Department | 240.37 | 30/09/2014 | 240.37
640 | Road | South Sikkim | South Sikkim | 20 | R201400013 | Construction of Link Road from Satam to Gangla | Roads & Bridges Department Department | 404.26 | 30/09/2014 | 404.25
641 | Irrigation | West Sikkim | West Sikkim | 20 | R201400016 | Construction of Jhora Training Work& Catch Water drain below Mangalbaria Bazar under Richenpong Consituency | Irrigation & Flood Control | 110.27 | 13/03/2015 | 93.24
642 | Water Supply | South Sikkim | South Sikkim | 22 | P2017170000000000027 | Construction of Kitam Water Supply Scheme from manpur Khola in South Sikkim | WS & Public Health & Engineering Department | 824.81 | 2017-03-27 | 824.77
643 | Road | West Sikkim | West Sikkim | 22 | P2017170000000000019 | Construction of Road from Tessithang to Chowri including a 25 mtr steel bridge | Roads & Bridges Department Department | 450 | 2017-01-03 | 450
644 | Road | East Sikkim | East Sikkim | 22 | P2017170000000000032 | Construction of link road from forest colony to Bye Pass and upgradation & extension of Dhupidara road from TNHS School (Including steel bridge of 10 m and 25 m) | Urban Development & Housing Dept. | 1089.21 | 2017-03-30 | 1089.2
645 | Road | West Sikkim | West Sikkim | 23 | P2018170000000000065 | Construction of link road from Gumpa Dara via Leksey colony to Bega Bazaar | Urban Development & Housing Dept. | 258.71 | 2017-12-08 | 258.71
646 | Road | West Sikkim | West Sikkim | 23 | P2018170000000000052 | Construction of approach road from Hee Goan to Hee Bazaar | Urban Development & Housing Dept. | 401.01 | 2017-06-09 | 401.01
647 | Road | West Sikkim | West Sikkim | 23 | P2018170000000000051 | Geometric improvement of curves and riding quality of Chongrang to Labdang Road | Roads & Bridges Department Department | 2527.58 | 2018-02-09 | 2527.578
648 | Road | West Sikkim | West Sikkim | 23 | P2018170000000000066 | Ugradation / Carpeting of Rimbi to Kheceparli Road | Roads & Bridges Department Department | 1353.01 | 2018-03-05 | 1353.01
649 | Road | East Sikkim | East Sikkim | 23 | P2018170000000000102 | Upgradation / Carpeting along Rongli-Dalapchand-Aritar Road | Roads & Bridges Department Department | 861.87 | 2018-03-19 | 861.85
650 | Road | South Sikkim | South Sikkim | 23 | P2018170000000000103 | Construction of new road from Namchi to Lower Salleybong | Roads & Bridges Department Department | 254.84 | 2018-03-19 | 254.835
651 | Road | South Sikkim | South Sikkim | 24 | P2018170000000000161 | Resurfacing strengthening and improvement of riding quality along Namchi - Kopchey Road to Lower Boomtar via Singithang | Roads & Bridges Department Department | 145.78 | 04.12.2018 | 145.78
652 | Road | South Sikkim | South Sikkim | 24 | P2018170000000000162 | Resurfacing strengthening and improvement of riding quality along Upper Ghurpisey to Phalidara | Roads & Bridges Department Department | 78.45 | 04.12.2018 | 78.45
653 | Road | East Sikkim | East Sikkim | 24 | P2018170000000000163 | Strengthening carpeting and drainage work along Pakyong-Karthok-Rai Goan Road | Roads & Bridges Department Department | 801 | 04.12.2018 | 801
654 | Road | East Sikkim | East Sikkim | 24 | P2018170000000000164 | Strengthening carpeting and drainage work along Pakyong-Dikling Road | Roads & Bridges Department Department | 189 | 04.12.2018 | 188.99
655 | Road | East Sikkim | East Sikkim | 24 | P2018170000000000165 | Resurfacing Strengthening and recarpeting of Tintek-Dikchu Road 1st to 11.48 km | Roads & Bridges Department Department | 1109.06 | 04.12.2018 | 1109.06
656 | Road | East Sikkim | East Sikkim | 24 | P2019170000000000008 | Installation of W Type Crash Barriers (on 25 roads) | Roads & Bridges Department Department | 337.5 | 03.01.2019 | 337.5
657 | Road | West Sikkim | West Sikkim | 24 | P2019170000000000010 | Installation of W Type Crash Barriers (on 18 roads) | Roads & Bridges Department Department | 450 | 03.01.2019 | 450
658 | Road | North Sikkim | North Sikkim | 24 | P2019170000000000007 | Installation of W Type Crash Barriers (on 2 roads) | Roads & Bridges Department Department | 112.5 | 03.01.2019 | 112.5
659 | Road | South Sikkim | South Sikkim | 24 | P2019170000000000009 | Installation of W Type Crash Barriers (on 13 roads) | Roads & Bridges Department Department | 450 | 03.01.2019 | 450
660 | Road | East Sikkim | East Sikkim | 25 | P2020170000000000024 | Construction of Double Lane Highway from Adampool to Ranka Sichey Road | Roads & Bridges Department Department | 3461.4 | 30.03.2020 | 3461.4

## Tranche PCR Status (hidden)
PCR DATA-TRANCHE-WISE
[19 empty] | 0 | 0
#REF! | No. of Projects | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | No. of PCRs received | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Remarks |  | %
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!

## Dept-wise (hidden)
PCR DATA-DEPARTMENT-WISE
Sl. No. | Department | No. of Projects | No. of PCRs Received
1 | DHFW | #REF! | #REF!
2 | MARKFED | #REF! | #REF!
3 | MPJNM | #REF! | #REF!
4 | MPSEB | #REF! | #REF!
5 | MPWLC | #REF! | #REF!
6 | NVDA | #REF! | #REF!
7 | PWD-Bridge | #REF! | #REF!
8 | PWD-Road | #REF! | #REF!
9 | RSK | #REF! | #REF!
10 | TE&SD | #REF! | #REF!
11 | W&CD/ICDS | #REF! | #REF!
12 | WRD | #REF! | #REF!
| TOTAL | #REF! | #REF!

## Dept&Tranch-1 (hidden)
PCR DATA-DEPATMENT-WISE AND TRANCHE-WISE
Tranche | Department | No. of Projects | No. of PCRs received
1 | DHFW | #REF! | #REF!
| MARKFED | #REF! | #REF!
| MPJNM | #REF! | #REF!
| MPSEB | #REF! | #REF!
| MPWLC | #REF! | #REF!
| NVDA | #REF! | #REF!
| PWD-Bridge | #REF! | #REF!
| PWD-Road | #REF! | #REF!
| RSK | #REF! | #REF!
| TE&SD | #REF! | #REF!
| W&CD/ICDS | #REF! | #REF!
| WRD | #REF! | #REF!
Sub Total |  | #REF! | #REF!
2 | DHFW | #REF! | #REF!
| MARKFED | #REF! | #REF!
| MPJNM | #REF! | #REF!
| MPSEB | #REF! | #REF!
| MPWLC | #REF! | #REF!
| NVDA | #REF! | #REF!
| PWD-Bridge | #REF! | #REF!
| PWD-Road | #REF! | #REF!
| RSK | #REF! | #REF!
| TE&SD | #REF! | #REF!
| W&CD/ICDS | #REF! | #REF!
| WRD | #REF! | #REF!
Sub Total |  | #REF! | #REF!
3 | DHFW | #REF! | #REF!
| MARKFED | #REF! | #REF!
| MPJNM | #REF! | #REF!
| MPSEB | #REF! | #REF!
| MPWLC | #REF! | #REF!
| NVDA | #REF! | #REF!
| PWD-Bridge | #REF! | #REF!
| PWD-Road | #REF! | #REF!
| RSK | #REF! | #REF!
| TE&SD | #REF! | #REF!
| W&CD/ICDS | #REF! | #REF!
| WRD | #REF! | #REF!
Sub Total |  | #REF! | #REF!
4 | DHFW | #REF! | #REF!
| MARKFED | #REF! | #REF!
| MPJNM | #REF! | #REF!
| MPSEB | #REF! | #REF!
| MPWLC | #REF! | #REF!
| NVDA | #REF! | #REF!
| PWD-Bridge | #REF! | #REF!
| PWD-Road | #REF! | #REF!
| RSK | #REF! | #REF!
| TE&SD | #REF! | #REF!
| W&CD/ICDS | #REF! | #REF!
| WRD | #REF! | #REF!
Sub Total |  | #REF! | #REF!
5 | DHFW | #REF! | #REF!
| MARKFED | #REF! | #REF!
| MPJNM | #REF! | #REF!
| MPSEB | #REF! | #REF!
| MPWLC | #REF! | #REF!
| NVDA | #REF! | #REF!
| PWD-Bridge | #REF! | #REF!
| PWD-Road | #REF! | #REF!
| RSK | #REF! | #REF!
| TE&SD | #REF! | #REF!
| W&CD/ICDS | #REF! | #REF!
| WRD | #REF! | #REF!
Sub Total |  | #REF! | #REF!
6 | DHFW | #REF! | #REF!
| MARKFED | #REF! | #REF!
| MPJNM | #REF! | #REF!
| MPSEB | #REF! | #REF!
| MPWLC | #REF! | #REF!
| NVDA | #REF! | #REF!
| PWD-Bridge | #REF! | #REF!
| PWD-Road | #REF! | #REF!
| RSK | #REF! | #REF!
| TE&SD | #REF! | #REF!
| W&CD/ICDS | #REF! | #REF!
| WRD | #REF! | #REF!
Sub Total |  | #REF! | #REF!
7 | DHFW | #REF! | #REF!
| MARKFED | #REF! | #REF!
| MPJNM | #REF! | #REF!
| MPSEB | #REF! | #REF!
| MPWLC | #REF! | #REF!
| NVDA | #REF! | #REF!
| PWD-Bridge | #REF! | #REF!
| PWD-Road | #REF! | #REF!
| RSK | #REF! | #REF!
| TE&SD | #REF! | #REF!
| W&CD/ICDS | #REF! | #REF!
| WRD | #REF! | #REF!
Sub Total |  | #REF! | #REF!
8 | DHFW | #REF! | #REF!
| MARKFED | #REF! | #REF!
| MPJNM | #REF! | #REF!
| MPSEB | #REF! | #REF!
| MPWLC | #REF! | #REF!
| NVDA | #REF! | #REF!
| PWD-Bridge | #REF! | #REF!
| PWD-Road | #REF! | #REF!
| RSK | #REF! | #REF!
| TE&SD | #REF! | #REF!
| W&CD/ICDS | #REF! | #REF!
| WRD | #REF! | #REF!
Sub Total |  | #REF! | #REF!
9 | DHFW | #REF! | #REF!
| MARKFED | #REF! | #REF!
| MPJNM | #REF! | #REF!
| MPSEB | #REF! | #REF!
| MPWLC | #REF! | #REF!
| NVDA | #REF! | #REF!
| PWD-Bridge | #REF! | #REF!
| PWD-Road | #REF! | #REF!
| RSK | #REF! | #REF!
| TE&SD | #REF! | #REF!
| W&CD/ICDS | #REF! | #REF!
| WRD | #REF! | #REF!
Sub Total |  | #REF! | #REF!
10 | DHFW | #REF! | #REF!
| MARKFED | #REF! | #REF!
| MPJNM | #REF! | #REF!
| MPSEB | #REF! | #REF!
| MPWLC | #REF! | #REF!
| NVDA | #REF! | #REF!
| PWD-Bridge | #REF! | #REF!
| PWD-Road | #REF! | #REF!
| RSK | #REF! | #REF!
| TE&SD | #REF! | #REF!
| W&CD/ICDS | #REF! | #REF!
| WRD | #REF! | #REF!
Sub Total |  | #REF! | #REF!
11 | DHFW | #REF! | #REF!
| MARKFED | #REF! | #REF!
| MPJNM | #REF! | #REF!
| MPSEB | #REF! | #REF!
| MPWLC | #REF! | #REF!
| NVDA | #REF! | #REF!
| PWD-Bridge | #REF! | #REF!
| PWD-Road | #REF! | #REF!
| RSK | #REF! | #REF!
| TE&SD | #REF! | #REF!
| W&CD/ICDS | #REF! | #REF!
| WRD | #REF! | #REF!
Sub Total |  | #REF! | #REF!
12 | DHFW | #REF! | #REF!
| MARKFED | #REF! | #REF!
| MPJNM | #REF! | #REF!
| MPSEB | #REF! | #REF!
| MPWLC | #REF! | #REF!
| NVDA | #REF! | #REF!
| PWD-Bridge | #REF! | #REF!
| PWD-Road | #REF! | #REF!
| RSK | #REF! | #REF!
| TE&SD | #REF! | #REF!
| W&CD/ICDS | #REF! | #REF!
| WRD | #REF! | #REF!
Sub Total |  | #REF! | #REF!
13 | DHFW | #REF! | #REF!
| MARKFED | #REF! | #REF!
| MPJNM | #REF! | #REF!
| MPSEB | #REF! | #REF!
| MPWLC | #REF! | #REF!
| NVDA | #REF! | #REF!
| PWD-Bridge | #REF! | #REF!
| PWD-Road | #REF! | #REF!
| RSK | #REF! | #REF!
| TE&SD | #REF! | #REF!
| W&CD/ICDS | #REF! | #REF!
| WRD | #REF! | #REF!
Sub Total |  | #REF! | #REF!
14 | DHFW | #REF! | #REF!
| MARKFED | #REF! | #REF!
| MPJNM | #REF! | #REF!
| MPSEB | #REF! | #REF!
| MPWLC | #REF! | #REF!
| NVDA | #REF! | #REF!
| PWD-Bridge | #REF! | #REF!
| PWD-Road | #REF! | #REF!
| RSK | #REF! | #REF!
| TE&SD | #REF! | #REF!
| W&CD/ICDS | #REF! | #REF!
| WRD | #REF! | #REF!
Sub Total |  | #REF! | #REF!
15 | DHFW | #REF! | #REF!
| MARKFED | #REF! | #REF!
| MPJNM | #REF! | #REF!
| MPSEB | #REF! | #REF!
| MPWLC | #REF! | #REF!
| NVDA | #REF! | #REF!
| PWD-Bridge | #REF! | #REF!
| PWD-Road | #REF! | #REF!
| RSK | #REF! | #REF!
| TE&SD | #REF! | #REF!
| W&CD/ICDS | #REF! | #REF!
| WRD | #REF! | #REF!
Sub Total |  | #REF! | #REF!
16 | DHFW | #REF! | #REF!
| MARKFED | #REF! | #REF!
| MPJNM | #REF! | #REF!
| MPSEB | #REF! | #REF!
| MPWLC | #REF! | #REF!
| NVDA | #REF! | #REF!
| PWD-Bridge | #REF! | #REF!
| PWD-Road | #REF! | #REF!
| RSK | #REF! | #REF!
| TE&SD | #REF! | #REF!
| W&CD/ICDS | #REF! | #REF!
| WRD | #REF! | #REF!
Sub Total |  | #REF! | #REF!
17 | DHFW | #REF! | #REF!
| MARKFED | #REF! | #REF!
| MPJNM | #REF! | #REF!
| MPSEB | #REF! | #REF!
| MPWLC | #REF! | #REF!
| NVDA | #REF! | #REF!
| PWD-Bridge | #REF! | #REF!
| PWD-Road | #REF! | #REF!
| RSK | #REF! | #REF!
| TE&SD | #REF! | #REF!
| W&CD/ICDS | #REF! | #REF!
| WRD | #REF! | #REF!
Sub Total |  | #REF! | #REF!
18 | DHFW | #REF! | #REF!
| MARKFED | #REF! | #REF!
| MPJNM | #REF! | #REF!
| MPSEB | #REF! | #REF!
| MPWLC | #REF! | #REF!
| NVDA | #REF! | #REF!
| PWD-Bridge | #REF! | #REF!
| PWD-Road | #REF! | #REF!
| RSK | #REF! | #REF!
| TE&SD | #REF! | #REF!
| W&CD/ICDS | #REF! | #REF!
| WRD | #REF! | #REF!
Sub Total |  | #REF! | #REF!
19 | DHFW | #REF! | #REF!
| MARKFED | #REF! | #REF!
| MPJNM | #REF! | #REF!
| MPSEB | #REF! | #REF!
| MPWLC | #REF! | #REF!
| NVDA | #REF! | #REF!
| PWD-Bridge | #REF! | #REF!
| PWD-Road | #REF! | #REF!
| RSK | #REF! | #REF!
| TE&SD | #REF! | #REF!
| W&CD/ICDS | #REF! | #REF!
| WRD | #REF! | #REF!
Sub Total |  | #REF! | #REF!
20 | DHFW | #REF! | #REF!
| MARKFED | #REF! | #REF!
| MPJNM | #REF! | #REF!
| MPSEB | #REF! | #REF!
| MPWLC | #REF! | #REF!
| NVDA | #REF! | #REF!
| PWD-Bridge | #REF! | #REF!
| PWD-Road | #REF! | #REF!
| RSK | #REF! | #REF!
| TE&SD | #REF! | #REF!
| W&CD/ICDS | #REF! | #REF!
| WRD | #REF! | #REF!
Sub Total |  | #REF! | #REF!
21 | DHFW | #REF! | #REF!
| MARKFED | #REF! | #REF!
| MPJNM | #REF! | #REF!
| MPSEB | #REF! | #REF!
| MPWLC | #REF! | #REF!
| NVDA | #REF! | #REF!
| PWD-Bridge | #REF! | #REF!
| PWD-Road | #REF! | #REF!
| RSK | #REF! | #REF!
| TE&SD | #REF! | #REF!
| W&CD/ICDS | #REF! | #REF!
| WRD | #REF! | #REF!
Sub Total |  | #REF! | #REF!
22 | DHFW | #REF! | #REF!
| MARKFED | #REF! | #REF!
| MPJNM | #REF! | #REF!
| MPSEB | #REF! | #REF!
| MPWLC | #REF! | #REF!
| NVDA | #REF! | #REF!
| PWD-Bridge | #REF! | #REF!
| PWD-Road | #REF! | #REF!
| RSK | #REF! | #REF!
| TE&SD | #REF! | #REF!
| W&CD/ICDS | #REF! | #REF!
| WRD | #REF! | #REF!
Sub Total |  | #REF! | #REF!
TOTAL |  | #REF! | #REF!

## Dept&Tranch-3 (hidden)
PCR DATA-DEPATMENT-WISE AND TRANCHE-WISE
Agency | Tranche | No. of Projects | PCRs Received | PCRs NOT Received
DHFW | #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
MARKFED | 18 | #REF! | #REF! | #REF!
MPJNM | 19 | #REF! | #REF! | #REF!
| 20 | #REF! | #REF! | #REF!
| 22 | #REF! | #REF! | #REF!
MPWLC | 17 | #REF! | #REF! | #REF!
| 18 | #REF! | #REF! | #REF!
NVDA | 15 | #REF! | #REF! | #REF!
| 16 | #REF! | #REF! | #REF!
| 17 | #REF! | #REF! | #REF!
| 18 | #REF! | #REF! | #REF!
| 20 | #REF! | #REF! | #REF!
| 21 | #REF! | #REF! | #REF!
| 22 | #REF! | #REF! | #REF!
PWD-Bridge | 15 | #REF! | #REF! | #REF!
| 16 | #REF! | #REF! | #REF!
| 17 | #REF! | #REF! | #REF!
| 19 | #REF! | #REF! | #REF!
| 20 | #REF! | #REF! | #REF!
| 21 | #REF! | #REF! | #REF!
| 22 | #REF! | #REF! | #REF!
PWD-Road | 15 | #REF! | #REF! | #REF!
| 16 | #REF! | #REF! | #REF!
| 17 | #REF! | #REF! | #REF!
| 18 | #REF! | #REF! | #REF!
| 19 | #REF! | #REF! | #REF!
| 20 | #REF! | #REF! | #REF!
| 21 | #REF! | #REF! | #REF!
| 22 | #REF! | #REF! | #REF!
TE&SD | 18 | #REF! | #REF! | #REF!
| 21 | #REF! | #REF! | #REF!
| 22 | #REF! | #REF! | #REF!
W&CD/ICDS | 18 | #REF! | #REF! | #REF!
WRD | 16 | #REF! | #REF! | #REF!
| 17 | #REF! | #REF! | #REF!
| 18 | #REF! | #REF! | #REF!
| 19 | #REF! | #REF! | #REF!
| 21 | #REF! | #REF! | #REF!
| 22 | #REF! | #REF! | #REF!
TOTAL |  | #REF! | #REF! | #REF!

## 13 (hidden)
Tranche | PIC | Project | District | Activity | Agency | Rv_Balance_Cost | NB sanction | Disbursement | Actual compl_dt | PCR recd date | Date of Field Visit | Status | Monitored by | Potential Envisaged | Potential created | Villages | Marketing centres | Remarks | DDM
13 | R132000002 | Bohna Nalla Tank Project | Chhindwara | MIS | WRD | 1418.26 | 1347.35 | 542.3 |  |  |  | Ongoing |  | 1995
13 | R132000003 | Likhari Tank Project | Chhindwara | MIS | WRD | 163.47 | 155.3 | 155.3 |  |  |  | Ongoing |  | 182
13 | R132000004 | Asrakund Tank Project | Dhar | MIS | WRD | 335.57 | 318.79 | 318.79 | 2010-06-10 | 2011-08-11 |  | Completed | DDM | 390 | 375 |  |  | 375 Ha potential created. WUA is yet to be formed. | DDM
13 | R132000006 | Dongargaon Tank Project | Indore | MIS | WRD | 179.14 | 171.29 | 171.29 | 2009-03-31 | 2010-11-01 |  | Completed | DDM | 210 | 190 |  |  | The project created irrigation potential 190 Ha. WUA is tet to be formed | DDM
13 | R132000007 | Khadi Tank Project | Indore | MIS | WRD | 296.66 | 283.3 | 283.3 | 2011-03-31 | 2011-09-16 |  | Completed | DDM | 330 | 308 |  |  | 308 Ha potential created. WUA is yet to be formed. | DDM
13 | R132000008 | Bhokriya Tank Project | Khandwa | MIS | WRD | 144.86 | 144.86 | 144.86 | 2009-03-31 | 2010-09-28 |  | Completed |  | 198 | 198.2 |  |  | Irrigation Potential of 198.20 Ha is created.WUA is not yet formed.
13 | R132000009 | Shrinagar Tank Project | Mandsaur | MIS | WRD | 163.8 | 158.93 | 139.12 | 2012-05-31 | 2013-02-07 |  | Completed |  | 200 | 186.16 |  |  | WUA not formed, Potential created-186.16 Ha
13 | R132000010 | Hadkho Tank Project | Mandsaur | MIS | WRD | 207.45 | 201.03 | 200.98 | 2012-12-31 | 2013-05-15 |  | Completed |  | 241 | 268 |  |  | Due to higher tender rates and charge of dam alignment actual exps increased .Potential created-268 Ha. WUA not formed
13 | R132000012 | Shahbad Tilendi Tank | Raisen | MIS | WRD | 455.31 | 432.54 | 432.54 |  |  |  | Ongoing | RO Officer | 496 |  |  |  |  | RO Officer
13 | R132000013 | Kalajhora Tank Project | Raisen | MIS | WRD | 270.57 | 270.57 | 270.57 | 2011-03-31 | 2012-11-07 |  | Completed |  | 405 | 405 |  |  | Formation of WUA in progress
13 | R132000014 | Hanoti Tank | Shajapur | MIS | WRD | 243.84 | 234.41 | 234.41 |  |  |  | Ongoing |  | 268
13 | R132000015 | Jamuniya Tank | Chhindwara | MIS | WRD | 160.91 | 152.86 | 126.59 | 2011-07-31 | 2012-03-18 |  | Completed |  | 270 | 97 |  |  | WUA to be formed, Potential created- Kharif 81 Ha & Rabi- 97 Ha
13 | R132000016 | Panwadi Tank Project | Mandsaur | MIS | WRD | 161.02 | 155.34 | 155.34 | 2011-06-30 | 2012-01-18 |  | Completed |  | 180 | 180 |  |  | WUA not formed. potential created 180 Ha
13 | R132000017 | Kharela Tank | Ujjain | MIS | WRD | 160.56 | 154.38 | 154.38 | 2012-03-31 | 2012-08-03 |  | Completed |  | 234 | 170 |  |  | WUA - NA. potential created 170 Ha
13 | R132000018 | Gureha Pipra Tank | Katni | MIS | WRD | 142.71 | 135.57 | 135.57 |  |  |  | Ongoing |  | 180
13 | R132000019 | Beejanagaree | Shajapur | MIS | WRD | 140.16 | 133.15 | 133.15 | 2010-07-31 | 2011-09-16 |  | Completed |  | 200 | 200 |  |  | 200 Ha potential created. WUA is yet to be formed.
13 | R132000020 | Kunwarpura Tank | Mandsaur | MIS | WRD | 124.89 | 120.09 | 120.09 | 2012-12-31 | 2013-02-07 |  | Completed |  | 160 | 143 |  |  | WUA not formed, Potential created - 143 Ha
13 | R132000021 | Imlia Nala Closure Scheme | Sagar | MIS | WRD | 121.81 | 116.93 | 85.75 |  |  |  | Completed |  | 242
13 | R132000022 | Jaalkhedi Tank | Mandsaur | MIS | WRD | 127.28 | 122.3 | 122.3 | 2011-06-30 | 2012-01-18 |  | Completed |  | 150 | 134.4 |  |  | WUA not formed. potential created 134.40
13 | R132000023 | Nayapura Tank | Raisen | MIS | WRD | 106.09 | 103.05 | 103.05 |  |  |  | Completed | DDM | 121 |  |  |  |  | DDM
13 | R132000024 | Bichhiya Weir | Sagar | MIS | WRD | 85.71 | 85.71 | 79.07 |  |  |  | Completed |  | 248
13 | R132000025 | Vijaypur Weir | Sagar | MIS | WRD | 83.24 | 83.24 | 83.24 |  |  |  | Ongoing | DDM | 212 |  |  |  |  | DDM
13 | R132000026 | Duttapura Nalla Closure Scheme | Sagar | MIS | WRD | 78.76 | 78.76 | 78.76 |  |  |  | Ongoing |  | 248
13 | R132000027 | Karonda Tank | Katni | MIS | WRD | 93.08 | 92.4 | 92.4 | 2010-06-30 | 2012-11-07 |  | Completed |  | 200 | 125 |  |  | WUA not formed, Potential created-Rabi 25 Ha & Kharif 100 Ha
13 | R132000028 | Simraha Tank | Katni | MIS | WRD | 88.09 | 88.09 | 88.09 | 2010-06-30 | 2012-11-07 |  | Completed |  | 121 | 133 |  |  | WUA to be formed, Potential created-Rabi 40 Ha & Kharif 93 Ha
13 | R132000029 | Lahori Tank | Shajapur | MIS | WRD | 91.51 | 86.93 | 86.93 | 2010-03-31 | 2011-09-16 |  | Completed | DDM | 90 | 88.46 |  |  | 88.46 Ha potential created. WUA is yet to be formed. | DDM
13 | R132000030 | Palsoda Solid Weir | Neemuch | MIS | WRD | 47.49 | 45.12 | 45.12 | 2008-05-28 | 2009-06-18 | 2010-02-25 | Completed | DDM | 61 | 61 |  |  | Potential created 61 Ha.WUA not formed. Completed on time COR due to high tender | DDM
13 | R132000031 | Tulsapura Tank | Ujjain | MIS | WRD | 65.85 | 65.85 | 65.85 | 2012-06-30 | 2009-09-06 |  | Completed |  | 115 | 115 |  |  | WUA to be formed, Potential created - 115 Ha
13 | R132000032 | Salakhedi Barrage | Ujjain | MIS | WRD | 57.31 | 54.73 | 54.73 | 2008-12-31 | 2010-10-19 |  | Completed |  | 75 | 70 |  |  | Irrigation potential of 70 Ha is created.WUA is yet to be formed.
13 | R132000033 | Dongargaon Pickup Weir | Shajapur | MIS | WRD | 70.68 | 67.15 | 67.15 | 2010-07-31 | 2011-09-16 |  | Completed |  | 80 | 90 |  |  | 90 Ha potential created. WUA is yet to be formed.
13 | R132000034 | Bijaura Tank | Katni | MIS | WRD | 60.96 | 61.91 | 61.91 | 2008-06-30 | 2012-11-07 |  | Completed |  | 67 | 67 |  |  | WUA to be formed, Potential created-Rabi 10 Ha & Kharif 57 Ha
13 | R132000035 | Kalukheda Koyalaghat Barragecumcaus | Ujjain | MIS | WRD | 49.98 | 47.77 | 47.77 | 2008-12-31 | 2010-10-19 |  | Completed |  | 65 | 65 |  |  | Irrigation Potential of 65 Ha is created.WUA is yet to be formed.
13 | R132000036 | Manasa Pickup Weir | Shajapur | MIS | WRD | 58.8 | 55.86 | 55.86 | 2010-06-30 | 2012-01-18 |  | Completed | DDM | 80 | 88 |  |  | WUA not formed. potential created 88 ha | DDM
13 | R132000037 | Bagula Mukhi Pickup Weir | Shajapur | MIS | WRD | 58.45 | 55.53 | 55.53 | 2009-03-31 | 2011-09-16 |  | Completed |  | 70 | 70 |  |  | 70 Ha potential created. WUA is yet to be formed.
13 | R132000038 | Arjun Baroda Tank | Indore | MIS | WRD | 41.69 | 41.69 | 34.21 | 2008-04-12 | 2010-09-03 |  | Completed |  | 100 | 90 |  |  | 90 Ha irrigation potential is created.
13 | R132000039 | Dehri Gurjar Pickup Weir | Shajapur | MIS | WRD | 53.81 | 51.12 | 51.12 | 2009-03-31 | 2011-09-16 |  | Completed |  | 75 | 75 |  |  | 75 Ha potential created. WUA is yet to be formed.
13 | R132000041 | Shivghat Barrage | Ujjain | MIS | WRD | 44.06 | 41.97 | 41.97 | 2009-03-31 | 2010-10-19 |  | Completed |  | 82 | 82 |  |  | 82 Ha irrigation Potential is created.WUA is yet to be formed.
13 | R132000042 | Mahurikhema Barrage | Ujjain | MIS | WRD | 18.09 | 17.29 | 17.29 | 2008-12-31 | 2010-10-19 |  | Completed | DDM | 43 | 43 |  |  | Irrigation potential of 43 Ha is created.WUA is yet to be formed. | DDM
13 | R132000043 | Dharola Pick-up Weir | Shajapur | MIS | WRD | 49.13 | 46.67 | 46.67 | 2010-03-31 | 2011-09-16 |  | Completed |  | 85 | 85 |  |  | 85 Ha potential created. WUA is yet to be formed.
13 | R132000044 | Arrolia Dewra Barrage | Ujjain | MIS | WRD | 27.98 | 26.85 | 26.85 | 2008-12-31 | 2010-10-19 |  | Completed | DDM | 42 | 42 |  |  | Irrigation potential of 42 Ha is created.WUA is yet to be formed. | DDM
13 | R132000045 | Malhargarh Barrage | Ujjain | MIS | WRD | 26.77 | 25.54 | 25.54 | 2012-03-31 | 2012-08-03 |  | Completed | DDM | 45 | 45 |  |  | WUA -not formed. potential created 45 Ha | DDM
13 | R132000046 | Bhilkhedi Weir | Shajapur | MIS | WRD | 46.94 | 44.59 | 44.59 | 2009-03-31 | 2011-09-16 |  | Completed | DDM | 80 | 80 |  |  | 80 Ha potential created. WUA is yet to be formed. | DDM
13 | R132000047 | Gundarlia Barrage | Ujjain | MIS | WRD | 40.11 | 38.31 | 38.31 | 2009-03-31 | 2010-10-19 |  | Completed |  | 53 | 53 |  |  | Irrigation Potential of 53 Ha is created. WUA is yet to be formed.
13 | R132000048 | Bilkeshwar (Dhaturia) Barrage | Ujjain | MIS | WRD | 34.49 | 32.99 | 32.99 | 2008-12-31 | 2010-10-19 |  | Completed |  | 57 | 45 |  |  | Irrigation Potential of 45 Ha is created. WUA is yet to be formed.
13 | R132000049 | Saloda Solid Weir | Neemuch | MIS | WRD | 18.08 | 18.08 | 17.39 | 2008-03-30 | 2008-11-06 |  | Completed |  | 71 | 71 |  |  | 1 Ha irrigation potential created . WUA is under process
13 | R132000050 | Burhi Barlai Tank | Indore | MIS | WRD | 25.51 | 25.51 | 6.72 | 2008-03-31 | 2010-09-03 |  | Completed | DDM | 70 | 70 |  |  | 70 Ha Irrigation potential is created. WUA formation is under progress. | DDM
13 | R132000051 | Shekhpur Barrage | Ujjain | MIS | WRD | 33.47 | 32.01 | 32.01 | 2009-03-31 | 2010-10-19 |  | Completed |  | 50 | 50 |  |  | Irrigation Potential of 50 Ha uis created. WUA is yet to be formegd.
13 | R132000052 | Kachhala Solid Weir | Neemuch | MIS | WRD | 1.86 | 1.86 | 0.43 | 2008-04-30 | 2009-01-07 |  | Completed | DDM | 75 | 75 |  |  | created 75 Ha potential. WUA not formed | DDM
13 | R132000053 | Indira Sagar Proj PhI &II | Khandwa | MJP | NVDA | 47163 | 4480.48 | 4480.48 |  |  |  | Ongoing |  | 62220
13 | R132000054 | Luharra-Kandipur-Chainpura-Hindoriy | Damoh | Road | PWD | 83.47 | 83.47 | 83.47 | 2008-04-30 | 2010-06-02 |  | Completed |  | 9.6 | 9.6 | 7 |  | road project of 9.6 km is executed. 7 villages are connected
13 | R132000055 | Hindoriya- Pipariya-Ronda Road | Damoh | Road | PWD | 67.39 | 67.39 | 67.39 | 2009-06-30 | 2010-06-02 |  | Completed | DDM | 10 | 10 | 8 |  | road project of 10 km is executed. 8 villages are connected | DDM
13 | R132000056 | Anoo- Bandakpur road | Damoh | Road | PWD | 91.83 | 91.83 | 65.76 | 2010-06-15 | 2010-11-29 |  | Completed |  | 5.5 | 5.5 | 9 |  | 5.50 km road contructed. 9 villages are connected
13 | R132000057 | Sanai Talwada Siganpur Road | Guna | Road | PWD | 122.4 | 122.4 | 122.4 | 2010-03-15 | 2010-08-18 |  | Completed | DDM | 7 | 7 |  |  | 7 km road is constructed. | DDM
13 | R132000058 | Ratatalai - Mangrul road | Harda | Road | PWD | 104.38 | 101.18 | 101.18 | 2009-03-31 | 2011-08-05 |  | Completed |  | 5 | 5 | 2 | 2 | 5.0 km length road is constructed. 2 villages & 2 Marketing centres connected.
13 | R132000059 | Kamadpur- Chainpura- Khedi- Sihod r | Indore | Road | PWD | 63.94 | 63.94 | 63.94 |  |  |  | Completed |  | 8
13 | R132000060 | Kanjarda - Diken road | Neemuch | Road | PWD | 308.53 | 291.98 | 291.98 |  |  |  | Ongoing |  | 15
13 | R132000061 | Seamou-Pipaliya-Tada Road | Raisen | Road | PWD | 159.82 | 151.68 | 151.68 | 2010-05-30 | 2011-08-05 |  | Completed |  | 8 | 8 | 18 | 3 | 8.0 km length road is constructed. 18 villages & 3 Marketing centres connected.
13 | R132000062 | Chandan Pipaliya Pratapgarh Road | Raisen | Road | PWD | 260.32 | 260.32 | 260.32 | 2009-06-30 | 2011-08-05 |  | Completed | DDM | 13.8 | 13.8 | 11 | 2 | 13.8 km length road is constructed. 18 villages & 3 Marketing centres connected. | DDM
13 | R132000063 | Bhyana Karlawad Road | Rajgarh | Road | PWD | 410.52 | 342.08 | 342.08 | 2007-06-18 | 2010-06-02 |  | Completed |  | 13.4 | 13.4 | 5 |  | road project of 13.4 km is executed. 5 villages are connected
13 | R132000064 | Semali Ramgarh Road | Rajgarh | Road | PWD | 264.6 | 254.43 | 254.43 | 2008-03-31 | 2010-11-29 |  | Completed |  | 12.8 | 12.8 | 7 | 2 | 12.80 km road constructed.7 villages 2 marketing centres connected
13 | R132000065 | Bonda Sendri Umari Kandara Kotari R | Rajgarh | Road | PWD | 328.86 | 312.69 | 312.69 | 2009-11-30 | 2010-06-02 |  | Completed |  | 11.6 | 11.6 | 10 |  | road project of 11.6 km is executed. 10 villages are connected
13 | R132000066 | Pidarua to Sagar Malthone Approach | Sagar | Road | PWD | 125.07 | 123.1 | 106.26 | 2008-12-17 | 2011-08-05 |  | Completed |  | 4.5 | 4.27 | 7 | 2 | 4.27 km length road is constructed. 7 villages & 2 Marketing centres connected.
13 | R132000067 | Longar-Semra-Lodhi-Parson-Madiya-Ro | Sagar | Road | PWD | 198.75 | 198.75 | 198.75 |  |  |  | Ongoing | RO Official | 16 |  |  |  |  | RO Official
13 | R132000068 | Bilkishganj to Neebukheda Road | Sehore | Road | PWD | 215.69 | 184.06 | 184.06 |  | 2011-08-05 |  | Completed | RO Official | 10 | 11.2 | 4 | 1 | 11.2 km length road is constructed. 4 villages & 1 Marketing centre connected. | RO Official
13 | R132000069 | Charnal-Chadwad- Gawa-Parasone road | Sehore | Road | PWD | 498.36 | 398.69 | 398.69 |  |  |  | Ongoing |  | 20
13 | R132000070 | Nandi - Shaila - Umarwada road | Seoni | Road | PWD | 231.66 | 185.33 | 185.33 |  |  |  | Ongoing |  | 8.5
13 | R132000071 | Maili - Tikari - Partapur road | Seoni | Road | PWD | 121.59 | 121.59 | 121.59 | 2009-07-07 | 2010-06-02 |  | Completed |  | 6.7 | 6.7 | 12 |  | road project of 6.7 km is executed. 12 villages are connected
13 | R132000072 | Gulana -Sakatkhedi-Nichma-Bumtalai | Shajapur | Road | PWD | 124.22 | 116.28 | 116.28 |  |  |  | Completed |  | 6.9
13 | R132000073 | Bachchukheda Runaheda Road | Ujjain | Road | PWD | 289.9 | 231.92 | 231.92 |  |  |  | Ongoing | DDM | 10 |  |  |  |  | DDM
13 | R132000074 | Chheerkheda to Nimkheda Road | Vidisha | Road | PWD | 39.74 | 39.74 | 39.74 |  |  |  | Completed |  | 4
13 | R132000075 | Kodi Mehgaon Sothiya Vidisha Road | Vidisha | Road | PWD | 90.36 | 90.36 | 90.36 | 2008-06-30 | 2011-08-05 |  | Completed | DDM | 14.8 | 14.8 | 5 | 4 | The project resulted in creation of 14.80 Km of road and connected 5 villages to 4 marketing centres. | DDM
13 | R132000076 | Mudra-Murraiya to Barkheda Jagir ro | Vidisha | Road | PWD | 365.49 | 365.49 | 365.49 | 2009-02-05 | 2011-11-09 |  | Completed | DDM | 25.6 | 25.6 | 9 | 2 | The project resulted in creation of 25.60 Km of road and connected 9 villages to 2 marketing centres. | DDM
13 | R132000077 | Madhura Bagal Harukhedi to Basoda S | Vidisha | Road | PWD | 91.19 | 91.19 | 91.19 | 2008-05-20 | 2011-11-09 |  | Completed |  | 6.5 | 6.5 | 6 | 1 | The project resulted in creation of 6.50 Km of road and connected 6 villages to 1 marketing centre.
13 | R132000078 | Ashoknagar Thubon Piplod Road | Ashoknagar | Road | PWD | 256.28 | 246.35 | 246.35 | 2007-11-19 | 2011-08-05 |  | Completed |  | 17.6 | 17.6 | 11 | 2 | 17.6 km length road is constructed. 11 villages & 2 Marketing centres connected. 12 km of distance has been reduced.
13 | R132000079 | Sehrai Achalgarh Piprai Road | Ashoknagar | Road | PWD | 180.26 | 180.26 | 180.26 | 2009-03-02 | 2011-08-05 |  | Completed |  | 15.3 | 15.3 | 17 | 3 | 15.3 km length road is constructed. 17 villages & 3 Marketing centres connected. 3 km of distance has been reduced.
13 | R132000080 | Balai Karaila Mata Mandir Road | Ashoknagar | Road | PWD | 172.39 | 172.39 | 172.39 | 2009-03-31 | 2010-05-04 |  | Completed |  | 18.4 | 18.4 | 10 | 2 | The project had cretaed 18 40 Km Road. It comnected 10 villages to 2 marketing centres
13 | R132000081 | Katedara - Tirodi -Khawasa Road | Balaghat | Road | PWD | 246.49 | 197.19 | 197.19 |  |  |  | Ongoing |  | 13
13 | R132000082 | Halditola -Badgaon -Dahedi- Mate - | Balaghat | Road | PWD | 273.56 | 218.85 | 218.85 |  |  |  | Ongoing | DDM | 14.8 |  |  |  |  | DDM
13 | R132000083 | Gohad- Dhamasha-Dhanulli road | Bhind | Road | PWD | 334.02 | 267.22 | 267.22 |  |  |  | Ongoing |  | 20
13 | R132000084 | Newton Mayavadi Road | Chhindwara | Road | PWD | 26.26 | 26.26 | 18.45 |  |  |  | Completed |  | 2.3
13 | R132000085 | Bansa - Deoran- Bhouransa Road | Damoh | Road | PWD | 85.97 | 85.97 | 85.97 |  |  |  | Completed |  | 6.5
13 | R132000086 | Bandakpur Hindoriya Road | Damoh | Road | PWD | 80.15 | 80.15 | 80.15 | 2008-03-31 | 2009-06-11 |  | Completed | DDM | 8.4 | 8.4 | 4 | 2 | The project resulted in a 8.4 Km road to connect 4 villages to 2 marketing centres | DDM
13 | R132000087 | Bhander - Sarsai - Dhamna Road | Datia | Road | PWD | 422.17 | 337.74 | 175.78 |  |  |  | Ongoing | DDM | 21.1 |  |  |  |  | DDM
13 | R132000088 | Kuda-Chandrani road | Dindori | Road | PWD | 221.34 | 201.07 | 201.07 |  |  |  | Completed |  | 9.6
13 | R132000089 | Ralamandal Tillorekhurd Tillorebuzu | Indore | Road | PWD | 176.21 | 176.21 | 176.21 | 2008-01-31 | 2010-08-18 |  | Completed |  | 15.6 | 15.35 | 6 | 4 | 15.35 km road was constructed. 6 villages and 4 marketing centres connected.
13 | R132000090 | Pondi - Bhita - Kainthra - Khatolid | Jabalpur | Road | PWD | 126 | 100.8 | 100.8 | 2008-10-30 | 2010-06-02 |  | Completed | DDM | 5.4 | 5.4 | 9 |  | road project of 5.4 km is executed. 9 villages are connected | DDM
13 | R132000091 | Tilsani- Baghraji Road | Jabalpur | Road | PWD | 425 | 340 | 340 |  | 2011-08-05 |  | Completed | DDM | 16.4 | 16.4 | 26 | 2 | 16.4 km length road is constructed. 26 villages & 2 Marketing centres connected. | DDM
13 | R132000092 | Sihora - Gourkha - Nandghat Road | Jabalpur | Road | PWD | 329.31 | 329.31 | 329.31 | 2010-11-30 | 2011-11-09 |  | Completed | DDM | 15.6 | 15.6 | 12 | 3 | The project resulted in creation of 15.60 Km of road and connected 12 villages to 3 marketing centres. | DDM
13 | R132000093 | Kudam - Chiraipani road | Jabalpur | Road | PWD | 275 | 220 | 220 | 2008-06-24 | 2009-06-11 |  | Completed |  | 11.35 | 11.36 | 8 | 2 | The project resulted in creation of 11.36 Km of road and connected 8 villages to 2 marketing centres.
13 | R132000094 | Kanjai - Sakri - Andua - Singaldip | Jabalpur | Road | PWD | 95.18 | 86.96 | 86.96 | 2008-03-19 | 2008-08-18 |  | Completed |  | 4.56 | 4.56 | 4 | 2 | Cost escalation due to tender percentages and difference of cost of material. 4.56 Km Road was constructed. The said infrastructure connectesd 4 villages with market yards at Budhagar and Indrana
13 | R132000095 | Ponda - Bachaiya Road | Katni | Road | PWD | 255 | 255 | 255 | 2008-11-24 | 2010-06-02 |  | Completed | DDM | 14.7 | 14.7 | 18 |  | road project of 14.7 km is executed. 18 villages are connected | DDM
13 | R132000096 | Vijayraghavgarh- Kharkhri-Padkhuri | Katni | Road | PWD | 393.37 | 314.7 | 314.7 | 2009-06-25 | 2010-06-02 |  | Completed |  | 14.85 | 14.85 |  |  | road project of 14.85 km is executed.
13 | R132000097 | Sleemnabad Bahoriband Road | Katni | Road | PWD | 204.66 | 182.2 | 182.2 | 2008-08-27 | 2010-06-02 |  | Completed | DDM | 9.33 | 9.33 |  |  | road project of 9.33 km is executed. | DDM
13 | R132000098 | Katni-Kailwara- Kharkhari -Hathkuri | Katni | Road | PWD | 249.08 | 249.08 | 249.08 | 2008-01-26 | 2010-06-02 |  | Completed | DDM | 22.2 | 22.2 |  |  | road project of 22.2 km is executed. | DDM
13 | R132000099 | Vilayatkalan Ganeshpur Salhna Road | Katni | Road | PWD | 526.93 | 421.54 | 421.54 |  |  |  | Ongoing |  | 21.43
13 | R132000100 | Bartari- Pakar - Masandha -Bakal ro | Katni | Road | PWD | 211.11 | 211.11 | 211.11 | 2008-04-02 | 2010-06-02 |  | Completed | DDM | 20.4 | 20.4 |  |  | road project of 20.4 km is executed. | DDM
13 | R132000101 | Dharampuri-Garangaon-Bhagwanpur roa | Khandwa | Road | PWD | 208.27 | 208.27 | 208.27 | 2009-06-29 | 2013-12-09 |  | Completed |  | 14.5 | 14.5
13 | R132000102 | Mandla Pindrai Nainpur Road | Mandla | Road | PWD | 213.63 | 213.63 | 213.63 | 2008-05-10 | 2010-11-29 |  | Completed |  | 24.4 | 24.4 | 20 | 3 | 24.4 km road constructed.20 villages & 3 mktg. centres constructed.
13 | R132000103 | Bichhiya Danitola Ghughri Road | Mandla | Road | PWD | 156.36 | 156.36 | 156.36 |  |  |  | Ongoing |  | 26.6
13 | R132000104 | Suwasra Guradiya Kalan Road | Mandsaur | Road | PWD | 236.53 | 236.53 | 186.09 | 2008-03-10 | 2009-07-27 |  | Completed | DDM | 21 | 21 |  |  | The project resulted in 21 Km of Road. | DDM
13 | R132000105 | Malhargarh Narayangarh Road | Mandsaur | Road | PWD | 82.78 | 66.55 | 66.55 |  |  |  | Completed |  | 7
13 | R132000106 | Runija Angari Road | Mandsaur | Road | PWD | 138.32 | 138.32 | 68.13 | 2007-10-20 | 2009-07-27 |  | Completed | DDM | 10.6 | 10.4 |  |  | The project resulted in 10.40 Km of road. | DDM
13 | R132000107 | Chichli Link road | Narsinghpur | Road | PWD | 110.91 | 88.73 | 88.73 | 2008-08-25 | 2011-11-09 |  | Completed | DDM | 3.4 | 3.4 | 2 | 2 | The project resulted in creation of 3.40 Km of road and connected 2 villages to 2 marketing centres. | DDM
13 | R132000108 | Narsinghpur Devkachachar Road | Narsinghpur | Road | PWD | 290.98 | 232.78 | 232.78 | 2009-03-31 | 2011-11-09 |  | Completed |  | 9.6 | 9.6 | 8 | 3 | The project resulted in creation of 9.60 Km of road and connected 8 villages to 3 marketing centres.
13 | R132000109 | Podar - Salichouka- Barha Road | Narsinghpur | Road | PWD | 364 | 291.2 | 291.2 | 2010-11-30 | 2011-11-09 |  | Completed |  | 14.6 | 14.6 | 5 | 2 | The project resulted in creation of 14.60 Km of road and connected 5 villages to 2 marketing centres.
13 | R132000110 | Manasa - Arniamali - Bordiakala roa | Neemuch | Road | PWD | 196.6 | 196.6 | 196.6 |  |  |  | Completed |  | 12
13 | R132000111 | Bhatkhedi - Jamunia Rao Ji - Lasoor | Neemuch | Road | PWD | 162.65 | 162.65 | 162.65 |  |  |  | Completed | DDM | 10.5 |  |  |  |  | DDM
13 | R132000112 | Talen - Kudlasa Road | Rajgarh | Road | PWD | 84.02 | 84.02 | 84.02 | 2008-04-30 | 2010-06-02 |  | Completed |  | 6.6 | 6.6 |  |  | road project of 6.6 km is executed.
13 | R132000113 | Chhapikheda- Nalkheda Road | Rajgarh | Road | PWD | 105.48 | 98.86 | 98.86 | 2009-06-10 | 2010-11-29 |  | Completed | DDM | 12 | 12 | 10 | 1 | 12 km road constructed.10 villages & 1 mktg. centre connected. | DDM
13 | R132000114 | Alot-Talode road | Ratlam | Road | PWD | 246.89 | 214.7 | 214.7 | 2008-12-31 | 2011-08-05 |  | Completed | DDM | 12.4 | 12.4 | 10 | 3 | 12.4 km length road is constructed. 10 villages & 3 Marketing centres connected. | DDM
13 | R132000115 | Dhodhar - Rola road | Ratlam | Road | PWD | 37.33 | 37.33 | 37.33 | 2008-06-30 | 2011-08-05 |  | Completed |  | 5.2 | 5.2 | 10 | 3 | 5.2 km length road is constructed. 10 villages & 3 Marketing centres connected.
13 | R132000116 | Bahera Dabar Piparahi Road | Rewa | Road | PWD | 440 | 352 | 302.88 | 2009-12-28 | 2011-08-29 |  | Completed |  | 20 | 20 | 11 | 2 | The project resulted in creation of 20.00 Km of road and connected 11 villages to 2 marketing centres.
13 | R132000117 | Pratapganj Hata Road | Rewa | Road | PWD | 356.23 | 284.98 | 284.98 |  |  |  | Ongoing | DDM | 17.2 |  |  |  |  | DDM
13 | R132000118 | Deo Talab Naigarhi Road | Rewa | Road | PWD | 305.34 | 244.27 | 244.27 | 2009-03-30 | 2011-08-29 |  | Completed |  | 16.2 | 16.2 | 10 | 2 | The project resulted in creation of 16.20 Km of road and connected 10 villages to 2 marketing centres.
13 | R132000119 | Naigarhi Garh road | Rewa | Road | PWD | 283.9 | 227.12 | 227.12 | 2010-12-30 | 2011-08-29 |  | Completed |  | 13.6 | 13.6 | 5 |  | The project resulted in creation of 13.60 Km of road and connected 11 villages to 2 marketing centres.
13 | R132000120 | Deotalab- Garh Road | Rewa | Road | PWD | 218.24 | 218.02 | 218.02 | 2009-04-30 | 2011-08-29 |  | Completed |  | 14.4 | 14.4 | 10 | 1 | The project resulted in creation of 14.40 Km of road and connected 10 villages to 1 marketing centre.
13 | R132000121 | Kuthuliya Hardi Road | Rewa | Road | PWD | 226.66 | 181.33 | 178.14 |  |  |  | Ongoing |  | 11
13 | R132000122 | Ichhawar- Ramnagar Road | Sehore | Road | PWD | 180.4 | 180.4 | 180.4 |  | 2011-08-05 |  | Completed |  | 13.2 | 12 | 6 | 2 | 12.0 km length road is constructed. 6 villages & 2 Marketing centres connected.
13 | R132000123 | Jamoniya- Semradangi Road | Sehore | Road | PWD | 124.16 | 124.16 | 124.16 |  | 2011-08-05 |  | Completed |  | 8.6 | 8.6 | 10 | 2 | 8.6 km length road is constructed. 10 villages & 2 Marketing centres connected. 15 km of distance has been reduced.
13 | R132000124 | Sunwara - Pindrai - Keolari Road | Seoni | Road | PWD | 32.18 | 32.18 | 32.18 | 2009-09-27 | 2011-06-15 |  | Completed | DDM | 11.6 | 8 | 6 | 3 | 8.00 km length road is constructed. 6 villages & 3 Marketing centres connected. | DDM
13 | R132000125 | Gohparu - Rasmohni- Burhar road | Shahdol | Road | PWD | 854.67 | 696.92 | 524.59 | 2011-03-31 | 2011-08-29 |  | Completed | DDM | 65 | 68 | 30 | 5 | The project resulted in creation of 68.00 Km of road and connected 30 villages to 5 marketing centres. | DDM
13 | R132000126 | Kanad-Pachlana Road | Shajapur | Road | PWD | 68.36 | 68.36 | 68.36 |  |  |  | Completed |  | 7.4
13 | R132000127 | Sundarsi-Khadi- Polay -Piparanva Ro | Shajapur | Road | PWD | 316.19 | 255.58 | 255.58 |  |  |  | Completed |  | 18.1
13 | R132000128 | Digora Mohangarh Road | Tikamgarh | Road | PWD | 109.66 | 109.66 | 109.66 | 2008-09-14 | 2009-10-29 |  | Completed |  | 19 | 19.2 |  |  | 19.20 Km road implemented
13 | R132000129 | Dablafanth - Sipawara Road | Ujjain | Road | PWD | 178.04 | 178.04 | 178.04 |  |  |  | Ongoing |  | 16.2
13 | R132000130 | Gogapur-Bappiya-Zutawad-Ranayarapee | Ujjain | Road | PWD | 198.37 | 198.37 | 196.59 | 2008-03-31 | 2009-07-27 |  | Completed |  | 17 | 21.5 |  |  | The project resyulted in 21.50 Km of road
13 | R132000131 | Zarda- Gelakhedi Nagpura road | Ujjain | Road | PWD | 89.22 | 89.22 | 65.65 |  |  |  | Ongoing |  | 9.85
13 | R132000132 | Sasstra Kathotiya Road | Umaria | Road | PWD | 73.73 | 73.73 | 73.73 |  |  |  | Ongoing |  | 30
13 | R132000133 | Barhi Singroli Manpur Road | Umaria | Road | PWD | 178.78 | 178.78 | 161.9 |  |  |  | Ongoing |  | 20.4
13 | R132000134 | HLB a/c Goi river in KM 1/6 | Badwani | Bridge | PWD | 291.45 | 233.16 | 233.16 |  |  |  | Ongoing |  | 196
13 | R132000135 | HLB a/c Khar Nala in KM 2/2 | Bhind | Bridge | PWD | 49.07 | 49.07 | 49.07 |  |  |  | Ongoing | DDM | 36 |  |  |  |  | DDM
13 | R132000136 | SB a/c Morar river in KM 2/2 | Bhind | Bridge | PWD | 54.87 | 51.82 | 47.53 |  |  |  | Ongoing | DDM | 30 |  |  |  |  | DDM
13 | R132000137 | SB a/c Vasily river in KM 1/2 | Bhind | Bridge | PWD | 44.16 | 40 | 40 |  |  |  | Ongoing |  | 16
13 | R132000138 | HLB a/c Vasily river in KM 1/2 | Bhind | Bridge | PWD | 96.39 | 91.7 | 91.7 |  |  |  | Ongoing | DDM | 54 |  |  |  |  | DDM
13 | R132000139 | HLB a/c Kunwari river in KM 2/2 | Bhind | Bridge | PWD | 1029.6 | 823.68 | 823.68 |  |  |  | Ongoing |  | 200
13 | R132000140 | HLB a/c Vasily river in KM 1/4-6 | Bhind | Bridge | PWD | 90.76 | 90.76 | 90.76 |  |  |  | Ongoing |  | 45
13 | R132000141 | HLB a/c Gouraiya river in KM 79/10 | Damoh | Bridge | PWD | 154.19 | 124.72 | 124.72 | 2011-02-14 | 2011-09-19 |  | Completed |  | 115 | 115 | 20 | 2 | Bridge of 115 m was constructed, which connected 20 villages to 2 marketing centres.
13 | R132000142 | HLB a/c Gouraiya river in KM 71/10 | Damoh | Bridge | PWD | 114.43 | 106.03 | 106.03 |  |  |  | Ongoing | DDM | 80 |  |  |  |  | DDM
13 | R132000143 | SB a/c Bairma river | Damoh | Bridge | PWD | 334.42 | 268.2 | 268.2 | 2010-06-14 | 2011-08-29 |  | Completed | OIC | 190 | 180 | 20 | 2 | Bridge of 180 m was constructed, which connected 20 villages to 2 marketing centres. 35 km of distance has been reduced. | OIC
13 | R132000144 | HLB a/c Sindh river in KM 2/2 | Datia | Bridge | PWD | 608.44 | 486.75 | 486.75 |  |  |  | Ongoing |  | 275
13 | R132000145 | HLB a/c Sukni river in KM 6/6 | Harda | Bridge | PWD | 89.88 | 77.23 | 77.23 |  |  |  | Ongoing |  | 45
13 | R132000146 | HLB a/c Abna river in KM 3/8 | Khandwa | Bridge | PWD | 59.8 | 51.06 | 51.06 |  |  |  | Ongoing |  | 24
13 | R132000147 | HLB a/c Karanj Nalla in KM 6/4 | Khandwa | Bridge | PWD | 66.65 | 66.65 | 66.65 | 2009-08-31 | 2011-08-03 |  | Completed |  | 60 | 60 | 12 | 1 | Bridge of 60 m was constructed, which connected 12 villages to 1 marketing centre. 18 km of distance has been reduced.
13 | R132000148 | HLB a/c Siltiya Nalla in KM 3/2 | Khandwa | Bridge | PWD | 44.62 | 38.84 | 38.84 |  |  |  | Ongoing |  | 24
13 | R132000149 | HLB a/c Ghorwa river in KM 2/6 | Khandwa | Bridge | PWD | 63.62 | 56.02 | 55.76 | 2009-07-15 | 2011-08-03 |  | Completed |  | 30 | 30 | 8 | 2 | Bridge of 30 m was constructed, which connected 08 villages to 2 marketing centres.
13 | R132000150 | HLB a/c Sukta river in KM 13/6 | Harda | Bridge | PWD | 170.06 | 145.47 | 145.47 | 2009-06-20 | 2011-08-03 |  | Completed |  | 100 | 100 | 12 | 3 | Bridge of 100 m was constructed, which connected 12 villages to 3 marketing centres. 20 km of distance has been reduced.
13 | R132000151 | HLB a/c Lasudia Nallah in KM 18/10 | Mandsaur | Bridge | PWD | 83.05 | 67.12 | 61.28 |  |  |  | Ongoing | DDM | 52 |  |  |  |  | DDM
13 | R132000152 | SB a/c Ken river in KM 15/2 | Panna | Bridge | PWD | 1167.25 | 936.11 | 936.11 | 2011-03-31 | 2012-02-23 |  | Completed |  | 378 | 378 |  |  | Ajaygarh to Chendla Bridge completed (378 mtr)
13 | R132000153 | HLB a/c Khand river in KM4 | Raisen | Bridge | PWD | 87.06 | 87.06 | 87.06 |  |  |  | Ongoing | DDM | 45 |  |  |  |  | DDM
13 | R132000154 | HLB a/c Ugal river in KM 22/10 | Rajgarh | Bridge | PWD | 159.64 | 128.61 | 128.61 |  |  |  | Ongoing | DDM | 105 |  |  |  |  | DDM
13 | R132000155 | SB a/c Parvati river | Rajgarh | Bridge | PWD | 425.42 | 341.34 | 341.34 |  |  |  | Ongoing | DDM | 210 |  |  |  |  | DDM
13 | R132000156 | HLB a/c Rojar river in KM 18/10 | Ratlam | Bridge | PWD | 120.12 | 97.5 | 95.76 |  |  |  | Ongoing |  | 45
13 | R132000157 | SB a/c Mandha River bridge in KM 19 | Rewa | Bridge | PWD | 93.12 | 75.46 | 70.27 | 2008-07-31 | 2008-12-17 |  | Completed |  | 48 | 48 | 16 | 2 | Bridge was executed with a cost of Rs.69.453 Lakh. Cost saving Time over run. 30000 Mandays created, connected 16 villages to 2 marketing centrea at Jawa and Shankargarh. Reduced travelling distance by 20 Km
13 | R132000158 | HLB a/c river Bihar in KM 2/10 | Rewa | Bridge | PWD | 96.27 | 96.27 | 93.06 | 2008-01-31 | 2008-10-10 |  | Completed | DDM | 90 | 90 | 18 |  | Slight saving on cost; Time over run by three -and -a half month;It generated 25000 non -recurring man days of employment;Connected 18 villages to marketing centre aqt Rewa. reduced travel distance by 12 Km | DDM
13 | R132000159 | SB a/c Narain river in KM 6/2 | Sagar | Bridge | PWD | 68.48 | 54.78 | 54 | 2009-02-25 | 2010-09-22 |  | Completed | DDM | 17.7 | 17.7 | 50 | 2 | bridge of 17.70 m was constructed, which connected 50 villages to 2 marketing centres | DDM
13 | R132000160 | HLB a/c Dhasan river in KM 25/8 | Sagar | Bridge | PWD | 170.27 | 136.22 | 94.28 |  |  |  | Ongoing | DDM | 150 |  |  |  |  | DDM
13 | R132000161 | HLB a/c Kaith river in KM 8/4 | Sagar | Bridge | PWD | 169.1 | 135.28 | 135.28 | 2011-07-15 | 2012-09-03 |  | Completed | DDM | 120 | 120 |  |  | Garhakota to Rehli bridge completed. | DDM
13 | R132000162 | SB a/c Sukha Nalla in KM 15/6 | Sagar | Bridge | PWD | 146.54 | 117.23 | 117.23 | 2009-03-30 | 2010-09-22 |  | Completed |  | 30 | 30 | 50 | 2 | Bridge of 30 m was constructed, which connected 50 villages to 2 marketing centres
13 | R132000163 | HLB a/c Jamni river in KM 6/4 | Tikamgarh | Bridge | PWD | 169.66 | 136.36 | 136.36 | 2011-03-18 | 2011-10-19 |  | Completed |  | 126 | 126 | 20 | 2 | Bridge of 126 m was constructed, which connected 20 villages to 2 marketing centres. 20 km of distance has been reduced.
13 | R132000164 | SB a/c Piliya Khal Nalla in KM 3/4 | Ujjain | Bridge | PWD | 118.74 | 96.58 | 96.58 |  |  |  | Ongoing |  | 60
13 | R132000165 | HLB a/c Sagad river in KM 2/6 | Vidisha | Bridge | PWD | 155.86 | 126.03 | 126.03 |  |  |  | Ongoing |  | 100
13 | R132000166 | HLB a/c Sapan river in KM 38/10 | Vidisha | Bridge | PWD | 263.81 | 213.8 | 213.8 |  |  |  | Ongoing | DDM | 100 |  |  |  |  | DDM
13 | R132000167 | Bansagar MJP UnitIICanals | Rewa | MJP | WRD | 132433 | 94358.75 | 94217.42 |  |  |  | Ongoing | OIC | 154687 |  |  |  |  | OIC

## Monitoring (hidden)
MONITORING DATA
Tranche | PIC | Name of Project | District | Agency | Activity | Date of Visit | Visited by | RIDF_Loan | Loan_Limit | Findings
1 | R012000145 | Rupniakhal | Ratlam | WRD | MIS | 2002-06-19 | DDM | 78.28 | RIDF Loan upto 10 crore | Completed
1 | R012000081 | Dholawad | Ratlam | WRD | MIP | 2002-06-15 | DDM | 362 | RIDF Loan upto 10 crore | Completed
1 | R012000082 | Khedi | Ratlam | WRD | MIS | 2002-06-13 | DDM | 9.38 | RIDF Loan upto 10 crore | Completed
1 | R012000036 | Mehgaon | Jabalpur | WRD | MIS | 2001-11-17 | DDM | 34.79 | RIDF Loan upto 10 crore | PCR Verification-Leakage from aquaduct and breach in canal at 3.4km is adversely affecting the command. Canal needs repair & maintenance as water is not reaching beyond 3km.
1 | R012000138 | Hatani | Alirajpur | WRD | MIS | 2001-03-27 | DDM | 58.26 | RIDF Loan upto 10 crore | Project completed, however irrigation not yet commenced (owing to drought conditions in the district, use of the stored water- 1 m above LSR was restricted for drinking purpose)
1 | R012000040 | Tilahari | Jabalpur | WRD | MIS | 2001-02-14 | DDM | 45.83 | RIDF Loan upto 10 crore | NB board not displayed, the project is complete, seepage from dam and canals and leakage from canal gates, the acreage under irrigation fell short of projections for leakage. WRD should examine the matter urgently and undertake the remedial measures.
1 | R012000011 | Kanhargaon | Chhindwara | WRD | MIP | 2001-01-25 | AFC(Agents) | 186.08 | RIDF Loan upto 10 crore | Project completed by 31/3/99, 2 WUAs formed in 2000 and area of 2964.28 ha brought under those WUAs), the project has created 3542 ha command area.
1 | R012000031 | Sitakapura | Gwalior | WRD | MIS | 2001-01-12 | DDM | 10.55 | RIDF Loan upto 10 crore | Project completed. It was observed that installed pumps were out of order for the last 2 months and stand by pump not provided. Maintenance aspects need to be looked after by competent authority.
1 | R012000086 | Kotar | Satna | WRD | MIS | 2001-01-10 | DDM | 30.54 | RIDF Loan upto 10 crore | Project complete, WUA not yet formed, unauthorised use of water from canal affecting availability of water during Rabi in command area, unsatisfactory quality of work.
1 | R012000074 | Dudhi | Rajgarh | WRD | MIP | 2001-01-05 | AFC(Agents) | 863 | RIDF Loan upto 10 crore | Slow progress, unlined canals being constructed, joining of minors to main canal being done, top of dam should be provided with tar road, Delay in fixing agency, LA, R&R, cost escalation Rs. 40 lacs reported.
1 | R012000018 | Sironj | Dhar | WRD | MIS | 2001-01-02 | DDM | 124.6 | RIDF Loan upto 10 crore | Project completed and PCR received, less water storage for Rabi 2000 due to less rainfall.
1 | R012000055 | Gorakhpur | Narsinghpur | WRD | MIS | 2000-11-20 | DDM | 21.68 | RIDF Loan upto 10 crore | Work affected for water scarcity/drought, NB board not displayed
1 | R012000150 | Berchi | Shajapur | WRD | MIS | 2000-11-18 | RO Official | 34.66 | RIDF Loan upto 10 crore | Project complete, basin has leakage problem, nallah flowing in higher reaches could be diverted, no arrangement has been made for measurement of seepage in the cross drains. V-notches at different sections may be installed, top of TBL has to be levelled.
1 | R012000054 | Patha | Narsinghpur | WRD | MIS | 2000-11-17 | DDM | 21.275 | RIDF Loan upto 10 crore | Work affected for water scarcity/drought, NB board not displayed
1 | R012000035 | Kotiazhiri | Indore | WRD | MIS | 2000-10-31 | DDM | 13.04 | RIDF Loan upto 10 crore | Project completed, however maintenance is not satisfactory, WUA formed but its functioning is not effective
1 | R012000030 | Lohari | Gwalior | WRD | MIS | 2000-10-24 | DDM | 20.03 | RIDF Loan upto 10 crore | Project completed, however electrical pumps are out of order since April 98, electrical connection is disconnected by MPEB for non-payment, canal bed is damaged for non-use for last 3 years, NB board not displayed
1 | R012000053 | 3 T.wells | Narsinghpur | WRD | MIS | 2000-10-17 | DDM | 26 | RIDF Loan upto 10 crore | NB board not displayed, loss of water due to seepage, improper electricity connection and non-posting of pump operator at Basanwari tubewell, no barbed wire fencing at Basanwari pump house.
1 | R012000145 | Rupniakhal | Ratlam | WRD | MIS | 2000-10-16 | DDM | 78.28 | RIDF Loan upto 10 crore | Project completed, nothing adverse reported
1 | R012000082 | Khedi | Ratlam | WRD | MIS | 2000-10-15 | DDM | 9.38 | RIDF Loan upto 10 crore | Project completed, benefits accruing, WUA status not indicated
1 | R012000081 | Dholawad | Ratlam | WRD | MIP | 2000-10-14 | DDM | 362 | RIDF Loan upto 10 crore | Work progress slow, time overrun likely, labour problem
1 | R012000011 | Kanhargaon | Chhindwara | WRD | MIP | 2000-06-27 | DDM | 186.08 | RIDF Loan upto 10 crore | Savings reported, NB board was not displayed at the site, observation of technical nature(construction of guide bund was not done properly and the same required repairy to avoid damage to the field adjoining spill channel).
1 | R012000014 | Tamia | Chhindwara | WRD | MIS | 2000-06-19 | DDM | 54.29 | RIDF Loan upto 10 crore | Quality of work was not satisfactory( immediate repairy was necessary for sluice valve, bund wall and canal), WUA was formed, farmers interviewed exressed dissatisfaction about location of the project site.
1 | R012000121 | 22 T.Wells(S) | Sidhi | WRD | MIS | 2000-05-31 | DDM | 40 | RIDF Loan upto 10 crore | Observation of technical nature(6 tubewells dropped).
1 | R012000122 | 22 T.Wells(R) | Sidhi | WRD | MIS | 2000-05-31 | DDM | 40 | RIDF Loan upto 10 crore | 12 tubewells were completed, 4 tubewells neared completion.
1 | R012000053 | 3 T.wells | Narsinghpur | WRD | MIS | 2000-05-25 | DDM | 26 | RIDF Loan upto 10 crore | Project completed. Irrigation commenced in about 20 ha area.
1 | R012000027 | Bandianalla | Guna | WRD | MIP | 2000-04-28 | DDM | 520.425 | RIDF Loan upto 10 crore | Project completed.
1 | R012000081 | Dholawad | Ratlam | WRD | MIP | 2000-04-10 | DDM | 362 | RIDF Loan upto 10 crore | Project completed, irrigation commenced in an area of 4400 ha.
1 | R012000003 | Bundala | Betul | WRD | MIP |  |  | 217.01 | RIDF Loan upto 10 crore
1 | R012000004 | Kherwada | Betul | WRD | MIS |  |  | 21.77 | RIDF Loan upto 10 crore
1 | R012000005 | Kursi | Betul | WRD | MIS |  |  | 85.43 | RIDF Loan upto 10 crore
1 | R012000006 | Deora | Chattarpur | WRD | MIS |  |  | 11.75 | RIDF Loan upto 10 crore
1 | R012000007 | Dhamantodi | Bhopal | WRD | MIS |  |  | 20.44 | RIDF Loan upto 10 crore
1 | R012000008 | Garetia | Bhopal | WRD | MIS |  |  | 115.86 | RIDF Loan upto 10 crore
1 | R012000012 | Khapabihar | Chhindwara | WRD | MIS |  |  | 9.95 | RIDF Loan upto 10 crore
1 | R012000013 | Banki | Chhindwara | WRD | MIS |  |  | 24.21 | RIDF Loan upto 10 crore
1 | R012000015 | Bhajia | Damoh | WRD | MIS |  |  | 143.84 | RIDF Loan upto 10 crore
1 | R012000016 | Gudri | Damoh | WRD | MIS |  |  | 86.91 | RIDF Loan upto 10 crore
1 | R012000017 | Sanjay | Dhar | WRD | MIS |  |  | 76.53 | RIDF Loan upto 10 crore
1 | R012000024 | Sanjay Sagar | Guna | WRD | MIP |  |  | 351.01 | RIDF Loan upto 10 crore
1 | R012000025 | Dehrikalan | Guna | WRD | MIS |  |  | 8 | RIDF Loan upto 10 crore
1 | R012000026 | Umaria | Ashoknagar | WRD | MIS |  |  | 13.44 | RIDF Loan upto 10 crore
1 | R012000028 | Makroda-Rampur | Guna | WRD | MIP |  |  | 580.82 | RIDF Loan upto 10 crore
1 | R012000029 | Ikodia | Guna | WRD | MIS |  |  | 11.3 | RIDF Loan upto 10 crore
1 | R012000033 | Amadehi | Hoshangabad | WRD | MIS |  |  | 10.87 | RIDF Loan upto 10 crore
1 | R012000034 | Choral | Indore | WRD | MIP |  |  | 613 | RIDF Loan upto 10 crore
1 | R012000037 | Sarra | Katni | WRD | MIS |  |  | 24.54 | RIDF Loan upto 10 crore
1 | R012000038 | Ghinochi | Katni | WRD | MIS |  |  | 14.32 | RIDF Loan upto 10 crore
1 | R012000039 | Baretha | Katni | WRD | MIS |  |  | 20.89 | RIDF Loan upto 10 crore
1 | R012000041 | Rampura | Alirajpur | WRD | MIS |  |  | 108.38 | RIDF Loan upto 10 crore
1 | R012000042 | Kalapipal | Jhabua | WRD | MIS |  |  | 26.47 | RIDF Loan upto 10 crore
1 | R012000043 | Dhamoi | Jhabua | WRD | MIS |  |  | 134.12 | RIDF Loan upto 10 crore
1 | R012000044 | Umda | Alirajpur | WRD | MIS |  |  | 28 | RIDF Loan upto 10 crore
1 | R012000045 | Matiyari | Mandla | WRD | MIP |  |  | 2132.3 | RIDF Loan 10.01-24.99 crore
1 | R012000046 | Narmada | Mandla | WRD | MIS |  |  | 47.64 | RIDF Loan upto 10 crore
1 | R012000047 | Chikhalitola | Mandla | WRD | MIS |  |  | 38.24 | RIDF Loan upto 10 crore
1 | R012000048 | Kahanideori | Mandla | WRD | MIS |  |  | 10.94 | RIDF Loan upto 10 crore
1 | R012000050 | Dudhakhadi | Mandsaur | WRD | MIS |  |  | 14 | RIDF Loan upto 10 crore
1 | R012000051 | Antri | Mandsaur | WRD | MIS |  |  | 54.72 | RIDF Loan upto 10 crore
1 | R012000056 | Bhapatpur | Panna | WRD | MIS |  |  | 38.85 | RIDF Loan upto 10 crore
1 | R012000069 | 50 T.Wells | Raisen | WRD | MIS |  |  | 40 | RIDF Loan upto 10 crore
1 | R012000070 | Noniabareli | Raisen | WRD | MIS |  |  | 38 | RIDF Loan upto 10 crore
1 | R012000071 | Manjashkhurd | Raisen | WRD | MIS |  |  | 38.48 | RIDF Loan upto 10 crore
1 | R012000072 | Bhimvatika | Raisen | WRD | MIS |  |  | 66.56 | RIDF Loan upto 10 crore
1 | R012000073 | Sarana | Raisen | WRD | MIS |  |  | 13.8 | RIDF Loan upto 10 crore
1 | R012000075 | Choma | Raisen | WRD | MIS |  |  | 16.07 | RIDF Loan upto 10 crore
1 | R012000076 | Dolaz | Raisen | WRD | MIS |  |  | 49.5 | RIDF Loan upto 10 crore
1 | R012000077 | Biaora Mandu | Raisen | WRD | MIS |  |  | 54.33 | RIDF Loan upto 10 crore
1 | R012000078 | Bhasora | Raisen | WRD | MIS |  |  | 51.075 | RIDF Loan upto 10 crore
1 | R012000083 | Baredia | Sagar | WRD | MIS |  |  | 15.2 | RIDF Loan upto 10 crore
1 | R012000084 | Mahuakheda | Sagar | WRD | MIS |  |  | 22.48 | RIDF Loan upto 10 crore
1 | R012000085 | Hinota | Satna | WRD | MIS |  |  | 22.55 | RIDF Loan upto 10 crore
1 | R012000087 | Rampura Khurd | Sehore | WRD | MIP |  |  | 533 | RIDF Loan upto 10 crore
1 | R012000088 | Khudwari | Seoni | WRD | MIS |  |  | 9.64 | RIDF Loan upto 10 crore
1 | R012000089 | Indawari | Seoni | WRD | MIS |  |  | 21.38 | RIDF Loan upto 10 crore
1 | R012000090 | Gorakhpur | Seoni | WRD | MIS |  |  | 24.66 | RIDF Loan upto 10 crore
1 | R012000091 | Kudari | Shahdol | WRD | MIS |  |  | 11.5 | RIDF Loan upto 10 crore
1 | R012000092 | Benibari | Anuppur | WRD | MIS |  |  | 26.65 | RIDF Loan upto 10 crore
1 | R012000093 | Silpari | Anuppur | WRD | MIS |  |  | 21 | RIDF Loan upto 10 crore
1 | R012000094 | Amjhor | Anuppur | WRD | MIS |  |  | 29 | RIDF Loan upto 10 crore
1 | R012000095 | Tillar | Shajapur | WRD | MIP |  |  | 784 | RIDF Loan upto 10 crore
1 | R012000096 | Budhna | Shivpuri | WRD | MIP |  |  | 360 | RIDF Loan upto 10 crore
1 | R012000097 | Arjunganwa | Shivpuri | WRD | MIS |  |  | 21.725 | RIDF Loan upto 10 crore
1 | R012000098 | Bairad | Shivpuri | WRD | MIS |  |  | 162.5 | RIDF Loan upto 10 crore
1 | R012000103 | Satpada | Vidisha | WRD | MIS |  |  | 53.42 | RIDF Loan upto 10 crore
1 | R012000109 | Piprana | Burhanpur | WRD | MIS |  |  | 8.6 | RIDF Loan upto 10 crore
1 | R012000110 | Chikholia | Khargone | WRD | MIS |  |  | 46.83 | RIDF Loan upto 10 crore
1 | R012000111 | Bhorwada | Khargone | WRD | MIS |  |  | 40.8 | RIDF Loan upto 10 crore
1 | R012000112 | Dasoda | Khargone | WRD | MIS |  |  | 13 | RIDF Loan upto 10 crore
1 | R012000117 | 25 t.wells (Isgh) | Guna | WRD | MIS |  |  | 30 | RIDF Loan upto 10 crore
1 | R012000118 | 25 t.wells (Rgh) | Guna | WRD | MIS |  |  | 15 | RIDF Loan upto 10 crore
1 | R012000119 | 20 T.wells | Jabalpur | WRD | MIS |  |  | 20 | RIDF Loan upto 10 crore
1 | R012000123 | Guradiya | Dewas | WRD | MIS |  |  | 39 | RIDF Loan upto 10 crore
1 | R012000124 | Dejladewda | Khargone | WRD | MIP |  |  | 1023.91 | RIDF Loan 10.01-24.99 crore
1 | R012000126 | Dudhiya | Burhanpur | WRD | MIS |  |  | 25.96 | RIDF Loan upto 10 crore
1 | R012000128 | Ranipur | Betul | WRD | MIS |  |  | 151.21 | RIDF Loan upto 10 crore
1 | R012000129 | Sasundra | Betul | WRD | MIS |  |  | 76.89 | RIDF Loan upto 10 crore
1 | R012000131 | Hirwa | Betul | WRD | MIS |  |  | 55 | RIDF Loan upto 10 crore
1 | R012000134 | Pankua-2 | Dewas | WRD | MIS |  |  | 32.9 | RIDF Loan upto 10 crore
1 | R012000135 | Hinotia | Hoshangabad | WRD | MIS |  |  | 12.57 | RIDF Loan upto 10 crore
1 | R012000136 | Singhan talai | Katni | WRD | MIS |  |  | 10.65 | RIDF Loan upto 10 crore
1 | R012000137 | Morjiri | Jhabua | WRD | MIS |  |  | 25.45 | RIDF Loan upto 10 crore
1 | R012000139 | Amliphaliya | Jhabua | WRD | MIS |  |  | 25 | RIDF Loan upto 10 crore
1 | R012000140 | Ralayata | Neemuch | WRD | MIS |  |  | 30.07 | RIDF Loan upto 10 crore
1 | R012000144 | Piplia | Raisen | WRD | MIS |  |  | 70 | RIDF Loan upto 10 crore
1 | R012000146 | Mogha | Raisen | WRD | MIS |  |  | 406.81 | RIDF Loan upto 10 crore
1 | R012000147 | Jhalpipli | Sehore | WRD | MIS |  |  | 41.02 | RIDF Loan upto 10 crore
1 | R012000148 | Lakhunder | Shajapur | WRD | MIP |  |  | 792 | RIDF Loan 10.01-24.99 crore
1 | R012000149 | Chkrod | Shajapur | WRD | MIS |  |  | 26.45 | RIDF Loan upto 10 crore
1 | R012000156 | Kotda bk | Mandsaur | WRD | MIS |  |  | 28 | RIDF Loan upto 10 crore
1 | R012000157 | Doroha | Sehore | WRD | MIP |  |  | 58.4 | RIDF Loan upto 10 crore
1 | R012000158 | Sidli | Shahdol | WRD | MIS |  |  | 4 | RIDF Loan upto 10 crore
1 | R012000159 | Bamera | Shahdol | WRD | MIS |  |  | 22 | RIDF Loan upto 10 crore
1 | R012000162 | Machalgaon | Khargone | WRD | MIS |  |  | 39.75 | RIDF Loan upto 10 crore
1 | R012000163 | Sangvi | Khargone | WRD | MIS |  |  | 220.16 | RIDF Loan upto 10 crore
1 | R012000001 | Sanghanpuri | Balaghat | WRD | MIS |  |  | 4.16 | RIDF Loan upto 10 crore
1 | R012000002 | Jagotianala | Balaghat | WRD | MIS |  |  | 22.76 | RIDF Loan upto 10 crore
2 | r022000036 | Jitudhana | Betul | WRD | MIS | 2005-10-01 | DDM | 109.75 | RIDF Loan upto 10 crore | Work is completed in December 2004. Irrigation benefit provided to 231 ha.
2 | R022000036 | Jitudhana | Betul | WRD | MIS | 2004-12-10 | DDM | 109.75 | RIDF Loan upto 10 crore | About 95% of the work is completed. NABARD Board was not displayed
2 | R022000004 | Rajeev sagar | Guna | WRD | MIS | 2004-03-23 | DDM | 1277.94 | RIDF Loan 10.01-24.99 crore | WUA not formed. NB board not displayed in the prescribed format.
2 | R022000046 | Pondi | Shahdol | WRD | MIS | 2004-03-13 | DDM | 34.69 | RIDF Loan upto 10 crore | WUA not formed.NB board not displayed.
2 | R022000036 | Jitudhana | Betul | WRD | MIS | 2004-03-12 | DDM | 109.75 | RIDF Loan upto 10 crore | Slow progress- nalla closure work not completed . NB board not displayed at site.
2 | R022000035 | Mandvi | Betul | WRD | MIS | 2004-02-22 | DDM | 118.34 | RIDF Loan upto 10 crore | NB board not displayed at site. WUA not formed.
2 | r022000027 | Mehni | Alirajpur | WRD | MIS | 2004-02-14 | DDM | 78.94 | RIDF Loan upto 10 crore | WUA not formed . NB board not displayed.
2 | R022000055 | Kohpani | Chhindwara | WRD | MIS | 2004-02-09 | DDM | 117.71 | RIDF Loan upto 10 crore | WUA not formed.
2 | R022000063 | Depalpur | Indore | WRD | MIS | 2004-01-30 | DDM | 36.61 | RIDF Loan upto 10 crore | The project is physically completed.
2 | r022000032 | Nimb | Burhanpur | WRD | MIS | 2004-01-08 | DDM | 153 | RIDF Loan upto 10 crore | WUA not formed, main canal needs repairs, NB Board not displayed.
2 | r022000061 | Umaria Dalel | Chhindwara | WRD | MIS | 2004-01-08 | DDM | 155.81 | RIDF Loan upto 10 crore | WUA not formed.
2 | r022000029 | Jamdhar | Khandwa | WRD | MIS | 2004-01-07 | DDM | 39.19 | RIDF Loan upto 10 crore | WUA not formed, main canal needs and sluice need repairs.
2 | r022000030 | Khari (kharona) | Khandwa | WRD | MIS | 2004-01-07 | DDM | 40.04 | RIDF Loan upto 10 crore | Pitching needs repairs, poor maintenance of main canal, NB Board not displayed.
2 | R022000008 | Sagonikala | Bhopal | WRD | MIS | 2003-03-11 | RO Official | 150.78 | RIDF Loan upto 10 crore | 70% earthwork in dam and 45% in spill way not completed, private forest land not acquired, delay in payment to contractor, project likely to be completed by Dec '03 as against the completion date June '02. NB not displayed in proper format.
2 | R022000009 | Semrikala | Bhopal | WRD | MIS | 2003-03-08 | RO Official | 126.14 | RIDF Loan upto 10 crore | Time overrun, Delay in tendering (dept. is finalising tenders for pending earthwork and flush bar),Land acquisition problem (delay in land acquisition for Unit I (0.56 ha) and Unit II (2.20 ha). NB board not displayed in proper format.
2
2 | R022000003 | Hareri | Narsinghpur | NVDA | MJP | 2003-01-16 | DDM | 1850 | RIDF Loan 10.01-24.99 crore | Delay in land acquisition payment. Delay in fixing agency for additional work.
2 | R022000006 | Bhaisatori | Guna | WRD | MIS | 2002-12-28 | DDM | 439.01 | RIDF Loan upto 10 crore | No proper supervision. WUA not formed.
2 | R022000046 | Pondi | Shahdol | WRD | MIS | 2002-06-18 | DDM | 34.69 | RIDF Loan upto 10 crore | Completed. Delay (contractor problem). Maintenance arrangements not satisfactory.
2 | R022000053 | Birmawal | Ratlam | WRD | MIS | 2002-06-18 | DDM | 179.72 | RIDF Loan upto 10 crore | Completed.
2 | R022000002 | Kunwarpur | Jabalpur | NVDA | MJP | 2002-06-13 | RO Official+C | 800 | RIDF Loan upto 10 crore | As per annexure
2 | R022000001 | Khajuri | Jabalpur | NVDA | MJP | 2002-06-12 | RO Official+C | 1600 | RIDF Loan 10.01-24.99 crore | As per annexure
2 | R022000041 | Chingun | Khargone | WRD | MIS | 2002-05-25 | DDM | 28.53 | RIDF Loan upto 10 crore | Completed
2 | R022000029 | Jamdhar | Khandwa | WRD | MIS | 2002-05-23 | DDM | 39.19 | RIDF Loan upto 10 crore | Turfing not complete.
2 | R022000031 | Rajur | Khandwa | WRD | MIS | 2002-05-23 | DDM | 38.97 | RIDF Loan upto 10 crore | Formation of WUA to be looked into.
2 | R022000018 | Chamleshwar | Neemuch | WRD | MIS | 2002-05-04 | RO Official+C | 894.45 | RIDF Loan 10.01-24.99 crore | As per annexure.
2 | R022000026 | Jhora no.2 | Alirajpur | WRD | MIS | 2002-04-10 | DDM | 57 | RIDF Loan upto 10 crore | Completed. Inadequate arrangement for maintenance. NB board to be displayed.
2 | R022000025 | Hirapur | Alirajpur | WRD | MIS | 2002-04-09 | DDM | 63.27 | RIDF Loan upto 10 crore | Completed. Inadequate arrangement for maintenance. NB board to be displayed.
2 | R022000010 | Shyampura | Shajapur | WRD | MIS | 2002-01-08 | RO Official+C | 127.5 | RIDF Loan upto 10 crore | Report as per Annexure
2 | R022000011 | Khadi | Shajapur | WRD | MIS | 2002-01-07 | RO Official+C | 91.68 | RIDF Loan upto 10 crore | Report as per Annexure.
2 | R022000030 | Khari (kharona) | Khandwa | WRD | MIS | 2001-12-22 | DDM | 40.04 | RIDF Loan upto 10 crore | Canal work abandoned by contractor. Aquaduct and one structure are also incomplete.
2 | R022000006 | Bhaisatori | Guna | WRD | MIS | 2001-12-21 | DDM+C | 439.01 | RIDF Loan upto 10 crore | Slow progress (project not completed as agaisnt original date of March '99).
2 | R022000004 | Rajeev sagar | Guna | WRD | MIS | 2001-12-20 | DDM+C | 1277.94 | RIDF Loan 10.01-24.99 crore | Right bank canal work not started due to LA problem.
2 | R022000036 | Jitudhana | Betul | WRD | MIS | 2001-11-23 | DDM | 109.75 | RIDF Loan upto 10 crore | Slow progress (contractor is working slowly and delaying the work).
2 | R022000018 | Chamleshwar | Neemuch | WRD | MIS | 2001-11-22 | RO Official+C | 894.45 | RIDF Loan 10.01-24.99 crore | Report received
2 | R022000019 | Dasani | Neemuch | WRD | MIS | 2001-11-21 | RO Official+C | 85.43 | RIDF Loan upto 10 crore | Report received
2 | R022000027 | Mehni | Alirajpur | WRD | MIS | 2001-10-30 | DDM+C | 78.94 | RIDF Loan upto 10 crore | Observations of technical nature (), Cost overrun likely (cost escalation estimated at Rs. 31.68 lacs).
2 | R022000029 | Jamdhar | Khandwa | WRD | MIS | 2001-10-22 | DDM | 39.19 | RIDF Loan upto 10 crore | Contractor abandoned work. Canal work not started. Turfing not done. Railing damaged.
2 | R022000032 | Nimb | Burhanpur | WRD | MIS | 2001-09-19 | DDM | 153 | RIDF Loan upto 10 crore | Slow progress of work (canal work incomplete), Delay in land acquisition (land for Unit II not yet acquired for higher compensation demand by the farmers), Cost overrun likely, NB board already erected needs replacement as it is worn out.
2 | R022000033 | Guradya | Burhanpur | WRD | MIS | 2001-09-19 | DDM | 75.75 | RIDF Loan upto 10 crore | Canal work to be completed soon
2 | R022000023 | New Rajnal | Dewas | WRD | MIS | 2001-09-11 | DDM | 200.1 | RIDF Loan upto 10 crore | Slow progress of work (project likely to be completed by the extended completion due date of 31/12/01 as against the actual due date of 31/3/99), funds constraints.
2 | R022000035 | Mandvi | Betul | WRD | MIS | 2001-08-31 | DDM | 118.34 | RIDF Loan upto 10 crore | Likely time overrun (due to frequent design changes), NB board not displayed.
2 | R022000029 | Jamdhar | Khandwa | WRD | MIS | 2001-06-27 | DDM | 39.19 | RIDF Loan upto 10 crore | Completed
2 | R022000030 | Khari (kharona) | Khandwa | WRD | MIS | 2001-06-27 | DDM | 40.04 | RIDF Loan upto 10 crore | Completed
2 | R022000031 | Rajur | Khandwa | WRD | MIS | 2001-06-27 | DDM | 38.97 | RIDF Loan upto 10 crore | Completed
2 | R022000032 | Nimb | Burhanpur | WRD | MIS | 2001-06-18 | DDM | 153 | RIDF Loan upto 10 crore | Canal work to be completed soon
2 | R022000051 | Rupdo Rupadeh | Sehore | WRD | MIS | 2001-05-30 | RO Official | 133.59 | RIDF Loan upto 10 crore | Slow progress, Project likely to be completed by Dec 2001, Delay in LA and forest clearance, Contractor problem, cost escalation Rs. 124.60 lacs on account of LA, Masonry Work , Earthwork , Fixed/other charges, NB board not displayed.
2 | R022000052 | Phudra | Sehore | WRD | MIS | 2001-05-30 | RO Official | 95.25 | RIDF Loan upto 10 crore | Slow progress, Delay in LA/tendering, Contractor problem, project likely to be completed by June 02 as against extended completion date of 31/12/01, cost escalation Rs. 106.7 lacs being on account of SOR, NB board not displayed.
2 | R022000002 | Kunwarpur | Jabalpur | NVDA | MJP | 2001-05-22 | DDM+C | 800 | RIDF Loan upto 10 crore | Report awaited
2 | R022000047 | Rampura | Raisen | WRD | MIS | 2001-05-01 | RO Official | 74.82 | RIDF Loan upto 10 crore | Project completed in March 01, PCR not received, irrigation not commenced, WUA not formed, top width of dam increased from 3-4.5 m, cost escalation Rs. 84.31 lacs was reported under ABCL components in Units I & II, revised AA not yet obtained).
2 | R022000049 | Nagri | Raisen | WRD | MIS | 2001-05-01 | RO Official | 54.38 | RIDF Loan upto 10 crore | Slow progress, project completing by 30/6/01 as against extended completion date of 31/3/01), Delay in LA, cost escalation of Rs. 87.18 lacs, NB board not displayed.
2 | R022000013 | Deorikheda | Rajgarh | WRD | MIS | 2001-04-28 | RO Official | 126.07 | RIDF Loan upto 10 crore | Work delayed due to slow execution of work, non-uniform boulder size used for pitching, boulder toe was disturbed at some places, downstream of dam needed dressing, vegetation had grown in canals, NB board not displayed
2 | R022000017 | Goghatpur | Rajgarh | WRD | MIS | 2001-04-28 | RO Official | 397.6 | RIDF Loan upto 10 crore | Slow progress, difficulty in obtaining black cotton soil, delay in LA & fixing agency, cost escalation Rs. 11.51 lacs on account of increase in cost of masonry, LBC originally proposed was dropped, TS for RBC not obtained.
2 | R022000014 | Pipliya | Rajgarh | WRD | MIS | 2001-04-27 | RO Official | 390.27 | RIDF Loan upto 10 crore | Cost escalation Rs. 100 lacs reported on account of LA and increase in structures, slow progress, delay in LA, TS, pitching disturbed at many places, turfing on downstream to be re-done, irrigation commenced in 250 ha by lift, NB board not displayed
2 | R022000015 | Banskheda | Rajgarh | WRD | MIS | 2001-04-27 | RO Official | 241.35 | RIDF Loan upto 10 crore | Slow progress, cost escalation Rs.65.31 lacs on account of LA, delay in LA, the project likely to be completed by June 02 as against the due date of March 01, alignment of RBC not approved, lining of canals not undertaken.
2 | R022000016 | Tandikhurd | Rajgarh | WRD | MIS | 2001-04-27 | RO Official | 139.79 | RIDF Loan upto 10 crore | Slow progress, delay in LA, contractor problem, project likely to be completed by March 02 as against due date of March 01, pitching stones used not of uniform size, flush bar was damaged at two locations needing repairy), NB board not displayed.
2 | R022000018 | Chamleshwar | Neemuch | WRD | MIS | 2001-04-25 | RO Official | 894.45 | RIDF Loan 10.01-24.99 crore | 45% headwork and 50% canal completed, delay in LA/tendering/budget allocation, project likely to be completed by 31/3/02 as against extended completion date of 31/3/01, cost escalation Rs. 775.40 lacs, NB board not displayed.
2 | R022000019 | Dasani | Neemuch | WRD | MIS | 2001-04-25 | RO Official | 85.43 | RIDF Loan upto 10 crore | Project completed, the cost escalation of Rs. 25.72 lacs was mainly on account of land acquisition.
2 | R022000054 | Roopnath | Katni | WRD | MIS | 2001-04-16 | RO Official+C | 85.81 | RIDF Loan upto 10 crore | Refer to Annexure I, observations of technical nature, time overrun likely, cost overrun likely, NB board not displayed
2 | R022000053 | Birmawal | Ratlam | WRD | MIS | 2001-04-10 | DDM | 179.72 | RIDF Loan upto 10 crore | Project completed, PCR however not yet received
2 | R022000028 | Girdha | Alirajpur | WRD | MIS | 2001-03-27 | DDM | 27.62 | RIDF Loan upto 10 crore | Owing to drought, limited water stored in tank, the department to ensure that there is no excessive loss of water through seepage in the canals and that there is no soil erosion due to flow of water down the spill channel.
2 | R022000035 | Mandvi | Betul | WRD | MIS | 2001-03-27 | DDM+C | 118.34 | RIDF Loan upto 10 crore | Deviation from sanctioned plan, time overrun likely, observations of technical nature, delay in land acquisition, delay on account of land acquisition, cost overrun likely (Refer to annexure VI)
2 | R022000036 | Jitudhana | Betul | WRD | MIS | 2001-03-27 | DDM+C | 109.75 | RIDF Loan upto 10 crore | Observations of technical nature, delay in land acquisition/delay on account of land acquisition, cost overrun likely (Refer to annexure VIII)
2 | R022000026 | Jhora no.2 | Alirajpur | WRD | MIS | 2001-03-26 | DDM | 57 | RIDF Loan upto 10 crore | 35% of earthwork in Unit II remained incomplete, limited water accumulated in tank owing to drought, the department to ensure no excessive loss of water through seepage.
2 | R022000027 | Mehni | Alirajpur | WRD | MIS | 2001-03-26 | DDM | 78.94 | RIDF Loan upto 10 crore | Funds constraints, slow progress, project likely to be completed by June 01 as against due date of March 01), excessive loss of water through seepage in canals and soil erosion due to flow of water down the spill channel).
2 | R022000056 | Mordongri | Chhindwara | WRD | MIS | 2001-03-25 | DDM | 159.52 | RIDF Loan upto 10 crore | Project complete except dressing of canal near spill channel, two wing walls at nalah for passing canal at 121 chain for preventing nalah water and silt entering into canal are necessary. PCR may be submitted after completion of the structure
2 | R022000024 | Anand Khedi | Dhar | WRD | MIS | 2001-03-23 | DDm | 121.86 | RIDF Loan upto 10 crore | Project almost complete, irrigation commenced (516 ha under irrigation, management of the project handed over to WUA in June 00)
2 | R022000038 | Mankui | Badwani | WRD | MIS | 2001-03-22 | RO Official+C | 40.41 | RIDF Loan upto 10 crore | Deviations from sanctioned plan, observations of technical nature (Refer to annexure IV)
2 | R022000005 | Aniray | Ashoknagar | WRD | MIS | 2001-03-21 | DDM | 87.8 | RIDF Loan upto 10 crore | Time overrun likely(project likely to be completed only by 30/6/01 as against the extended due date of 31/3/01), masonry (30%) and earthwork (20%) in unit-II pending, cost overrun likely (on account of land acquisition and masonry work in Unit-I)
2 | R022000061 | Umaria Dalel | Chhindwara | WRD | MIS | 2001-03-18 | DDM | 155.81 | RIDF Loan upto 10 crore | Slow progress of canal work, delay in land acquisition for canal work (farmers not cooperating as payment of land compensation is pending for long), time overrun likely (project likely to be completed by March 2002 as against the due date of March 01)
2 | R022000055 | Kohpani | Chhindwara | WRD | MIS | 2001-03-14 | DDM+C | 117.71 | RIDF Loan upto 10 crore | Observations of technical nature,delay in land acquisition, delay on account of land acquisition,cost overrun likely, (Refer to annexure VIII)
2 | R022000025 | Hirapur | Alirajpur | WRD | MIS | 2001-03-09 | DDM | 63.27 | RIDF Loan upto 10 crore | Project completed, limited water stored in tank owing to drought, NB board not displayed, seepage in the canals and soil erosion due to flow of water down the spill channel.
2 | R022000043 | Teergarh | Damoh | WRD | MIS | 2001-02-24 | RO Official | 55.47 | RIDF Loan upto 10 crore | Cost overrun due to changes in design/SOR, slow progress, project likely to be completed by June 02 as against due date of March 01.
2 | R022000042 | Kalapani | Damoh | WRD | MIS | 2001-02-23 | RO Official | 139 | RIDF Loan upto 10 crore | Deviation from design and implication on cost not advised to NABARD, project likely to be completed by June 01 as against due date of 31/3/01), No provision for lining of canal has been made.
2 | R022000002 | Kunwarpur | Jabalpur | NVDA | MJP | 2001-02-22 | DDM | 800 | RIDF Loan upto 10 crore | Delay in land acquisition. (2) Time overrun likely (project likely to spell over beyond the extended due date of 31/3/01) (3) NB board not displayed. (4) Unsatisfactory quality of work in respect of some structures.
2 | R022000004 | Rajeev sagar | Guna | WRD | MIS | 2001-02-16 | DDM | 1277.94 | RIDF Loan 10.01-24.99 crore | Slow progress of work in the initial stages, time overrun likely (project likely to be completed by 30/6/2001 as against the due date of 31 March 2001), cost escalation reported
2 | R022000001 | Khajuri | Jabalpur | NVDA | MJP | 2001-02-15 | DDM | 1600 | RIDF Loan 10.01-24.99 crore | Delay in land acquisition (for canals), time overrun likely (project likely to spill over beyond the extended due date of 31/3/01), NB board not displayed
2 | R022000002 | Kunwarpur | Jabalpur | NVDA | MJP | 2001-02-15 | DDM | 800 | RIDF Loan upto 10 crore | Delay in land acquisition (for canals), time overrun likely (project likely to spill over beyond the extended due date of 31/3/01), NB board not displayed
2 | R022000001 | Khajuri | Jabalpur | NVDA | MJP | 2001-01-25 | DDM | 1600 | RIDF Loan 10.01-24.99 crore | Time overrun likely(project to spill over beyond the extended due date of31/3/01), delay in land acquisition for canal work, NB board not displayed.
2 | R022000046 | Pondi | Shahdol | WRD | MIS | 2001-01-16 | DDM | 34.69 | RIDF Loan upto 10 crore | Slow progress of work, NB board not displayed, Progress need to be monitored. Likely completion by June 2001.
2 | R022000022 | Sarvankheda | Ujjain | WRD | MIS | 2001-01-15 | DDM | 101.65 | RIDF Loan upto 10 crore | Slow progress of work due to delay in land acquisition and contractor problem, revised cost proposal submitted for approval. The WRD should take up matter with concerned authorities to solve LA problem expeditiously.
2 | R022000058 | Mann | Dhar | NVDA | MJP | 2001-01-04 | DDM | 4400 | RIDF Loan 25 crore & above | Work under progress but the project may be delayed upto March 2003, efforts are needed for early completion of the project.
2 | R022000060 | Gora Feeder | Chattarpur | WRD | MIS | 2000-11-29 | RO Official+C | 88.58 | RIDF Loan upto 10 crore | Cost overrun likely, time overrun likely, test reports for morter/concrete were not available at site/office, suggestions of technical nature(refer to annexure I)
2 | R022000057 | Ahilo | Singrauli | WRD | MIS | 2000-11-24 | RO Official+C | 167.23 | RIDF Loan upto 10 crore | Time overrun likely, funds constraints, there is no inspection vehicle in the division, suggestions of technical nature (refer to annexure V)
2 | R022000063 | Depalpur | Indore | WRD | MIS | 2000-11-23 | DDM | 36.61 | RIDF Loan upto 10 crore | PCR verified, NB board not displayed, seepage, unsatisfactory maintenance, service road dug at many places, cross-regulators need proper maintenance, gates are broken, water does not reach the tail end of the project, WUA not effective
2 | R022000003 | Hareri | Narsinghpur | NVDA | MJP | 2000-11-21 | DDM | 1850 | RIDF Loan 10.01-24.99 crore | Time overrun likely, NB board not displayed
2 | R022000012 | Imlikheda | Shajapur | WRD | MIS | 2000-11-18 | RO Official | 71.03 | RIDF Loan upto 10 crore | Construction of flush bar needs to be done again, big voids are left in pitching work, on downstream arrangement for measurement of seepage in cross drains not made, proper compaction and dressing is needed to give the required slope to the tank
2 | R022000010 | Shyampura | Shajapur | WRD | MIS | 2000-11-17 | RO Official | 127.5 | RIDF Loan upto 10 crore | Project completed, no arrangement made for measurement of seepage, installation of V-notches may be taken up, turfing and dressing of earthwork may be done on downstream side of the tank, MPEB may remove HT wire located on left side of tank
2 | R022000011 | Khadi | Shajapur | WRD | MIS | 2000-11-17 | RO Official | 91.68 | RIDF Loan upto 10 crore | Project completed, in spill channel outfall portion towards nallah needs review, excavation of spill channel may be required, on downstream arrangement for measurement of seepage in crossed drains not made, installation of V-notches may be taken up
2 | R022000053 | Birmawal | Ratlam | WRD | MIS | 2000-10-16 | DDM | 179.72 | RIDF Loan upto 10 crore | Land acquisition problem
2 | R022000055 | Kohpani | Chhindwara | WRD | MIS | 2000-10-16 | DDM | 117.71 | RIDF Loan upto 10 crore | Work progress slow, time overrun likely, unsatisfactory quality of work, visit by quality control department of the govt./RO official and consultant suggested for several shortcomings in work completed
2 | R022000056 | Mordongri | Chhindwara | WRD | MIS | 2000-10-15 | DDM | 159.52 | RIDF Loan upto 10 crore | Unsatisfactory quality of work (canals, chute falls), land acquisition problem for left over canal work
2 | R022000006 | Bhaisatori | Guna | WRD | MIS | 2000-10-11 | DDM | 439.01 | RIDF Loan upto 10 crore | Time overrun likely, NB board not displayed
2 | R022000061 | Umaria Dalel | Chhindwara | WRD | MIS | 2000-09-29 | DDM | 155.81 | RIDF Loan upto 10 crore | Work progress slow, time overrun likely, land acquisition problem for canals, spill channel needs cleaning
2 | R022000046 | Pondi | Shahdol | WRD | MIS | 2000-09-13 | DDM | 34.69 | RIDF Loan upto 10 crore | Contractor problem (slow execution of work, restarted the work in August 00), project is likely to be completed only by the extended completion date of 31/3/01, NB board not displayed.
2 | R022000022 | Sarvankheda | Ujjain | WRD | MIS | 2000-07-06 | DDM | 101.65 | RIDF Loan upto 10 crore | Contractor problem, delay in land acquisition.
2 | R022000023 | New Rajnal | Dewas | WRD | MIS | 2000-04-20 | DDM | 200.1 | RIDF Loan upto 10 crore | Permission for closure of nallah portion was obtained and the same was being taken up in October 2000.
2 | R022000058 | Mann | Dhar | NVDA | MJP | 2000-04-20 | DDM | 4400 | RIDF Loan 25 crore & above | Dam work could not be raised as rehabilitation of the villages was not done.
2 | R022000037 | Garaghat | Khargone | WRD | MIS | 2000-03-07 | DDM | 85.11 | RIDF Loan upto 10 crore | Project completed, irrigation commenced in the entire command area of 17 ha, handing over of operations and maintenance of project to WUA needed to be expedited.
2 | R022000007 | Kunwarpura | Guna | WRD | MIS |  |  | 55.97 | RIDF Loan upto 10 crore
2 | R022000020 | Mundri | Mandsaur | WRD | MIS |  |  | 119.8 | RIDF Loan upto 10 crore
2 | R022000021 | Indergarh | Mandsaur | WRD | MIS |  |  | 343.62 | RIDF Loan upto 10 crore
2 | R022000034 | Sukta (Replace.) | Khandwa | WRD | MIS |  |  | 370.3 | RIDF Loan upto 10 crore
2 | R022000039 | Palasi | Khargone | WRD | MIS |  |  | 32.36 | RIDF Loan upto 10 crore
2 | R022000040 | Ambak nala | Khargone | WRD | MIS |  |  | 1103.18 | RIDF Loan 10.01-24.99 crore
2 | R022000044 | Amha | Panna | WRD | MIS |  |  | 334.8 | RIDF Loan upto 10 crore
2 | R022000045 | Madhar | Shivpuri | WRD | MIS |  |  | 519.41 | RIDF Loan upto 10 crore
2 | R022000048 | Jojharpur | Raisen | WRD | MIS |  |  | 124.91 | RIDF Loan upto 10 crore
2 | R022000050 | Upper Palakmati | Raisen | WRD | MIS |  |  | 438.09 | RIDF Loan upto 10 crore
2 | R022000059 | Bhangarnala | Balaghat | WRD | MIS |  |  | 58.55 | RIDF Loan upto 10 crore
2 | R022000064 | Birul | Khargone | WRD | MIS |  |  | 62.96 | RIDF Loan upto 10 crore
3 | R032000219 | Parda | Neemuch | WRD | MIS | 2006-03-16 | DDM | 266.49 | RIDF Loan upto 10 crore | PCR verified. Project complete in all respects
3 | R032000225 | Manori | Seoni | WRD | MIS | 2006-03-10 | DDM | 263.61 | RIDF Loan upto 10 crore | Project is complete and WUA formed. Lesser funds were made available for maintenance.
3 | r032000079 | Tawa Bridge Itarsi Mandi Road | Hoshangabad | PWD | Road | 2006-01-11 | DDM | 48.33 | RIDF Loan upto 10 crore | PCR verified. Project completed in March 2003. Maintenance is poor.
3 | R032000218 | Amarpura | Neemuch | WRD | MIS | 2005-05-25 | DDM | 340.67 | RIDF Loan upto 10 crore | The progress is slow on account of land acquisition problem. The design of the project was also required to be altered due to local geological conditionss. NABARD Board was not displayed.
3 | R032000273 | Kalmoda | Jhabua | WRD | MIS | 2005-03-02 | DDM | 76.83 | RIDF Loan upto 10 crore | Only 30% of the earthwork and 100% of canal work is completed. 9 hectares of forest land was coming under catchment area, as such earthwork is held up. NABARD Board was not displayed.
3 | R032000213 | Hasanpur | Burhanpur | WRD | MIS | 2005-02-28 | DDM | 56.15 | RIDF Loan upto 10 crore | Projects is completed. Saving is reported. WAU is formed
3 | R032000013 | Khedi | Khargone | WRD | MIS | 2005-02-21 | DDM | 41.53 | RIDF Loan upto 10 crore | Report yet to be submitted.
3 | R032000093 | Siptan d/s | Khargone | WRD | MIS | 2005-02-09 | DDM | 220.49 | RIDF Loan upto 10 crore | head work is incomplete. bent noticed in iron pillars of gate due to high velocity of water. The problem is required to be discussed with the experts and take remedial measure. Likely dt of completion of project is 31.3.06.
3 | R032000093 | Siptan d/s | Khargone | WRD | MIS | 2005-02-09 | DDM | 220.49 | RIDF Loan upto 10 crore | head work is incomplete as iron gates of spill washed away during monsoon. bent noticed in iron pillars of gate due to high velocity of water. Likely date of completion of project is 31.03.06
3 | R032000218 | Amarpura | Neemuch | WRD | MIS | 2005-01-17 | DDM | 340.67 | RIDF Loan upto 10 crore | The work is progressing with a slow pace owing to the problems of land acquisition. The design of the project was also changed due to local conditions.
3 | R032000104 | Pamli - Guramkhedi Road | Hoshangabad | PWD | Road | 2004-10-09 | DDM | 109.13 | RIDF Loan upto 10 crore | No monitoring was done by E.E. The sanctioned length of the road is 12.2 kms but actual required is for 12.6 kms.
3 | R032000103 | Chourahat - Fortala Road | Hoshangabad | PWD | Road | 2004-10-09 | DDM | 53.3 | RIDF Loan upto 10 crore | Project completed in June 2004. Advised to PWD to send PCR in proper format.
3 | R032000055 | Shobhapur-Rewa Bankhedi | Hoshangabad | PWD | Road | 2004-10-04 | DDM | 78.38 | RIDF Loan upto 10 crore | The project has been completed in May 2004. PCR not sent in proper format. The quality of the work is not satisfactory.
3 | R032000002 | Maheri | Sagar | WRD | MIS | 2004-09-16 | DDM | 76.58 | RIDF Loan upto 10 crore | The work relating to unit I is completed,however the canal work has not completed. In case of unit II the major problem is land acquisition.
3 | R032000152 | Ashoknagar Aron Road to Panwari Hat | Guna | PWD | Road | 2004-08-18 | DDM | 64.86 | RIDF Loan upto 10 crore | Work actually completed on 23.12.2001.No maintenance since last three years. The present condition of the road is not good.
3 | R032000250 | Sirsi | Guna | WRD | MIS | 2004-03-24 | DDM | 45.91 | RIDF Loan upto 10 crore | WUA not formed. NB board not displayed.
3 | R032000136 | Narayana-Panbihar Road | Ujjain | PWD | Road | 2004-03-16 | DDM | 53.25 | RIDF Loan upto 10 crore | BT not done on km5 to km8.NB board not displayed.
3 | R032000137 | Mahidpur Semaliya Road | Ujjain | PWD | Road | 2004-03-16 | DDM | 46.98 | RIDF Loan upto 10 crore | BT not done on 400m of 9th km. NB board not displayed on other side of the road.
3 | R032000026 | Dhudhakhedi-Satalkhedi | Mandsaur | PWD | Road | 2004-03-09 | DDM | 33.06 | RIDF Loan upto 10 crore | Poor maintainance.
3 | R032000093 | Siptan d/s | Khargone | WRD | MIS | 2004-02-24 | DDM | 220.49 | RIDF Loan upto 10 crore | Slow progress- masonry& earth work of Unit -II yet to be completed.
3 | R032000013 | Khedi | Khargone | WRD | MIS | 2004-02-21 | DDM | 41.53 | RIDF Loan upto 10 crore | Contractor problem- work stopped by contractor. Slow progress-masonry & earth work not completed Time overrun- project likely to be completed June 04 as against March 04.
3 | R032000057 | Banmor-Sanichra-Rithora | Morena | PWD | Road | 2004-02-15 | DDM | 53.42 | RIDF Loan upto 10 crore | Work done is satisfactory.Road has also sunked at few places on CDs as the hume pipes have broken due to heavy vehicles passing on the road.
3 | R032000057 | Banmor-Sanichra-Rithora | Morena | PWD | Road | 2004-02-15 | DDM | 53.42 | RIDF Loan upto 10 crore | Road on CD 17/10 has been washed off. The BT seems to be very thin. NABARD Board has not displayed.
3 | r032000075 | Ashoknagar Thubon Road | Guna | PWD | Road | 2004-02-04 | DDM | 65.2 | RIDF Loan upto 10 crore | Poor maintainance.NB board not displayed.
3 | r032000016 | Mandvi | Chhindwara | WRD | MIS | 2004-02-01 | DDM | 495.42 | RIDF Loan upto 10 crore | WUA not formed.
3 | R032000016 | Mandvi | Chhindwara | WRD | MIS | 2004-02-01 | DDM | 495.42 | RIDF Loan upto 10 crore | Project has been completed in all respect and utilisation is 100% in the first year itself.
3 | r032000264 | Akbarpur | Vidisha | WRD | MIS | 2004-01-28 | DDM | 43.24 | RIDF Loan upto 10 crore | Delay in tendering for unit II and III. NB Board not displayed, power problem - MPSEB connection not received so far.
3 | r032000154 | Ashoknagar Aron Road upto Sindh river | Guna | PWD | Road | 2004-01-19 | DDM | 66.64 | RIDF Loan upto 10 crore | Poor maintainance. NB board not displayed.
3 | r032000159 | Shadora Naisari Road upto Dungsara | Guna | PWD | Road | 2004-01-19 | DDM | 25.94 | RIDF Loan upto 10 crore | Poor maintainance.NB board not displayed.
3 | r032000153 | Sarsakhedi Naisarai Road | Guna | PWD | Road | 2004-01-19 | DDM | 96.3 | RIDF Loan upto 10 crore | Poor maintainance.NB board not displayed.
3 | R032000072 | Bichhua Khamarpani Road | Chhindwara | PWD | Road | 2004-01-18 | DDM | 165.47 | RIDF Loan upto 10 crore | Poor maintenance
3 | R032000007 | Indira Gandhi | Dhar | WRD | MIS | 2004-01-15 | DDM | 284.51 | RIDF Loan upto 10 crore | Branch canal is not provided upto 3000km so main canal is broken take water to field.
3 | r032000073 | Chandan Gaon Meghdon Road | Chhindwara | PWD | Road | 2004-01-14 | DDM | 47.4 | RIDF Loan upto 10 crore | Sleepage betweem 3/2 -3/4 KM, NB Board not displayed.
3 | R032000073 | Chandan Gaon Meghdon Road | Chhindwara | PWD | Road | 2004-01-14 | DDM | 47.4 | RIDF Loan upto 10 crore | Work is physically completed and quality of work is poor.NB board not displayed.
3 | r032000076 | Teonda Khurai via Pathari Road | Vidisha | PWD | Road | 2004-01-13 | DDM | 279.96 | RIDF Loan upto 10 crore | Most of the part of entire road are damaged.
3 | r032000022 | Kaithuli Approach Rd. | Mandsaur | PWD | Road | 2004-01-09 | DDM | 60.04 | RIDF Loan upto 10 crore | Poor maintenance, NB Board not displayed.
3 | r032000213 | Hasanpur | Burhanpur | WRD | MIS | 2004-01-08 | DDM | 56.15 | RIDF Loan upto 10 crore | WUA not formed, main canal needs repairs
3 | R032000281 | Pulpuldoh | Chhindwara | WRD | MIS | 2004-01-08 | DDM | 240.7 | RIDF Loan upto 10 crore | WUA not formed.NB board not displayed.
3 | r032000275 | Dokarwani | Jhabua | WRD | MIS | 2004-01-08 | DDM | 105.43 | RIDF Loan upto 10 crore | WUA not formed. NB board not displayed.
3 | R032000271 | Mansarovar | Dhar | WRD | MIS | 2004-01-08 | DDM | 414.52 | RIDF Loan upto 10 crore | Due to heavy rain main canal ,bank canal earth was flushed away resulted in water supply problem to the Bajadi area.
3 | R032000281 | Pulpuldoh | Chhindwara | WRD | MIS | 2004-01-08 | DDM | 240.7 | RIDF Loan upto 10 crore | Work is physically completed and quality of the work is good.
3 | r032000077 | Andiakala Pachama Road | Vidisha | PWD | Road | 2004-01-06 | DDM | 124.1 | RIDF Loan upto 10 crore | NB Board not displayed, improper maintenance.
3 | r032000272 | Sajwani | Jhabua | WRD | MIS | 2004-01-06 | DDM | 71.95 | RIDF Loan upto 10 crore | WUA not formed.NB board not displayed.
3 | R032000223 | Gudbehli | Ratlam | WRD | MIS | 2004-01-06 | DDM | 33.12 | RIDF Loan upto 10 crore | project is completed.
3 | R032000215 | Karam | Dhar | WRD | MIS | 2004-01-02 | DDM | 448.55 | RIDF Loan upto 10 crore | Quality of the work is satisfactory.
3 | R032000057 | Banmor-Sanichra-Rithora | Morena | PWD | Road | 2003-11-12 | RO Official | 53.42 | RIDF Loan upto 10 crore | The road is in very bad shape. Poor maintenence of road
3 | R032000248 | Anandpur-Bhagawantpur | Vidisha | PWD | Road | 2003-11-06 | DDM | 92.14 | RIDF Loan upto 10 crore | Some portion of road is damaged due to heavy rain.
3 | R032000263 | Bhagwantpur | Vidisha | WRD | MIS | 2003-10-22 | RO Official | 37.47 | RIDF Loan upto 10 crore | Progress is very slow due to contractor problem.
3 | R032000225 | Manori | Seoni | WRD | MIS | 2003-10-15 | RO Official | 263.61 | RIDF Loan upto 10 crore | Balance work in hear work is in progress.
3 | R032000038 | Lateri-Shamsabad | Vidisha | PWD | Road | 2003-09-18 | DDM | 298.23 | RIDF Loan upto 10 crore | Project is completed.
3 | R032000077 | Andiakala Pachama Road | Vidisha | PWD | Road | 2003-09-02 | DDM | 124.1 | RIDF Loan upto 10 crore | Quality of work is poor. NABARD Board is not displayed.
3 | R032000246 | Maharajpur Shahajpur | Sagar | PWD | Road | 2003-03-13 | DDM | 131.93 | RIDF Loan upto 10 crore | Unsatisfactory quality of work (the road condition from Maharajpur side has started to deteriorate). NB board not displayed in proper format.
3 | R032000034 | Kesli-ISahaspur | Sagar | PWD | Road | 2003-03-11 | DDM | 79.36 | RIDF Loan upto 10 crore | NB board not displayed in proper format.
3 | R032000105 | Sangakheda - Fortala Road | Hoshangabad | PWD | Road | 2003-03-10 | DDM | 87.25 | RIDF Loan upto 10 crore | Inadequate monitoring mechanism (EE and above the rank of EE have not visited the site).
3 | R032000213 | Hasanpur | Burhanpur | WRD | MIS | 2003-02-18 | DDM | 56.15 | RIDF Loan upto 10 crore | Time overrun (progress of masonry work related to sluice is 60%, construction of flush bar work yet to commence).
3 | R032000187 | Nargarh 3/2-4 | Datia | PWD | Bridge | 2003-02-04 | RO Official | 9.34 | RIDF Loan upto 10 crore | Change in technical design (increase in length of approach road from 200 to 365 m. Cost overrun (cost overrun by Rs. 9.98 lakh). Project completed. NB board not displayed in proper format.
3 | R032000241 | Baktara-Barkach | Raisen | PWD | Road | 2003-01-22 | RO Official | 27.57 | RIDF Loan upto 10 crore | Tendering done for 5 times. Repair work done which has led to time overrun and cost overrun. At 6/2, 7/7-7/8,7/1-7/2 potholes have been observed. BT has not been done at Km 4/0-5/10 km. This has led to time and cost overrun. NB board not displayed.
3 | R032000245 | Gugalwara Dehrikalan Sankheda | Raisen | PWD | Road | 2003-01-22 | RO Official | 62.4 | RIDF Loan upto 10 crore | Contractor problem. In Dehri Kalan village, LA done without sanction. Potholes observed at km 2/4. Pipelines were laying across road, WBM and BT yet to be done, No work has been done upto 50 m from Km 6/2. NB board not displayed.
3 | R032000065 | Nirandarpur | Sagar | WRD | MIS | 2002-11-26 | DDM | 236.98 | RIDF Loan upto 10 crore | LA award has not been passed. The dept. is keeping in touch with SDM Deori for LA cases. Forest Dept. has stopped the work of felling of trees in view of Supreme Court's decision, hence contractor for Unit I has left the side.
3 | R032000066 | Jhiria | Sagar | WRD | MIS | 2002-11-26 | DDM | 221.74 | RIDF Loan upto 10 crore | Contractor for Unit I unable to bring machinery. Further, LA for canal has suffered as award has not been passed by Revenue Officials. New tender to be called for Unit I depending upon the progress. Contractor problem (contractors quoting lower rates).
3 | R032000135 | Padarkheda | Shivpuri | WRD | MIS | 2002-10-22 | DDM | 80.92 | RIDF Loan upto 10 crore | Slow work progress. Tender not invited for appraoch road. NB board not displayed
3 | R032000079 | Tawa Bridge Itarsi Mandi Road | Hoshangabad | PWD | Road | 2002-10-18 | OIC+C | 48.33 | RIDF Loan upto 10 crore | Main distribution line for water supply to Itarsi town passes alongside road with huge leakage, thus damaging the road.
3 | R032000124 | Sonasawari - Sawalkheda Road | Hoshangabad | PWD | Road | 2002-10-18 | OIC+C | 100.46 | RIDF Loan upto 10 crore | Land owners were not allowing excavation of earth for subgrade as well as demarcation of land due to non-receipt of LA compensation. NB board not displayed.
3 | R032000038 | Lateri-Shamsabad | Vidisha | PWD | Road | 2002-10-10 | DDM | 298.23 | RIDF Loan upto 10 crore | Slow work progress. Test report not submitted by QC dept. A few sections of road in damaged condition. NB board not displayed.
3 | R032000076 | Teonda Khurai via Pathari Road | Vidisha | PWD | Road | 2002-10-09 | DDM | 279.96 | RIDF Loan upto 10 crore | Slow work progress. Monitoring mechanism not satisfactory. Test report not submitted by QC dept. Road damaded in most of sections. A patch of about 2 km near Pathari village not yet undertaken by contractor.
3 | R032000138 | Kaytha-Bhatani Road | Ujjain | PWD | Road | 2002-09-25 | DDM | 56.1 | RIDF Loan upto 10 crore | Quality of road not satisfactory. Flanking is not proper at several places. In Km 16 a railway crossing gate is constructed and about 10 m of road has been damaged.
3 | R032000139 | Talod-Fatiabad Road | Ujjain | PWD | Road | 2002-09-25 | DDM | 65.55 | RIDF Loan upto 10 crore | PCR Verification. Work of very poor quality. The entire length of the road is uneven and no. of potholes have surfaced. BT has not been done from 9 km to 10.8 km and WBM done is uneven. A big tank has been constructed by the side of the road (4th km).
3 | R032000199 | Korni 139/6 | Hoshangabad | PWD | Bridge | 2002-08-02 | OIC+C | 88.52 | RIDF Loan upto 10 crore | (Summary report issued.) NB board to be displayed. To ensure simultaneous completion of bridge & appraoches, it is suggested to have a single tender for both.
3 | R032000058 | Nurabad-Padmawali-Barham | Morena | PWD | Road | 2002-07-19 | DDM | 42.69 | RIDF Loan upto 10 crore | NB board not displayed. Completed, except a small patch of 10-12 m after a CD wor, which is left out. Road has been cut at many places. A few pot holes to be rectified.
3 | R032000180 | Kanhan 4/6 | Chhindwara | PWD | Bridge | 2002-06-08 | DDM | 141.2 | RIDF Loan upto 10 crore | Slow progress (not completed by original date). Contractor problem (slow due to late payments).
3 | R032000023 | Lodkiya-Kundaliya Road | Neemuch | PWD | Road | 2002-05-29 | RO Official+C | 45.32 | RIDF Loan upto 10 crore | BT worn out at no. of places. Side berms to be done as per specifications.
3 | R032000024 | Manasa-Morwan Rd. | Neemuch | PWD | Road | 2002-05-28 | RO Official+C | 77.29 | RIDF Loan upto 10 crore | Surface is undulating. BT worn out at no. of places. Side berms to be done as per specification.
3 | R032000092 | Adhampur | Khargone | WRD | MIS | 2002-05-22 | DDM | 225.9 | RIDF Loan upto 10 crore | Completed. WUA to be formed.
3 | R032000276 | Chandgarh | Khargone | WRD | MIS | 2002-05-22 | DDM | 242.87 | RIDF Loan upto 10 crore | Completed. WUA to be formed
3 | R032000016 | Mandvi | Chhindwara | WRD | MIS | 2002-05-21 | DDM | 495.42 | RIDF Loan upto 10 crore | Slow progress (scheduled to be comleted by 3/2000, but work on railway crossing for canal not done). Contractor problem (contractor not executing work on railway crossing for canal)
3 | R032000027 | Amarawad-Bharkatch | Raisen | PWD | Road | 2002-05-16 | OIC+C | 91.86 | RIDF Loan upto 10 crore | Report issued to PWD
3 | R032000242 | Chainpur Gaganwada | Raisen | PWD | Road | 2002-05-16 | OIC+C | 64.45 | RIDF Loan upto 10 crore | Report issued to PS,PWD
3 | R032000218 | Amarpura | Neemuch | WRD | MIS | 2002-05-04 | RO Official+C | 340.67 | RIDF Loan upto 10 crore | As per annexure.
3 | R032000219 | Parda | Neemuch | WRD | MIS | 2002-05-04 | RO Official+C | 266.49 | RIDF Loan upto 10 crore | As per annexure
3 | R032000192 | Sehrao 9/6 | Rewa | PWD | Bridge | 2002-05-03 | DDM | 11.21 | RIDF Loan upto 10 crore | Completed. Arrangement for maintenance to be ensured.
3 | R032000216 | Achhalgarh | Guna | WRD | MIS | 2002-04-30 | DDM | 34.23 | RIDF Loan upto 10 crore | Completed
3 | R032000106 | Rengatola - Changera - Beni Road | Balaghat | PWD | Road | 2002-04-26 | RO Official | 130.88 | RIDF Loan upto 10 crore | Completed. Time overrun of 1 year due to delay in fixing agency.
3 | R032000191 | Sehrao 6/8 | Rewa | PWD | Bridge | 2002-04-25 | DDM | 16.7 | RIDF Loan upto 10 crore | Completed. PCR verified. Arrangements for maintenance may be ensured.
3 | R032000004 | Khairana | Sagar | WRD | MIS | 2002-04-19 | AFC(Agents) | 127.98 | RIDF Loan upto 10 crore | NB board to be displayed. Slow progress (project sanctioned in 97-98 is still incomplete).
3 | R032000038 | Lateri-Shamsabad | Vidisha | PWD | Road | 2002-04-19 | DDM | 298.23 | RIDF Loan upto 10 crore | Slow progress (project sanctioned in 98-99 is still incomplete.
3 | R032000077 | Andiakala Pachama Road | Vidisha | PWD | Road | 2002-04-19 | DDM | 124.1 | RIDF Loan upto 10 crore | Road is damaged at few places.
3 | R032000248 | Anandpur-Bhagawantpur | Vidisha | PWD | Road | 2002-04-19 | DDM | 92.14 | RIDF Loan upto 10 crore | Road is damaged at few places.
3 | R032000223 | Gudbehli | Ratlam | WRD | MIS | 2002-04-18 | DDM | 33.12 | RIDF Loan upto 10 crore | LA problem (payment not made to land owners). Completed.
3 | R032000224 | Kolwakhedi | Ratlam | WRD | MIS | 2002-04-17 | DDM | 475.61 | RIDF Loan upto 10 crore | NB board not displayed.
3 | R032000076 | Teonda Khurai via Pathari Road | Vidisha | PWD | Road | 2002-04-16 | DDM | 279.96 | RIDF Loan upto 10 crore | Slow progress (progress sanctioned in 98-99 still incomplete). NB board not displayed.
3 | R032000263 | Bhagwantpur | Vidisha | WRD | MIS | 2002-04-16 | DDM | 37.47 | RIDF Loan upto 10 crore | Slow progress (project sanctioned in 98-99 is still incomplete, inadequate attention by dept.)
3 | R032000264 | Akbarpur | Vidisha | WRD | MIS | 2002-04-16 | DDM | 43.24 | RIDF Loan upto 10 crore | Slow progress (project sanctioned in 98-99 is still incomplete, inadequate attention by dept.)
3 | R032000124 | Sonasawari - Sawalkheda Road | Hoshangabad | PWD | Road | 2002-04-13 | DDM | 100.46 | RIDF Loan upto 10 crore | Inadequate monitoring by department (monitoring by officers of the rank of EE & above not done), likely time overrun (may be completed only by March 2003). Likely cost overrun (side earth not available for filling),
3 | R032000103 | Chourahat - Fortala Road | Hoshangabad | PWD | Road | 2002-04-12 | DDM | 53.3 | RIDF Loan upto 10 crore | Slow progress (Although 2 years extension upto 12/2002 is given, progress is only about 30%), delay in tendering (no agency has been appointed still)
3 | R032000104 | Pamli - Guramkhedi Road | Hoshangabad | PWD | Road | 2002-04-12 | DDM | 109.13 | RIDF Loan upto 10 crore | progress is only about 30%), Inadequate monitoring by department (monitoring by officers of the rank of EE & above not done), Likely time overrun (works likely to be completed only by March 2003 against target date of December 2002)
3 | R032000272 | Sajwani | Jhabua | WRD | MIS | 2002-03-28 | DDM | 71.95 | RIDF Loan upto 10 crore | Slow progress (not completed within scheduled date of 3/2000). Forest clearance for EW required. NB board not displayed.
3 | R032000274 | Badibawadi | Jhabua | WRD | MIS | 2002-03-27 | DDM | 85.67 | RIDF Loan upto 10 crore | Slow progress (not completed within scheduled date of 3/2000). Forest clearance for EW required.
3 | R032000052 | Sandiya-Sahalwara | Hoshangabad | PWD | Road | 2002-03-23 | DDM | 24.73 | RIDF Loan upto 10 crore | Inadequate monitoring by department (monitoring by officers of the rank of EE & above not done)
3 | R032000054 | Shobhapur-Kharikalan | Hoshangabad | PWD | Road | 2002-03-23 | DDM | 34.68 | RIDF Loan upto 10 crore | Inadequate monitoring by department (monitoring by officers of the rank of EE & above not done), contractor problem (contractor not started the work)
3 | R032000273 | Kalmoda | Jhabua | WRD | MIS | 2002-03-23 | DDM | 76.83 | RIDF Loan upto 10 crore | Slow progress (not completed within scheduled date of 3/2000). Forest clearance for EW required.
3 | R032000275 | Dokarwani | Jhabua | WRD | MIS | 2002-03-20 | DDM | 105.43 | RIDF Loan upto 10 crore | Canal work in progress.
3 | R032000049 | Isharpur-Rani-Gohan | Hoshangabad | PWD | Road | 2002-03-16 | DDM | 20.13 | RIDF Loan upto 10 crore | Very slow progress (Although 2 years extension upto 12/2002 is given, progress is only about 30%), Delay in tendering (tenders not settled yet), Inadequate monitoring by department (monitoring by officers of the rank of EE & above not done)
3 | R032000051 | Paraswada-Doomar | Hoshangabad | PWD | Road | 2002-03-16 | DDM | 40.74 | RIDF Loan upto 10 crore | Slow progress (Although 2 years extension upto 12/2002 is given, progress is only about 30%), Contractor problem (contractor not started the work)
3 | R032000140 | Sitamau Jaora Road | Mandsaur | PWD | Road | 2002-02-27 | RO Official | 134.59 | RIDF Loan upto 10 crore | Delay in LA, change in design of two medium bridges approved by competent authority, Cost overrun on account of change in design, SOR, higher compensation for LA and tender premium).
3 | R032000050 | Kanhwar Punor Road | Hoshangabad | PWD | Road | 2002-02-22 | DDM | 37.37 | RIDF Loan upto 10 crore | Slow progress ((Although 2 years extension upto 12/2002 is given, progress is only about 80%), farmers are breaking the road to carry canal water to their fields and this adversely affects the life of road,
3 | R032000053 | Shobhapur-Bhatgaon | Hoshangabad | PWD | Road | 2002-02-22 | DDM | 27.21 | RIDF Loan upto 10 crore | Contractor problem, Slow progress, poor quality of work, farmers breaking road to carry canal water to fields, Inadequate monitoring by department (monitoring by officers of the rank of EE & above not done)
3 | R032000065 | Nirandarpur | Sagar | WRD | MIS | 2002-02-22 | DDM | 236.98 | RIDF Loan upto 10 crore | Nalla closure held up due to non-cutting of trees by forest dept.,land acquisition needs to be completed raely, NABARD board not displayed,no pucca approach road.
3 | R032000103 | Chourahat - Fortala Road | Hoshangabad | PWD | Road | 2002-02-22 | DDM | 53.3 | RIDF Loan upto 10 crore | Slow progress, delay in tendering, AA problem, farmers likely to break road to carry canal water to fields, Inadequate monitoring by department (monitoring by officers of the rank of EE & above not done)
3 | R032000002 | Maheri | Sagar | WRD | MIS | 2002-02-21 | DDM | 76.58 | RIDF Loan upto 10 crore | land acquisition under unit-II not cmpleted, MPEB high tension pole needs relocation,tender process for part of unit I and unit II needs to be expedited, slow execution of work by contractor.
3 | R032000079 | Tawa Bridge Itarsi Mandi Road | Hoshangabad | PWD | Road | 2002-02-21 | DDM | 48.33 | RIDF Loan upto 10 crore | Slow progress, road condition is very bad with pot-holes and jungle growth, sub-base and Gr-II thickness is not as per specification, monitoring by EE & above not done, Cost overrun likely (due to special repairs, jungle clearance, CD works etc.)
3 | R032000102 | Sangakheda- Satwasa Road | Hoshangabad | PWD | Road | 2002-02-21 | DDM | 34.26 | RIDF Loan upto 10 crore | Progress is only about 50%, CE's approval for realignment of road at Patni is pending), NB board not displayed, Inadequate monitoring by department (monitoring by officers of the rank of EE & above not done)
3 | R032000133 | Aari | Guna | WRD | MIS | 2002-01-23 | DDM | 96.17 | RIDF Loan upto 10 crore | Slow progress (not completed by target date of 31-3-02)
3 | R032000250 | Sirsi | Guna | WRD | MIS | 2002-01-23 | DDM | 45.91 | RIDF Loan upto 10 crore | Slow progress (not completed by target date of 31-3-02)
3 | R032000150 | Aron-Raghogarh Road | Guna | PWD | Road | 2002-01-15 | DDM | 27.3 | RIDF Loan upto 10 crore | Not visited actually. Work closed without completing the project (out of 3 km sanctioned only 2.65 km is executed).
3 | R032000153 | Sarsakhedi Naisarai Road | Guna | PWD | Road | 2002-01-15 | DDM | 96.3 | RIDF Loan upto 10 crore | For proper mainteannce of road, side berms are required.
3 | R032000003 | Gugrakhurd | Sagar | WRD | MIS | 2002-01-10 | DDM | 61.78 | RIDF Loan upto 10 crore | Sluice gates constructed prior to NB sanction are leaking and affecting the benefits
3 | R032000048 | Bhonkhedi(Gujarkhedi)Sonsarkhed | Hoshangabad | PWD | Road | 2002-01-10 | DDM | 67.5 | RIDF Loan upto 10 crore | Slow progress (Although 2 years extension upto 12/2002 is given, progress is only about 30%), Contractor problem (stopped work due to non-payment), Inadequate monitoring by department (monitoring by officers of the rank of EE & above not done)
3 | R032000055 | Shobhapur-Rewa Bankhedi | Hoshangabad | PWD | Road | 2002-01-09 | DDM | 78.38 | RIDF Loan upto 10 crore | Although 2 years extension upto 12/2002 is given, progress is only about 40%, contract terminated, Sub-base and Gr-II thickness is not as per specification, Inadequate monitoring by department (monitoring by officers of the rank of EE & above not done)
3 | R032000005 | Hinota Kharmau | Sagar | WRD | MIS | 2002-01-05 | DDM | 86.39 | RIDF Loan upto 10 crore | Slow progress (not completed within schedule date of 31-3-00)
3 | R032000004 | Khairana | Sagar | WRD | MIS | 2001-12-28 | DDM+C | 127.98 | RIDF Loan upto 10 crore | NB board not displayed. LA (LA funds deposited but acquisition not completed)
3 | R032000066 | Jhiria | Sagar | WRD | MIS | 2001-12-28 | DDM+C | 221.74 | RIDF Loan upto 10 crore | Slow progress (40% work done although prject should have been compelted by 3/2000, TS for Unit II not done, surveying not done)
3 | R032000063 | Ganesh ganj-Sunwara | Seoni | PWD | Road | 2001-12-27 | RO Official | 93.48 | RIDF Loan upto 10 crore | Road complete and PCR submitted, road cut opened by farmers for pipeline, funds constraints, Cost escalation Rs 41.72 lakhs reported, NB Boards were not displayed at the two ends of the road.
3 | R032000110 | Sunwara Pindrai Keolari | Seoni | PWD | Road | 2001-12-27 | RO Official | 42.33 | RIDF Loan upto 10 crore | The road complete and PCR submitted, Maintenance not satisfactory, Road cut opened by farmers for pipeline, Cost escalation Rs 16.09 lakhs reported, NB Boards were not displayed at the two ends of the road.
3 | R032000104 | Pamli - Guramkhedi Road | Hoshangabad | PWD | Road | 2001-12-20 | DDM | 109.13 | RIDF Loan upto 10 crore | Very slow progress (Although 2 years extension upto 12/2002 is given, progress is only about 20% no work was initiated on stretch of 2 kms), Farmers are breaking the road to carry canal water to their fields and this adversely affects the life of road
3 | R032000105 | Sangakheda - Fortala Road | Hoshangabad | PWD | Road | 2001-12-20 | DDM | 87.25 | RIDF Loan upto 10 crore | Departmental delay (proposal of EE for 16 additional CD works is pending for approval by CE), Inadequate monitoring by department (monitoring by officers of the rank of EE & above not done)
3 | R032000124 | Sonasawari - Sawalkheda Road | Hoshangabad | PWD | Road | 2001-12-20 | DDM | 100.46 | RIDF Loan upto 10 crore | Slow progress (Although 2 years extension upto 12/2002 is given, progress is only about 50%)
3 | R032000213 | Hasanpur | Burhanpur | WRD | MIS | 2001-12-20 | DDM | 56.15 | RIDF Loan upto 10 crore | NB board not displayed.
3 | R032000059 | Pahargarh-Saharam Rd. | Sheopur | PWD | Road | 2001-12-13 | RO Official+C | 89.15 | RIDF Loan upto 10 crore | Report as per Annexure.
3 | R032000262 | Bijroni | Shivpuri | WRD | MIS | 2001-12-10 | DDM | 93.37 | RIDF Loan upto 10 crore | Physical work not yet commenced
3 | R032000093 | Siptan d/s | Khargone | WRD | MIS | 2001-12-07 | DDM | 220.49 | RIDF Loan upto 10 crore | Slow progress (not completed within scheduled date i.e. 3/2000)
3 | R032000251 | Tejakhedi | Guna | WRD | MIS | 2001-12-07 | DDM | 53.78 | RIDF Loan upto 10 crore | Approach to site is affected due to standing crops. LA problem.
3 | R032000132 | Tatujkhedi | Guna | WRD | MIS | 2001-12-06 | DDM | 103.05 | RIDF Loan upto 10 crore | Contractor problem (not cooperating wiht dept. 1st agency terminated).
3 | R032000254 | Dongar | Guna | WRD | MIS | 2001-12-06 | DDM | 84.71 | RIDF Loan upto 10 crore | Completed.
3 | R032000218 | Amarpura | Neemuch | WRD | MIS | 2001-11-21 | RO Official+C | 340.67 | RIDF Loan upto 10 crore | Report received
3 | R032000219 | Parda | Neemuch | WRD | MIS | 2001-11-21 | RO Official+C | 266.49 | RIDF Loan upto 10 crore | Report not yet received
3 | R032000263 | Bhagwantpur | Vidisha | WRD | MIS | 2001-11-06 | DDM | 37.47 | RIDF Loan upto 10 crore | Slow execution of work, Inadequate monitoring by the department (progress of implementation not being reviewed by EE/SE/CE), NB board not displayed, General (substantial progress of work observed as compared to earlier visit on 24/4/01)
3 | R032000264 | Akbarpur | Vidisha | WRD | MIS | 2001-11-06 | DDM | 43.24 | RIDF Loan upto 10 crore | Project likely to be completed only by June 02 as against the extended completion due date of 31/3/02), Inadequate monitoring by the department (progress of implementation not being reviewed by EE/SE/CE), NB board not displayed
3 | R032000038 | Lateri-Shamsabad | Vidisha | PWD | Road | 2001-11-01 | DDM | 298.23 | RIDF Loan upto 10 crore | Slow progress, Unsatisfactory quality of work, project likely to be completed by 30/6/02 as against the extended completion date of 31/3/02, progress of implementation not being reviewed regularly by EE/SE/CE), NB board not displayed.
3 | R032000248 | Anandpur-Bhagawantpur | Vidisha | PWD | Road | 2001-11-01 | DDM | 92.14 | RIDF Loan upto 10 crore | Progress of implementation satisfactory, project is nearly complete
3 | R032000058 | Nurabad-Padmawali-Barham | Morena | PWD | Road | 2001-10-31 | DDM | 42.69 | RIDF Loan upto 10 crore | Project completed, road cut at many places by the villagers for carrying water, small patch of road near village Barahet in Bhind district if resurfaced may increase utility of project, NB board not displayed.
3 | R032000184 | Deb 4/2 | Badwani | PWD | Bridge | 2001-10-29 | RO Official+C | 41.76 | RIDF Loan upto 10 crore | Report received
3 | R032000217 | Semalkhedi | Jhabua | WRD | MIS | 2001-10-09 | DDM | 46.31 | RIDF Loan upto 10 crore | Slow progress (canal work not completed)
3 | R032000213 | Hasanpur | Burhanpur | WRD | MIS | 2001-09-19 | DDM | 56.15 | RIDF Loan upto 10 crore | NB board not displayed
3 | R032000175 | Gohirari 5/2 | Shahdol | PWD | Bridge | 2001-09-13 | DDM | 16.99 | RIDF Loan upto 10 crore | NB board not displayed. Deep cuts to the approach road observed. Bridge reported complete but finishing and painting is not done.
3 | R032000173 | Satna 9/6 | Satna | PWD | Bridge | 2001-09-03 | DDM | 25.83 | RIDF Loan upto 10 crore | PCR Verification
3 | R032000149 | Aron to Ashoknagar Road | Guna | PWD | Road | 2001-08-30 | DDM | 14.05 | RIDF Loan upto 10 crore | Completed. Maintenance after completion needs attention. NB board not displayed.
3 | R032000152 | Ashoknagar Aron Road to Panwari Hat | Guna | PWD | Road | 2001-08-30 | DDM | 64.86 | RIDF Loan upto 10 crore | NB board not displayed. Dept. to give attention to maintenance.
3 | R032000154 | Ashoknagar Aron Road upto Sindh river | Guna | PWD | Road | 2001-08-30 | DDM | 66.64 | RIDF Loan upto 10 crore | NB board not dislayed. Requires proper maintenance.
3 | R032000212 | Borgaon 2 | Betul | WRD | MIS | 2001-08-29 | DDM | 56.75 | RIDF Loan upto 10 crore | LA problem (80% of money deposited but award is pending which is delaying canal work), NB board not displayed.
3 | R032000057 | Banmor-Sanichra-Rithora | Morena | PWD | Road | 2001-07-13 | DDM | 53.42 | RIDF Loan upto 10 crore | Slow progress, project likely to spill over, Funds constraints, road developed cracks/pot holes, NB board not displayed, Quality of work not satisfactory, hume pipe not laid properly, height of nallah side walls more than height of road.
3 | R032000018 | Ajnod-Banedia | Indore | PWD | Road | 2001-06-04 | DDM | 52.56 | RIDF Loan upto 10 crore | Slow progress, project likely to be completed by extended completion date of 31/3/02, Delay in LA/tendering, CDs required, stop dam at Ujalia over river Gambhir needed, connectivity of project road not established, NB board not displayed.
3 | R032000260 | Achharoi | Sehore | WRD | MIS | 2001-05-31 | RO Official | 61.74 | RIDF Loan upto 10 crore | Slow progress, Delay in LA, Contractor problem, cost escalation of Rs. 24.65 lacs was on account of LA, Masonry work, Earthwork, Pumping system, Fixed & Other charges).
3 | R032000037 | Arniyakalan-Kotharikalan | Shajapur | PWD | Road | 2001-05-23 | RO Official | 10.93 | RIDF Loan upto 10 crore | Project complete, quality of work completed not satisfactory for which monitoring thereof by the department needed to be stepped up, no senior officer from the department above the rank of EE had undertaken any field visit
3 | R032000118 | Sarangpur Eklera | Shajapur | PWD | Road | 2001-05-22 | RO Official | 35.63 | RIDF Loan upto 10 crore | Project completed, cost overrun likely,observations of technical nature (quality of work completed not satisfactory, BT work needed repairy, no senior officer from the department above the rank of EE had undertaken any field visit).
3 | R032000115 | Susner - Patpada | Shajapur | PWD | Road | 2001-05-21 | RO Official | 57.39 | RIDF Loan upto 10 crore | Project completed, cost overrun likely owing to lead paid for E/W and higher tender, quality of work not satisfactory, BT needed repair, no senior officer above EE visited site, road length restricted to 13.8 km as against sanction of 16.0 km.
3 | R032000116 | Nalkheda Chapiheda | Shajapur | PWD | Road | 2001-05-21 | RO Official | 60.49 | RIDF Loan upto 10 crore | Project completed, cost overrun likely, pot holes appeared throughout the road length, no senior officer EE had undertaken any field visit, 200 m of road length was saved due to change in alignment at Kalisingh bridge).
3 | R032000117 | Tanodia Madkuta | Shajapur | PWD | Road | 2001-05-21 | RO Official | 66.37 | RIDF Loan upto 10 crore | Project completed, cost overrun likely, observations of technical nature (quality of work completed not satisfactory, BT needed repairy, no senior officer from the department above the rank of EE had undertaken any field visit)
3 | R032000215 | Karam | Dhar | WRD | MIS | 2001-05-18 | DDM | 448.55 | RIDF Loan upto 10 crore | Delay in LA (land acquisition for canals not yet completed), 5% masonry work and 18% earthwork for spill channel in Unit I remained incomplete, time overrun likely (project likely to be completed only by June 01 as against the due date of March 01)
3 | R032000252 | Musreli | Guna | WRD | MIS | 2001-05-17 | DDM | 66.24 | RIDF Loan upto 10 crore | Project completed, PCR not received, NB board not displayed, irrigation commenced, cropping intensity increased, 40% of water is lost due to seepage.
3 | R032000092 | Adhampur | Khargone | WRD | MIS | 2001-05-16 | DDM | 225.9 | RIDF Loan upto 10 crore | project likely to be completed only by June 01 as against the due date of March 01, LA-30%, masonry-55% and earthwork-17% remained incomplete, 13/29 structures of main canal and minors also remained incomplete.
3 | R032000123 | Soyat Machalpur | Rajgarh | PWD | Road | 2001-05-16 | RO Official | 47.71 | RIDF Loan upto 10 crore | Project complete, PCR not received, saving Rs. 40.02 lacs on account of lesser tender and change in alignment, no senior officer above EE visited, pot holes/rough BT observed, shoulder work not undertaken, additional WBM necessary.
3 | R032000122 | Chatukheda Sustani | Rajgarh | PWD | Road | 2001-05-15 | RO Official | 88.72 | RIDF Loan upto 10 crore | Slow progress of work, project likely to be completed by November 01 as against the due date of March 01), cost escalation on account of delay in fixing agency and higher tender, road length completed at width of 5 m only as against the sanctioned 6 m.
3 | R032000029 | Kurawar-Eklera Rd. | Rajgarh | PWD | Road | 2001-05-14 | RO Official | 111.91 | RIDF Loan upto 10 crore | Slow progress, cost overrun on account of additional CDs and higher tender, revised AA and TS not obtained, 7 additional CDs reported to be necessary, no senior officer from the department above EE had undertaken any visit.
3 | R032000271 | Mansarovar | Dhar | WRD | MIS | 2001-05-09 | DDM | 414.52 | RIDF Loan upto 10 crore | 75% masonry work and 14% earthwork for Unit II- canals remained incomplete, Time overrun likely (project likely to be completed only by June 01 as against the due date of March 01).
3 | R032000042 | Nandanwari Mohagaon | Chhindwara | PWD | Road | 2001-05-04 | DDM | 134.43 | RIDF Loan upto 10 crore | Project completed, PCR not received, 40 m road length washed away during rains, no face wall to CD structure at 20/2 km, about 2 km road length was slightly damaged and pot holes were developed although BT was done only 3 years back)
3 | R032000276 | Chandgarh | Khargone | WRD | MIS | 2001-05-03 | DDM | 242.87 | RIDF Loan upto 10 crore | Project completed, PCR however not yet received, irrigation commenced from Kharif 01-02 for the entire command area (400 ha), WUA however not yet formed.
3 | R032000073 | Chandan Gaon Meghdon Road | Chhindwara | PWD | Road | 2001-05-01 | DDM | 47.4 | RIDF Loan upto 10 crore | Project completed, however PCR not yet received, NB board not displayed.
3 | R032000170 | Sehrao 9/2 | Rewa | PWD | Bridge | 2001-05-01 | DDM | 9.8 | RIDF Loan upto 10 crore | Approach roads incomplete, agency for approach road on Keoti side not yet fixed, delay in land acquisition (land acquisition for approach road on Keoti side not yet completed), time overrun (project spilled over beyond the extended due date of 31/3/01)
3 | R032000155 | Hadai Gorpani Road | Chhindwara | PWD | Road | 2001-04-30 | DDM | 53.32 | RIDF Loan upto 10 crore | Project completed, PCR however not yet received, NB board not displayed at one end of the road.
3 | R032000019 | Akasoda-Karadiya-Guhar Atawada | Indore | PWD | Road | 2001-04-28 | DDM | 68.62 | RIDF Loan upto 10 crore | Progress of work slow owing to scarcity of water for drought conditions in the district, time overrun likely (project likely to be completed only by Dec 01 as against the due date of March 01), final WBM coat and subsequent BT remained to be completed
3 | R032000072 | Bichhua Khamarpani Road | Chhindwara | PWD | Road | 2001-04-27 | DDM | 165.47 | RIDF Loan upto 10 crore | project likely to be completed by June 01 against the due date of March 01), WBM on 2.5 km and BT on 7 km pending, if the BT is not completed before onset of monsoon, the WBM work will be damaged which may subsequently require renewal, contractor problem
3 | R032000259 | Jaisinghpura | Rajgarh | WRD | MIS | 2001-04-27 | RO Official | 54.88 | RIDF Loan upto 10 crore | 35% of the dam work and entire canal work remained incomplete, TS for canal work not yet obtained, agency for canal work not yet fixed, time overrun likely (project likely to be completed only by March 02 as against the due date of March 01)
3 | R032000218 | Amarpura | Neemuch | WRD | MIS | 2001-04-26 | RO Official | 340.67 | RIDF Loan upto 10 crore | Delay in LA, delay in tendering, project likely to be completed only by June 2003, cost escalation Rs. 93.60 lacs on account of SOR, NB board not displayed.
3 | R032000219 | Parda | Neemuch | WRD | MIS | 2001-04-26 | RO Official | 266.49 | RIDF Loan upto 10 crore | Work not commenced, Delay in LA,forest clearence required, Delay in tendering, Delay in fixing agency, project likely to be completed only by June 2003, the cost escalation of Rs. 175.18 lacs was on account of SOR, NB board not displayed.
3 | R032000236 | Chandla-Sarwai-Gourihar Majoudh | Chattarpur | PWD | Road | 2001-04-26 | RO Official | 68.85 | RIDF Loan upto 10 crore | Funds constraints, cost overrun likely, project likely to be completed by 30/6/01, approach roads on Kel river damaged rains, E-in-C office should study the problem and also decide about the agency to undertake appropriate remedial measures.
3 | R032000237 | Chhatarpur - Vikrampur Road | Chattarpur | PWD | Road | 2001-04-25 | RO Official | 56.26 | RIDF Loan upto 10 crore | Contractor problem, project likely to be completed by 31/3/02, a medium bridge at km 18/2 was proposed, revised TS and AA not obtained, cost overrun likely.
3 | R032000238 | Karri Vikrampur | Chattarpur | PWD | Road | 2001-04-25 | RO Official | 37.94 | RIDF Loan upto 10 crore | Project completed, PCR not received, deviations from technical sanctions owing to site conditions, cost overrun reported owing to addition WBM, higher cost of CD and higher tender percent),RAA however not yet received.
3 | R032000131 | Tawa | Chhindwara | WRD | MIS | 2001-04-24 | DDM | 416.18 | RIDF Loan upto 10 crore | Funds constraints, time overrun (project should have been completed by March 2001), dam height of around 8 ft and 20% of the canal work yet to be completed, Cost overrun reported.
3 | R032000254 | Dongar | Guna | WRD | MIS | 2001-04-24 | DDM | 84.71 | RIDF Loan upto 10 crore | Slow progress, delay in tendering (tendering for Units II & III still in process), time overrun likely (project likely to be completed only by 31/3/02 as against the due date of 31/3/01), contractor problem (slow progress), NB board not displayed.
3 | R032000263 | Bhagwantpur | Vidisha | WRD | MIS | 2001-04-24 | DDM | 37.47 | RIDF Loan upto 10 crore | Slow progress of work, time overrun likely (project likely to be completed only by 31/12/01 as against the due date of 31/3/01), contractor problem (slow progress), less than adequate supervision by the executing dept, NB board not displayed.
3 | R032000043 | Karoli-Ekalwara | Dhar | PWD | Road | 2001-04-19 | DDM | 27.61 | RIDF Loan upto 10 crore | Project completed, PCR however not yet received, maintenance of the road needed to be stepped up(pot holes were observed near the villages)
3 | R032000030 | Majhiyar-Padri-Pathari Road | Rewa | PWD | Road | 2001-04-18 | DDM | 23.54 | RIDF Loan upto 10 crore | Slow progress of work, cost escalation likely, NB board not displayed, observations of technical nature (retaining wall construction to be taken up at 3 places and some pulias to be constructed to avoid road damage during rainy season.
3 | R032000212 | Borgaon 2 | Betul | WRD | MIS | 2001-03-26 | DDM+C | 56.75 | RIDF Loan upto 10 crore | Time overrun likely, observations of technical nature, deviation from sanctioned plan, NB board not displayed, delay in land acquisition, delay on account of land acquisition, delay in fixing agency, cost overrun likely (Refer to annexure V)
3 | R032000032 | Deori-Chadpur | Sagar | PWD | Road | 2001-03-25 | DDM | 80.04 | RIDF Loan upto 10 crore | Project likely to be completed by May 01 as against the due date of March 01, NB board not displayed, contractor problem, road length 6.85 km not covered under RIDF in bad condition, road constructed under RIDF showed deterioration.
3 | R032000033 | Deori-Sahajpur | Sagar | PWD | Road | 2001-03-25 | DDM | 75.96 | RIDF Loan upto 10 crore | Slow progress, contractor problem, project likely to be completed by Dec 01 as against the due date of March 01), NB board not displayed, road level fall below land level.
3 | R032000034 | Kesli-ISahaspur | Sagar | PWD | Road | 2001-03-25 | DDM | 79.36 | RIDF Loan upto 10 crore | Slow progress, project likely to be completed only by June 01 as against the due date of March 01, NB board not displayed, contractor problem, approach road of 0.8 km on Deori side not commenced, road level fall below land level.
3 | R032000011 | Gujari | Khargone | WRD | MIS | 2001-03-23 | DDM | 40.36 | RIDF Loan upto 10 crore | Project completed, PCR however not yet received, WUA not yet formed, irrigation likely to commence from coming monsoon.
3 | R032000093 | Siptan d/s | Khargone | WRD | MIS | 2001-03-23 | DDM | 220.49 | RIDF Loan upto 10 crore | Slow progress of work, time overrun likely, only the preliminary work- 100% in Unit I and 80% in Unit II and masonry work- 15% in Unit I completed till date.
3 | R032000038 | Lateri-Shamsabad | Vidisha | PWD | Road | 2001-03-22 | DDM | 298.23 | RIDF Loan upto 10 crore | Project likely to be completed by March 2002 against the due date of March 2001, NB board not displayed, multiplicity of contractors, Approval from forest not received, PWD should take up the matter with the Forest Department.
3 | R032000248 | Anandpur-Bhagawantpur | Vidisha | PWD | Road | 2001-03-22 | DDM | 92.14 | RIDF Loan upto 10 crore | Likely to be completed by Dec 2001 against the due date of March 2001, non-availability of labour/skilled labour during festival season), NB board not displayed, delay in receipt of clearance from forest dept. for undetaking the road work.
3 | R032000096 | Bilwani | Badwani | WRD | MIS | 2001-03-21 | HO Official | 71.18 | RIDF Loan upto 10 crore | Project completed, observations of technical nature, cost overrun (Refer to annexure I)
3 | R032000216 | Achhalgarh | Guna | WRD | MIS | 2001-03-21 | DDM | 34.23 | RIDF Loan upto 10 crore | Delay in tendering, time overrun likely (likely to be completed by June 2001), NB board not displayed, discrepancy in the loan amount sanctioned and the amount communicated to field level by WRD
3 | R032000278 | Chitrai | Badwani | WRD | MIS | 2001-03-21 | RO Official+C | 40.24 | RIDF Loan upto 10 crore | Observations of technical nature (Refer to annexure III)
3 | R032000280 | Salkheda | Badwani | WRD | MIS | 2001-03-21 | RO Official+C | 37.05 | RIDF Loan upto 10 crore | Deviations from sanctioned plan,observations of technical nature,cost overrun likely (Refer to annexure II)
3 | R032000002 | Maheri | Sagar | WRD | MIS | 2001-03-18 | DDM | 76.58 | RIDF Loan upto 10 crore | Slow progress, project likely to be completed by Sept 2002 against extended due date of 31.3.01), no LA done for Unit-II), delay in commencement of work.
3 | R032000016 | Mandvi | Chhindwara | WRD | MIS | 2001-03-16 | DDM | 495.42 | RIDF Loan upto 10 crore | Slow progress of work, contractor problem (contractor in group-I abondoned the nalah closure and pitching work), land acquisition problem (which affected canal work), railway crossing problem (there is railway crossing in canal)
3 | R032000044 | Tilgara-Satkunda | Dhar | PWD | Road | 2001-03-16 | DDM | 18.85 | RIDF Loan upto 10 crore | Project completed on 7/2/2001, NB board not displayed at one of the two ends of the road
3 | R032000224 | Kolwakhedi | Ratlam | WRD | MIS | 2001-03-16 | DDM | 475.61 | RIDF Loan upto 10 crore | Funds constraints, NB board not displayed, slow progress of work, time overrun likely (project likely to be completed by June 02 against the extended due date of 31/3/01)
3 | R032000281 | Pulpuldoh | Chhindwara | WRD | MIS | 2001-03-15 | DDM+C | 240.7 | RIDF Loan upto 10 crore | Observations of technical nature(deviation from sanctioned plan),time overrun likely,cost overrun likely, NB Board not displayed,delay in land acquisition, delay on account of land acquisition (Refer to annexure IX)
3 | R032000091 | Tipan 4/10 | Shahdol | PWD | Bridge | 2001-03-14 | DDM | 66.87 | RIDF Loan upto 10 crore | Bridge completed but 25.20m out of 45.20 m of approach road was incomplete, time overrun likely (project likely to be completed only by 31/5/01 as against the due date of 31/3/01).
3 | R032000148 | Bamori Bishanwada Road | Guna | PWD | Road | 2001-03-09 | DDM | 53.9 | RIDF Loan upto 10 crore | Project already complete, PCR however not yet submitted, cost escalation reported
3 | R032000275 | Dokarwani | Jhabua | WRD | MIS | 2001-03-09 | DDM | 105.43 | RIDF Loan upto 10 crore | Project almost completed (masonry work- 100% and earthwork- 70% under Unit II remained incomplete), however owing to drought conditions no water was accumulated in the tank.
3 | R032000108 | Seoti - Singola via Dewalgaon - Ladsa | Balaghat | PWD | Road | 2001-03-08 | RO Official+C | 89.11 | RIDF Loan upto 10 crore | Observation of technical nature, delay in fixing agency, time overrun likely, cost overrun likely (Refer to annexure I)
3 | R032000229 | Bhajiyadand Jhiriya Kachhe Khani | Balaghat | PWD | Road | 2001-03-08 | RO Official+C | 22.89 | RIDF Loan upto 10 crore | The project likely to be completed within the extended period of March 01 and sanctioned limit,Observation of technical nature(the downstream protection work of CD at km 6/8 has been washed away and needed repairy on top priority)
3 | R032000223 | Gudbehli | Ratlam | WRD | MIS | 2001-03-01 | DDM | 33.12 | RIDF Loan upto 10 crore | Project already complete, WUA not formed although irrigation started, NB board not displayed
3 | R032000025 | Melkheda-Sathkheda | Mandsaur | PWD | Road | 2001-02-27 | RO Official+C | 26.77 | RIDF Loan upto 10 crore | Cost escalation Rs. 7.67 lacs due to increase in SOR, project likely to be completed by 31.3.2001, action to pay land compensation and obtain revised AA and TS need to be taken on priority, it was reported that the estimates were pending with EE.
3 | R032000021 | Jat-Gwalior Kalan Sukhanand Road | Neemuch | PWD | Road | 2001-02-26 | RO Official+C | 79.01 | RIDF Loan upto 10 crore | Length of 7 km at village Jat end requires BT, as against sanction of Rs. 79.01 lacs, the project is likely to cost Rs. 89.62 lacs.
3 | R032000022 | Kaithuli Approach Rd. | Mandsaur | PWD | Road | 2001-02-26 | RO Official+C | 60.04 | RIDF Loan upto 10 crore | cost escalation of Rs.7 lacs due to increase in tender, works completed except one filling in 2 kms. in some kms., berms are higher than the riding surface which need to be scraped, action to obtain revised AA needs to be taken on priority.
3 | R032000026 | Dhudhakhedi-Satalkhedi | Mandsaur | PWD | Road | 2001-02-26 | RO Official+C | 33.06 | RIDF Loan upto 10 crore | Cost escalation Rs. 7 lacs due to increase in SOR, action to pay land compensation and obtain revised AA and TS need to be taken on priority.
3 | R032000226 | Tolapiparia | Seoni | WRD | MIS | 2001-02-26 | RO Official+C | 129.93 | RIDF Loan upto 10 crore | Slow progress, work of spill channel excavation, waste wier, RBC head sluice not completed, no monitoring by EE and CE, NB board not displayed, delay in LA, cost escalation on account of LA of 1.30 ha and construction of 2 sluices and 1 waste wier.
3 | R032000206 | Bandakpur Semer | Damoh | WRD | MIS | 2001-02-24 | RO Official | 104.06 | RIDF Loan upto 10 crore | Work likely to be completed only by 31/12/02 as against the due date of 31/3/01, delay in fixing agencies, cost overrun likely for increase in width of chutefall and increase in tender rates, the progress of the project should be monitored regularly.
3 | R032000272 | Sajwani | Jhabua | WRD | MIS | 2001-02-24 | DDM | 71.95 | RIDF Loan upto 10 crore | Project likely to be completed only by May 01, NB board not displayed, excessive loss of water through seepage and soil erosion due to flow of water, there should be a provision of approach road for monitoring the project even in rainy season).
3 | R032000205 | Pondi Jaitgarh | Damoh | WRD | MIS | 2001-02-23 | RO Official | 116.48 | RIDF Loan upto 10 crore | Cost overrun likely for change in design. slow work progress, time overrun likely, WRD may examine the proposal of change in design and accord required technical sanction expeditiously, progress of the project need to be monitored regularly.
3 | R032000207 | Hathna | Damoh | WRD | MIS | 2001-02-23 | RO Official | 83.69 | RIDF Loan upto 10 crore | Only small work mainly relating to earthwork in spill channel has been done, LA problem in Unit I has also affected the canal work, time overrun likely, progress of the work should be monitored regularly since the project has already been much delayed
3 | R032000007 | Indira Gandhi | Dhar | WRD | MIS | 2001-02-22 | DDM | 284.51 | RIDF Loan upto 10 crore | Slow progress of work,time overrun likely (project likely to be completed by 30/6/2001 only).
3 | R032000076 | Teonda Khurai via Pathari Road | Vidisha | PWD | Road | 2001-02-22 | DDM | 279.96 | RIDF Loan upto 10 crore | Slow progress of work, multiplicity of contractors (performance of 2 out of 3 contractors is not satisfactory ), time overrun likely (project likely to be completed by June 01 as against the due date of March 01), NB board not displayed.
3 | R032000077 | Andiakala Pachama Road | Vidisha | PWD | Road | 2001-02-22 | DDM | 124.1 | RIDF Loan upto 10 crore | Slow progress, project likely to be completed by May/June 2001 as against the due date of March 2001), NB board not displayed, BT work for 6.57 km though completed recently is damaged, CD work not completed.
3 | R032000048 | Bhonkhedi(Gujarkhedi)Sonsarkhed | Hoshangabad | PWD | Road | 2001-02-20 | DDM | 67.5 | RIDF Loan upto 10 crore | Multiplicity of contractors, contractor problem, funds constraints, material problem, observations of technical nature (Refer to Annexure XI)
3 | R032000051 | Paraswada-Doomar | Hoshangabad | PWD | Road | 2001-02-20 | DDM | 40.74 | RIDF Loan upto 10 crore | Multiplicity of contractors, contractor problem, funds constraints, material problem, delay in tendering (Refer to Annexure X)
3 | R032000055 | Shobhapur-Rewa Bankhedi | Hoshangabad | PWD | Road | 2001-02-20 | DDM | 78.38 | RIDF Loan upto 10 crore | Slow work progress,Multiplicity of contractors, Contractor problem, Funds constraints, Material problem, Time overrun likely,Refer to Annexure IX.
3 | R032000273 | Kalmoda | Jhabua | WRD | MIS | 2001-02-19 | DDM | 76.83 | RIDF Loan upto 10 crore | Slow progress, delay in tendering, drought condition, project likely to be completed only by June 01, NB board not displayed, there should be provision of approach road for monitoring the project in rainy season).
3 | R032000049 | Isharpur-Rani-Gohan | Hoshangabad | PWD | Road | 2001-02-17 | DDM | 20.13 | RIDF Loan upto 10 crore | Delay in tendering, observations of technical nature, (Refer to Annexure VI)
3 | R032000050 | Kanhwar Punor Road | Hoshangabad | PWD | Road | 2001-02-17 | DDM | 37.37 | RIDF Loan upto 10 crore | Delay in according sanction for special repairs work, for Gr-III work sanction was accorded for 60 mm only as against the requirement of 75 mm, contractor problem (slow execution, limited capacity)
3 | R032000052 | Sandiya-Sahalwara | Hoshangabad | PWD | Road | 2001-02-17 | DDM | 24.73 | RIDF Loan upto 10 crore | Multiplicity of contractors, contractor problem, funds constraints, material problem, observations of technical nature (Refer to Annexure VII)
3 | R032000053 | Shobhapur-Bhatgaon | Hoshangabad | PWD | Road | 2001-02-17 | DDM | 27.21 | RIDF Loan upto 10 crore | Multiplicity of contractors, funds constraints, material problem, observations of technical nature, (Refer to Annexure VIII)
3 | R032000054 | Shobhapur-Kharikalan | Hoshangabad | PWD | Road | 2001-02-17 | DDM | 34.68 | RIDF Loan upto 10 crore | BT abondoned, tendering if not expedited by EE/CE/Zila Sarkar may result in cutting off the work done due to rain canal water in rainy season, project likely to be completed by Dec 2001 only as against the due date of March 2001
3 | R032000065 | Nirandarpur | Sagar | WRD | MIS | 2001-02-17 | DDM | 236.98 | RIDF Loan upto 10 crore | Tendering for Unit-II not initiated, time overrun likely (project likely to be completed by March 2002 as against the due date of March 2001), delay in land acquisition (Unit-II), delay in clearing the land to be submerged, NB board not displayed.
3 | R032000217 | Semalkhedi | Jhabua | WRD | MIS | 2001-02-16 | DDM | 46.31 | RIDF Loan upto 10 crore | Project likely to be completed by June 01 as against the due date of March 01, NB board not displayed, there should be provision of approach road for monitoring the project even in rainy season).
3 | R032000274 | Badibawadi | Jhabua | WRD | MIS | 2001-02-16 | DDM | 85.67 | RIDF Loan upto 10 crore | Slow progress, project likely to be completed only by 30/6/01, NB board not displayed, department to ensure no excessive loss of water through seepage in the canals and that there is no soil erosion due to flow of water down the spill channel.
3 | R032000103 | Chourahat - Fortala Road | Hoshangabad | PWD | Road | 2001-02-15 | DDM | 53.3 | RIDF Loan upto 10 crore | Delay in tendering (tendering for works like murum base Gr-I to III and BT is still under process)
3 | R032000104 | Pamli - Guramkhedi Road | Hoshangabad | PWD | Road | 2001-02-15 | DDM | 109.13 | RIDF Loan upto 10 crore | Delay in land acquisition, multiplicity of contractors, contractor problem, funds constraints, cost overrun likely, (Refer to Annexure IV).
3 | R032000105 | Sangakheda - Fortala Road | Hoshangabad | PWD | Road | 2001-02-15 | DDM | 87.25 | RIDF Loan upto 10 crore | Slow progress, revised proposal submitted by EE for alternate route is awaiting approval by the Competent Authority,PWD,E-in-C office should look into the matter urgently and solve the problem, Time overrun likely ,Refer to Annexure V.
3 | R032000079 | Tawa Bridge Itarsi Mandi Road | Hoshangabad | PWD | Road | 2001-02-07 | DDM | 48.33 | RIDF Loan upto 10 crore | Delay in tendering, multiplicity of contractors, contractor problem, observations of technical nature, (Refer to Annexure III).
3 | R032000102 | Sangakheda- Satwasa Road | Hoshangabad | PWD | Road | 2001-02-07 | DDM | 34.26 | RIDF Loan upto 10 crore | Time overrun likely (project likely to be completed by June 2001 against the due date of March 2001)
3 | R032000124 | Sonasawari - Sawalkheda Road | Hoshangabad | PWD | Road | 2001-02-07 | DDM | 100.46 | RIDF Loan upto 10 crore | Contractor problem, multiplicity of contractors, funds constraints, material problem, observations of technical nature, (Refer to Annexure II).
3 | R032000074 | Teligaon Suthaliya Road | Guna | PWD | Road | 2001-01-25 | DDM | 49.16 | RIDF Loan upto 10 crore | Progress satisfactory. Only 1.7 km BT work is balance on which work is in progress. Project likely to be completed by March 2001.
3 | R032000146 | Kumbhraj to Bhariwad Road | Guna | PWD | Road | 2001-01-25 | DDM | 40.51 | RIDF Loan upto 10 crore | Project completed in all respect. Quality satisfactory.
3 | R032000215 | Karam | Dhar | WRD | MIS | 2001-01-21 | DDM | 448.55 | RIDF Loan upto 10 crore | Time overrun likely (project likely to be completed by June 2001 against the due date of March 2001),
3 | R032000139 | Talod-Fatiabad Road | Ujjain | PWD | Road | 2001-01-18 | DDM | 65.55 | RIDF Loan upto 10 crore | Progress is very slow. Quality of implemented road work is also not satisfactory. PWD may make efforts to solve the cointractor problem urgently to avoid undue delay. Quality aspects also need to be seen by the completent authority.
3 | R032000138 | Kaytha-Bhatani Road | Ujjain | PWD | Road | 2001-01-17 | DDM | 56.1 | RIDF Loan upto 10 crore | 3 km road length (at Km 4, 5 & 6) not covered under NABARD sanction is in bad condition. 100 m road length at the end after Km 18 also need rennovation. The PWD may examine the matter for effective utilisation of completed road.
3 | R032000136 | Narayana-Panbihar Road | Ujjain | PWD | Road | 2001-01-15 | DDM | 53.25 | RIDF Loan upto 10 crore | progress slow, cost escalation of Rs. 86.98 lacs due to inclusion of 3 km of additional road length as also some other items. Medium bridge work delayed for want of design. Quality of work not satisfactory.
3 | R032000137 | Mahidpur Semaliya Road | Ujjain | PWD | Road | 2001-01-15 | DDM | 46.98 | RIDF Loan upto 10 crore | Progress of work slow. Cost escalatin of Rs. 45.19 lacs. 300 m of road passing through Semalia village remains waterlogged during rainy season.
3 | R032000271 | Mansarovar | Dhar | WRD | MIS | 2001-01-12 | DDM | 414.52 | RIDF Loan upto 10 crore | Time overrun likely (projects likely to be completed by June 2001 against the due date of March 2001)
3 | R032000075 | Ashoknagar Thubon Road | Guna | PWD | Road | 2001-01-10 | DDM | 65.2 | RIDF Loan upto 10 crore | Progress satisfactory. Works on 1 CD work and on a small portion of road i.e. 0.20 km are in progress. Expected completed by March 2001.
3 | R032000036 | Sundra-Singhpur Rd. | Satna | PWD | Road | 2001-01-09 | DDM | 38.26 | RIDF Loan upto 10 crore | Work progress slow, lax supervision by PWD, time overrun likely, poor quality of works.
3 | R032000172 | Semrawar 17/6 | Satna | PWD | Bridge | 2001-01-09 | DDM | 7.4 | RIDF Loan upto 10 crore | Bridge complete. Approach roads in progress. NB board not displayed, extensive repairing of the existing roads on both sides of the bridge suggested as they are in very bad shape
3 | R032000227 | Kathotiya | Shahdol | WRD | MIS | 2001-01-09 | DDM | 82.93 | RIDF Loan upto 10 crore | Slow progress of work. Tendering for Unit II still under progress. Progress need to be monitored regularly.
3 | R032000043 | Karoli-Ekalwara | Dhar | PWD | Road | 2000-12-26 | DDM | 27.61 | RIDF Loan upto 10 crore | Project completed, however PCR not received
3 | R032000085 | Galchua 5/2 | Rewa | PWD | Bridge | 2000-12-21 | DDM | 12.87 | RIDF Loan upto 10 crore | Unsatisfactory quality of work, cost escalation likely, slow progress of work (bridge under construction since 1989), land for approach road on both sides of the bridge not yet acquired, NB board not displayed
3 | R032000180 | Kanhan 4/6 | Chhindwara | PWD | Bridge | 2000-12-17 | DDM | 141.2 | RIDF Loan upto 10 crore | Work progress slow, time overrun likely, funds constraints, technical design of the bridge reported to be faulty.
3 | R032000031 | Simanghat-Barroan Rd. | Rewa | PWD | Road | 2000-12-15 | DDM | 25.09 | RIDF Loan upto 10 crore | Cost escalation likely, earth work on birms pending, NB board not displayed, suggestion of technical nature( retaining walls at 3 places be constructed)
3 | R032000131 | Tawa | Chhindwara | WRD | MIS | 2000-12-14 | DDM | 416.18 | RIDF Loan upto 10 crore | time overrun likely, land acquisition problem
3 | R032000014 | Ahirkheda | Khargone | WRD | MIS | 2000-12-06 | DDM | 87.47 | RIDF Loan upto 10 crore | Funds constraints, NB board not displayed
3 | R032000009 | Sasyakhedi | Khargone | WRD | MIS | 2000-12-02 | DDM | 44.6 | RIDF Loan upto 10 crore | NB board not displayed.
3 | R032000010 | Baghkheda | Khargone | WRD | MIS | 2000-12-02 | DDM | 59.38 | RIDF Loan upto 10 crore | NB board not displayed
3 | R032000277 | Kakadgaon | Khargone | WRD | MIS | 2000-12-02 | DDM | 30.94 | RIDF Loan upto 10 crore | NB board not displayed
3 | R032000142 | Bamuliya Approach Road | Sehore | PWD | Road | 2000-11-30 | RO Official+C | 52.1 | RIDF Loan upto 10 crore | Cost overrun likely, roadside farmers are encroaching on the road land which will cause hindrance in smooth flow of traffic and to remove the problem immediate action be taken to obtain awards for payment of land compensation,
3 | R032000143 | Neelkanth Approach Road | Sehore | PWD | Road | 2000-11-30 | RO Official+C | 21.84 | RIDF Loan upto 10 crore | As per annexure
3 | R032000265 | Kakarhai | Panna | WRD | MIS | 2000-11-30 | RO Official+C | 71.3 | RIDF Loan upto 10 crore | Cost escalation likely, time overrun likely, work not yet commenced, suggestions of technical nature (refer to annexure III)
3 | R032000266 | Hardua | Panna | WRD | MIS | 2000-11-30 | RO Official+C | 32.95 | RIDF Loan upto 10 crore | Cost overrun likely, suggestions of technical nature( refer to annexure II).
3 | R032000141 | Khadi Chamsi Kurawar Marawar | Sehore | PWD | Road | 2000-11-29 | RO Official+C | 45.86 | RIDF Loan upto 10 crore | Cost overrun likely, contractor problem, unsatisfactory quality of work, no field tests undertaken, action to obtain revised AA needs to be taken, senior officer needs to inspect the road and decide action for resurfacing of the already laid BT carpet
3 | R032000144 | Bahuakhedi Amalaha Dhamdona | Sehore | PWD | Road | 2000-11-29 | RO Official+C | 94.83 | RIDF Loan upto 10 crore | Cost overrun likely, no field tests undertaken, action needs be taken to prepare revised cost estimates and to obtain revised AA, quality control tests are lacking, no visits undertaken by senior officers of the executing dept above the rank of EE
3 | R032000145 | Shampur Bichha | Sehore | PWD | Road | 2000-11-29 | RO Official+C | 12.21 | RIDF Loan upto 10 crore | Cost overrun likely, no field tests undertaken, in km 5/2 a big tree exists on embankment which fouls movement of traffic, revised AA needs to be obtained on priority basis, no visits undertaken by senior officers above the rank of EE
3 | R032000078 | Intkhedi Ajitnagar Road | Raisen | PWD | Road | 2000-11-25 | RO Official | 87.41 | RIDF Loan upto 10 crore | Nothing adverse reported
3 | R032000228 | Ganjri | Sidhi | WRD | MIS | 2000-11-25 | RO Official+C | 76.34 | RIDF Loan upto 10 crore | Land acquisition problem (Unit I), the number of quality control tests for compression strength of concrete used for chute fall and morter fall short of the prescribed norms, suggestions of technical nature (refer to annexure VI)
3 | R032000208 | Gopaldas | Sidhi | WRD | MIS | 2000-11-23 | RO Official+C | 63.28 | RIDF Loan upto 10 crore | Time overrun likely, work not yet commenced, suggestions of technical nature (refer to annexure VII)
3 | R032000251 | Tejakhedi | Guna | WRD | MIS | 2000-11-18 | DDM | 53.78 | RIDF Loan upto 10 crore | Work progress slow, time overrun likely, land acquisition problem for standing crops, accesibility problem for remoteness
3 | R032000132 | Tatujkhedi | Guna | WRD | MIS | 2000-11-17 | DDM | 103.05 | RIDF Loan upto 10 crore | Suggestion of technical nature (additional chutefall for soil conservation in Unit 1 suggested
3 | R032000255 | Jhiri | Guna | WRD | MIS | 2000-11-17 | DDM | 98.3 | RIDF Loan upto 10 crore | Suggestion of technical nature (additional chutefall for soil conservation may be needed)
3 | R032000155 | Hadai Gorpani Road | Chhindwara | PWD | Road | 2000-11-16 | DDM | 53.32 | RIDF Loan upto 10 crore | Report not received
3 | R032000042 | Nandanwari Mohagaon | Chhindwara | PWD | Road | 2000-11-14 | DDM | 134.43 | RIDF Loan upto 10 crore | Work affected for water scarcity/drought
3 | R032000072 | Bichhua Khamarpani Road | Chhindwara | PWD | Road | 2000-11-14 | DDM | 165.47 | RIDF Loan upto 10 crore | Report not received
3 | R032000029 | Kurawar-Eklera Rd. | Rajgarh | PWD | Road | 2000-11-09 | RO Official+C | 111.91 | RIDF Loan upto 10 crore | Slow progress, cost overrun likely, deviation in design, laboratory tests found short of norms, visits by senior officicers required, wearing coat in existing vented causeway needs repair, action needed to protect land from encroachment by farmers.
3 | R032000122 | Chatukheda Sustani | Rajgarh | PWD | Road | 2000-11-09 | RO Official+C | 88.72 | RIDF Loan upto 10 crore | Work progress slow, time/cost overrun likely, delay in tendering, rebuilding the bund required, two flush causeway needed in village portion, revised AA and TS needed, Collector Rajgarh needs to be reminded for expeditious action in land acquisition.
3 | R032000073 | Chandan Gaon Meghdon Road | Chhindwara | PWD | Road | 2000-11-06 | DDM | 47.4 | RIDF Loan upto 10 crore | Work progress slow, funds constraints, NB board not displayed
3 | R032000091 | Tipan 4/10 | Shahdol | PWD | Bridge | 2000-10-23 | DDM | 66.87 | RIDF Loan upto 10 crore | Nothing adverse reported
3 | R032000243 | Dehgaon Bamhori | Raisen | PWD | Road | 2000-10-21 | OIC | 114.08 | RIDF Loan upto 10 crore | Deviation from technical design, profile and camber correction required at some places along the road length, time/cost overrun likely, the proposal with complete technical details needs be submitted to NB urgently for consideration
3 | R032000244 | Garhi Ahemadpur | Raisen | PWD | Road | 2000-10-21 | OIC | 86.12 | RIDF Loan upto 10 crore | Time/cost overrun likely, deviation from sanctioned technical design, removal of earth work from shoulders required, cost escalation proposal should be put up to NB expeditiously senior officer should personally discuss the matter to sort out the issue
3 | R032000176 | Tinsara | Narsinghpur | PWD | Bridge | 2000-10-19 | DDM | 16.36 | RIDF Loan upto 10 crore | NB board not displayed, suggestion of technical nature (pipe railings not provided), work of approach roads on both sides of the bridge not yet commenced.
3 | R032000170 | Sehrao 9/2 | Rewa | PWD | Bridge | 2000-10-18 | DDM | 9.8 | RIDF Loan upto 10 crore | NB board not displayed, project complete
3 | R032000171 | Mahana 5/4 | Rewa | PWD | Bridge | 2000-10-18 | DDM | 3.95 | RIDF Loan upto 10 crore | NB board not displayed, project complete
3 | R032000191 | Sehrao 6/8 | Rewa | PWD | Bridge | 2000-10-18 | DDM | 16.7 | RIDF Loan upto 10 crore | NB board not displayed, project complete
3 | R032000194 | Tada 11/4 | Narsinghpur | PWD | Bridge | 2000-10-18 | DDM | 25.18 | RIDF Loan upto 10 crore | Project completed, however NB board not displayed, suggestion of technical nature (pipe railings not provided)
3 | R032000195 | Gahedua 2/2 | Narsinghpur | PWD | Bridge | 2000-10-18 | DDM | 14.89 | RIDF Loan upto 10 crore | NB board not displayed, suggestion of technical nature (pipe railings not provided), construction of approach roads on both sides of the bridge not yet commenced.
3 | R032000135 | Padarkheda | Shivpuri | WRD | MIS | 2000-10-17 | DDM | 80.92 | RIDF Loan upto 10 crore | Work progress slow, time overrun likely, contractor problem, NB board not displayed
3 | R032000136 | Narayana-Panbihar Road | Ujjain | PWD | Road | 2000-10-17 | DDM | 53.25 | RIDF Loan upto 10 crore | Work progress slow, funds constraints, delay in tendering, unsatisfactory quality of work (patches, undulations), NB board not displayed, work affected for water scarcity/drought, km 11-14 not included in the project though in very bad shape
3 | R032000137 | Mahidpur Semaliya Road | Ujjain | PWD | Road | 2000-10-17 | DDM | 46.98 | RIDF Loan upto 10 crore | Work affected for water scarcity/drought, funds constraints
3 | R032000018 | Ajnod-Banedia | Indore | PWD | Road | 2000-10-16 | DDM | 52.56 | RIDF Loan upto 10 crore | Work progress slow, time overrun likely, suggestion of technical nature (stop dam needed)
3 | R032000019 | Akasoda-Karadiya-Guhar Atawada | Indore | PWD | Road | 2000-10-16 | DDM | 68.62 | RIDF Loan upto 10 crore | Work progress slow, time overrun likely, work affected for water scarcity/drought
3 | R032000139 | Talod-Fatiabad Road | Ujjain | PWD | Road | 2000-10-16 | DDM | 65.55 | RIDF Loan upto 10 crore | Work progress slow, funds constraints, contractor problem (poor resources), unsatisfactory quality of work (undulations), work affected for water scarcity/drought, labour problem, instead of big tendering, small tenders are suggested
3 | R032000147 | Guna Ashoknagar to Karod Guna Mhow | Guna | PWD | Road | 2000-10-16 | DDM | 48.61 | RIDF Loan upto 10 crore | Work progress slow, unsatisfactory quality of work
3 | R032000149 | Aron to Ashoknagar Road | Guna | PWD | Road | 2000-10-16 | DDM | 14.05 | RIDF Loan upto 10 crore | Work progress slow, unsatisfactory quality of work
3 | R032000016 | Mandvi | Chhindwara | WRD | MIS | 2000-10-15 | DDM | 495.42 | RIDF Loan upto 10 crore | Time overrun likely, land acquisition problem for canals, work affected for water scarcity/drought
3 | R032000223 | Gudbehli | Ratlam | WRD | MIS | 2000-10-15 | DDM | 33.12 | RIDF Loan upto 10 crore | Project completed, however benefits not yet accruing, WUA not yet formed
3 | R032000138 | Kaytha-Bhatani Road | Ujjain | PWD | Road | 2000-10-13 | DDM | 56.1 | RIDF Loan upto 10 crore | Work affected for water scarcity/drought, suggestion of technical nature (km 4-6 not included in project though in bad shape), funds constraints.
3 | R032000123 | Soyat Machalpur | Rajgarh | PWD | Road | 2000-10-11 | RO Official+C | 47.71 | RIDF Loan upto 10 crore | Cost overrun likely, QC tests fall short of norms, unsatisfactory quality of work, nallah upstream and downstream needs to be channelised, approach road needs to be started, revised AA and TS needed, no visits undertaken by officers above EE.
3 | R032000133 | Aari | Guna | WRD | MIS | 2000-10-11 | DDM | 96.17 | RIDF Loan upto 10 crore | Work progress slow, time overrun likely, funds constraints, labour problem
3 | R032000183 | Kalisindh 6/4 | Rajgarh | PWD | Bridge | 2000-10-11 | RO Official+C | 121.62 | RIDF Loan upto 10 crore | Work completed, bridge be handed over expeditiously to PWD for maintenance, rain cuts and slips needs repairing, approaches should be black topped from the provisions of Soyat-Machalpur road sanctioned under RIDF, NB board not displayed
3 | R032000250 | Sirsi | Guna | WRD | MIS | 2000-10-11 | DDM | 45.91 | RIDF Loan upto 10 crore | Time overrun likely, NB board not displayed
3 | R032000281 | Pulpuldoh | Chhindwara | WRD | MIS | 2000-09-28 | DDM | 240.7 | RIDF Loan upto 10 crore | NB board displayed but not on road side
3 | R032000227 | Kathotiya | Shahdol | WRD | MIS | 2000-09-14 | DDM | 82.93 | RIDF Loan upto 10 crore | Slow progress (railings for sluice approach, 1 foot moorum layer on nallah closing, grass turfing, 10% digging at chutefall, flush bar and 11 nos. culverts not yet completed), project likely to be completed by extended completion date of 31/3/01.
3 | R032000224 | Kolwakhedi | Ratlam | WRD | MIS | 2000-09-11 | DDM | 475.61 | RIDF Loan upto 10 crore | Work progress slow, time overrun likely, funds constraints, land acquisition problem,
3 | R032000147 | Guna Ashoknagar to Karod Guna Mhow | Guna | PWD | Road | 2000-07-07 | DDM | 48.61 | RIDF Loan upto 10 crore | Progress of work was satisfactory, cost overrun reproted on account of higher tenders, project likely to be completed by December 2000, i.e. before the completion date of 31.3.2001
3 | R032000158 | Guna Umri Sirsi Road | Guna | PWD | Road | 2000-07-07 | DDM | 91.06 | RIDF Loan upto 10 crore | Progress of work was satisfactory, cost escalation reported on account of higher tenders, project likely to be completed by December 2000 i.e. before the extended completion date of 31.3.2001.
3 | R032000007 | Indira Gandhi | Dhar | WRD | MIS | 2000-06-21 | DDM | 284.51 | RIDF Loan upto 10 crore | Delay in tendering( tendering for canal was yet to be taken up).
3 | R032000178 | Titoriya 13/10 | Chhindwara | PWD | Bridge | 2000-06-19 | DDM | 12.35 | RIDF Loan upto 10 crore | NB board was not displayed at the site, observation of technical nature( protective walls should be constructed for protection of abutments of the bridge as both the abutments were dangerously exposed to the force of the river water).
3 | R032000175 | Gohirari 5/2 | Shahdol | PWD | Bridge | 2000-06-08 | DDM | 16.99 | RIDF Loan upto 10 crore | NB board was not displayed at the site.
3 | R032000193 | Kased 16 | Shahdol | PWD | Bridge | 2000-06-08 | DDM | 49.32 | RIDF Loan upto 10 crore | NB board was not dislayed at the site, cost escalation of Rs. 2.97 lacs was reported.
3 | R032000044 | Tilgara-Satkunda | Dhar | PWD | Road | 2000-06-02 | DDM | 18.85 | RIDF Loan upto 10 crore | Work progress was satisfactory.
3 | R032000030 | Majhiyar-Padri-Pathari Road | Rewa | PWD | Road | 2000-05-31 | DDM | 23.54 | RIDF Loan upto 10 crore | Material problem(non-availability of asphalt )slow progress of work.
3 | R032000031 | Simanghat-Barroan Rd. | Rewa | PWD | Road | 2000-05-31 | DDM | 25.09 | RIDF Loan upto 10 crore | Delay in tendering, time overrun likely.
3 | R032000085 | Galchua 5/2 | Rewa | PWD | Bridge | 2000-05-31 | DDM | 12.87 | RIDF Loan upto 10 crore | Bridge completed
3 | R032000171 | Mahana 5/4 | Rewa | PWD | Bridge | 2000-05-31 | DDM | 3.95 | RIDF Loan upto 10 crore | Bridge completed
3 | R032000253 | Rusia | Guna | WRD | MIS | 2000-05-26 | DDM | 34.27 | RIDF Loan upto 10 crore | 1. Work almost complete(only the electricity connection was pending), 2. WRD should make efforts to get the electricity connection early.
3 | R032000015 | Bither | Khargone | WRD | MIS | 2000-05-25 | DDM | 91.44 | RIDF Loan upto 10 crore | As per annexure
3 | R032000135 | Padarkheda | Shivpuri | WRD | MIS | 2000-05-23 | DDM | 80.92 | RIDF Loan upto 10 crore | Delay in obtaining clearance from the Forest Department(earthwork for 150 m damlength was yet to be taken up due to non-compliance of conditions of forest department),delay in land acquisition, contractor problem(slow execution of work).
3 | R032000021 | Jat-Gwalior Kalan Sukhanand Road | Neemuch | PWD | Road | 2000-05-12 | RO Official | 79.01 | RIDF Loan upto 10 crore | Funds constraints, slow progress of work due to non-availability of funds as per requirement.
3 | R032000094 | Gawala | Khargone | WRD | MIS | 2000-05-12 | DDM | 19.69 | RIDF Loan upto 10 crore | Project completed, cost overrun reported, proposal for cost overrun was under preparation.
3 | R032000020 | Billod - Sanjeet | Mandsaur | PWD | Road | 2000-05-11 | RO Official | 17.8 | RIDF Loan upto 10 crore | Funds constraints, slow progress of work for non-availability of funds.
3 | R032000235 | Bangrasiya-Bilkhiriya | Bhopal | PWD | Road | 2000-05-11 | RO Official | 103.58 | RIDF Loan upto 10 crore | Delay in fixing agency, there was an increase in the road length which was justified by PWD.
3 | R032000025 | Melkheda-Sathkheda | Mandsaur | PWD | Road | 2000-05-10 | RO Official | 26.77 | RIDF Loan upto 10 crore | Funds constraints, slow progress of work, time overrun likely.
3 | R032000012 | Domara | Khargone | WRD | MIS | 2000-05-06 | DDM | 34.51 | RIDF Loan upto 10 crore | Project completed, cost overrun reported.
3 | R032000180 | Kanhan 4/6 | Chhindwara | PWD | Bridge | 2000-05-02 | DDM | 141.2 | RIDF Loan upto 10 crore | Contractor problem( very slow execution of the work from the beginning).
3 | R032000264 | Akbarpur | Vidisha | WRD | MIS | 2000-03-23 | DDM | 43.24 | RIDF Loan upto 10 crore | Funds constraints, delay in tendering and fixing agencies, slow progress of work, time overrun likely.
3 | R032000076 | Teonda Khurai via Pathari Road | Vidisha | PWD | Road | 2000-03-16 | DDM | 279.96 | RIDF Loan upto 10 crore | Funds constraints, slow progress of work.
3 | R032000077 | Andiakala Pachama Road | Vidisha | PWD | Road | 2000-03-15 | DDM | 124.1 | RIDF Loan upto 10 crore | Funds constraints, slow progress of work.
3 | R032000001 | Manki | Rajgarh | WRD | MIS |  |  | 72.11 | RIDF Loan upto 10 crore
3 | R032000008 | Bangwa | Khargone | WRD | MIS |  |  | 14.27 | RIDF Loan upto 10 crore
3 | R032000017 | Khajuri-Entkhedi-Mungaliachhad | Bhopal | PWD | Road |  |  | 69.95 | RIDF Loan upto 10 crore
3 | R032000028 | Umraoganj App.Road | Raisen | PWD | Road |  |  | 35.88 | RIDF Loan upto 10 crore
3 | R032000035 | Maharajpur-Jhamera | Sagar | PWD | Road |  |  | 63.08 | RIDF Loan upto 10 crore
3 | R032000039 | Waraseoni-Beni | Balaghat | PWD | Road |  |  | 51.6 | RIDF Loan upto 10 crore
3 | R032000056 | Ajapura-Awda Rd. | Sheopur | PWD | Road |  |  | 68.04 | RIDF Loan upto 10 crore
3 | R032000062 | Banjari-Shikara | Seoni | PWD | Road |  |  | 68.45 | RIDF Loan upto 10 crore
3 | R032000071 | Guwara | Dindori | WRD | MIS |  |  | 100.31 | RIDF Loan upto 10 crore
3 | R032000084 | Charanganga 59/10 | Umaria | PWD | Bridge |  |  | 54.7 | RIDF Loan upto 10 crore
3 | R032000088 | Chhatarpur Satai Rd 12/2 (R) | Chattarpur | PWD | Bridge |  |  | 17.59 | RIDF Loan upto 10 crore
3 | R032000089 | Chhatarpur Satai Rd 18/8(B) | Chattarpur | PWD | Bridge |  |  | 42.42 | RIDF Loan upto 10 crore
3 | R032000095 | Balia | Khargone | WRD | MIS |  |  | 141.6 | RIDF Loan upto 10 crore
3 | R032000097 | Ganeshpura | Shajapur | WRD | MIS |  |  | 1040.83 | RIDF Loan 10.01-24.99 crore
3 | R032000098 | Padariya | Chattarpur | WRD | MIS |  |  | 144.58 | RIDF Loan upto 10 crore
3 | R032000107 | Dongarmali Ghoti | Balaghat | PWD | Road |  |  | 35.52 | RIDF Loan upto 10 crore
3 | R032000111 | Ghansor Shikara | Seoni | PWD | Road |  |  | 52.82 | RIDF Loan upto 10 crore
3 | R032000151 | Ruthiyai Dharnawada Parwati Road | Guna | PWD | Road |  |  | 24.15 | RIDF Loan upto 10 crore
3 | R032000156 | Kamtada Sirali Makarai | Harda | PWD | Road |  |  | 54.39 | RIDF Loan upto 10 crore
3 | R032000157 | Shirali charwa road | Harda | PWD | Road |  |  | 56.73 | RIDF Loan upto 10 crore
3 | R032000174 | Alan 2/8 | Shahdol | PWD | Bridge |  |  | 21.34 | RIDF Loan upto 10 crore
3 | R032000177 | Kanhar 8/10 | Mandla | PWD | Bridge |  |  | 36.06 | RIDF Loan upto 10 crore
3 | R032000179 | Portitolla 15/2 | Balaghat | PWD | Bridge |  |  | 5.81 | RIDF Loan upto 10 crore
3 | R032000181 | Patney 42/8 | Panna | PWD | Bridge |  |  | 4 | RIDF Loan upto 10 crore
3 | R032000182 | Kel 31/4 | Chattarpur | PWD | Bridge |  |  | 33.75 | RIDF Loan upto 10 crore
3 | R032000185 | Paronch 16/2 | Shivpuri | PWD | Bridge |  |  | 23.87 | RIDF Loan upto 10 crore
3 | R032000186 | Sindh 10/8 | Guna | PWD | Bridge |  |  | 45.5 | RIDF Loan upto 10 crore
3 | R032000196 | Chakrar 13/8 | Dindori | PWD | Bridge |  |  | 30.85 | RIDF Loan upto 10 crore
3 | R032000197 | Wainganga 5/8 | Seoni | PWD | Bridge |  |  | 27 | RIDF Loan upto 10 crore
3 | R032000198 | Ghisari 5/10 | Balaghat | PWD | Bridge |  |  | 36 | RIDF Loan upto 10 crore
3 | R032000202 | Beda 2/8 | Khargone | PWD | Bridge |  |  | 40.45 | RIDF Loan upto 10 crore
3 | R032000204 | Barkheda Rathore | Mandsaur | WRD | MIS |  |  | 114.52 | RIDF Loan upto 10 crore
3 | R032000230 | Katangi Nandora | Balaghat | PWD | Road |  |  | 44.63 | RIDF Loan upto 10 crore
3 | R032000232 | Harda-Magardha | Harda | PWD | Road |  |  | 183.8 | RIDF Loan upto 10 crore
3 | R032000233 | Gorakhpur Gopalpur Chada | Dindori | PWD | Road |  |  | 150.82 | RIDF Loan upto 10 crore
3 | R032000239 | Muderi-Gaurihar | Chattarpur | PWD | Road |  |  | 59.56 | RIDF Loan upto 10 crore
3 | R032000240 | Rajnagar-Vikrampur | Chattarpur | PWD | Road |  |  | 29 | RIDF Loan upto 10 crore
3 | R032000247 | Patha Budera Kishanpur | Tikamgarh | PWD | Road |  |  | 133.25 | RIDF Loan upto 10 crore
3 | R032000249 | Majna Palera Road | Tikamgarh | PWD | Road |  |  | 199.65 | RIDF Loan upto 10 crore
3 | R032000256 | Sundi | Rajgarh | WRD | MIS |  |  | 47.45 | RIDF Loan upto 10 crore
3 | R032000257 | Hirankhedi | Rajgarh | WRD | MIS |  |  | 35.78 | RIDF Loan upto 10 crore
3 | R032000258 | Bhartendra | Rajgarh | WRD | MIS |  |  | 336.18 | RIDF Loan upto 10 crore
3 | R032000261 | Nipaniya | Shajapur | WRD | MIS |  |  | 427.7 | RIDF Loan upto 10 crore
3 | R032000279 | Khadkel | Khargone | WRD | MIS |  |  | 24.48 | RIDF Loan upto 10 crore
4 | r042000113 | Jujhari | Mandla | WRD | MIS | 2007-02-24 | Mandla DDM | 115.78 | RIDF Loan upto 10 crore | NABARD board has been displayed. Work is incomplete in regard to schut fall, cross drainage and canal work. At present the storage capacity of the tank is only 50% for want of schut fall. WRD to complete the project at the earliest.
4 | r042000153 | Bhatgaon | Mandla | WRD | MIS | 2007-02-24 | Mandla DDM | 96.68 | RIDF Loan upto 10 crore | 60 meter long schut fall, 225 mt of spill channel work and small amount of canal work is yet to be completed. Contractor has left due to difference in design of schut fall and expenditure involved. WRD to finish the project at the earliest.
4 | r042000100 | Patra | Satna | WRD | MIS | 2007-01-19 | Satna DDM | 252.88 | RIDF Loan upto 10 crore | PCR VERIFICATION. Interaction with the local population revealed that the construction of tank has benefitted them increasing irrigation of their fields. NABARD board is displayed at the tank site.
4 | r042000100 | Patra | Satna | WRD | MIS | 2007-01-19 | Satna DDM | 252.88 | RIDF Loan upto 10 crore | NABARD board has been displayed at the tank site instead of near the village where canal has been constructed. 28 Colaba pipes was not laid as they were not supplied. Turfing not done.
4 | r042000109 | Kachhari | Dindori | WRD | MIS | 2007-01-11 | Mandla DDM | 148.24 | RIDF Loan upto 10 crore | NABARD board has been displayed. Due to land acquisition problem the contractor has abandoned work since two years. Since June 2005 the work has been abandoned.
4 | R042000092 | Maloni | Guna | WRD | MIS | 2006-04-26 | Guna DDM | 120.55 | RIDF Loan upto 10 crore | Drainage work not carried out.
4 | r042000146 | Jagdhar | Betul | WRD | MIS | 2006-04-04 | Betul DDM | 146.94 | RIDF Loan upto 10 crore | It has benefitted cropping and fisheries development
4 | r042000117 | Magraura | Satna | WRD | MIS | 2006-01-13 | DDM | 88.92 | RIDF Loan upto 10 crore | Headworks completed. Pumps installed for lifting. Land acquisition is yet to be completed.
4 | R042000147 | Gopinathpur | Betul | WRD | MIS | 2005-08-25 | DDM | 111.85 | RIDF Loan upto 10 crore | PCR verified.
4 | R042000118 | Majhgawan | Satna | WRD | MIS | 2005-08-04 | OIC | 136.93 | RIDF Loan upto 10 crore | Report not submitted.
4 | R042000148 | Kanhasagar | Chhindwara | WRD | MIS | 2005-02-28 | DDM | 207.26 | RIDF Loan upto 10 crore | Project is completed in all respect
4 | R042000186 | Shivlal Dhana | Chhindwara | WRD | MIS | 2005-02-14 | DDM | 236.03 | RIDF Loan upto 10 crore | Project completed in all respect
4 | R042000146 | Jagdhar | Betul | WRD | MIS | 2005-01-05 | DDM | 146.94 | RIDF Loan upto 10 crore | Nala closure has been started. The work is likely to be completed by March 2005.
4 | R042000089 | Bijnakhedi | Shajapur | WRD | MIS | 2004-12-23 | DDM | 560.71 | RIDF Loan upto 10 crore | Report yet to be submitted.
4 | R042000147 | Gopinathpur | Betul | WRD | MIS | 2004-12-11 | DDM | 111.85 | RIDF Loan upto 10 crore | 995 of the work has been completed. NABARD Board was displayed on the road but not on site.
4 | R042000033 | Babirmatia | Sagar | WRD | MIS | 2004-12-10 | DDM | 553.85 | RIDF Loan upto 10 crore | Work relating to spill way and canals was in progress.WUA is not yet functional.
4 | R042000033 | Babirmatia | Sagar | WRD | MIS | 2004-12-10 | RO Official | 553.85 | RIDF Loan upto 10 crore | Report submitted
4 | R042000092 | Maloni | Guna | WRD | MIS | 2004-10-20 | DDM | 120.55 | RIDF Loan upto 10 crore | The work is held up due to rainy season. NABARD Board not displayed.
4 | R042000091 | Roopgarh | Jhabua | WRD | MIS | 2004-08-31 | DDM | 322.19 | RIDF Loan upto 10 crore | WUA should be formed. NABARD Board not displayed. Maintenance arrangements should be made.
4 | R042000180 | Hinoti | Rajgarh | WRD | MIS | 2004-06-30 | OIC+RO Officials | 88.51 | RIDF Loan upto 10 crore | The project has been physically completed. NABARD Board was not displayed.
4 | R042000092 | Maloni | Guna | WRD | MIS | 2004-04-24 | DDM | 120.55 | RIDF Loan upto 10 crore | 1)LA prob prevented work from starting on time 2)NB board not displayed 3)WUA not formed 4)Preliminary(I,II)/LA(I,II)/Earthwork(II)/Pumps(III):100%, Masonry(I):80%, Rising Main/MPEB connection:50%, Masonry(II):40%
4 | R042000224 | Pipliya Sehore | Ratlam | WRD | MIS | 2004-04-15 | DDM | 458.84 | RIDF Loan upto 10 crore | 1) Unit I - LA and preiliminary works completed.Dam:98.78%, Spill:95.58%, Masonry:33% 2) Unit II - Preliminary:52%, LA:19%, Masonry:62%, Earthwork:26%
4 | R042000069 | Naina 35/10 | Rewa | PWD | Bridge | 2004-04-11 | DDM | 155.35 | RIDF Loan upto 10 crore | LA not yet complete for approach road construction to start. Slow progress. Foundation of bridge yet to be completed. Superstructure work yet to commence. Substructure work in progress. NB board not displayed. Foundation:34.57%, Sub-structure:43.03%
4 | R042000113 | Jujhari | Mandla | WRD | MIS | 2004-03-24 | DDM | 115.78 | RIDF Loan upto 10 crore | Slow progress-earthwork & mesonry work not completed. Delay in LA for Unit-II. Time overrun- project likely to be completed by June 04 as against March 04. no officer above the rank of EE has visited the site . NB board not displayed.
4 | R042000153 | Bhatgaon | Mandla | WRD | MIS | 2004-03-24 | DDM | 96.68 | RIDF Loan upto 10 crore | Unit-I mesonry work not commenced & earthwork not completed. Incase of Unit-II earthwork not commenced & mesonry work not completed. Delay in LA process for Unit-I. Project likely to be completed by June 04 as against March 04.NB board not displayed.
4 | R042000176 | Ukhama 13/2 | Rewa | PWD | Bridge | 2004-03-23 | DDM | 149.08 | RIDF Loan upto 10 crore | Poor maintainance.NB board not displayed.
4 | R042000096 | Renjhai | Guna | WRD | MIS | 2004-03-22 | DDM | 63.34 | RIDF Loan upto 10 crore | NB board not displayed in the prescribed format.
4 | R042000079 | Hatpiplia - Tappa | Dewas | PWD | Road | 2004-03-22 | DDM | 33.76 | RIDF Loan upto 10 crore | 1) Project completed in March 2001. Lack of maintenance has led to damaged road surface at various places, road shoulders are missing. 2) Villagers of Deogarh find the road link useful for the accessiblity it provides to mandis of Hatpipliya and Sonk.
4 | R042000147 | Gopinathpur | Betul | WRD | MIS | 2004-03-16 | DDM | 111.85 | RIDF Loan upto 10 crore | WUA not formed
4 | R042000044 | Batkidoh | Betul | WRD | MIS | 2004-03-16 | DDM | 10.72 | RIDF Loan upto 10 crore | Project completed
4 | r042000148 | Kanhasagar | Chhindwara | WRD | MIS | 2004-03-15 | DDM | 207.26 | RIDF Loan upto 10 crore | Project completed.
4 | R042000034 | Khadda | Shahdol | WRD | MIS | 2004-03-13 | DDM | 68.4 | RIDF Loan upto 10 crore | WUA not formed.No proper maintainance.
4 | R042000088 | Rajendrgram Ghoghari | Anuppur | PWD | Road | 2004-03-12 | DDM | 234.09 | RIDF Loan upto 10 crore | Time overrun- project likely to be completed by May 2005 as against March 2004. Slow progress-overall progress is 92%.WBM, BT & CD work not completed.NB board to be displayed at other end.
4 | R042000069 | Naina 35/10 | Rewa | PWD | Bridge | 2004-03-11 | DDM | 155.35 | RIDF Loan upto 10 crore | tendering process for approach road not intiated. foundation & sub structure work not completed & super structure work not commenced. slow progress in LA of approach road. NB board not displayed.
4 | R042000157 | Sone 9/10 | Anuppur | PWD | Bridge | 2004-03-10 | DDM | 72.13 | RIDF Loan upto 10 crore | NB board not displayed.
4 | R042000178 | Sone 6/4 | Bhind | PWD | Bridge | 2004-02-28 | Consultant | 87.86 | RIDF Loan upto 10 crore | Project completed on 31/11/2000.
4 | R042000218 | Salkanpur Mardonpur | Sehore | PWD | Road | 2004-02-20 | Consultant | 67.31 | RIDF Loan upto 10 crore | Road settlement in patches were found,Premix metals from the BT surface have dispersed /scattered.and the WBM metals have exposed several places.
4 | R042000155 | Kolar | Sehore | WRD | MIP | 2004-02-20 | Consultant | 525.79 | RIDF Loan upto 10 crore | KPdiv-nasrulagunj water courses have not been constructedand the water scattered from field to field.
4 | R042000019 | Guaria | Sehore | WRD | MIS | 2004-02-19 | Consultant | 96.96 | RIDF Loan upto 10 crore | land acquisition is main hurdle in progress of the work .works related to headworks and pumping system ,constuction of control room have been completed.main canal work is in progress.
4 | R042000020 | Bagwara | Sehore | WRD | MIS | 2004-02-19 | Consultant | 70.21 | RIDF Loan upto 10 crore | land acquisition is main bottleneck in execution of the project.problems arises from landowner also.
4 | R042000166 | Mahan 104/10 | Sidhi | PWD | Bridge | 2004-02-18 | Consultant | 35.63 | RIDF Loan upto 10 crore | Project completed.
4 | R042000101 | Sehara | Sidhi | WRD | MIS | 2004-02-18 | Consultant | 163.65 | RIDF Loan upto 10 crore | masonry & earthwork yet to br completed. Contractor problem- chute fall work could not be done. Quality control-proper testing has not been done & no records available at site. Timeoverrun- project likely to be completed by June 04 as against March 04.
4 | R042000217 | Jontala Nawdner | Sehore | PWD | Road | 2004-02-17 | Consultant | 69.28 | RIDF Loan upto 10 crore | Number of potholes are formed on the BT surface.
4 | r042000099 | Rajali | Satna | WRD | MIS | 2004-02-15 | DDM | 103.49 | RIDF Loan upto 10 crore | WUA not formed.
4 | R042000009 | Noorabad Kharagpur BharrandPadawali | Morena | PWD | Road | 2004-02-15 | DDM | 56.1 | RIDF Loan upto 10 crore | Work is physically completed .Work done is satisfactory.Stone pitching is done at places .
4 | R042000009 | Noorabad Kharagpur BharrandPadawali | Morena | PWD | Road | 2004-02-15 | DDM | 56.1 | RIDF Loan upto 10 crore | Few damages to the road was observed. The BT seems to be very thin. NABARD Board was not displayed.
4 | r042000100 | Patra | Satna | WRD | MIS | 2004-02-12 | DDM | 252.88 | RIDF Loan upto 10 crore | Earth work not completed.NB board not dis played.
4 | R042000054 | Ganeshpura | Rajgarh | WRD | MIS | 2004-02-12 | Consultant | 222.94 | RIDF Loan upto 10 crore | Work completed.
4 | R042000206 | Mangrol Bagalwada | Raisen | PWD | Road | 2004-02-11 | Consultant | 157.38 | RIDF Loan upto 10 crore | The road's work has been completed.
4 | R042000205 | Bareli Bagalwada | Raisen | PWD | Road | 2004-02-11 | Consultant | 80.19 | RIDF Loan upto 10 crore | General workmanship appears to be satisfactory .Mandatory tests were carried out.
4 | R042000180 | Hinoti | Rajgarh | WRD | MIS | 2004-02-11 | Consultant | 88.51 | RIDF Loan upto 10 crore | Time overrun- project likely to be completed by September 04 as against March 04.
4 | R042000208 | Chatukheda Bamlabe | Rajgarh | PWD | Road | 2004-02-11 | Consultant | 198.93 | RIDF Loan upto 10 crore | Work completed.
4 | R042000136 | Baras Approach | Raisen | PWD | Road | 2004-02-10 | Consultant | 19.09 | RIDF Loan upto 10 crore | work has been completed.
4 | R042000075 | Udaipura - Silwani Road | Raisen | PWD | Road | 2004-02-10 | Consultant | 94.82 | RIDF Loan upto 10 crore | Delay in tendering ,cost escalation is likely,slow work progress
4 | R042000209 | Suthaliya Narsingarh | Rajgarh | PWD | Road | 2004-02-10 | Consultant | 241.94 | RIDF Loan upto 10 crore | CD works & BT not completed. work likely to be completed by June 04 as against March 04.Agency to be fixed for initial 15 kms. cracks developed on culverts,berns undersized, seal coat not provided & bridge approach at 20/10 km has been eroded.
4 | R042000117 | Magraura | Satna | WRD | MIS | 2004-02-09 | DDM | 88.92 | RIDF Loan upto 10 crore | Progress of implementation is unsatisfactory.Compensation for land acquisition is yet to be paid.
4 | R042000077 | Begamganj Sultanganj Road | Raisen | PWD | Road | 2004-02-09 | Consultant | 82.59 | RIDF Loan upto 10 crore | Road work has been completed but maintenance problem is there.
4 | R042000207 | Boda Borkheda | Rajgarh | PWD | Road | 2004-02-09 | Consultant | 214.77 | RIDF Loan upto 10 crore | Poor quality of works- CD work has developed cracks in many places,bern width is undersized at several places & seal coat not properly laid.
4 | R042000074 | Rajoda-Kailod | Dewas | PWD | Road | 2004-02-09 | DDM | 58.51 | RIDF Loan upto 10 crore | LA problem- one CD work yet to be completed due to LA .Inadequate Budgetary provision.Time overrun- work likely to be completed by June 04 as against March 04.
4 | R042000087 | Kailod-Double Chouki | Dewas | PWD | Road | 2004-02-09 | DDM | 131.54 | RIDF Loan upto 10 crore | LA problem- one km WBM & BT not done due to dispute.
4 | r042000128 | Khaparkheda-Chandon | Hoshangabad | PWD | Road | 2004-01-31 | DDM | 72.85 | RIDF Loan upto 10 crore | Poor maintainance .Monitoring mechanism- no officer above the rank of SDO has visited the site.
4 | R042000052 | Naharkhedi | Indore | WRD | MIS | 2004-01-31 | DDM | 301.85 | RIDF Loan upto 10 crore | WUA not formed.
4 | r042000126 | Roalgaon Magardha | Harda | PWD | Road | 2004-01-30 | Consultant | 118.75 | RIDF Loan upto 10 crore | Poor maintenance. The road is settled at a few location due to stagnation of irrigation water, canal water was flowing over the road near Mahanpur village. The thickness of BT Layer were formed at few places less than 20mm thickness.
4 | r042000127 | Harda Chhipaner | Harda | PWD | Road | 2004-01-29 | Consultant | 179.18 | RIDF Loan upto 10 crore | Slow progress - BT not done , as against 35 CD work only 24 CD work have been executed and time over run. Project is likely to be completed by June04 as against March'04, poor maintenance - the existing WBM is heavily eroded.
4 | r042000213 | Khurai Rajwans | Sagar | PWD | Road | 2004-01-29 | DDM | 236.72 | RIDF Loan upto 10 crore | Slow progress-the bridge work on the side of Sagar sub unit not completed.Contractor problem-due to lack of intrest of the contractor; the progress at Ujnethi to Khurai sector is slow.Funds problem
4 | r042000128 | Khaparkheda-Chandon | Hoshangabad | PWD | Road | 2004-01-28 | DDM | 72.85 | RIDF Loan upto 10 crore | Poor maintainance.Monitoring mechanism- no officer above SDO has visited the site.
4 | r042000132 | Runija Parasali | Mandsaur | PWD | Road | 2004-01-21 | DDM | 65.72 | RIDF Loan upto 10 crore | Project completed.
4 | R042000090 | Karanpura Tank No 2 | Dhar | WRD | MIS | 2004-01-15 | DDM | 37.76 | RIDF Loan upto 10 crore | The project is physically completed .Quality of work is not upto the mark.
4 | r042000141 | Singniwas Khurrai | Shivpuri | PWD | Road | 2004-01-14 | DDM | 84.4 | RIDF Loan upto 10 crore | NB Board not displayed
4 | r042000197 | Sanwer Panod Biloda Nayata | Indore | PWD | Road | 2004-01-12 | DDM | 19.03 | RIDF Loan upto 10 crore | NB Board not displayed, poor maintenance - condition of road in 0-2 & 2-5 KM is poor.
4 | r042000220 | Basoda Gurod | Vidisha | PWD | Road | 2004-01-06 | DDM | 39.21 | RIDF Loan upto 10 crore | Improper maintenance
4 | R042000220 | Basoda Gurod | Vidisha | PWD | Road | 2004-01-06 | DDM | 39.21 | RIDF Loan upto 10 crore | Most of the portions along the completed road are damaged. Locals are happy about the connectivity to Basoda Mandi that the road has provided. Separate agency has been fixed to look after maintenance of the road but nothing seems to have been done.
4 | r042000111 | Daulatpura | Jhabua | WRD | MIS | 2004-01-02 | DDM | 82.2 | RIDF Loan upto 10 crore | WUA not formed.NB board not displayed.
4 | r042000133 | Dhuankhedi Approach | Mandsaur | PWD | Road | 2003-12-31 | DDM | 39.45 | RIDF Loan upto 10 crore | NB Board not displayed
4 | R042000174 | Midasan 13/6 | Panna | PWD | Bridge | 2003-12-12 | RO Official | 48.76 | RIDF Loan upto 10 crore | 1. Poor maintenance of approach road.
4 | R042000190 | Buxwaha Nainagir Road | Chattarpur | PWD | Road | 2003-12-11 | RO Official | 113.08 | RIDF Loan upto 10 crore | Potholes observed at 8/2-9/4 KM & 18/6-18/8 KM, Slow progress, WBM & BT to be done at 1/2-1/6,14/10-17/10,19/10-21/10& about 10 meteres from 23/2 KM. Medium bridge to be completed at 21/2,21/8,23/2 & 23/8 KMs. No work since 2003 due to delay in payment.
4 | R042000123 | Bijawar Bajana | Chattarpur | PWD | Road | 2003-12-11 | RO Official | 252.19 | RIDF Loan upto 10 crore | Slow progress. Delay in payment, Nabard board not displayed at Bajna site.
4 | R042000002 | Jeoreha Barigarh Ghawara | Chattarpur | PWD | Road | 2003-12-10 | RO Official | 74.95 | RIDF Loan upto 10 crore | Project completed. PCR verified. Poor maintenance. Pot holes observed at 10,17/6,17/10,18/10,19/2,19/10,20/2,20/6,21/4,21/6,22/4, BT to be done at 18/10 about 60 meters, 27/6, 27/8 & few feets at 23/4 , 25/6-25/7 & 25/8-25/10 & 26/8 & 27/6-27/8 KMs
4 | R042000189 | Buxwaha Bajna Road | Chattarpur | PWD | Road | 2003-12-10 | RO Official | 102.45 | RIDF Loan upto 10 crore | 1. Potholes observed at 38/2 - 39/10, 40/2-40/8, 41/10-42/8, 44/4-44/8, 47/8-48/2 kms. 2. slow progress. Medium bridge at 45/8 53/6 km to be completed. At 53/6 - 53/8 kms WBM and BT to be done. 3. NB board not displayed at Bajna site.
4 | R042000024 | Sujara | Tikamgarh | WRD | MIS | 2003-12-09 | RO Official | 34.38 | RIDF Loan upto 10 crore | Electricity connection yet to be done by MPSEB.
4 | R042000088 | Rajendrgram Ghoghari | Anuppur | PWD | Road | 2003-11-30 | DDM | 234.09 | RIDF Loan upto 10 crore | Slow progress.
4 | R042000050 | Bardhanalla | Sheopur | WRD | MIS | 2003-11-13 | RO Official | 525.6 | RIDF Loan upto 10 crore | Delay due to Land Acquisition problem .
4 | r042000033 | Babirmatia | Sagar | WRD | MIS | 2003-11-07 | DDM | 553.85 | RIDF Loan upto 10 crore | LA problem for canal work, incase of unit - II masonery and earth work not completed.
4 | R042000091 | Roopgarh | Jhabua | WRD | MIS | 2003-10-28 | DDM | 322.19 | RIDF Loan upto 10 crore | 1. NB board not displayed. 2. Slow progress, time over-run, project completion date is June'04 as against March'03.
4 | R042000017 | Khoot Lohara Raitwari | Seoni | PWD | Road | 2003-10-16 | RO Official | 30.88 | RIDF Loan upto 10 crore | Project is completed.However in some stretch road condition is bad due to poor maintenance.
4 | R042000023 | Chhuleta | Vidisha | WRD | MIS | 2003-10-16 | RO Official | 66.15 | RIDF Loan upto 10 crore | Progress is very slow due to contractor problem
4 | R042000224 | Pipliya Sehore | Ratlam | WRD | MIS | 2003-10-15 | DDM | 458.84 | RIDF Loan upto 10 crore | Project Completed
4 | R042000052 | Naharkhedi | Indore | WRD | MIS | 2003-08-21 | OIC | 301.85 | RIDF Loan upto 10 crore | Project completed
4 | R042000224 | Pipliya Sehore | Ratlam | WRD | MIS | 2003-07-20 | DDM | 458.84 | RIDF Loan upto 10 crore | Land acquisition problem is hampering the work as only 31% and 19% is achievement in Unit I and Unit II for LA.
4 | R042000144 | Tajpur Najarpur | Ujjain | PWD | Road | 2003-05-13 | OIC | 147.93 | RIDF Loan upto 10 crore | WBM and BT not complete at Km 1. NB board not displayed.
4 | R042000011 | Lalgaon Mangawan | Rewa | PWD | Road | 2003-04-13 | OIC+RO Officials | 36.12 | RIDF Loan upto 10 crore | 3 speed breakers between Km 8/4 and 7/6 causing traffic problem, sink at Km 3/2, NB board not displayed.
4 | R042000092 | Maloni | Guna | WRD | MIS | 2003-03-18 | DDM | 120.55 | RIDF Loan upto 10 crore | Land acquisition problem (delay in land acquisition), contractor problem (agency's failure to take up work for jackwell), inadequate monitoring mechanism (project not monitored by officer above EE rank). NB board not displayed in proper format.
4 | R042000123 | Bijawar Bajana | Chattarpur | PWD | Road | 2003-03-12 | RO Official | 252.19 | RIDF Loan upto 10 crore | Contractor problem (Aug 02-Jan 03,no work was done by contractor, WBM&BT not done on 1/10, 3/8-3/10,5/10-6/2,23/2-26/8km, BT not done on CDs at 9/6,10/4,11/6,11/8,11/10&13/10km & at 14/2-14/10 km portion of road & about 100m length area at 17/6 km
4 | R042000213 | Khurai Rajwans | Sagar | PWD | Road | 2003-03-10 | DDM | 236.72 | RIDF Loan upto 10 crore | Contractor problem (contractor not taking interest), slow progress (the work Ujnethi to Khurai is very slow due to low budget. NB board not displayed in proper format.
4 | R042000074 | Rajoda-Kailod | Dewas | PWD | Road | 2003-02-19 | DDM | 58.51 | RIDF Loan upto 10 crore | Slow progress (the project delayed due to change in agency and revision of specifications), Land acquisition problem (for CD at 1/8 km), WBM work of several portion of road not taken up, Quality of work (the quality of BT surface is very poor).
4 | R042000087 | Kailod-Double Chouki | Dewas | PWD | Road | 2003-02-19 | DDM | 131.54 | RIDF Loan upto 10 crore | the first contractor left the work incomplete, land dispute pending in court, due to long gap in fixing second contractor, the surface got damaged, in some patches the shoulder have been left unfilled due to which edges of the road have been damaged
4 | R042000196 | Maharajganj Simrol | Indore | PWD | Road | 2003-01-21 | DDM | 38.63 | RIDF Loan upto 10 crore | Time overrun, land acquisition problem (due to land acquisition problem work could not be taken up), payment of Rs 5.35 lakh has been made to Revenue Dept., likely date of completion March 2004.
4 | R042000193 | Bhonra Kohan | Guna | PWD | Road | 2003-01-14 | DDM | 94.14 | RIDF Loan upto 10 crore | Road surface not plane, compaction of earthwork not proper, CDs in dilapidated condition, cracks observed on CDs), no officer above SDO visited the site), project completed. NB board not displayed in proper format.
4 | R042000194 | Kohan Hamirpur | Guna | PWD | Road | 2003-01-14 | DDM | 63.56 | RIDF Loan upto 10 crore | Unsatisfactory quality (road surface not plane, the compaction of earth work is not done properly, CDs were in dilapidated condition, cracks have been observed on the side walls of CDs), project completed. NB board not displayed in proper format.
4 | R042000091 | Roopgarh | Jhabua | WRD | MIS | 2002-12-31 | DDM | 322.19 | RIDF Loan upto 10 crore | Time overrun (80% of earthwork of headwork completed, canal work yet to be started), no arrangement for maintenance, NB board not displayed.
4 | R042000148 | Kanhasagar | Chhindwara | WRD | MIS | 2002-12-29 | DDM | 207.26 | RIDF Loan upto 10 crore | Project completed.
4 | R042000115 | Gangapur | Guna | WRD | MIS | 2002-12-27 | DDM | 124.43 | RIDF Loan upto 10 crore | Supervision not proper. Work of construction of overhead tank not yet started. Seepage of water has caused delay in laying inlet water pipes from river bank to jack-well.
4 | R042000052 | Naharkhedi | Indore | WRD | MIS | 2002-12-24 | DDM | 301.85 | RIDF Loan upto 10 crore | Land acquisition problem. WUA not formed.
4 | R042000224 | Pipliya Sehore | Ratlam | WRD | MIS | 2002-12-13 | DDM | 458.84 | RIDF Loan upto 10 crore | Land acquisition progress should be made fast.
4 | R042000033 | Babirmatia | Sagar | WRD | MIS | 2002-11-18 | DDM | 553.85 | RIDF Loan upto 10 crore | Slow progress (completion is 45% though commenced in 1998).
4 | R042000060 | Tipan 3/8 | Anuppur | PWD | Bridge | 2002-10-18 | DDM | 95.03 | RIDF Loan upto 10 crore | NB board not displayed. Slow progress.
4 | R042000082 | Anuppur - Mediaras Amlai Road | Anuppur | PWD | Road | 2002-10-17 | DDM | 25.61 | RIDF Loan upto 10 crore | Black topping damaged at many places. Quality of work is poor. NB board not displayed. Delay in tendering. Slow progress.
4 | R042000088 | Rajendrgram Ghoghari | Anuppur | PWD | Road | 2002-10-05 | DDM | 234.09 | RIDF Loan upto 10 crore | NB board displayed at one end only. Road has damaged at 15 places. Poor monitoring and supervision.
4 | R042000143 | Jawasiya Talod | Ujjain | PWD | Road | 2002-09-25 | DDM | 49.22 | RIDF Loan upto 10 crore | Flanking has not been done at several places. There is no maintenance of road after construction.
4 | R042000084 | Amliya - Harrai - Semaria | Satna | PWD | Road | 2002-08-22 | DDM | 30.34 | RIDF Loan upto 10 crore | NB board not displayed. km 7 & 8 have been submerged under command area of Bansagar dam
4 | R042000214 | Ahirgaon Ramgarh Mukundpur | Satna | PWD | Road | 2002-08-22 | DDM | 117.6 | RIDF Loan upto 10 crore | Completed. BT edges require protection by providing shoulders
4 | R042000216 | Kharamseda Kirhai Ramgarh | Satna | PWD | Road | 2002-08-22 | DDM | 97 | RIDF Loan upto 10 crore | Completed. Approach of CD works not included under RIDF, need to be done with dept funds as these have been left as gaps
4 | R042000139 | Khardonekala Ugli Shujalpur | Shajapur | PWD | Road | 2002-07-03 | RO Official | 252.79 | RIDF Loan upto 10 crore | BT work in a stretch of 10 km from Shujalpur end is damaged and undulating, contractor is slow, Slow Progress ( WBM + BT is yet to be done in Km 1 to 4, Km 7/4 and Km 18-19), Others (road has been cut at Km 25 & 23/6)
4 | R042000034 | Khadda | Shahdol | WRD | MIS | 2002-06-18 | DDM | 68.4 | RIDF Loan upto 10 crore | Slow progress (delay in tendering).
4 | R042000001 | Konhor Baraso | Bhind | PWD | Road | 2002-06-12 | RO Official+C | 42.03 | RIDF Loan upto 10 crore | Report as per Annexure.
4 | R042000113 | Jujhari | Mandla | WRD | MIS | 2002-06-11 | DDM | 115.78 | RIDF Loan upto 10 crore | Slow progress (sanctioned in 98-99 but tender settled in 4/2002, tender called in 10/2001). NB board to be displayed.
4 | R042000153 | Bhatgaon | Mandla | WRD | MIS | 2002-06-11 | DDM | 96.68 | RIDF Loan upto 10 crore | Slow progress (sanctioned in 98-99 but tender settled in 4/2002, tender called in 10/2001). NB board to be displayed.
4 | R042000071 | Linga - Chhitapar Bhourjir Road | Narsinghpur | PWD | Road | 2002-06-07 | DDM | 45.13 | RIDF Loan upto 10 crore | Slow progress (originally it was to be compelted by 3/2001, but still incomplete).
4 | R042000134 | Gadarwara-Tendukheda Kakaraghat | Narsinghpur | PWD | Road | 2002-06-06 | DDM | 93.09 | RIDF Loan upto 10 crore | Slow progress (originally it was to be compelted by 3/2001, but still incomplete).
4 | R042000135 | Singoli-Tilasma | Neemuch | PWD | Road | 2002-05-28 | RO Official+C | 70.31 | RIDF Loan upto 10 crore | NB board not displayhed. Surface is not to camber
4 | R042000056 | Nimgul | Khargone | WRD | MIS | 2002-05-23 | DDM | 96.21 | RIDF Loan upto 10 crore | Completed. WUA to be formed.
4 | R042000003 | Boriya Malhanwara Kotalbarri Umrahar | Chhindwara | PWD | Road | 2002-05-20 | DDM | 95.66 | RIDF Loan upto 10 crore | Completed.
4 | R042000018 | Phunga Semariha | Anuppur | PWD | Road | 2002-05-15 | DDM | 56.08 | RIDF Loan upto 10 crore | Completed. Poor quality (BT damaged in some places). NB board to be displayed.
4 | R042000083 | Dulhara-Pipriya-Kasapagna | Anuppur | PWD | Road | 2002-05-15 | DDM | 90.37 | RIDF Loan upto 10 crore | Slow progress (late tendering). Original date of completion ws 3/2001). NB board to be displayed.
4 | R042000210 | Ratlam Dhawasuth | Ratlam | PWD | Road | 2002-05-15 | DDM | 95.45 | RIDF Loan upto 10 crore | NB board to be displayed. Completed. PCR verified.
4 | R042000219 | Deori Devgiwan | Shahdol | PWD | Road | 2002-05-15 | DDM | 55.05 | RIDF Loan upto 10 crore | Slow progress (late tendering). Original date of completion ws 3/2001). NB board to be displayed.
4 | R042000096 | Renjhai | Guna | WRD | MIS | 2002-05-14 | DDM | 63.34 | RIDF Loan upto 10 crore | Completed. NB board not displayed.
4 | R042000023 | Chhuleta | Vidisha | WRD | MIS | 2002-05-07 | DDM | 66.15 | RIDF Loan upto 10 crore | Slow progress (inadequate attention from dept. staff). Contractor problem (contractor changed).
4 | R042000074 | Rajoda-Kailod | Dewas | PWD | Road | 2002-05-03 | DDM | 58.51 | RIDF Loan upto 10 crore | Dept. has not prepared estimate as per actual site conditions, which is resulting in inadequate provision for crust thickness and LA. Revised estimate is pending for approval with govt.
4 | R042000011 | Lalgaon Mangawan | Rewa | PWD | Road | 2002-04-30 | DDM | 36.12 | RIDF Loan upto 10 crore | Slow progress. NB board not displayed. Contractor problem.
4 | R042000186 | Shivlal Dhana | Chhindwara | WRD | MIS | 2002-04-29 | DDM | 236.03 | RIDF Loan upto 10 crore | Slow progress (contractor is slow). LA (delay in payment of compensation)
4 | R042000187 | Borgaon | Chhindwara | WRD | MIS | 2002-04-28 | DDM | 115.79 | RIDF Loan upto 10 crore | Slow progress (work sanctioned in 98-99 was started only in Mar 02). Contractor problem (not showin interest and has sublet the work)
4 | R042000078 | Jaora - Sitamau | Ratlam | PWD | Road | 2002-04-24 | DDM | 148.46 | RIDF Loan upto 10 crore | In progress
4 | R042000067 | Sindh 12/2 | Shivpuri | PWD | Bridge | 2002-04-23 | DDM | 104.7 | RIDF Loan upto 10 crore | Slow progress (approach road of 0.37 km not done, contract terminated, approval for design change pending at CE office).
4 | R042000134 | Gadarwara-Tendukheda Kakaraghat | Narsinghpur | PWD | Road | 2002-04-20 | RO Official+C | 93.09 | RIDF Loan upto 10 crore | As per annexure
4 | R042000224 | Pipliya Sehore | Ratlam | WRD | MIS | 2002-04-19 | DDM | 458.84 | RIDF Loan upto 10 crore | NB board not displayed. Slow progress (work sanctioned in 98-99 is still incomplete).
4 | R042000140 | Gora-Pichhore | Shivpuri | PWD | Road | 2002-04-16 | DDM | 190.9 | RIDF Loan upto 10 crore | Contractor problem (work terminated due to poor quality). Others (CD work and approaches to CD not done due to funds constraint).
4 | R042000223 | Dholka | Ratlam | WRD | MIS | 2002-04-16 | DDM | 65.33 | RIDF Loan upto 10 crore | NB board to be displayed.
4 | R042000141 | Singniwas Khurrai | Shivpuri | PWD | Road | 2002-04-12 | DDM | 84.4 | RIDF Loan upto 10 crore | Berms of 1-1/2 feet on both sides for 14 km not taken up.
4 | R042000142 | Mohana-Pohari to AB Road | Shivpuri | PWD | Road | 2002-04-12 | DDM | 158.68 | RIDF Loan upto 10 crore | Slow progress (CD work contract terminated due to slow progress). Berms 1-1/2 feet on both sides for 12 km not done.
4 | R042000185 | Ambadungra | Jhabua | WRD | MIS | 2002-04-12 | DDM | 34 | RIDF Loan upto 10 crore | Slow progress (delayed by more than 1 year). NB board to be displayed
4 | R042000130 | Kothara Approach Road | Hoshangabad | PWD | Road | 2002-04-11 | DDM | 37.47 | RIDF Loan upto 10 crore | dispute between contractor and dept., contractor is slow in work due to non-payment of bills, progress is only about 30%) , Inadequate monitoring by department (monitoring by officers of the rank of EE & above not done)
4 | R042000124 | Bhitarwar Karaiya | Gwalior | PWD | Road | 2002-04-09 | DDM | 73.35 | RIDF Loan upto 10 crore | Filling of flanks on both sides for about 10 km stretch is yet to be completed. BT eroded at certain places to be repaired.
4 | R042000085 | Rehli Salwara Gourjhamar | Sagar | PWD | Road | 2002-03-18 | DDM | 109.31 | RIDF Loan upto 10 crore | Report awaited
4 | R042000085 | Rehli Salwara Gourjhamar | Sagar | PWD | Road | 2002-03-18 | DDM | 109.31 | RIDF Loan upto 10 crore | NB board not displayed. Slow progress (LA, CD works).
4 | R042000112 | Rewamandhi | Jhabua | WRD | MIS | 2002-03-15 | DDM | 62.85 | RIDF Loan upto 10 crore | NB board not displayed.
4 | R042000133 | Dhuankhedi Approach | Mandsaur | PWD | Road | 2002-02-28 | RO Official | 39.45 | RIDF Loan upto 10 crore | Observations of technical nature (Two additional CDs proposed at Km 4/8 and Km 6/6 which according to the dept. were necessary considering the site conditions -which aspect however was overlooked at the time of preparation of proposal for NB sanction.
4 | R042000132 | Runija Parasali | Mandsaur | PWD | Road | 2002-02-27 | RO Official | 65.72 | RIDF Loan upto 10 crore | additional work of stop dam on vented causeway with shutters undertaken), RAA not yet received, Cost overrun likely for increase in rate and quantity of work, work likely to be completed by June 02 as against the extended completion date of 31-3-02.
4 | R042000110 | Rehanda | Jhabua | WRD | MIS | 2002-02-05 | DDM | 49.64 | RIDF Loan upto 10 crore | NABARD board not displayed.
4 | R042000112 | Rewamandhi | Jhabua | WRD | MIS | 2002-02-01 | DDM | 62.85 | RIDF Loan upto 10 crore | No arrangement for maintenance has been made, NABARD board not displayed, WUA not yet formed.
4 | R042000137 | Nirtala-Bhapsone | Sagar | PWD | Road | 2002-01-31 | DDM | 61.6 | RIDF Loan upto 10 crore | Embankment height and crust requirement not asessed properly as per site condition, work held up.
4 | R042000213 | Khurai Rajwans | Sagar | PWD | Road | 2002-01-31 | DDM | 236.72 | RIDF Loan upto 10 crore | Design of crust not done as per site condition.
4 | R042000148 | Kanhasagar | Chhindwara | WRD | MIS | 2002-01-25 | DDM | 207.26 | RIDF Loan upto 10 crore | Work in progress.
4 | R042000174 | Midasan 13/6 | Panna | PWD | Bridge | 2002-01-23 | RO Official | 48.76 | RIDF Loan upto 10 crore | Length of approach reduced from 500 to 305 m. Pitching to be done. PWD may review the extension of toe wall. Dept. to follow up with Collector for expediting LA award. Likely cost overrun due to higher cost of approach, tender premium.
4 | R042000006 | Jabalpur Purena | Jabalpur | PWD | Road | 2002-01-22 | DDM | 48.06 | RIDF Loan upto 10 crore | Completed, quality control register not maintained, pot holes observed at a few places, road level lower than adjoining fields
4 | R042000007 | Panagar Belkhadu | Jabalpur | PWD | Road | 2002-01-22 | DDM | 33.88 | RIDF Loan upto 10 crore | Completed, quality control register not maintained, pot holes observed at a few places.
4 | R042000128 | Khaparkheda-Chandon | Hoshangabad | PWD | Road | 2002-01-10 | DDM | 72.85 | RIDF Loan upto 10 crore | Slow progress (Although 2 years extension upto 12/2002 is given, progress is only about 40%), Quality not satisfactory (condition bad with pot-holes, sub-base and Gr-II thickness is not as per specification)
4 | R042000086 | Bhabhara - Katthiwara Road | Alirajpur | PWD | Road | 2002-01-09 | DDM | 66.46 | RIDF Loan upto 10 crore | NB board not displayed, BT worn out
4 | R042000116 | Mahmoodpur | Rewa | WRD | MIS | 2002-01-01 | DDM | 56.81 | RIDF Loan upto 10 crore | LA problem (LA compensation not paid), power not available due to pending bills, minor canal 13.50 m to be undertaken
4 | R042000063 | Keotan 7/2 | Vidisha | PWD | Bridge | 2001-12-27 | DDM | 43.96 | RIDF Loan upto 10 crore | NB board not displayed.
4 | R042000220 | Basoda Gurod | Vidisha | PWD | Road | 2001-12-27 | DDM | 39.21 | RIDF Loan upto 10 crore | Poor quality (road is damaged). NB board not displayed.
4 | R042000226 | Khorhary | Anuppur | WRD | MIS | 2001-12-26 | DDM | 22.56 | RIDF Loan upto 10 crore | Project likely to be withdrawn (Ref. EE, WRD, Shahdol's letter dated 10/12/01 addressed to DDM)
4 | R042000093 | Dehri | Guna | WRD | MIS | 2001-12-21 | DDM | 164 | RIDF Loan upto 10 crore | Not started.
4 | R042000130 | Kothara Approach Road | Hoshangabad | PWD | Road | 2001-12-19 | DDM | 37.47 | RIDF Loan upto 10 crore | Slow progress (work stopped due to non payment of bills), Contractor problem (dispute between contractor and dept), material problem (side earth not available for filling), Others(monsoon in 2001 damaged the WBM and EW)
4 | R042000009 | Noorabad Kharagpur BharrandPadawali | Morena | PWD | Road | 2001-11-30 | DDM | 56.1 | RIDF Loan upto 10 crore | Slow progress (Work stopped, contract cancelled and awardede to new contractor)
4 | R042000113 | Jujhari | Mandla | WRD | MIS | 2001-11-22 | DDM | 115.78 | RIDF Loan upto 10 crore | Slow progress due to late receipt of funds, Requires close supervision as it is already delayed.
4 | R042000153 | Bhatgaon | Mandla | WRD | MIS | 2001-11-22 | DDM | 96.68 | RIDF Loan upto 10 crore | Slow progress (LA- money to be released, funds received late), Requires close supervision as it is already delayed.
4 | R042000122 | Donchara Gopalpura | Bhind | PWD | Road | 2001-11-08 | RO Official+C | 143.49 | RIDF Loan upto 10 crore | No physical work commenced at site, Abnormal delay in tendering (tenders were due on 9-11-01 and hence no work agency could be fixed till date of visit), Time overrun likely
4 | R042000023 | Chhuleta | Vidisha | WRD | MIS | 2001-11-07 | DDM | 66.15 | RIDF Loan upto 10 crore | work not yet commenced, project likely to be completed by June 03 as against the extended completion due date of 31/3/02, agency fixed earlier for road work abondoned the work, progress of implementation not being reviewed by EE/SE/CE
4 | R042000069 | Naina 35/10 | Rewa | PWD | Bridge | 2001-11-07 | DDM | 155.35 | RIDF Loan upto 10 crore | Slow progress (work just commenced). Acquisition for approach road to be completed. NB board not displayed.
4 | R042000074 | Rajoda-Kailod | Dewas | PWD | Road | 2001-11-06 | DDM+C | 58.51 | RIDF Loan upto 10 crore | Report received
4 | R042000068 | Asan 8/8 | Morena | PWD | Bridge | 2001-10-31 | DDM | 137.83 | RIDF Loan upto 10 crore | PCR Verification-On Sumawali side approach road is required for full utility of the road
4 | R042000214 | Ahirgaon Ramgarh Mukundpur | Satna | PWD | Road | 2001-10-31 | DDM | 117.6 | RIDF Loan upto 10 crore | Slow progress (shoulders not included in the original sanction), Bt done earlier is damaged.
4 | R042000216 | Kharamseda Kirhai Ramgarh | Satna | PWD | Road | 2001-10-31 | DDM | 97 | RIDF Loan upto 10 crore | Slow progress (approach roads of Cd works not included originally, requires revised approval), Requires close supervision as it is already delayed.
4 | R042000091 | Roopgarh | Jhabua | WRD | MIS | 2001-10-29 | DDM+C | 322.19 | RIDF Loan upto 10 crore | Slow progress of work (), Funds constraints (inadequate allotment for the years 99-00 & 00-01), Delay in tendering (), Time overrun likely (project likely to be completed only by June 02 as against the extended due date of 31/3/02)
4 | R042000111 | Daulatpura | Jhabua | WRD | MIS | 2001-10-29 | DDM+C | 82.2 | RIDF Loan upto 10 crore | Slow progress, Delay in tendering, project likely to be completed by June 02 as against the extended completion date of 31/3/02), progress of implementation not being reviewed regularly by EE/SE/CE, NB board not displayed.
4 | R042000044 | Batkidoh | Betul | WRD | MIS | 2001-10-24 | DDM | 10.72 | RIDF Loan upto 10 crore | work not yet commenced, Delay in tendering, Inadequate monitoring by the department (progress of implementation not being reviewed by EE/SE/CE), NB board not displayed.
4 | R042000147 | Gopinathpur | Betul | WRD | MIS | 2001-10-24 | DDM | 111.85 | RIDF Loan upto 10 crore | Slow progress of work (work not yet commenced), Delay in tendering (although the project was sanctioned during 98-99, no tenders were floated till date of visit), Delay in land acquisition (land not yet acquired -10.25 ha in Unit I & 5.66 ha in Unit II).
4 | R042000117 | Magraura | Satna | WRD | MIS | 2001-10-19 | DDM | 88.92 | RIDF Loan upto 10 crore | Delay in land acquisition (9.16 ha land under Unit II not yet acquired), Delay in tendering (tendering under Units II & III not yet initiated in absence of TS), Slow progress of work (land acquisition, masonry earthwork under Unit II not yet commenced
4 | R042000099 | Rajali | Satna | WRD | MIS | 2001-10-17 | DDM | 103.49 | RIDF Loan upto 10 crore | Delay in land acquisition (9.1 ha land under Unit I and 5.38 ha land under Unit II not yet acquired), Slow progress of work (no progress of work except the preliminary work under Units I & II), Time overrun likely
4 | R042000110 | Rehanda | Jhabua | WRD | MIS | 2001-10-12 | DDM | 49.64 | RIDF Loan upto 10 crore | Slow progress (work not started)
4 | R042000111 | Daulatpura | Jhabua | WRD | MIS | 2001-10-11 | DDM | 82.2 | RIDF Loan upto 10 crore | Slow progress (canal work not completed)
4 | R042000185 | Ambadungra | Jhabua | WRD | MIS | 2001-10-10 | DDM | 34 | RIDF Loan upto 10 crore | Slow progress (canal work not started), NB board not displayed
4 | R042000118 | Majhgawan | Satna | WRD | MIS | 2001-10-09 | DDM | 136.93 | RIDF Loan upto 10 crore | Delay in tendering (tendering under Unit I in process and that under Units II & III not yet initiated), Delay in land acquisiton (0.3 ha land under Unit I and 13.86 ha land under Unit II not yet acquired),
4 | R042000074 | Rajoda-Kailod | Dewas | PWD | Road | 2001-10-08 | DDM | 58.51 | RIDF Loan upto 10 crore | Slow progress, Delay in LA, unsatisfactory quality of work, inadequate monitoring by department, contractor problem, absence of regular EE and want of inspection vehicles in the division is found to be affecting the progress of work.
4 | R042000087 | Kailod-Double Chouki | Dewas | PWD | Road | 2001-10-08 | DDM | 131.54 | RIDF Loan upto 10 crore | Slow progress, Delay in tendering, Delay in LA, Contractor problem, project likely to be completed only by June 02, Unsatisfactory quality of work, progress of implementation not reviewed by EE/SE/CE.
4 | R042000034 | Khadda | Shahdol | WRD | MIS | 2001-09-18 | DDM | 68.4 | RIDF Loan upto 10 crore | Work not yet commenced), Delay in tendering (although the project was sanctioned during 98-99, the tendering for Units I & II not yet finalised), Time overrun likely (project likely to spill over beyond the extended completion due date of 31/3/02)
4 | R042000100 | Patra | Satna | WRD | MIS | 2001-09-11 | DDM | 252.88 | RIDF Loan upto 10 crore | Slow work progress (Earthwork for dam only in progress), Cost overrun likely, Time overrun likely (project likely to spill over beyond the extended completion due date of 31.3.02), Delay in tendering
4 | R042000210 | Ratlam Dhawasuth | Ratlam | PWD | Road | 2001-07-03 | DDM | 95.45 | RIDF Loan upto 10 crore | Work in progress, Nothing particular reported, PCR format used for monitoring.
4 | R042000195 | Baghana Baloda Takun Road | Indore | PWD | Road | 2001-06-01 | DDM | 61.52 | RIDF Loan upto 10 crore | Slow progress of work (WBM for 4.115 km out of 9.115 km, BT for the entire road length of 9.115 km and 4 out of 11 CDs remained incomplete), Delay in fixing agency (agency fixed only recently).
4 | R042000196 | Maharajganj Simrol | Indore | PWD | Road | 2001-06-01 | DDM | 38.63 | RIDF Loan upto 10 crore | Slow progress of work (WBM and BT for 2.60 km out of 7.60 km and all 4 CDs remained incomplete), PWD may speed up the work so as to complete it before the extended completion date of 31/3/02, Delay in fixing agency (agencies fixed only recently).
4 | R042000197 | Sanwer Panod Biloda Nayata | Indore | PWD | Road | 2001-06-01 | DDM | 19.03 | RIDF Loan upto 10 crore | Slow progress of work (both CDs remained incomplete), Delay in fixing agency (agency has been fixed only recently), NB board not displayed, PWD may note to complete the project before the extended completion date of 31/3/02.
4 | R042000131 | Mohas-Lalpurpal | Katni | PWD | Road | 2001-05-26 | RO Official | 132.86 | RIDF Loan upto 10 crore | Physical progress of work (76%, subbase-7.6 km out of 9 km of balance work, WBM- I-7.6 km, II-7.6 km, III-12.0 km out of 17 km of balance work, BT 12 km out of 17 km, CD 28 out of 30 structures proposed), contractor problem
4 | R042000008 | Basadi Badawara | Katni | PWD | Road | 2001-05-25 | RO Official | 41.8 | RIDF Loan upto 10 crore | Project completed on 11/12/00, NB board not displayed.
4 | R042000076 | Vijay Raghavgarh Katni Amari Road | Katni | PWD | Road | 2001-05-25 | RO Official | 87.32 | RIDF Loan upto 10 crore | Contractor problem, project is likely to be completed only by June 2001, quality of work completed not satisfactory (shoulders are not properly dressed), NB board not displayed.
4 | R042000176 | Ukhama 13/2 | Rewa | PWD | Bridge | 2001-05-24 | DDM | 149.08 | RIDF Loan upto 10 crore | Bridge was complete but approach roads were incomplete, NB board not displayed, suggestion that damaged connecting road on Jadua side be repaired immediately to ensure proper utilization of the bridge.
4 | R042000200 | Phanwani Dhakarwah | Katni | PWD | Road | 2001-05-24 | RO Official | 47.93 | RIDF Loan upto 10 crore | Contractor problem (E-in-C, PWD has accorded sanction vide letter dt. 10/3/99, tenders were called for on 21/5/99 and work order issued to M/s. Balaji Construction &Boring Co., Teekamgarh on 15/7/99. Contractor did not start work.
4 | R042000201 | Sunguli Kamhni | Katni | PWD | Road | 2001-05-24 | RO Official | 38.44 | RIDF Loan upto 10 crore | Contactor problem (E-in-C, PWD has accorded sanction vide letter dt. 10/3/99. Tenders were called for on 11/6/99 and work order was issued to M/s. Balaji Constn. & Boring Co., Teekamgarh on 15/7/99. Contractor did not start the work.
4 | R042000090 | Karanpura Tank No 2 | Dhar | WRD | MIS | 2001-05-23 | DDM | 37.76 | RIDF Loan upto 10 crore | Masonry work-15%, earthwork-20% for dam and 50% for spill under Unit I and entire work under Unit II except the preliminary work remained incomplete.
4 | R042000208 | Chatukheda Bamlabe | Rajgarh | PWD | Road | 2001-05-15 | RO Official | 198.93 | RIDF Loan upto 10 crore | Time overrun likely (project likely to be completed only by March 02 as against the due date of March 01), entire WBM, BT and 70% of CDs remained incomplete, work affected owing to scarcity of water for drought conditions in the district.
4 | R042000207 | Boda Borkheda | Rajgarh | PWD | Road | 2001-05-14 | RO Official | 214.77 | RIDF Loan upto 10 crore | Time overrun likely (project likely to be completed only by March 02 as against the due date of March 01), cost overrun likely on account of delay in fixation of agency and higher tender rates, WBM, BT and 30% of the CDs remained incomplete.
4 | R042000209 | Suthaliya Narsingarh | Rajgarh | PWD | Road | 2001-05-14 | RO Official | 241.94 | RIDF Loan upto 10 crore | Time overrun likely (project likely to be completed only by March 02 as against the due date of March 01), 70% sub-base, 50% sub-grade, 30% WBM, the entire BT and 10 out of 30 CDs remained incomplete, work affected owing to water scarcity.
4 | R042000220 | Basoda Gurod | Vidisha | PWD | Road | 2001-05-09 | DDM | 39.21 | RIDF Loan upto 10 crore | Project completed in March 2001, PCR however not received, NB board not displayed, observations of technical nature (BT is only 2 cm thick and may not sustain coming monsoon).
4 | R042000198 | Mankhedi Patan | Jabalpur | PWD | Road | 2001-05-08 | DDM | 71.15 | RIDF Loan upto 10 crore | Slow progress of work (8 out of 9 CD work remained incomplete), time overrun likely (project likely to be completed only by July 01 as against the due date of March 01), observations of technical nature (berms near CDs need extra strengthening as slope.
4 | R042000199 | Unda Sakar Road | Jabalpur | PWD | Road | 2001-05-08 | DDM | 63.22 | RIDF Loan upto 10 crore | Slow progress of work (54% of WBM and entire CD work remained incomplete), time overrun likely (project likely to be completed only by 31/3/02 as against the due date of 31/3/01), labour problem.
4 | R042000003 | Boriya Malhanwara Kotalbarri Umrahar | Chhindwara | PWD | Road | 2001-05-02 | DDM | 95.66 | RIDF Loan upto 10 crore | Time overrun likely (project likely to be completed only by June 01 against the due date of 31/3/01), NB board not displayed at one end of the road
4 | R042000002 | Jeoreha Barigarh Ghawara | Chattarpur | PWD | Road | 2001-04-26 | RO Official | 74.95 | RIDF Loan upto 10 crore | Slow progress, new CDs and bridges proposed, revised AA and TS not obtained, project likely to be completed only by 30/6/02, cost escalation of Rs. 125 lacs due to SOR, the progress of the work needs to be monitored closely by the PWD
4 | R042000070 | Nowgong - Baldeogarh Road | Chattarpur | PWD | Road | 2001-04-25 | RO Official | 83.76 | RIDF Loan upto 10 crore | Project likely to be completed only by 30/6/01, NB board not displayed, road in village Isanagar be repaired and also widened at the earliest to ensure optimal connectivity through the project road.
4 | R042000023 | Chhuleta | Vidisha | WRD | MIS | 2001-04-24 | DDM | 66.15 | RIDF Loan upto 10 crore | Delay in tendering (tendering not initiated so far), work not yet commenced, time overrun likely (project likely to be completed only by June 03 as against the due date of March 01), NB board not displayed.
4 | R042000079 | Hatpiplia - Tappa | Dewas | PWD | Road | 2001-04-23 | DDM | 33.76 | RIDF Loan upto 10 crore | Project almost completed, NB board not displayed, stretch of the road just prior to project road be repaired as it was in very bad shape with big pot holes and damaged surface to ensure full benefits from the project road.
4 | R042000211 | Naiya Mishirigawa Bannapanti | Rewa | PWD | Road | 2001-04-21 | DDM | 32 | RIDF Loan upto 10 crore | Time overrun likely (project likely to be completed only by June 01 as against the due date of March 01), NB board not displayed, material and equipment problem
4 | R042000011 | Lalgaon Mangawan | Rewa | PWD | Road | 2001-04-20 | DDM | 36.12 | RIDF Loan upto 10 crore | NB board not displayed, slow progress of work (WBM and BT of 10 km and 17 CDs not yet undertaken), contractor problem (slow progress of work)
4 | R042000078 | Jaora - Sitamau | Ratlam | PWD | Road | 2001-04-20 | DDM | 148.46 | RIDF Loan upto 10 crore | Project nearing completion(sub-base 42%,sub-grade 35%,WBM 6% ,BT 4% and 3 out of 34 CDs remained incomplete)
4 | R042000160 | Mayir 6/6 | Sidhi | PWD | Bridge | 2001-04-18 | RO Official | 24.17 | RIDF Loan upto 10 crore | Physical progress of work (bridge has been completed on 10/5/2000), NB board not displayed.
4 | R042000166 | Mahan 104/10 | Sidhi | PWD | Bridge | 2001-04-18 | RO Official | 35.63 | RIDF Loan upto 10 crore | Physical progress of work (the construction of bridge is complete except approach road), contractor problem (the contractor has abandoned the work of approach road and hence contract was terminated.
4 | R042000167 | Mahan 1/10 | Singrauli | PWD | Bridge | 2001-04-18 | RO Official | 58.43 | RIDF Loan upto 10 crore | The bridge completed as on 25/6/2000, cost reported to have gone up from sanctioned Rs. 62.34 lacs to Rs. 83.19 lacs. NB board not displayed.
4 | R042000045 | Malhan | Katni | WRD | MIS | 2001-04-17 | RO Official+C | 83.08 | RIDF Loan upto 10 crore | Refer to Annexure III, Observations of technical nature, Delay in fixing agency, Time overrun likely, NB board not displayed.
4 | R042000047 | Jhampi | Katni | WRD | MIS | 2001-04-17 | RO Official+C | 80.43 | RIDF Loan upto 10 crore | Refer to Annexure V, Observations of technical nature, Delay in fixing agency, Delay in land acquisition/delay on account of land acquisition, Time overrun likely.
4 | R042000052 | Naharkhedi | Indore | WRD | MIS | 2001-04-17 | DDM | 301.85 | RIDF Loan upto 10 crore | project likely to be completed by June 02 as against the due date of March 01), canal work yet to commence, permission from forest not obtained, work affected owing to drought conditions in the district.
4 | R042000053 | Bhatkhedi | Indore | WRD | MIS | 2001-04-17 | DDM | 38.76 | RIDF Loan upto 10 crore | Slow progress, canal work not commenced, LA problem, project likely to be completed only by June 02 as against the due date of March 01).
4 | R042000121 | Barehti | Katni | WRD | MIS | 2001-04-17 | RO Official+C | 153.89 | RIDF Loan upto 10 crore | Refer to Annexure IV, Funds constraints, Observations of technical nature, Delay in fixing agency, Time overrun likely, Cost overrun likely.
4 | R042000152 | Salaiya | Katni | WRD | MIS | 2001-04-17 | RO Official+C | 64.74 | RIDF Loan upto 10 crore | Refer to Annexure VI, Observations of technical nature, Delay in fixing agency, Time overrun likely, Cost overrun likely.
4 | R042000046 | Pondi Padariya | Katni | WRD | MIS | 2001-04-16 | RO Official+C | 43.36 | RIDF Loan upto 10 crore | Refer to annexure II, Observations of technical nature, Delay in fixing agency, Time overrun likely, Cost overrun likely, NB board not displayed.
4 | R042000108 | Phuledi | Dhar | WRD | MIS | 2001-04-12 | DDM | 176.11 | RIDF Loan upto 10 crore | Pproject likely to be completed only by June 01 as against the due date of March 01, NB board not displayed, work remaining incomplete was LA-10%,masonry-50%, earthwork for dam-35% & spill-59% under Unit I and all work under unit II except preliminary
4 | R042000223 | Dholka | Ratlam | WRD | MIS | 2001-04-07 | DDM | 65.33 | RIDF Loan upto 10 crore | Delay in fixing agency, work not yet commenced, project likely to be completed only by March 02 as against the due date of March 01, funds constraints, delay in LA (Rs. 1.25 lacs deposited with LAO as against the requirement of Rs. 9.00 lacs
4 | R042000012 | Mangawan Gurh | Rewa | PWD | Road | 2001-03-30 | DDM | 40.82 | RIDF Loan upto 10 crore | Time overrun likely (project likely to be completed only by June 01 as against the due date of March 01), road work not yet commenced, 6 out of 20 CDs yet to be constructed, NB board not displayed.
4 | R042000032 | Deori amagaon | Katni | WRD | MIS | 2001-03-29 | DDM | 34.52 | RIDF Loan upto 10 crore | Funds constraints, the department to assess whether or not lining of the canal is necessary, project likely to be completed only by June 02, NB board not displayed, no steps were initiated for obtaining power connection.
4 | R042000224 | Pipliya Sehore | Ratlam | WRD | MIS | 2001-03-28 | DDM | 458.84 | RIDF Loan upto 10 crore | Funds constraints, no work commenced, time overrun likely (the project to spill over beyond the due date of March 01)
4 | R042000058 | Barsalay | Khargone | WRD | MIS | 2001-03-23 | DDM | 25.72 | RIDF Loan upto 10 crore | Time overrun likely (project to spill over beyond due date of 31/3/01), masonry work- 50% in Unit I and 38% in Unit II, earthwork- 10% for dam and 25% for spill channel in Unit I and 43% in Unit II pending
4 | R042000108 | Phuledi | Dhar | WRD | MIS | 2001-03-23 | DDM | 176.11 | RIDF Loan upto 10 crore | Slow progress of work, agency for canal work not yet fixed,NB board not displayed.
4 | R042000116 | Mahmoodpur | Rewa | WRD | MIS | 2001-03-23 | DDM | 56.81 | RIDF Loan upto 10 crore | Delay in tendering (last date for receipt of tenders was 25/4/01), time overrun likely (project likely to be completed only by March 02 as against the due date of March 01), canal work from 1890 m to 3200 m and 4 minors remained incomplete.
4 | R042000141 | Singniwas Khurrai | Shivpuri | PWD | Road | 2001-03-23 | DDM | 84.4 | RIDF Loan upto 10 crore | Road and CD works are now progressing well which initially were delayed due to funds constraints,Time overrun(the work is expected to be completed only by June 2001 as against the completion date of 31.3.01)
4 | R042000142 | Mohana-Pohari to AB Road | Shivpuri | PWD | Road | 2001-03-23 | DDM | 158.68 | RIDF Loan upto 10 crore | Work progressing well,Land acquisition in about 0.5km is to be made, PWD may expedite land acquisition for road length of 0.5 km
4 | R042000018 | Phunga Semariha | Anuppur | PWD | Road | 2001-03-22 | DDM | 56.08 | RIDF Loan upto 10 crore | Slow progress, delay in tendering, project likely to be completed only by March 02, NB board not displayed, quality of work completed did not appear to be satisfactory, the BT was damaged at some places and no repairy was done).
4 | R042000081 | Annuppur- Jaitpur | Anuppur | PWD | Road | 2001-03-22 | DDM | 44.07 | RIDF Loan upto 10 crore | Slow progress, delay in tendering, project likely to be completed only by June 01, NB board not displayed, quality of work not satisfactory, the BT was damaged at some places and had sunk at 2 places, no repairy was undertaken).
4 | R042000082 | Anuppur - Mediaras Amlai Road | Anuppur | PWD | Road | 2001-03-22 | DDM | 25.61 | RIDF Loan upto 10 crore | Slow progress, delay in tendering, project likely to be completed only by June 01, NB board not displayed, quality of work not satisfactory, the BT was damaged at some places and had sunk at 2 places, no repairy was undertaken).
4 | R042000083 | Dulhara-Pipriya-Kasapagna | Anuppur | PWD | Road | 2001-03-22 | DDM | 90.37 | RIDF Loan upto 10 crore | BT for 10.70 km and 9 CDs remained incomplete, delay in tendering, project likely to be completed by March 02 as against the due date of March 01, NB board not displayed, quality of work not satisfactory, BT damaged at some places.
4 | R042000219 | Deori Devgiwan | Shahdol | PWD | Road | 2001-03-22 | DDM | 55.05 | RIDF Loan upto 10 crore | Slow progress sub-base-2 km was not undertaken, WBM renewal was completed for 1.65 km, 2/5 CDs completed, delay in tendering, NB board not displayed, quality of work not satisfactory, BT damaged at some places
4 | R042000071 | Linga - Chhitapar Bhourjir Road | Narsinghpur | PWD | Road | 2001-03-20 | DDM | 45.13 | RIDF Loan upto 10 crore | Slow progress, NB board not displayed, of the total road length of 13.6 km, road length of 7.6 km only is covered under NB project, condition of balance 6 km is very poor, which requires to be improved to ensure optimal utility of the project road).
4 | R042000134 | Gadarwara-Tendukheda Kakaraghat | Narsinghpur | PWD | Road | 2001-03-19 | DDM | 93.09 | RIDF Loan upto 10 crore | Only CD works initiated till date, Special repair work to be required in 6.8 km and the division is stated to have prepared and submitted estimate for this. The PWD should examine the need for special repair works and take decision accordingly.
4 | R042000088 | Rajendrgram Ghoghari | Anuppur | PWD | Road | 2001-03-15 | DDM | 234.09 | RIDF Loan upto 10 crore | Slow progress of work (only 6.60 km of road length covered under WBM and BT, no progress since earlier visit on 11/12/00, 29 out of 102 CDs completed), delay in tendering, time overrun likely
4 | R042000060 | Tipan 3/8 | Anuppur | PWD | Bridge | 2001-03-14 | DDM | 95.03 | RIDF Loan upto 10 crore | Slow progress of work (only 9.6% of the foundation and 78% of the earthwork of approach road was completed), time overrun likely (project likely to be completed only by 31/12/01 as against the due date of 31/3/01), NB board not displayed
4 | R042000157 | Sone 9/10 | Anuppur | PWD | Bridge | 2001-03-14 | DDM | 72.13 | RIDF Loan upto 10 crore | Time overrun likely (project likely to be completed only by 30/6/01 as against the due date of 31/3/01), NB board not displayed, Project delayed due to delay in according technical sanction (drawing for abutment 2 received late).
4 | R042000193 | Bhonra Kohan | Guna | PWD | Road | 2001-03-09 | DDM | 94.14 | RIDF Loan upto 10 crore | Project already completed, PCR however not yet submitted, cost escalation reported
4 | R042000124 | Bhitarwar Karaiya | Gwalior | PWD | Road | 2001-03-08 | DDM | 73.35 | RIDF Loan upto 10 crore | Slow progress of work (work is in progress only in CD and medium submersible bridge,Contractor problem which needs to be solved early, NB board not displayed,
4 | R042000125 | Chimak-Badki Sarai | Gwalior | PWD | Road | 2001-03-08 | DDM | 28.24 | RIDF Loan upto 10 crore | The BT surface is not even and may require at least one pass of roller, work of 3rd CD affected for non-availability of space for temporary diversion which is expected to be available only after March 2001 once the standing crops are harvested
4 | R042000198 | Mankhedi Patan | Jabalpur | PWD | Road | 2001-03-03 | DDM | 71.15 | RIDF Loan upto 10 crore | Road work upto WBM completed,BT work not yet started,CD work/EW on shoulders under progress,Observation of technical nature(adequate water has not been used at the time of rolling/compacting as a result of which the road may get depressed.
4 | R042000199 | Unda Sakar Road | Jabalpur | PWD | Road | 2001-03-03 | DDM | 63.22 | RIDF Loan upto 10 crore | (1) NB board not displayed. (2) Observations of technical nature- adequate water has not been used for rolling/compacting and as such the road may get depressed during rainy season at certain places, BC soil used in shoulders may not give strength.
4 | R042000049 | Dongaria | Seoni | WRD | MIS | 2001-02-27 | RO Official+C | 107.49 | RIDF Loan upto 10 crore | tendering yet to be finalised, work likely to be completed by June 2002, cost escalation of Rs.7.70 lacs reported on account of construction of foot bridge not contemplated earlier across the nalla to access the dam side during rainy season.
4 | R042000059 | Talla talli | Seoni | WRD | MIS | 2001-02-27 | RO Official+C | 216.12 | RIDF Loan upto 10 crore | Agitation by local villagers and delay in settlement of LA, Keolari, tendering programme not yet finalised, work not yet commenced, project likely to be completed only by June 2003 as against the due date of March 2001.
4 | R042000225 | Barelipar | Seoni | WRD | MIS | 2001-02-27 | RO Official+C | 57.74 | RIDF Loan upto 10 crore | work not yet commenced, project likely to be completed by June 2002 as against the due date of March 2001, cost escalation of Rs. 9.583 lacs reported on account of construction of a foot bridge-not contemplated earlier- for crossing the spill channel
4 | R042000063 | Keotan 7/2 | Vidisha | PWD | Bridge | 2001-02-22 | DDM | 43.96 | RIDF Loan upto 10 crore | Project completed in May 2000, NB board not displayed, suggestion of technical nature (all 4 piers are surrounded by deep ditches which are required to be filled up to avoid water logging at the basis of piers)
4 | R042000090 | Karanpura Tank No 2 | Dhar | WRD | MIS | 2001-02-22 | DDM | 37.76 | RIDF Loan upto 10 crore | Slow progress of work, time overrun likely special attention of WRD required for monitoring of progress.
4 | R042000004 | Ramakona Sawarni | Chhindwara | PWD | Road | 2001-02-15 | DDM | 80.22 | RIDF Loan upto 10 crore | Project almost complete (except for few minor masonry structures, repairy of a small damaged bridge at 15/8 RD and completion of balance road towards Bichua), a patch of about 700-800 m is damaged near Rangari which requires repairy.
4 | R042000187 | Borgaon | Chhindwara | WRD | MIS | 2001-02-15 | DDM | 115.79 | RIDF Loan upto 10 crore | Slow progress of work, contractor problem (low bidding and limited capacity), time overrun likely, NB board not displayed at site, delay in land acquisition, water scarcity (for curing work), delay in tendering (tenders for canal not yet finalised)
4 | R042000067 | Sindh 12/2 | Shivpuri | PWD | Bridge | 2001-02-13 | DDM | 104.7 | RIDF Loan upto 10 crore | Delay in commencement of work, NB board not displayed, cost overrun likely owing to change in design, 2 CD works proposed additionally- one on each side, length of the approach road proposed to be increased from 2 km to 2.94 km.
4 | R042000114 | Kisanpur | Chhindwara | WRD | MIS | 2001-02-07 | DDM | 105.25 | RIDF Loan upto 10 crore | NB board not displayed, canals in damaged condition, unless the canals are repaired no water can be provided for irrigation, renovation of chutefall by concreting is to be done as masonry work was already done before taking up the project under RIDF.
4 | R042000186 | Shivlal Dhana | Chhindwara | WRD | MIS | 2001-02-02 | DDM | 236.03 | RIDF Loan upto 10 crore | Slow progress of work, cost overrun likely, delay in land acquisition (compensation of about Rs. 45 lacs not paid to the farmers which has affected land acquisition for nalah closure), funds constraints.
4 | R042000098 | Bagala | Ujjain | WRD | MIS | 2001-01-25 | DDM | 201.4 | RIDF Loan upto 10 crore | Tendering of both Unit I & II completed. Implementation started on 30.12.2000. Final payment towards LA for canal works still tobe made. NB board not displayed. Concerned authorities may be pursued by WRD for early payment of LA.
4 | R042000143 | Jawasiya Talod | Ujjain | PWD | Road | 2001-01-18 | DDM | 49.22 | RIDF Loan upto 10 crore | Work progressing satisfactorily. Quality of work good. NB board not displayed. Likely completion by 31 March 2001.
4 | R042000144 | Tajpur Najarpur | Ujjain | PWD | Road | 2001-01-17 | DDM | 147.93 | RIDF Loan upto 10 crore | Tendering for entire CD works and about 50% road length is complete. For balance road length, tenders have been recalled. Work is progressing satisfactorily by finalised agencies but BT work in about 100 m length in Km 3 needs rectification.
4 | R042000034 | Khadda | Shahdol | WRD | MIS | 2001-01-16 | DDM | 68.4 | RIDF Loan upto 10 crore | Tendering still not completed. WRD should make efforts for removing the bottleneck in tendering immediately.
4 | R042000169 | Bamadehi1/6 | Sagar | PWD | Bridge | 2001-01-14 | DDM | 42.27 | RIDF Loan upto 10 crore | Report received only in February
4 | R042000223 | Dholka | Ratlam | WRD | MIS | 2001-01-12 | DDM | 65.33 | RIDF Loan upto 10 crore | Work not yet commenced, delay in tendering, time overrun likely (project likely to be completed only by June 02 as against the due date of March 02), NB board not displayed
4 | R042000134 | Gadarwara-Tendukheda Kakaraghat | Narsinghpur | PWD | Road | 2001-01-09 | DDM | 93.09 | RIDF Loan upto 10 crore | Tendering for CD works only completed. The same for road work is still in progress which needs to be expedited.
4 | R042000140 | Gora-Pichhore | Shivpuri | PWD | Road | 2001-01-09 | DDM | 190.9 | RIDF Loan upto 10 crore | Work progress slow. A portion of road of about 1.5 km passing through forest area. Changes made in design of CD works as per site condition requirements. Progress of works need to be properly monitored so that project is completed in time.
4 | R042000071 | Linga - Chhitapar Bhourjir Road | Narsinghpur | PWD | Road | 2001-01-04 | DDM | 45.13 | RIDF Loan upto 10 crore | Work progress slow, NB board not displayed, suggestion that balance road length of 6 km (of the total road length of 13.6 km) not sanctioned under RIDF be repaired immediately as it is in very bad condition
4 | R042000141 | Singniwas Khurrai | Shivpuri | PWD | Road | 2001-01-04 | DDM | 84.4 | RIDF Loan upto 10 crore | Tendering of road and CD works completed. CD work on Parvati river not yet started. The project may be completed by June 2001 if CD work referred to is initiated immediately.
4 | R042000142 | Mohana-Pohari to AB Road | Shivpuri | PWD | Road | 2001-01-04 | DDM | 158.68 | RIDF Loan upto 10 crore | Tendering of road and CD works completed. A part of road passing through sugarcane field and so land not available for road works. CD work on Parvati river not yet started.
4 | R042000003 | Boriya Malhanwara Kotalbarri Umrahar | Chhindwara | PWD | Road | 2000-12-24 | DDM | 95.66 | RIDF Loan upto 10 crore | Slow work progress, funds constraints, NB board not displayed on one of the two ends of the road, multiplicity of agencies (5 nos) resulting in lack of proper coordination
4 | R042000018 | Phunga Semariha | Anuppur | PWD | Road | 2000-12-12 | DDM | 56.08 | RIDF Loan upto 10 crore | slow work progress, delay in tendering, unsatisfactory quality of work, NB board not displayed
4 | R042000081 | Annuppur- Jaitpur | Anuppur | PWD | Road | 2000-12-12 | DDM | 44.07 | RIDF Loan upto 10 crore | slow progress of work, delay in tendering, unsatisfactory quality of work, NB board not displayed
4 | R042000082 | Anuppur - Mediaras Amlai Road | Anuppur | PWD | Road | 2000-12-12 | DDM | 25.61 | RIDF Loan upto 10 crore | slow progress of work, delay in tendering, unsatisfactory quality of work, NB board not displayed
4 | R042000083 | Dulhara-Pipriya-Kasapagna | Anuppur | PWD | Road | 2000-12-12 | DDM | 90.37 | RIDF Loan upto 10 crore | slow progress of work, delay in tendering, unsatisfactory quality of work, NB board not displayed
4 | R042000219 | Deori Devgiwan | Shahdol | PWD | Road | 2000-12-12 | DDM | 55.05 | RIDF Loan upto 10 crore | slow progress of work, delay in tendering, unsatisfactory quality of work, NB board not displayed
4 | R042000075 | Udaipura - Silwani Road | Raisen | PWD | Road | 2000-11-25 | RO Official | 94.82 | RIDF Loan upto 10 crore | Time/cost overrun likely, work not commenced, at many places along the road length the status of sub-grade/sub-base and WBM was very bad though not included in the project, cost escalation proposed should also be submitted to NB for sanction
4 | R042000077 | Begamganj Sultanganj Road | Raisen | PWD | Road | 2000-11-25 | RO Official | 82.59 | RIDF Loan upto 10 crore | Time/cost overrun likely, deviation in technical design, cost escalation proposed should be submitted to NB for sanction, delay in tendering- the dept should expeditiously finalise the agency and also take steps for land acquisition
4 | R042000136 | Baras Approach | Raisen | PWD | Road | 2000-11-25 | RO Official | 19.09 | RIDF Loan upto 10 crore | Project under litigation- contractor has stopped the work indicating insufficient crust thickness to undertake BT work on the left over road length, unsatisfactory quality of work- BT already completed has sunk at many places.
4 | R042000144 | Tajpur Najarpur | Ujjain | PWD | Road | 2000-11-25 | DDM | 147.93 | RIDF Loan upto 10 crore | Work progress slow, delay in tendering, tendering in parts to 3 different agencies, NB board not displayed
4 | R042000141 | Singniwas Khurrai | Shivpuri | PWD | Road | 2000-11-16 | DDM | 84.4 | RIDF Loan upto 10 crore | Funds constraints
4 | R042000142 | Mohana-Pohari to AB Road | Shivpuri | PWD | Road | 2000-11-16 | DDM | 158.68 | RIDF Loan upto 10 crore | Delay in land acquisition (although 0.5 km of road length passes through fields, no action initiated)
4 | R042000088 | Rajendrgram Ghoghari | Anuppur | PWD | Road | 2000-11-12 | DDM | 234.09 | RIDF Loan upto 10 crore | Slow work progress, delay in tendering, NB board not displayed, there was hump formation on CDs which needed to be smoothened, no drains were provided in the reaches from 3/4 to 3/6 km and 4/6 to 4/8 km where there were hills on both sides of the road.
4 | R042000140 | Gora-Pichhore | Shivpuri | PWD | Road | 2000-11-10 | DDM | 190.9 | RIDF Loan upto 10 crore | Slow progress, NB board not displayed, suggestion of technical nature (considering the site conditions, change in design of the CD work is proposed at one place- medium bridge would be more appropriate instead of the box culvert proposed at present).
4 | R042000078 | Jaora - Sitamau | Ratlam | PWD | Road | 2000-11-08 | DDM | 148.46 | RIDF Loan upto 10 crore | Nothing particular reported, PCR format used for monitoring
4 | R042000210 | Ratlam Dhawasuth | Ratlam | PWD | Road | 2000-11-08 | DDM | 95.45 | RIDF Loan upto 10 crore | Nothing particular reported, PCR format used for monitoring
4 | R042000060 | Tipan 3/8 | Anuppur | PWD | Bridge | 2000-10-23 | DDM | 95.03 | RIDF Loan upto 10 crore | NB board not displayed
4 | R042000157 | Sone 9/10 | Anuppur | PWD | Bridge | 2000-10-23 | DDM | 72.13 | RIDF Loan upto 10 crore | NB board not displayed, suggestion of technical nature (drawing of abutment 2 not yet approved)
4 | R042000195 | Baghana Baloda Takun Road | Indore | PWD | Road | 2000-10-23 | DDM | 61.52 | RIDF Loan upto 10 crore | Work progress slow, time overrun likely, NB board not displayed, delay in tendering, tendering not called for the entire road length, work affected for water scarcity/drought.
4 | R042000196 | Maharajganj Simrol | Indore | PWD | Road | 2000-10-23 | DDM | 38.63 | RIDF Loan upto 10 crore | Work progress nil, time overrun likely, NB board not displayed, suggestion of technical nature (Though not provided in the project, WBM grade 3 renewal is necessary without which black topping will not hold).
4 | R042000197 | Sanwer Panod Biloda Nayata | Indore | PWD | Road | 2000-10-23 | DDM | 19.03 | RIDF Loan upto 10 crore | Time overrun likely, NB board not displayed, work affected for drought, The ditch at 6/6 is too long and cross drainage as proposed at present is not appropriate, instead vented causeway with RCC construction would be more appropriate.
4 | R042000124 | Bhitarwar Karaiya | Gwalior | PWD | Road | 2000-10-21 | DDM | 73.35 | RIDF Loan upto 10 crore | Work progress slow, contractor problem (poor resources, experience), NB board not displayed
4 | R042000125 | Chimak-Badki Sarai | Gwalior | PWD | Road | 2000-10-21 | DDM | 28.24 | RIDF Loan upto 10 crore | Nothing adverse reported
4 | R042000143 | Jawasiya Talod | Ujjain | PWD | Road | 2000-10-16 | DDM | 49.22 | RIDF Loan upto 10 crore | NB board not displayed, work affected for water scarcity/drought
4 | R042000224 | Pipliya Sehore | Ratlam | WRD | MIS | 2000-10-11 | DDM | 458.84 | RIDF Loan upto 10 crore | Work progress slow, time overrun likely, work not yet commenced, delay in tendering, funds constraints, land acquisition problem
4 | R042000052 | Naharkhedi | Indore | WRD | MIS | 2000-09-28 | DDM | 301.85 | RIDF Loan upto 10 crore | Work progress slow, time overrun likely, funds constraints
4 | R042000053 | Bhatkhedi | Indore | WRD | MIS | 2000-09-28 | DDM | 38.76 | RIDF Loan upto 10 crore | Cost escalation likely .
4 | R042000176 | Ukhama 13/2 | Rewa | PWD | Bridge | 2000-05-31 | DDM | 149.08 | RIDF Loan upto 10 crore | 1. Delay in land acquisition (land acquisition case for approach roads was reported to be pending with the Collector).
4 | R042000212 | Shahpur Barroan | Rewa | PWD | Road | 2000-05-31 | DDM | 13.56 | RIDF Loan upto 10 crore | 1. Observation of technical nature (construction of retaining wall should be taken up along with construction of the road for longer life of the road).
4 | R042000004 | Ramakona Sawarni | Chhindwara | PWD | Road | 2000-04-29 | DDM | 80.22 | RIDF Loan upto 10 crore | The progress of the work was found to be as per phasing, quality of work was satisfactory.
4 | R042000187 | Borgaon | Chhindwara | WRD | MIS | 2000-04-29 | DDM | 115.79 | RIDF Loan upto 10 crore | Time overrun likely.
4 | R042000006 | Jabalpur Purena | Jabalpur | PWD | Road | 2000-04-24 | DDM | 48.06 | RIDF Loan upto 10 crore | Work not yet commenced.
4 | R042000007 | Panagar Belkhadu | Jabalpur | PWD | Road | 2000-04-24 | DDM | 33.88 | RIDF Loan upto 10 crore | Work not yet commenced.
4 | R042000186 | Shivlal Dhana | Chhindwara | WRD | MIS | 2000-04-14 | DDM | 236.03 | RIDF Loan upto 10 crore | Delay in LA (delay in passing award for land acquisition was reported to be the main constraint),delay in tendering( tenders for construction of canals were not yet floated),funds constraints( uncertainity in receipt of LOC)m, time overrun likely.
4 | R042000193 | Bhonra Kohan | Guna | PWD | Road | 2000-03-10 | DDM | 94.14 | RIDF Loan upto 10 crore | Funds constraints, slow progress of work for funds constraints, time overrun likely, department may look into the requirement of extra work to be done.
4 | R042000194 | Kohan Hamirpur | Guna | PWD | Road | 2000-03-10 | DDM | 63.56 | RIDF Loan upto 10 crore | Funds constraints,slow progress of work for non-availability of funds as per requirement,time overrun likely.
4 | R042000013 | Pahadi Barrown Bicchar Hata | Rewa | PWD | Road |  |  | 18.32 | RIDF Loan upto 10 crore
4 | R042000021 | Ramnagar | Sehore | WRD | MIS |  |  | 19.37 | RIDF Loan upto 10 crore
4 | R042000048 | Jampati | Badwani | WRD | MIS |  |  | 171.32 | RIDF Loan upto 10 crore
4 | R042000051 | Barkhoa | Guna | WRD | MIS |  |  | 37.61 | RIDF Loan upto 10 crore
4 | R042000057 | Ved Barrage | Khargone | WRD | MIS |  |  | 44.23 | RIDF Loan upto 10 crore
4 | R042000061 | Bairma 7/2 | Damoh | PWD | Bridge |  |  | 26.01 | RIDF Loan upto 10 crore
4 | R042000064 | Kalisindh 3/6 | Shajapur | PWD | Bridge |  |  | 57.15 | RIDF Loan upto 10 crore
4 | R042000066 | Kalisindh 13/8 | Shajapur | PWD | Bridge |  |  | 91.4 | RIDF Loan upto 10 crore
4 | R042000080 | Sulkhama - Itma | Satna | PWD | Road |  |  | 33.57 | RIDF Loan upto 10 crore
4 | R042000095 | Mareva | Khargone | WRD | MIS |  |  | 8.98 | RIDF Loan upto 10 crore
4 | R042000097 | Pangara | Sehore | WRD | MIS |  |  | 85.44 | RIDF Loan upto 10 crore
4 | R042000129 | Mathani - Umardha Road | Hoshangabad | PWD | Road |  |  | 66.61 | RIDF Loan upto 10 crore
4 | R042000138 | Khimasa Malthone | Sagar | PWD | Road |  |  | 57.89 | RIDF Loan upto 10 crore
4 | R042000149 | Panda | Damoh | WRD | MIS |  |  | 184.65 | RIDF Loan upto 10 crore
4 | R042000161 | Bhadar 4/8 | Damoh | PWD | Bridge |  |  | 25.33 | RIDF Loan upto 10 crore
4 | R042000172 | Gouraiya 3/10 | Damoh | PWD | Bridge |  |  | 47.71 | RIDF Loan upto 10 crore
4 | R042000173 | Newaj 18/8 | Rajgarh | PWD | Bridge |  |  | 53.1 | RIDF Loan upto 10 crore
4 | R042000177 | Veda 3/2 | Khargone | PWD | Bridge |  |  | 142.05 | RIDF Loan upto 10 crore
4 | R042000188 | Badli Barkheridev | Bhopal | PWD | Road |  |  | 60.41 | RIDF Loan upto 10 crore
4 | R042000215 | Amarpatan Rampur Road | Satna | PWD | Road |  |  | 53.36 | RIDF Loan upto 10 crore
4 | R042000221 | Banwar | Damoh | WRD | MIS |  |  | 92.36 | RIDF Loan upto 10 crore
5 | r052000094 | Package 2 (LBC 15 - 31.5 KM) | Jabalpur | NVDA | MJP | 2007-03-13 | Jabalpur DDM | 1563.59 | RIDF Loan 10.01-24.99 crore | NABARD board has not been displayed. Work has been completed. Maintenance of canal is not being done.
5 | r052000093 | Package 1(LBC 0.16 - 15 KM) | Jabalpur | NVDA | MJP | 2007-03-13 | Jabalpur DDM | 2130.5 | RIDF Loan 10.01-24.99 crore | NABARD board has not been displayed. No maintenance of canal.
5 | r052000095 | Package 3 (LBC 31.5 - 51 KM)) | Jabalpur | NVDA | MJP | 2007-03-13 | Jabalpur DDM | 1890.96 | RIDF Loan 10.01-24.99 crore | NABARD board has been displayed. The canal is not being maintained by the Dept.
5 | R052000002 | Bargi | Dindori | WRD | MIS | 2007-01-19 | Mandla DDM | 90.66 | RIDF Loan upto 10 crore | About one Km length of canal yet to be completed. LA problem. As the physical work and amount involved is small the work may be carried out departmentally and project may be completed at the earliest to reap full project benefits.
5 | r052000115 | Harmala Pipaliya Bisniya | Mandsaur | PWD | Road | 2006-12-30 | Mandsaur DDM | 42.52 | RIDF Loan upto 10 crore | PCR VERIFICATION. Due to heavy rains during 2006, earthwork eroded at two places. The road has provided connectivity to three villages and the road is a great relief during monsoons.
5 | r052000044 | Budner 4/4 | Mandla | PWD | Bridge | 2006-11-10 | Mandla DDM | 83.69 | RIDF Loan upto 10 crore | Quality of work is satisfactory.
5 | R052000051 | Chandrapura Bhadan Kanjarda | Neemuch | PWD | Road | 2006-05-30 | Mandsaur DDM | 275.46 | RIDF Loan upto 10 crore | The progress is very slow due to contractor problem. Quality of work is poor.
5 | r052000106 | Hapakhedi-Panwarihat-via-Mohasa Dagrai-Amkheda | Guna | PWD | Road | 2006-04-29 | Guna DDM | 123.06 | RIDF Loan upto 10 crore | PCR Verification. NABARD board displayed in one end. Road connecting Guna and Ashoknagar district has benefitted 22 villages. Road constructed with many turns which could have been avoided.
5 | r052000108 | Shadora-Madikanung-Bijapur | Guna | PWD | Road | 2006-04-29 | Guna DDM | 190.5 | RIDF Loan upto 10 crore | PCR Verification. NABARD board has been displayed on one side. Few beneficiaries opined that with the construction of the dam the level of water in their wells has gone up. The farmers have also changed cropping pattern.
5 | r052000106 | Hapakhedi-Panwarihat-via-Mohasa Dagrai-Amkheda | Guna | PWD | Road | 2006-04-29 | Guna DDM | 123.06 | RIDF Loan upto 10 crore | PCR verification. NABARD board displayed only in one end. Too many curves.
5 | R052000021 | Sone 7/8 | Sidhi | PWD | Bridge | 2006-02-04 | DDM | 793.17 | RIDF Loan upto 10 crore | Bridge is completed. Work on approach road is in progress. NABARD board is not displayed.
5 | R052000023 | Bhanpura-Bhansoda | Mandsaur | PWD | Road | 2006-01-25 | DDM | 101.13 | RIDF Loan upto 10 crore | Project completed. Quality of works is satisfactory. PCR to be submitted by the Dept. NABARD board is not displayed.
5 | R052000064 | Garoth Rly Stn. to Bardia Amra | Mandsaur | PWD | Road | 2006-01-25 | DDM | 76.03 | RIDF Loan upto 10 crore | Project completed excepting for black topping. Fresh tenders are invited by the Dept for BT work. Likely to be completed by March 2006.
5 | R052000120 | Kukade Shawar Tomchi Amed | Neemuch | PWD | Road | 2005-11-12 | DDM | 99.45 | RIDF Loan upto 10 crore | (1) Construction of road completed. (2) 8 CD works have been taken up against 11 sanctioned. (3) A portion of road passing through Kukdeshwar village is damaged and needs repair.
5 | R052000074 | Kanthal 3/10 | Shajapur | PWD | Bridge | 2005-11-10 | DDM | 95.9 | RIDF Loan upto 10 crore | Project completed. PCR verified. Approach road needs improvement. NB board not displayed.
5 | R052000140 | Baghaw-Amiliya | Sidhi | PWD | Road | 2005-10-05 | DDM | 239.26 | RIDF Loan upto 10 crore | Quality not satisfactory. Progress slow. The road is damaged at several places.NABARD board has not been displayed. PWD is required to ensure to carry out repairs of the road with emphasis on quality and arrange to get NABARD board displayed.
5 | R052000063 | Ashok nagar Piparai | Ashoknagar | PWD | Road | 2005-09-29 | DDM | 103.65 | RIDF Loan upto 10 crore | 1. Road is completed in March 2004. 2. Damage due to waterlogging observed at KM 13/4. 3. Adequate maintenance should be provided
5 | R052000105 | Ashoknagar Vidisha Rd. to Chhipon via Rajpur | Guna | PWD | Road | 2005-09-29 | DDM | 94.14 | RIDF Loan upto 10 crore | 1. Road work completed in May 2003. 2. Maintenance is found to be inadequate
5 | R052000051 | Chandrapura Bhadan Kanjarda | Neemuch | PWD | Road | 2005-09-23 | DDM | 275.46 | RIDF Loan upto 10 crore | The project complete on 31-3-05 with delay of one year due to contractor problem. The quality of work is poor as BT is intermittently poor at various stretches. The department should arrange to submit the PCR.
5 | R052000115 | Harmala Pipaliya Bisniya | Mandsaur | PWD | Road | 2005-05-26 | DDM | 42.52 | RIDF Loan upto 10 crore | The WBM work and black topping of entire 6.5 Kms. of the road length is over. Black topping of a few meters over one CD is yet to be done. However this portion is not covered under NABARD sanction.The road has been opened for public use.
5 | R052000116 | Barkheda Devdungari to Malhargarh | Mandsaur | PWD | Road | 2005-05-26 | DDM | 43.5 | RIDF Loan upto 10 crore | The work was delayed due to contractor problem. The road has since been completed except sides. The road has been opened for public use in the incomplete stage.
5 | R052000117 | Lasudiya Kadmala | Mandsaur | PWD | Road | 2005-05-26 | DDM | 38.8 | RIDF Loan upto 10 crore | The road construction is over except 100 mtrs. of black topping in Pipliya Bisnia village. The work was delayed due to problem of land acquisition. NABARD board may be displayed on Narayangarh side of the road.
5 | R052000142 | Bhourasa-Malhargarh | Vidisha | PWD | Road | 2005-04-12 | DDM | 174.87 | RIDF Loan upto 10 crore | Progress slow, contractor problem. The material used is not of good quality. Most of the parts of road damaged due to rains. Quality of material used for repairing work is also of substandard.
5 | R052000060 | Damoh Patharia | Damoh | PWD | Road | 2005-03-29 | DDM | 170.41 | RIDF Loan upto 10 crore | NABARD board not displayed. The part towards Pathriya needs to be properly maintained. The road specifications are poor, layers of 50 mm + 25 mm should have been provided instead of present height which is likely to be damaged due to heavy traffic.
5 | R052000011 | Patharia - Kerbana | Damoh | PWD | Road | 2005-03-29 | DDM | 99.73 | RIDF Loan upto 10 crore | The work is already complete. NABARD board was not displayed. The road was damaged slightly on various segments.
5 | R052000016 | Kumbharaj - Singanpur - Mrigwas | Guna | PWD | Road | 2005-03-29 | DDM | 153.91 | RIDF Loan upto 10 crore | PCR monitoring - The work has been completed on 31.03.2001. Annual maintenance of road could not be done on account of funds from State Govt.
5 | R052000130 | Baikunthpur Dewas Lalgaon | Rewa | PWD | Road | 2005-03-12 | DDM | 68.54 | RIDF Loan upto 10 crore | Slow Progress due to fund problem.
5 | R052000045 | Narmada 9/10 | Narsinghpur | PWD | Bridge | 2005-02-17 | DDM | 589.46 | RIDF Loan upto 10 crore | The progress is very slow. NABARD board was not displayed.
5 | R052000051 | Chandrapura Bhadan Kanjarda | Neemuch | PWD | Road | 2005-02-16 | DDM | 275.46 | RIDF Loan upto 10 crore | Slow progress due to contractor's problem. Quality of BT work is very poor
5 | R052000140 | Baghaw-Amiliya | Sidhi | PWD | Road | 2005-02-15 | DDM | 239.26 | RIDF Loan upto 10 crore | Slow progress. There was dispute with contractor regarding payment. Departmental enquiry is against some officials. No record of visits by EE/CE and also Quality Control register was maintained at site. NABARD Board is not displayed in revised format.
5 | R052000116 | Barkheda Devdungari to Malhargarh | Mandsaur | PWD | Road | 2005-02-14 | DDM | 43.5 | RIDF Loan upto 10 crore | The work has been delayed due to contractor problem. The road has been opened for public use in the incomplete stage. Dept. should arrange for display of NABARD board immediately on the Malhargarh side of the road.
5 | R052000117 | Lasudiya Kadmala | Mandsaur | PWD | Road | 2005-02-14 | DDM | 38.8 | RIDF Loan upto 10 crore | The road construction is over except 100 mts. of black topping in Pipliya Bisnia village. The construction of the road was delayed due to the problems of land acquisition.
5 | R052000115 | Harmala Pipaliya Bisniya | Mandsaur | PWD | Road | 2005-02-14 | DDM | 42.52 | RIDF Loan upto 10 crore | WBM and BT of entire 6.5 km is over. Black topping of a few meters over one CD is yet to be done.However, this portion is not covered under NABARD sanction. The road has been opened for public use.Dept. should arrange for submission of PCR.
5 | R052000144 | Sindh 15/6 | Bhind | PWD | Bridge | 2005-02-12 | DDM | 558.72 | RIDF Loan upto 10 crore | Work is in progress. 4 slabs between 5 piers were laid. 5th slab was in progress. The earthwork of approach road was in progress. NABARD board should be repaired/repainted. One more board on Amayan side also should be erected.
5 | R052000136 | Kalapipal-Khamlai-Amlai | Shajapur | PWD | Road | 2005-01-20 | DDM | 251.7 | RIDF Loan upto 10 crore | Work likely to be completed by 30.06.05 as against the due date of 31.03.03. Single contractor executing work slowly, contract period expired on 31.07.04. No extension sought thereafter. No concerted efforts. NABARD Board was not displayed.
5 | R052000096 | Package 4 (Belkhedi System)) | Jabalpur | NVDA | MJP | 2005-01-19 | OIC+C | 1914.61 | RIDF Loan 10.01-24.99 crore | Overall 83% of the work has been completed. The progress is satisfactory. The work can be completed by 10.03.05.The major bottleneck was non availability of good CNS material at approved quarry.Sorting of boulders from CNS delayed the lining work.
5 | R052000137 | Modi-Soyat-Khurd | Shajapur | PWD | Road | 2005-01-19 | DDM | 141.09 | RIDF Loan upto 10 crore | Time overrun, work likely to be completed by 31.03.05 as against the due date of 31.03.03. Cost overrun, estimates approved with 1992 SOR, whereas the tender opened with 2002 SOR, NABARD Board not displayed.
5 | R052000120 | Kukade Shawar Tomchi Amed | Neemuch | PWD | Road | 2005-01-13 | DDM | 99.45 | RIDF Loan upto 10 crore | Road at ghat section yet to be completed. Work delayed owing to changes in design twice. Dept. proposes to consruct drainage channels instead of two CDs on ghat. The Dept. also proposes to widen road on ghat section to 5.5 mts. to aviod accidents.
5 | R052000097 | Package 5 (Patan 9.74 - 14.4) | Jabalpur | NVDA | MJP | 2004-11-30 | RO Official | 1260.93 | RIDF Loan 10.01-24.99 crore | Report submitted
5 | R052000096 | Package 4 (Belkhedi System)) | Jabalpur | NVDA | MJP | 2004-11-30 | RO Official | 1914.61 | RIDF Loan 10.01-24.99 crore | Report submitted
5 | R052000096 | Package 4 (Belkhedi System)) | Jabalpur | NVDA | MJP | 2004-10-21 | DDM | 1914.61 | RIDF Loan 10.01-24.99 crore | Overall 80% of the work has been completed. The progress is satisfactory. Looking in to problms faced due to BC soil in the canal area, strategies may be evolved to prevent damage to linings.
5 | R052000021 | Sone 7/8 | Sidhi | PWD | Bridge | 2004-10-20 | DDM | 793.17 | RIDF Loan upto 10 crore | The progress is slow. The bridge work is completed. However approach road work is on initial stage. NABARD Board was not displyed.
5 | R052000097 | Package 5 (Patan 9.74 - 14.4) | Jabalpur | NVDA | MJP | 2004-10-20 | DDM | 1260.93 | RIDF Loan 10.01-24.99 crore | Structure and lining work yet to be completed. In Lohari coping damaged and cracks developed between tiles laid due to settling of soil.
5 | R052000023 | Bhanpura-Bhansoda | Mandsaur | PWD | Road | 2004-10-19 | DDM | 101.13 | RIDF Loan upto 10 crore | The work is completed. NABARD board not displayed.
5 | R052000101 | Dharampur Tarapur Mandu | Dhar | PWD | Road | 2004-10-08 | DDM | 270.19 | RIDF Loan upto 10 crore | Milo meter were not installed. Seal coat quality was poor. Patri feeling is not done properly. There was delay in construction on account of improper followup with the contractor. NABARD Board at Tarapur side was not installed.
5 | R052000095 | Package 3 (LBC 31.5 - 51 KM)) | Jabalpur | NVDA | MJP | 2004-10-06 | DDM | 1890.96 | RIDF Loan 10.01-24.99 crore | 44 out of 354 structures and 29.625 kms of lining was completed. Work was halted due to rainy season. The progress is very slow.
5 | R052000064 | Garoth Rly Stn. to Bardia Amra | Mandsaur | PWD | Road | 2004-09-22 | DDM | 76.03 | RIDF Loan upto 10 crore | The WBM work of 6.7 Kms. of the road is over. Black topping is yet to be done. CD work numbering 8 have been laid.
5 | R052000142 | Bhourasa-Malhargarh | Vidisha | PWD | Road | 2004-09-21 | DDM | 174.87 | RIDF Loan upto 10 crore | The progress is very slow and not satisfactory. Quality of the work was not upto the mark.
5 | R052000038 | Jakhoda | Gwalior | WRD | MIS | 2004-09-10 | DDM | 103.89 | RIDF Loan upto 10 crore | There is time and cost overrun. No budget is made available during the current year. Monitring mechanism is satisfactory. Nabard Board was not displayed.
5 | r052000093 | Package 1(LBC 0.16 - 15 KM) | Jabalpur | NVDA | MJP | 2004-08-28 | DDM | 2130.5 | RIDF Loan 10.01-24.99 crore | Over 77.79% of the physical work is completed. Financial achievement is about 95%.
5 | R052000094 | Package 2 (LBC 15 - 31.5 KM) | Jabalpur | NVDA | MJP | 2004-08-28 | DDM | 1563.59 | RIDF Loan 10.01-24.99 crore | More than 96% of the work is completed. Silts to be removed from the bed of the canal.
5 | R052000034 | Tons 1/8 | Rewa | PWD | Bridge | 2004-08-25 | DDM | 341.57 | RIDF Loan upto 10 crore | No records regarding visits by CT and SE maintained at site. NABARD Board was not displayed. Approach road work not covered by Black-Topping.
5 | R052000123 | Devendranagar Kakarhati | Panna | PWD | Road | 2004-08-24 | DDM | 80.42 | RIDF Loan upto 10 crore | Slow progress.BT work has not started due to shortage of funds.
5 | R052000106 | Hapakhedi-Panwarihat-via-Mohasa Dagrai-Amkheda | Guna | PWD | Road | 2004-08-18 | DDM | 123.06 | RIDF Loan upto 10 crore | The quality of the work was not satisfactory. No proper and regular supervision by PWD Engineers.
5 | R052000100 | Kanta Phod Punjapura | Dewas | PWD | Road | 2004-07-27 | DDM | 208.3 | RIDF Loan upto 10 crore | No progress since March 2003. PWd has reported that the balance work is being undertaken under Fast Track Scheme. PWD has invited tenders for a work of Rs. 73.00 lakhs under the scheme.
5 | R052000037 | Alapur | Gwalior | WRD | MIS | 2004-06-24 | OIC+RO Officials | 631.79 | RIDF Loan upto 10 crore | Project completed. NB board not displayed.
5 | R052000146 | Chopat 3/6 | Guna | PWD | Bridge | 2004-04-10 | DDM | 73.74 | RIDF Loan upto 10 crore | 1)LA problem, now solved, slowed constr of approach road.2) NB board not displayed.3) Bridge work is complete.4)Foundation/Sub-struc/Super-struc:100%, Approach Rd:90%
5 | R052000030 | Kanti 9/2 | Guna | PWD | Bridge | 2004-04-10 | DDM | 31.75 | RIDF Loan upto 10 crore | NB board not displayed. Raw materials are checked in their QC Lab. Change in original plan of bridge has caused inflation in cost and delay in progress. LA prob delayed construction of bridge. Foundation/Sub-struc/Super-struc:100%, Approach Rd:75%
5 | R052000020 | Ataraila-Jawa Road | Rewa | PWD | Road | 2004-04-01 | DDM | 75.4 | RIDF Loan upto 10 crore | Slow progress-no physical progress since November 02 .Delay in LA process .BT not done
5 | R052000020 | Ataraila-Jawa Road | Rewa | PWD | Road | 2004-04-01 | DDM | 75.4 | RIDF Loan upto 10 crore | No work was going on at site. As reported work was going on upto Nov.2002. BT was not done at all.
5 | R052000073 | Bina 11/6-8 | Sagar | PWD | Bridge | 2004-03-26 | DDM | 96.75 | RIDF Loan upto 10 crore | Slow progress-Abutments , super structure & approach road work not completed.
5 | R052000093 | Package 1(LBC 0.16 - 15 KM) | Jabalpur | NVDA | MJP | 2004-03-12 | DDM | 2130.5 | RIDF Loan 10.01-24.99 crore | Over 66% of the work has been completed. Land acquisition needs to be expidited Lining of PBC between RD 4 to 7 Kms needs to be repaired
5 | R052000094 | Package 2 (LBC 15 - 31.5 KM) | Jabalpur | NVDA | MJP | 2004-03-12 | DDM | 1563.59 | RIDF Loan 10.01-24.99 crore | Agreements executed and work order issued. The work has been completed about 68% in case of RD 24 -25 and in case of RD 30-32 the same is about 45%.
5 | R052000095 | Package 3 (LBC 31.5 - 51 KM)) | Jabalpur | NVDA | MJP | 2004-03-09 | DDM | 1890.96 | RIDF Loan 10.01-24.99 crore | Lining of 32 Km was completed. Due to release of water in canals lining work was halted.The progress is very slow.
5 | R052000056 | Lahar-Seondha | Bhind | PWD | Road | 2004-02-28 | Consultant | 63.93 | RIDF Loan upto 10 crore | Project complrted.
5 | R052000144 | Sindh 15/6 | Bhind | PWD | Bridge | 2004-02-27 | Consultant | 558.72 | RIDF Loan upto 10 crore | Time overrun- project likely to be completed by June 05 as against March 04.Slow progress-physical progress is too low (30%).
5 | R052000006 | Rarikatha-Achalpura | Bhind | PWD | Road | 2004-02-26 | Consultant | 30.08 | RIDF Loan upto 10 crore | Project completed on June 2001.
5 | R052000008 | Rawatpura-Jaitpura | Bhind | PWD | Road | 2004-02-26 | Consultant | 36.31 | RIDF Loan upto 10 crore | Poor maintainance- pot holes observed at 4/4,4/8 5/6 & 6/4 kms.
5 | R052000048 | Daboh Khajoori | Bhind | PWD | Road | 2004-02-25 | Consultant | 115.91 | RIDF Loan upto 10 crore | Slow progress-due to higher tender percentage & improper design physical progress of the project is slow .
5 | R052000049 | Rurai Alampur | Bhind | PWD | Road | 2004-02-25 | Consultant | 47.02 | RIDF Loan upto 10 crore | project completed.
5 | R052000131 | Mandi Bamora sanai Earan | Sagar | PWD | Road | 2004-02-25 | DDM | 154.26 | RIDF Loan upto 10 crore | Road damaged at 11km. Sub-grade (berms) & BT work not completed.
5 | R052000007 | Bhind-Kacho-Gara | Bhind | PWD | Road | 2004-02-23 | Consultant | 33.04 | RIDF Loan upto 10 crore | Project completed.Department does not maintain the records in proper way.
5 | R052000050 | Mehgaon Gona | Bhind | PWD | Road | 2004-02-23 | Consultant | 97.63 | RIDF Loan upto 10 crore | Contractor problem- no progress since last two years.Department should solve the dispute immediately.
5 | R052000130 | Baikunthpur Dewas Lalgaon | Rewa | PWD | Road | 2004-02-20 | DDM | 68.54 | RIDF Loan upto 10 crore | Progress in implementation is slow.There were 3-4 patches including 800 meters patch in Lalgaon village where BT was not done due to water logging .
5 | R052000068 | Keoti Katra Lalgaon | Rewa | PWD | Road | 2004-02-20 | DDM | 72.79 | RIDF Loan upto 10 crore | Progress in implementation is slow and the project extented upoto 30/06/03,yet it is not completed .comlpetion of work is depending on the sanction of revised estimate.NB board not displayed.
5 | R052000140 | Baghaw-Amiliya | Sidhi | PWD | Road | 2004-02-19 | Consultant | 239.26 | RIDF Loan upto 10 crore | The excavated debris of canal construction is touching the road & drains are completely chocked which has resulted over flow of rain water on road. Poor quality- seal coat on BT not provided.
5 | R052000132 | Pipaliya Hathnora Sardarnagar | Sehore | PWD | Road | 2004-02-17 | Consultant | 29.31 | RIDF Loan upto 10 crore | The agency is doing this work alone .Work upto G-iii of WBM has been done for the length 5.8 km .The G-iii metal were found oversize on the road.
5 | R052000021 | Sone 7/8 | Sidhi | PWD | Bridge | 2004-02-17 | Consultant | 793.17 | RIDF Loan upto 10 crore | Slow progress- approach road work not started .Time overrun- work likely to be completed by June 04 as against March 04.
5 | R052000069 | Semaradangi- Jharkheda | Sehore | PWD | Road | 2004-02-16 | Consultant | 85.06 | RIDF Loan upto 10 crore | The work has been executed as per time scedule and the work is completed by march 2003.A number of potholes have developed on the BT surface .The level of shoulders at different locations were found above.
5 | R052000085 | Barna | Raisen | WRD | MJP | 2004-02-14 | Consultant | 350.21 | RIDF Loan upto 10 crore | Preliminary work has been completed and works are in progress .
5 | R052000086 | Jatalnalla | Balaghat | WRD | MIS | 2004-02-13 | Consultant | 128.4 | RIDF Loan upto 10 crore | The work is likely to be completed by June 2004.The quality of the work was found to be satisfactory.
5 | R052000001 | Amanalla | Balaghat | WRD | MIS | 2004-02-12 | Consultant | 80.13 | RIDF Loan upto 10 crore | Land aquisition money is yet to be paid .Kalaba has not been fixed.
5 | R052000096 | Package 4 (Belkhedi System)) | Jabalpur | NVDA | MJP | 2004-02-12 | DDM | 1914.61 | RIDF Loan 10.01-24.99 crore | Time overrun- project likely to be completed by Jan 05 as against March 04.Slow progress- physical progress of masonary is 16%. Delay in LA process.
5 | R052000098 | Birsola Mohgaon | Balaghat | PWD | Road | 2004-02-10 | Consultant | 30.97 | RIDF Loan upto 10 crore | The execution of works on the road completed.No deficiency was noticed.
5 | R052000034 | Tons 1/8 | Rewa | PWD | Bridge | 2004-02-07 | DDM | 341.57 | RIDF Loan upto 10 crore | slow progress approach road is yet to be completed.
5 | r052000063 | Ashok nagar Piparai | Ashoknagar | PWD | Road | 2004-02-04 | DDM | 103.65 | RIDF Loan upto 10 crore | CD work not completed. NB board not displayed in proper format.
5 | R052000093 | Package 1(LBC 0.16 - 15 KM) | Jabalpur | NVDA | MJP | 2004-02-03 | OIC+RO Officials | 2130.5 | RIDF Loan 10.01-24.99 crore | Slow progress.
5 | R052000037 | Alapur | Gwalior | WRD | MIS | 2004-01-31 | DDM | 631.79 | RIDF Loan upto 10 crore | Nala closure work was almost complete.Final finishing work was to be done.
5 | R052000038 | Jakhoda | Gwalior | WRD | MIS | 2004-01-30 | DDM | 103.89 | RIDF Loan upto 10 crore | Due to frequent change of SDOs of the concerned project ,non availability of adequate funds for the project ,difficulty in getting labour are problem area for completion of the project.
5 | r052000115 | Harmala Pipaliya Bisniya | Mandsaur | PWD | Road | 2004-01-19 | DDM | 42.52 | RIDF Loan upto 10 crore | Nb Board not displayed. Local people have dug the road at two places for lying the pipe-line. Deptt should take steps to prevent such incidents.
5 | r052000116 | Barkheda Devdungari to Malhargarh | Mandsaur | PWD | Road | 2004-01-19 | DDM | 43.5 | RIDF Loan upto 10 crore | Slow progress, physical progress of sub-base, sub-grade & WBM is 52%,5% & 76% respectively, BT not done. Funds constraints, work stopped for want of funds. NB Board not displayed.
5 | r052000117 | Lasudiya Kadmala | Mandsaur | PWD | Road | 2004-01-19 | DDM | 38.8 | RIDF Loan upto 10 crore | NB Board not displayed.
5 | r052000108 | Shadora-Madikanung-Bijapur | Guna | PWD | Road | 2004-01-19 | DDM | 190.5 | RIDF Loan upto 10 crore | Time overrun- project likely to be completed by May04 as against March 04.NB board not displayed in proper format. Monitoring mechanism-No officer above the rank of EE has visited the site.
5 | R052000100 | Kanta Phod Punjapura | Dewas | PWD | Road | 2004-01-15 | DDM | 208.3 | RIDF Loan upto 10 crore | Slow progress-overall progress is 18%.Progress of Sub grade & sub base & BT work is NIL .NB board not displayed.
5 | r052000113 | Ataheda-Padaliya | Indore | PWD | Road | 2004-01-12 | DDM | 86.29 | RIDF Loan upto 10 crore | Poor maintenance, NB Board not displayed.
5 | r052000142 | Bhourasa-Malhargarh | Vidisha | PWD | Road | 2004-01-09 | DDM | 174.87 | RIDF Loan upto 10 crore | 6-20 KM road damaged badly, slow progress, medium bridges to be completed.
5 | r052000097 | Package 5 (Patan 9.74 - 14.4) | Jabalpur | NVDA | MJP | 2004-01-08 | DDM | 1260.93 | RIDF Loan 10.01-24.99 crore | Tendering problem- delay in fixation work agency. Time overrun- project likely to be completed by March 05 as against March 04 Slow progress- physical progress of masonary is 15% Delay in fixation of work agency.
5 | r052000064 | Garoth Rly Stn. to Bardia Amra | Mandsaur | PWD | Road | 2004-01-07 | DDM | 76.03 | RIDF Loan upto 10 crore | BT not done, funds constraints - contractor stopped the work.
5 | R052000101 | Dharampur Tarapur Mandu | Dhar | PWD | Road | 2004-01-01 | DDM | 270.19 | RIDF Loan upto 10 crore | Work is in progress.Milo meter were not installed.Seal coat quality is poor.
5 | r052000023 | Bhanpura-Bhansoda | Mandsaur | PWD | Road | 2003-12-31 | DDM | 101.13 | RIDF Loan upto 10 crore | Funds constraints, contractor stopped the work, slow progress - BT not completed, NB Board not displayed.
5 | R052000109 | Chachoda-Sunasheda via Amaser Kalapipal | Guna | PWD | Road | 2003-12-15 | DDM | 155.3 | RIDF Loan upto 10 crore | 1. NB Board not displayed. 2. BT and CD work should be done on expeditious basis to complete the project in time.
5 | R052000125 | Sakaria Kakarhati Gunour | Panna | PWD | Road | 2003-12-12 | RO Official | 72.32 | RIDF Loan upto 10 crore | 1. Project completed, PCR not received. 2. Poor maintenance, potholes observed at 9/2-9/4,12/2-12/8,14/2-14/6,14/8-15/4,16/2-16/8,17/2-17/4.
5 | R052000123 | Devendranagar Kakarhati | Panna | PWD | Road | 2003-12-12 | RO Official | 80.42 | RIDF Loan upto 10 crore | 1. Slow progress. 2. BT not done at 6/6 to 14/8 KMs. 3. Medium bridge at 14/4,11/4,9/4 to be completed & on their approach road WBM & BT to be done. 4. CD at 11/2 to be repaired at 6/2 KM about 100 meters WBM & BT not done.
5 | R052000107 | A.B.Road to Pantondi Barsat | Guna | PWD | Road | 2003-11-15 | DDM | 127.14 | RIDF Loan upto 10 crore | 1. Water logging problem at CDs. 2. NB Board not displayed in proper format. 3. Project completed, department should sent PCR.
5 | R052000037 | Alapur | Gwalior | WRD | MIS | 2003-11-12 | RO Official | 631.79 | RIDF Loan upto 10 crore | Delay due to Land Acquisition problem.
5 | R052000094 | Package 2 (LBC 15 - 31.5 KM) | Jabalpur | NVDA | MJP | 2003-11-07 | DDM | 1563.59 | RIDF Loan 10.01-24.99 crore | 1. Delay in fixation by work agencies.
5 | R052000093 | Package 1(LBC 0.16 - 15 KM) | Jabalpur | NVDA | MJP | 2003-11-06 | DDM | 2130.5 | RIDF Loan 10.01-24.99 crore | 1. Delay in LA. 2. The Lining of Patan branch canal (PBC) between RD 4 to 7 is in bad shape. This may be got repaired, slow progress, physical progress in only 46%.
5 | R052000095 | Package 3 (LBC 31.5 - 51 KM)) | Jabalpur | NVDA | MJP | 2003-11-04 | DDM | 1890.96 | RIDF Loan 10.01-24.99 crore | 1. Slow progress - the work should be taken up on expeditious basis to avoid time and cost-overrun. 2. Delay in fixation of work agencies. 3. Without approval of NABARD LA dropped in two minors due to change in design.
5 | R052000133 | Bhoma Deoti | Seoni | PWD | Road | 2003-10-16 | RO Official | 39.14 | RIDF Loan upto 10 crore | Road stretch of 5 Km out of 7 Km is in Bad shape. Project is completed
5 | R052000025 | Salakhedi-Bhatpachalana | Ratlam | PWD | Road | 2003-10-14 | DDM | 227.7 | RIDF Loan upto 10 crore | Work in progress
5 | R052000034 | Tons 1/8 | Rewa | PWD | Bridge | 2003-09-26 | DDM | 341.57 | RIDF Loan upto 10 crore | Land acquisition in approach road. Slow Progress. NABARD Board is not displayed
5 | R052000141 | Basoda-Bareth-Basoda Sirong Approach | Vidisha | PWD | Road | 2003-09-02 | DDM | 21.46 | RIDF Loan upto 10 crore | Quality of work is poor. NABARD Board not displayed.
5 | R052000101 | Dharampur Tarapur Mandu | Dhar | PWD | Road | 2003-08-22 | OIC | 270.19 | RIDF Loan upto 10 crore | Slow progress. WBM done 11.40 Km as against 23.40 Km. BT done 2 Km as against 23.40 Km. CD yet to be done.
5 | R052000141 | Basoda-Bareth-Basoda Sirong Approach | Vidisha | PWD | Road | 2003-08-22 | DDM | 21.46 | RIDF Loan upto 10 crore | Slow progress
5 | R052000025 | Salakhedi-Bhatpachalana | Ratlam | PWD | Road | 2003-07-24 | DDM | 227.7 | RIDF Loan upto 10 crore | NABARD board not displayed.
5 | R052000037 | Alapur | Gwalior | WRD | MIS | 2003-06-12 | DDM | 631.79 | RIDF Loan upto 10 crore | Funds constraint and budgetary problem-budget allocation during 2002-03 was Rs 20 lakh, however, Rs 50 lakh to contractor and Rs 80 lakh for LA is to be paid. No balance LoC is available with the department.
5 | R052000142 | Bhourasa-Malhargarh | Vidisha | PWD | Road | 2003-05-28 | DDM | 174.87 | RIDF Loan upto 10 crore | Contractor problem (contractor not ready to complete the work), poor quality of work-most of the parts of the road have been damaged badly.
5 | R052000093 | Package 1(LBC 0.16 - 15 KM) | Jabalpur | NVDA | MJP | 2003-04-16 | DDM | 2130.5 | RIDF Loan 10.01-24.99 crore | Lining of Patan branch canal between RD 4-7 is in bad shape, this may be got repaired
5 | R052000066 | Gangeo Jorout Phool | Rewa | PWD | Road | 2003-04-13 | OIC+RO Officials | 89.91 | RIDF Loan upto 10 crore | Contractor problem - contractor negligent, no work since last 3 months. Complete road could not be monitored as construction material was lying on the road. NB board not displayed.
5 | R052000067 | Paharakha Dewas | Rewa | PWD | Road | 2003-04-13 | OIC+RO Officials | 55.3 | RIDF Loan upto 10 crore | BT not done at Km 1/1 to 3/2 km, WBM at Km 3/2 to 3/4 due to land dispute with farmers BT at CD Km 8/6, seal coating at Km 9/8, sink at Km 9/0 to 9/10 km.. 7 speed breakers between km 6/4 to 7/2 causing traffic problem, NB board not displayed
5 | R052000068 | Keoti Katra Lalgaon | Rewa | PWD | Road | 2003-04-13 | OIC+RO Officials | 72.79 | RIDF Loan upto 10 crore | 3 speed breakers at Km 5/2 to 5/6, BT not done at 7/2 km CD, dept. may review the requirement of speed breakers, NB board not displayed in proper format.
5 | R052000130 | Baikunthpur Dewas Lalgaon | Rewa | PWD | Road | 2003-04-13 | OIC+RO Officials | 68.54 | RIDF Loan upto 10 crore | 7 speed breakers between Km 7/10 to 11/4 which were causing traffic problem, dept. may review requirement of speed breakers, BT not done at CD at 11/4 km.
5 | R052000101 | Dharampur Tarapur Mandu | Dhar | PWD | Road | 2003-03-27 | DDM | 270.19 | RIDF Loan upto 10 crore | Contractor problem (contractor not attending balance work), NB board not displayed in proper format.
5 | R052000108 | Shadora-Madikanung-Bijapur | Guna | PWD | Road | 2003-03-15 | DDM | 190.5 | RIDF Loan upto 10 crore | out of 22 km, 9 km, WBM and BT not done. 5 CDs not done), due to adjoining houses within the road land boundary, road has become very narrow in Amouda village. it may cause accident. NB board not displayed.
5 | R052000053 | Urmil 31/2 | Chattarpur | PWD | Bridge | 2003-03-13 | RO Official | 128.03 | RIDF Loan upto 10 crore | Slow progress (approach road work not started, although the work order has been issued on 18-2-02). NB board not displayed in proper format.
5 | R052000037 | Alapur | Gwalior | WRD | MIS | 2003-02-05 | RO Official | 631.79 | RIDF Loan upto 10 crore | Satisfactory.
5 | R052000085 | Barna | Raisen | WRD | MJP | 2003-01-21 | RO Official | 350.21 | RIDF Loan upto 10 crore | Delay in commencement of work due to land acquisition and alignment approval. Restructuring for bar structure and tonga minor. This has resulted time overrun. Likely date of completion Sept '03. NB board not displayed.
5 | R052000121 | Simariya Mohendra Raipura | Panna | PWD | Road | 2003-01-17 | RO Official | 230.1 | RIDF Loan upto 10 crore | Provision of passing places to be made as per relevant specification, time overrun, approach not made to CD at 9/4, 11/8, 11/10, 29/10, 30/2 km, potholes observed at 0/0, 3/0, 4/2, 4/4, 5/4, 6/4, 7/8, 7/10, 10/8, 11/4, 14/10, 15/2, 28/6, 28/10, 29/6 km.
5 | R052000124 | Seleha Pawai Mohenda | Panna | PWD | Road | 2003-01-17 | RO Official | 421.68 | RIDF Loan upto 10 crore | Provision of passing places needs to be made as per relevant specification, potholes have been observed in Km 42/1, 46/8, 53/9, 61/4, quality lapses (the road surface is wavy / undulating throughout), there is road cutting by farmers at Km 16/8, 42/8.
5 | R052000126 | Shahnagar Zukehi | Panna | PWD | Road | 2003-01-17 | RO Official | 91 | RIDF Loan upto 10 crore | Slow progres - there is no progress in the portion 0/0 to 5/0 km and in reach 30/00 - 51/00 km, provision of passing places to be made as per relevant specification, km stones not installed at all, contractor problem, funds problem, time overrun.
5 | R052000127 | Shahnagar Hardwua via Thepabori | Panna | PWD | Road | 2003-01-17 | RO Official | 347.63 | RIDF Loan upto 10 crore | Slow progress, Time overrun - approach not made to CD at Km 12/2, 17/4, 22/8, 23/10, 24/8, 25/2, 27/10, 39/4, shoulders not provided at 27/10, 35/2, 35/8, 36/4 km, potholes have been observed at 37/2 km.
5 | R052000122 | Makranganj harduahi Gunour | Panna | PWD | Road | 2003-01-16 | RO Official | 92.21 | RIDF Loan upto 10 crore | Provision of passing places needs to be done as per relevant specification, potholes have been observed at Km 17/2, 19/5, 9/4, the road cutting by farmers at Km 20/4, NB board not displayed, funds constraint, no officer above EE visited the site.
5 | R052000097 | Package 5 (Patan 9.74 - 14.4) | Jabalpur | NVDA | MJP | 2003-01-08 | DDM | 1260.93 | RIDF Loan 10.01-24.99 crore | Tendering problem, Time overrun and cost overrun problem, LA revised to 140.39 ha as against sanctioned 127.05 ha. Due to this the cost of LA is Rs. 323.08 lakh against sanction of Rs 127.05 lakh.
5 | R052000096 | Package 4 (Belkhedi System)) | Jabalpur | NVDA | MJP | 2003-01-07 | DDM | 1914.61 | RIDF Loan 10.01-24.99 crore | Delay in LA, tendering, project likely to be completed only by June'04 as against the extended completion date of March '04.
5 | R052000095 | Package 3 (LBC 31.5 - 51 KM)) | Jabalpur | NVDA | MJP | 2003-01-03 | DDM | 1890.96 | RIDF Loan 10.01-24.99 crore | Time overrun (project likely to be completed by June'04 as against the extended completion date of March'04), only 3.62 km of lining and 1 structure has been completed, the progress of earthwork is very slow, release of water in canals.
5 | R052000094 | Package 2 (LBC 15 - 31.5 KM) | Jabalpur | NVDA | MJP | 2003-01-02 | DDM | 1563.59 | RIDF Loan 10.01-24.99 crore | contractor problem, work completed is 68% and 45% respectively, slow progress due to discharge of water for irrigation in canal on account of demand / pressure from farmers.
5 | R052000025 | Salakhedi-Bhatpachalana | Ratlam | PWD | Road | 2002-12-26 | DDM | 227.7 | RIDF Loan upto 10 crore | Satisfactory.
5 | R052000055 | Bhainsdehi Khamala Kukru | Betul | PWD | Road | 2002-12-14 | DDM | 113.29 | RIDF Loan upto 10 crore | Tarring of approach road of minor bridges yet to be completed.
5 | R052000034 | Tons 1/8 | Rewa | PWD | Bridge | 2002-10-22 | DDM | 341.57 | RIDF Loan upto 10 crore | Slow progress. NB board not displayed.
5 | R052000037 | Alapur | Gwalior | WRD | MIS | 2002-10-22 | DDM | 631.79 | RIDF Loan upto 10 crore | Payment not made to contractor due to non-availability of LOC.
5 | R052000082 | Ren 16/4 | Hoshangabad | PWD | Bridge | 2002-08-02 | OIC+C | 42.58 | RIDF Loan upto 10 crore | (summary report issued) To properly protect the bank around abutment, toe wall and pitching to be provided.
5 | R052000136 | Kalapipal-Khamlai-Amlai | Shajapur | PWD | Road | 2002-07-03 | RO Official | 251.7 | RIDF Loan upto 10 crore | Slow Progress (contractor is slow inexecuting the work), LA problem ( LA process to be expedited), NABARD board not displayed, Others (OH HT Line 15 passing over the CD work at Km 2/6 which needs to be shifted in consultation with Electricity Board)
5 | R052000003 | Surajmal | Ratlam | WRD | MIS | 2002-06-18 | DDM | 73.13 | RIDF Loan upto 10 crore | Head works completed. Canal work in progress.
5 | R052000037 | Alapur | Gwalior | WRD | MIS | 2002-06-14 | DDM | 631.79 | RIDF Loan upto 10 crore | Slow progress (major work on Unit II i.e. spill channel may be started soon to avoid any damage to structure.
5 | R052000144 | Sindh 15/6 | Bhind | PWD | Bridge | 2002-06-12 | RO Official+C | 558.72 | RIDF Loan upto 10 crore | Report as per Annexure.
5 | R052000038 | Jakhoda | Gwalior | WRD | MIS | 2002-06-08 | DDM | 103.89 | RIDF Loan upto 10 crore | Slow progress (nala closure work stoppe by contractor. Spill channel work is very slow). Contractor problem (stopped the work).
5 | R052000024 | Sainkheda-Jhinkoli | Narsinghpur | PWD | Road | 2002-06-06 | DDM | 37.62 | RIDF Loan upto 10 crore | Slow progress (not completed by target dte of 3/2002).
5 | R052000119 | Gadarwara Barha | Narsinghpur | PWD | Road | 2002-06-06 | DDM | 114.71 | RIDF Loan upto 10 crore | Completed.
5 | R052000051 | Chandrapura Bhadan Kanjarda | Neemuch | PWD | Road | 2002-05-29 | RO Official+C | 275.46 | RIDF Loan upto 10 crore | Unsatisfactory quality (cleaning of WBM before tack coat is inadequate, camber is not proper, humps at approaches to CD work).
5 | R052000025 | Salakhedi-Bhatpachalana | Ratlam | PWD | Road | 2002-05-24 | DDM | 227.7 | RIDF Loan upto 10 crore | Slow progress (although completion date is 7/2002, only 45% work is done.
5 | R052000067 | Paharakha Dewas | Rewa | PWD | Road | 2002-05-23 | DDM | 55.3 | RIDF Loan upto 10 crore | NB board not displayed. Slow progress (not completed within stipulated period).
5 | R052000128 | Tal Madhopur | Ratlam | PWD | Road | 2002-05-21 | DDM | 48.21 | RIDF Loan upto 10 crore | Completed
5 | R052000142 | Bhourasa-Malhargarh | Vidisha | PWD | Road | 2002-05-09 | DDM | 174.87 | RIDF Loan upto 10 crore | Others (inadequate attention from dept. staff).
5 | R052000068 | Keoti Katra Lalgaon | Rewa | PWD | Road | 2002-05-02 | DDM | 72.79 | RIDF Loan upto 10 crore | Slow progress (contractor is slow, already into extension period).
5 | R052000130 | Baikunthpur Dewas Lalgaon | Rewa | PWD | Road | 2002-04-30 | DDM | 68.54 | RIDF Loan upto 10 crore | Slow progress (not completed within stipulated period), Contractor problem (negligent contractor)
5 | R052000062 | Mungaoli Piprai | Ashoknagar | PWD | Road | 2002-04-29 | DDM | 119.4 | RIDF Loan upto 10 crore | NB board to be displayed. Others (inaction of Railway authorities in starting the level crossing work is delaying the work)
5 | R052000106 | Hapakhedi-Panwarihat-via-Mohasa Dagrai-Amkheda | Guna | PWD | Road | 2002-04-29 | DDM | 123.06 | RIDF Loan upto 10 crore | NB board to be displayed.
5 | R052000108 | Shadora-Madikanung-Bijapur | Guna | PWD | Road | 2002-04-29 | DDM | 190.5 | RIDF Loan upto 10 crore | Slow progress (work sanctioned in 99-2000 has not started yet). Delay in tendering (nearly 2 years for settling tenders).
5 | r052000098 | Birsola Mohgaon | Balaghat | PWD | Road | 2002-04-26 | RO Official | 30.97 | RIDF Loan upto 10 crore | BT to be done.
5 | R052000066 | Gangeo Jorout Phool | Rewa | PWD | Road | 2002-04-24 | DDM | 89.91 | RIDF Loan upto 10 crore | Slow progress (not completed within stipulated period). Contractor problem (financial/physical constraints)
5 | R052000005 | Amla-Bordehi | Betul | PWD | Road | 2002-04-11 | DDM | 164.17 | RIDF Loan upto 10 crore | NB board not displayed.
5 | R052000004 | Multaikhedli-Bordehi | Betul | PWD | Road | 2002-04-10 | DDM | 59.9 | RIDF Loan upto 10 crore | NB board not displayed. BT is not completed.
5 | R052000111 | Mohna Patai | Gwalior | PWD | Road | 2002-04-05 | DDM | 61.51 | RIDF Loan upto 10 crore | Slow progress (work is not completed although scheduled date was 11/2000 & 1/2002 for road and CD works respectively)
5 | R052000107 | A.B.Road to Pantondi Barsat | Guna | PWD | Road | 2002-03-20 | DDM | 127.14 | RIDF Loan upto 10 crore | NB board not displayed. Others (shifting of houses located on alignment).
5 | R052000109 | Chachoda-Sunasheda via Amaser Kalapipal | Guna | PWD | Road | 2002-03-20 | DDM | 155.3 | RIDF Loan upto 10 crore | Slow prgress (pace to be accelarated).
5 | R052000140 | Baghaw-Amiliya | Sidhi | PWD | Road | 2002-03-20 | RO Official | 239.26 | RIDF Loan upto 10 crore | Report as per Annexure.
5 | R052000021 | Sone 7/8 | Sidhi | PWD | Bridge | 2002-03-19 | RO Official | 793.17 | RIDF Loan upto 10 crore | Delay in tendering (tender for approach road not invited). Likely cost overrun (due to increased foundation depth).
5 | R052000023 | Bhanpura-Bhansoda | Mandsaur | PWD | Road | 2002-02-28 | RO Official | 101.13 | RIDF Loan upto 10 crore | Observation of technical nature (Two additional CDs at Km 3/8 and Km 3/10 proposed which according to the dept. will ensure all weather connectivity between Bhanpura and Maisoda mandis, which aspect was overlooked during preparation of proposal for NB.
5 | R052000131 | Mandi Bamora sanai Earan | Sagar | PWD | Road | 2002-01-31 | DDM | 154.26 | RIDF Loan upto 10 crore | Crust requirement has not been assessed properly as per site condtions (only one layer WBM+BT has been proposed), work has stopped.
5 | R052000076 | Gurari 9/4 | Tikamgarh | PWD | Bridge | 2002-01-29 | RO Official | 57.43 | RIDF Loan upto 10 crore | Observations of technical nature (Deviations have been made from the sanctioned design-depth of foundation have been increased by 2 to 3 m, length of approaches have been increased from 200 m to 520 m to avoid sharp turn near the bridge.
5 | R052000034 | Tons 1/8 | Rewa | PWD | Bridge | 2002-01-09 | DDM | 341.57 | RIDF Loan upto 10 crore | Slow progress (approach road on Sitalama side to be taken up)
5 | R052000002 | Bargi | Dindori | WRD | MIS | 2002-01-08 | RO Official | 90.66 | RIDF Loan upto 10 crore | Work under Unit II to be started.
5 | R052000019 | Patehar-Sita-Laha Road | Rewa | PWD | Road | 2002-01-06 | DDM | 40.58 | RIDF Loan upto 10 crore | In order to utilise this road the bridge work at Tons river and this approach road is to be speeded up, NB board to be displayed
5 | R052000020 | Ataraila-Jawa Road | Rewa | PWD | Road | 2002-01-04 | DDM | 75.4 | RIDF Loan upto 10 crore | Initial zoom not done due to electric poles and built-up area and agriculture land - compensation to be effected
5 | R052000044 | Budner 4/4 | Mandla | PWD | Bridge | 2001-12-28 | DDM | 83.69 | RIDF Loan upto 10 crore | Completed. NB board not displayed
5 | R052000133 | Bhoma Deoti | Seoni | PWD | Road | 2001-12-28 | RO Official | 39.14 | RIDF Loan upto 10 crore | Shoulder dressing required to be undertaken, Road cut opened by farmers at a few places for the pipe line CD alignment at 8/8km near Chattarpur village very acute and accident prone, no caution sign was displayed, NB Board not displayed.
5 | R052000135 | Duter to Joinkeolari ugli | Seoni | PWD | Road | 2001-12-28 | RO Official | 50.28 | RIDF Loan upto 10 crore | Although road alignment at several places was very acute and therefore accident prone, no caution signs were displayed-e.g. at 4/10km,9/2km,11/2km-near Arjunjhir village & 13/2km, Protective work like boulder pitching observed to be necessary.
5 | R052000141 | Basoda-Bareth-Basoda Sirong Approach | Vidisha | PWD | Road | 2001-12-27 | DDM | 21.46 | RIDF Loan upto 10 crore | Inadequate monitoring by dept. (no officer above EE level has visited). NB board not displayed. Contractor problem (insufficient manpower).
5 | R052000048 | Daboh Khajoori | Bhind | PWD | Road | 2001-11-09 | RO Official+C | 115.91 | RIDF Loan upto 10 crore | No physical work commenced at site, Abnormal delay in tendering (tender for the work was called and submitted to E-in-C on 17-10-01, the same however was not finalised till date of visit), Time overrun likely.
5 | R052000050 | Mehgaon Gona | Bhind | PWD | Road | 2001-11-09 | RO Official+C | 97.63 | RIDF Loan upto 10 crore | Observation of technical nature (presently the zero point is the end of the Mehgaon Nagar Panchayat road which is in the bad state of repairs. A diversion of about 900 m has been proposed to join in Km 2/4 of Mehgaon Mhow road to avoid traffic.
5 | R052000144 | Sindh 15/6 | Bhind | PWD | Bridge | 2001-11-08 | RO Official+C | 558.72 | RIDF Loan upto 10 crore | No physical work commenced at site, Delay in tendering (although the project was sanctioned on 25/3/2000, the tenders have been invited only on 29/8/2001 i.e. with a time lag of 17 months; also the tenders invited were pending with the department.
5 | R052000071 | Gangul 18/4 | Betul | PWD | Bridge | 2001-11-07 | DDM | 84.48 | RIDF Loan upto 10 crore | Budgetary constraint (only Rs 10 lakh provision is available against expenditure of Rs 37 lakh).
5 | R052000112 | Sumtha-Ganga-Jalkhedi-Nandra-Banedia | Indore | PWD | Road | 2001-11-07 | DDM | 120.4 | RIDF Loan upto 10 crore | Delay in tendering (although the division received intimation of sanction of prject on 13/4/00, first agency was finalised on 6/1/01 and another one was finalised on 8/5/01), Slow progress of work, Work likely to be affected owing to water scarcity.
5 | R052000113 | Ataheda-Padaliya | Indore | PWD | Road | 2001-11-07 | DDM | 86.29 | RIDF Loan upto 10 crore | Slow progress of work due to contractor problem (only CD work in progress), Delay in tendering (although the division received intimation of sanction of project in July 00, the agency was fixed only on 15/2/01), Time overrun likely.
5 | R052000125 | Sakaria Kakarhati Gunour | Panna | PWD | Road | 2001-11-07 | DDM | 72.32 | RIDF Loan upto 10 crore | Work not yet commenced, Delay in tendering (tendering for road work not yet finalised), General (no progress of work since earlier visit on 21.4.01).
5 | R052000100 | Kanta Phod Punjapura | Dewas | PWD | Road | 2001-11-06 | DDM+C | 208.3 | RIDF Loan upto 10 crore | Report received
5 | R052000142 | Bhourasa-Malhargarh | Vidisha | PWD | Road | 2001-11-02 | DDM | 174.87 | RIDF Loan upto 10 crore | Slow progress of work, Contractor problem (slow execution of work, quality of material used appeared to be sub-standard), Time overrun likely (project likely to be completed only by 31/3/03 as against the completion due date of 31/3/02).
5 | R052000005 | Amla-Bordehi | Betul | PWD | Road | 2001-10-31 | DDM | 164.17 | RIDF Loan upto 10 crore | Work progress satisfactory, Contractor problem (work regarding tarring of approach roads of 7 CDs abondoned, contract terminated), NB board not displayed
5 | R052000004 | Multaikhedli-Bordehi | Betul | PWD | Road | 2001-10-25 | DDM | 59.9 | RIDF Loan upto 10 crore | Work progress satisfactory (only the tarring of approach roads of minor bridges and culverts to be completed), NB board not displayed
5 | R052000045 | Narmada 9/10 | Narsinghpur | PWD | Bridge | 2001-10-23 | DDM+C | 589.46 | RIDF Loan upto 10 crore | No physical work commenced at site, There has been unusual delay in starting the work. The department floated tenders for detailed survey, box results and structural design only after the project was approved by NABARD.
5 | R052000119 | Gadarwara Barha | Narsinghpur | PWD | Road | 2001-10-22 | DDM+C | 114.71 | RIDF Loan upto 10 crore | project likely to be completed by 31/3/03 as against the completion due date of 31/3/02, cost escalation Rs. 28.10 lacs on account of change in specifications, Inadequate monitoring by the department
5 | R052000038 | Jakhoda | Gwalior | WRD | MIS | 2001-10-16 | DDM | 103.89 | RIDF Loan upto 10 crore | Delay in land acquisition (land for Unit I & II not yet acquired, land under acquisition for Unit I admeasures 38.20 ha and is forest land, compensation for which -Rs. 34.41 lakhs has been paid to the forest dept by August 01), Delay in tendering.
5 | R052000003 | Surajmal | Ratlam | WRD | MIS | 2001-09-11 | DDM | 73.13 | RIDF Loan upto 10 crore | In progress.
5 | R052000014 | Aron-Barod-Panwarihat | Guna | PWD | Road | 2001-08-30 | DDM | 69.34 | RIDF Loan upto 10 crore | Completed
5 | R052000065 | Ratlam- Nagada | Ratlam | PWD | Road | 2001-07-11 | DDM | 108.08 | RIDF Loan upto 10 crore | Slow progress of work (Construction of road not yet commenced, one out of 4 CDs not yet completed), Time overrun likely, Delay in tendering, NB board not displayed.
5 | R052000129 | Gogapur-Alot-Suwasra | Ratlam | PWD | Road | 2001-07-10 | DDM | 89.63 | RIDF Loan upto 10 crore | Delay in tendering, work not yet commenced, NB board not displayed.
5 | R052000102 | Gandhwani Chikhli | Dhar | PWD | Road | 2001-05-24 | DDM | 61.1 | RIDF Loan upto 10 crore | Project nearing completion, only the BT-2km out of 8.6km remained incomplete.
5 | R052000101 | Dharampur Tarapur Mandu | Dhar | PWD | Road | 2001-05-19 | DDM | 270.19 | RIDF Loan upto 10 crore | Slow progress of work, only the stone cutting in ghat section and one submersible bridge completed till date.
5 | R052000141 | Basoda-Bareth-Basoda Sirong Approach | Vidisha | PWD | Road | 2001-05-09 | DDM | 21.46 | RIDF Loan upto 10 crore | Progress of work slow owing to scarcity of water for drought conditions in the district, NB board not displayed, sub-base/WBM/BT not yet undertaken and 20% of the CDs pending as on date
5 | R052000142 | Bhourasa-Malhargarh | Vidisha | PWD | Road | 2001-05-09 | DDM | 174.87 | RIDF Loan upto 10 crore | Slow progress of work owing to scarcity of water for drought conditions in the district, of the 20.6 km road length proposed, earthwork is completed only for 2 km road length, NB board not displayed.
5 | R052000042 | Khajri 8/4 | Chhindwara | PWD | Bridge | 2001-05-03 | DDM | 25.97 | RIDF Loan upto 10 crore | Project completed, PCR however not yet received
5 | R052000119 | Gadarwara Barha | Narsinghpur | PWD | Road | 2001-05-03 | DDM | 114.71 | RIDF Loan upto 10 crore | Progress of work slow(work for SG/SB &WBM was initiated and of the 27CDs,11CDs were under construction and excavation for other 8 CDs was completed), observations of technical nature (one renewal coat of Grade II may be necessary for road length.
5 | R052000112 | Sumtha-Ganga-Jalkhedi-Nandra-Banedia | Indore | PWD | Road | 2001-04-28 | DDM | 120.4 | RIDF Loan upto 10 crore | Work not in progress, work also likely to be affected owing to water scarcity for drought conditions in the district, NB board not displayed, observations of technical nature (Sumtha to Gangajalkhedi (3.5 km) oversize though completed previously.
5 | R052000113 | Ataheda-Padaliya | Indore | PWD | Road | 2001-04-28 | DDM | 86.29 | RIDF Loan upto 10 crore | Slow progress of work due to contractor problem, NB board not displayed, observations of technical nature (the road was constructed some 10 years back from the Collector's funds. The condition of the road appeared to be very poor.
5 | R052000061 | Tappa- Siddi- Kigang | Dewas | PWD | Road | 2001-04-23 | DDM | 81.19 | RIDF Loan upto 10 crore | Project almost completed (only the approaches to 2 out of 4 CDs remained incomplete), NB board not displayed, observations of technical nature (there was hump formation on CDs which needed to be smoothened, no drains were provided in the reaches.
5 | R052000128 | Tal Madhopur | Ratlam | PWD | Road | 2001-04-23 | DDM | 48.21 | RIDF Loan upto 10 crore | Delay in tendering, work progress slow, balance work WBM- 71%, BT-100% and CDs-100% as on date.
5 | R052000025 | Salakhedi-Bhatpachalana | Ratlam | PWD | Road | 2001-04-21 | DDM | 227.7 | RIDF Loan upto 10 crore | Sub-base and WBM near completion for 3 km road length out of the total road length of 27.60 km, 10 out of 41 CDs near completion.
5 | R052000020 | Ataraila-Jawa Road | Rewa | PWD | Road | 2001-04-19 | DDM | 75.4 | RIDF Loan upto 10 crore | There was encroachment on road by cluster of houses and no road construction was taken up at that point, 2 electrical poles stood erected on the road which required removal, CD work required to be taken up at canal.
5 | R052000021 | Sone 7/8 | Sidhi | PWD | Bridge | 2001-04-17 | RO Official | 793.17 | RIDF Loan upto 10 crore | Physical progress (foundation-41.31%, sub-structure-59.82%, superstructure-32.25%, approach road- NIL), project likely to be completed by December 2002 as against the completion/extended completion date of 31/3/2002), NB board not displayed.
5 | R052000041 | Pench 12/10 | Chhindwara | PWD | Bridge | 2001-04-17 | DDM | 65.7 | RIDF Loan upto 10 crore | Slow progress of work, project likely to be completed by June 02 as against the due date of March 01, 50% of work remained incomplete, delay in construction of bridge is affecting utility of the newly constructed roads on both sides of the bridge
5 | R052000111 | Mohna Patai | Gwalior | PWD | Road | 2001-03-29 | DDM | 61.51 | RIDF Loan upto 10 crore | Delay in tendering (tendering for road work was finalised only in 1st week of Jan 01, no tender was floated for CDs- 2 nos.- by the bridge division of PWD- the agency which was to construct those CDs), cost escalation likely.
5 | R052000024 | Sainkheda-Jhinkoli | Narsinghpur | PWD | Road | 2001-03-19 | DDM | 37.62 | RIDF Loan upto 10 crore | Slow progress, delay in tendering, NB board not displayed, repair required for sub-base and base-course Gr-I Gr-II base course is required for the entire road length of 8.8 km, The PWD should examine the matter and take appropriate decision.
5 | R052000036 | Sone 21/6-8 | Anuppur | PWD | Bridge | 2001-03-14 | DDM | 54.98 | RIDF Loan upto 10 crore | Slow progress of work (although the bridge was complete, work for approach road not yet commenced), NB board not displayed,
5 | R052000102 | Gandhwani Chikhli | Dhar | PWD | Road | 2001-03-07 | DDM | 61.1 | RIDF Loan upto 10 crore | Agency fixed and 50%of the WBM completed,Sanctioned CD work also completed,BT work however not initiated which needs to be completed during the current year,NB board not displayed.
5 | R052000129 | Gogapur-Alot-Suwasra | Ratlam | PWD | Road | 2001-02-09 | DDM | 89.63 | RIDF Loan upto 10 crore | Delay in tendering, work not yet commenced, NB board not displayed.
5 | R052000073 | Bina 11/6-8 | Sagar | PWD | Bridge | 2001-01-31 | DDM | 96.75 | RIDF Loan upto 10 crore | Report not received
5 | R052000041 | Pench 12/10 | Chhindwara | PWD | Bridge | 2001-01-26 | DDM | 65.7 | RIDF Loan upto 10 crore | Project complete in all respect and open to traffic. Quality of work satisfactory. PCR need to be submitted soon.
5 | R052000042 | Khajri 8/4 | Chhindwara | PWD | Bridge | 2001-01-26 | DDM | 25.97 | RIDF Loan upto 10 crore | Side drains incomplete. Payment for LA pending. The project is expected to complete by March 2001. Quality satisfactory. A bridge on neighbouring nallah and road towards Ramgarh side need to be constructed for establishing proper connectivity.
5 | R052000065 | Ratlam- Nagada | Ratlam | PWD | Road | 2001-01-23 | DDM | 108.08 | RIDF Loan upto 10 crore | Work not yet commenced, time overrun likely, delay in tendering, NB board not displayed.
5 | R052000037 | Alapur | Gwalior | WRD | MIS | 2001-01-12 | DDM | 631.79 | RIDF Loan upto 10 crore | Work not yet commenced. Delay in according technical sanction. Tender for head works floated.
5 | R052000024 | Sainkheda-Jhinkoli | Narsinghpur | PWD | Road | 2001-01-09 | DDM | 37.62 | RIDF Loan upto 10 crore | Tendering for CD works only completed. Agency for road work still not finalised. Contractor not coming forward due to non-availability of material in nearby areas. PWD should look into the matter with a view to fixing of agency early.
5 | R052000038 | Jakhoda | Gwalior | WRD | MIS | 2000-11-21 | DDM | 103.89 | RIDF Loan upto 10 crore | Work not yet commenced, delay in tendering, funds constraints, forest clearance required
5 | R052000037 | Alapur | Gwalior | WRD | MIS | 2000-11-16 | DDM | 631.79 | RIDF Loan upto 10 crore | Work not yet commenced, delay in tendering, funds constraints
5 | R052000111 | Mohna Patai | Gwalior | PWD | Road | 2000-11-14 | DDM | 61.51 | RIDF Loan upto 10 crore | work not yet commenced, delay in tendering, NB board not displayed
5 | R052000025 | Salakhedi-Bhatpachalana | Ratlam | PWD | Road | 2000-11-08 | DDM | 227.7 | RIDF Loan upto 10 crore | Nothing particular reported
5 | R052000036 | Sone 21/6-8 | Anuppur | PWD | Bridge | 2000-10-23 | DDM | 54.98 | RIDF Loan upto 10 crore | NB board not displayed
5 | R052000034 | Tons 1/8 | Rewa | PWD | Bridge | 2000-05-31 | DDM | 341.57 | RIDF Loan upto 10 crore | The progress of work was satisfactory.
5 | R052000009 | Fatehpur-Bhilonimadiado | Damoh | PWD | Road |  |  | 150.92 | RIDF Loan upto 10 crore
5 | R052000010 | Hathni-Jhapan | Damoh | PWD | Road |  |  | 175.96 | RIDF Loan upto 10 crore
5 | R052000012 | Bakayan-Phutera | Damoh | PWD | Road |  |  | 143.08 | RIDF Loan upto 10 crore
5 | R052000015 | Bhonra-Rampur | Guna | PWD | Road |  |  | 32.71 | RIDF Loan upto 10 crore
5 | R052000017 | Ukawad - Naseerpur- Suthaliya | Guna | PWD | Road |  |  | 102.84 | RIDF Loan upto 10 crore
5 | R052000040 | Chainpura | Sehore | WRD | MIS |  |  | 234.45 | RIDF Loan upto 10 crore
5 | R052000043 | Bairama 30/10 | Damoh | PWD | Bridge |  |  | 80.15 | RIDF Loan upto 10 crore
5 | R052000046 | Bhatan 7/8 | Shajapur | PWD | Bridge |  |  | 28.81 | RIDF Loan upto 10 crore
5 | R052000047 | Bagawat 1/8 | Shajapur | PWD | Bridge |  |  | 26.43 | RIDF Loan upto 10 crore
5 | R052000052 | Kel 6/8 | Chattarpur | PWD | Bridge |  |  | 69.7 | RIDF Loan upto 10 crore
5 | R052000057 | Bhaisaghat Selwada Tendukheda | Damoh | PWD | Road |  |  | 141 | RIDF Loan upto 10 crore
5 | R052000058 | Patera raneh | Damoh | PWD | Road |  |  | 107.09 | RIDF Loan upto 10 crore
5 | R052000059 | Hindoria Bilai | Damoh | PWD | Road |  |  | 57.52 | RIDF Loan upto 10 crore
5 | R052000070 | Tawa 7/10 | Betul | PWD | Bridge |  |  | 128.2 | RIDF Loan upto 10 crore
5 | R052000077 | Bantha 20/2 | Dewas | PWD | Bridge |  |  | 36.9 | RIDF Loan upto 10 crore
5 | R052000099 | Batiagarh Khanderi Kerbana | Damoh | PWD | Road |  |  | 26.84 | RIDF Loan upto 10 crore
5 | R052000104 | Guna Aron Barkhedi Gird | Guna | PWD | Road |  |  | 41.84 | RIDF Loan upto 10 crore
5 | R052000110 | Parsol Sirni Indar kadwaya | Ashoknagar | PWD | Road |  |  | 111.62 | RIDF Loan upto 10 crore
5 | R052000114 | Salaia-Bakal-Bahori Band upto NH7 | Katni | PWD | Road |  |  | 112.06 | RIDF Loan upto 10 crore
5 | R052000134 | Mandla Ghansore | Seoni | PWD | Road |  |  | 31.4 | RIDF Loan upto 10 crore
5 | R052000138 | Pipalwas - Pacahalna | Shajapur | PWD | Road |  |  | 86.45 | RIDF Loan upto 10 crore
5 | R052000139 | Pipliyanagar Rly.Stn-Nandani | Shajapur | PWD | Road |  |  | 91.86 | RIDF Loan upto 10 crore
5 | R052000151 | Wainganga 5/2 | Seoni | PWD | Bridge |  |  | 210.23 | RIDF Loan upto 10 crore
6 | r062000113 | Kusmania Harangaon Deepgaon | Dewas | PWD | Road | 2008-02-20 | Dewas DDM | 699.58 | RIDF Loan upto 10 crore | The overall condition of the road was good. Out of 51 Km road sanctioned, 45 KM (approx) work is complete. The balance portion is near the river and requires cement conrete. The work has already started.
6 | R062000154 | LBMC 72km-84km-with its dist. excl Deory dist. | Narsinghpur | NVDA | MJP | 2008-02-15 | Narsinghpur DDM | 2169.3 | RIDF Loan 10.01-24.99 crore | The work in main canal is almost complete. The Dept. should take effective steps to complete the project without any further delay.
6 | r062000127 | LBMC 63.42-72.00 dist.sys | Narsinghpur | NVDA | MJP | 2008-02-08 | Narsinghpur DDM | 1713.04 | RIDF Loan 10.01-24.99 crore | NABARD board has been displayed. As per DDM the work relating to structures and lining particularly in the distribution system is still to be completed but the PCR has been submitted.
6 | r062000107 | Deori Distributory | Narsinghpur | NVDA | MJP | 2008-02-06 | Narsinghpur DDM | 634.65 | RIDF Loan upto 10 crore | The progress of work is very slow. The department should take effective steps to avoid further delay. NABARD board has been displayed.
6 | r062000104 | Patan Branch (9.86 - 18.74) | Jabalpur | NVDA | MJP | 2007-12-15 | Jabalpur DDM | 638.91 | RIDF Loan upto 10 crore | NABARD board not displayed. No records maintained at the project site. Canal to be maintained and cleaned at regular intervals. Cracks developed at many places on the lining of the canal.
6 | r062000106 | LBC Lining RD 51 to 63.4 | Jabalpur | NVDA | MJP | 2007-12-15 | Jabalpur DDM | 1380.96 | RIDF Loan 10.01-24.99 crore | NABARD board has been displayed. Regular visits are not being undertaken. Maintenance of canal not being done. Silt clearing, raising of canal banks, clearance of shrubs, and other related works to be undertaken.
6 | r062000023 | Jobat | Alirajpur | NVDA | MIP | 2007-11-29 | Jhabua DDM | 7653.31 | RIDF Loan 25 crore & above | Labour and contractor problem. 120 families of 4 villages not yet ready for settlement. Monitoring done regularly. NABARD board displayed.
6 | r062000004 | Shajapur-Bijana-Chomo | Shajapur | PWD | Road | 2007-05-18 | Shajapur DDM | 203.22 | RIDF Loan upto 10 crore | LA problem. NABARD board not displayed. The road has a dangerous dip at 3/8 KM no caution board erected. Road cut at several places without notice of the Dept. Shoulders/Berms all along the road length require dressing. Cost overrun. Time overrun.
6 | r062000108 | Shahpura Distributory | Jabalpur | NVDA | MJP | 2007-03-13 | Jabalpur DDM | 1163.34 | RIDF Loan 10.01-24.99 crore | Tenders have not been finalised. NABARD board has not been displayed.
6 | r062000114 | Tendukheda Gadarwara | Narsinghpur | PWD | Road | 2007-01-17 | Narsinghpur DDM | 108.51 | RIDF Loan upto 10 crore | Deep ruts and potholes have developed on the road and the road is cut at several places. At a few places the road has sunk below the shoulder level. The pace and quality of repair work is poor.
6 | r062000139 | Dhabala Mohan Khadawada | Mandsaur | PWD | Road | 2007-01-12 | Mandsaur DDM | 206.95 | RIDF Loan upto 10 crore | PCR VERIFICATION. Surface on most portion of the road worn off. Approach of two culverts washed away due to heavy rains. The road has provided connectivity to 6 villages. The road is under three years performance guarantee by the contractor.
6 | r062000127 | LBMC 63.42-72.00 dist.sys | Narsinghpur | NVDA | MJP | 2007-01-09 | Narsinghpur DDM | 1713.04 | RIDF Loan 10.01-24.99 crore | The lining work of main canal between RD 69.2 KM to RD 69.9 KM is yet to be completed.
6 | r062000016 | Samai-Vijaypur | Morena | PWD | Road | 2007-01-05 | Morena DDM | 123.03 | RIDF Loan upto 10 crore | NABARD board has not been displayed. The quality of road is not good. WBM has loosened at many places. The road has developed pot holes at many places and requires repairs. The road has reduced the distance between Rampurkalan and Morena.
6 | r062000140 | Shamgarh Khajuri Panth | Mandsaur | PWD | Road | 2006-12-30 | Mandsaur DDM | 78.33 | RIDF Loan upto 10 crore | PCR VERIFICATION: At two places in Dhabla Gujar village, drainage water is passing through road. The road is very useful during monsoons and it has connected 11 villages to the mandi at Skhamgadh.
6 | r062000004 | Shajapur-Bijana-Chomo | Shajapur | PWD | Road | 2006-12-29 | Shajapur DDM | 203.22 | RIDF Loan upto 10 crore | No work done in 900 metres of the choma-bijana segment due to land dispute between Dept. and owner. Road cut at various places NABARD board has not been displayed. Shoulders/Berms all along with road length might require dressing.
6 | r062000022 | Sunera-Khoriya | Shajapur | PWD | Road | 2006-12-29 | Shajapur DDM | 119.7 | RIDF Loan upto 10 crore | No work done in 600 m from 3/2-3/6 from Sunera end of the road owing to a dispute between Dept. and owner. BT on rest of the road lenght has not been smooth. No milestones have been fixed along the road length. NABARD board has not been displayed.
6 | R062000131 | Tonk Khurd Gandrupuri Pipatasa | Dewas | PWD | Road | 2006-12-20 | Dewas DDM | 500.92 | RIDF Loan upto 10 crore | Work is incomplete and stopped. The condition is very poor. Many pot holes are not patched up. At some places BT was worn out. Follow-up and maintenance is very poor. NABARD board has not been displayed. Very difficult to locate the road.
6 | R062000113 | Kusmania Harangaon Deepgaon | Dewas | PWD | Road | 2006-12-19 | Dewas DDM | 699.58 | RIDF Loan upto 10 crore | NABARD board not displayed. Project yet to be completed. The overall condition of the road was good except for some potholes.
6 | R062000023 | Jobat | Alirajpur | NVDA | MIP | 2006-11-08 | Jhabua DDM | 7653.31 | RIDF Loan 25 crore & above | Project to be completed by March 2007. NABARD board displayed. 24 villages will be benefited.
6 | r062000112 | Ubhegaon Gondra Rajana Bichhua | Chhindwara | PWD | Road | 2006-09-14 | Chindwara DDM | 187.77 | RIDF Loan upto 10 crore | Connecting roads not in good condition. NABARD board has been displayed. Department to ensure construction/maintenance of existing roads also.
6 | r062000111 | Marud Itawa | Chhindwara | PWD | Road | 2006-09-11 | Chindwara DDM | 163.56 | RIDF Loan upto 10 crore | NABARD board displayed on both the ends. The road has increased mobility to Pandhurna and Maharashtra.
6 | R062000023 | Jobat | Alirajpur | NVDA | MIP | 2006-06-06 | OIC+Consultant | 7653.31 | RIDF Loan 25 crore & above | NVDA to ensure all balance work are completed in all respects by March 2007.
6 | R062000107 | Deori Distributory | Narsinghpur | NVDA | MJP | 2006-05-09 | Narsinghpur DDM | 634.65 | RIDF Loan upto 10 crore | Structures are getting damaged and degenerated due to non-use. Work should be expedited. Implementation is reportedly very poor. NABARD board not displayed.
6 | R062000154 | LBMC 72km-84km-with its dist. excl Deory dist. | Narsinghpur | NVDA | MJP | 2006-05-05 | Narsinghpur DDM | 2169.3 | RIDF Loan 10.01-24.99 crore | The progress of implementation is poor due to poor performance of the contractor
6 | R062000138 | Bardia Amra Balod | Mandsaur | PWD | Road | 2006-05-02 | Mandsaur DDM | 476.05 | RIDF Loan upto 10 crore | Quality of road is poor. Name of NABARD in the Board is not bold.
6 | R062000139 | Dhabala Mohan Khadawada | Mandsaur | PWD | Road | 2006-05-02 | Mandsaur DDM | 206.95 | RIDF Loan upto 10 crore | One end of the road is damaged and needs repairs. Land acquisition claims yet to be settled.
6 | R062000017 | Sihoniya-Porsa | Morena | PWD | Road | 2006-03-29 |  | 53.97 | RIDF Loan upto 10 crore
6 | R062000130 | Aghera Dhabala Khalsa | Dewas | PWD | Road | 2006-03-28 | DDM | 209.18 | RIDF Loan upto 10 crore | Project is complete.
6 | R062000146 | Kedarpur Dhanwahi | Seoni | PWD | Road | 2006-03-25 | DDM | 77.52 | RIDF Loan upto 10 crore | Nearly 70% work completed.
6 | R062000145 | Ghagharimal Khamaria | Seoni | PWD | Road | 2006-03-25 | DDM | 193 | RIDF Loan upto 10 crore | Subgrade, subbase and WBM completed in 16 out of 18 km length. 25 CD works completed against 29 sanctioned. Work is in progress.
6 | R062000117 | Balpur Dhanora-Kachi Budhawara Agaria Ghogharima | Seoni | PWD | Road | 2006-03-24 | DDM | 170.05 | RIDF Loan upto 10 crore | Subgrade and subbase completed in 13 km and WBM in 9 km against total length of 16.6 km sanctioned. 25 CD works out of 26 sanctioned have been completed. Progress is slow.
6 | R062000103 | Nonghati Damehari | Anuppur | PWD | Road | 2006-03-01 | DDM | 202.56 | RIDF Loan upto 10 crore | Project completed upto 94.15%. Slow work progress. Contractor is not doing work as per agreement.
6 | R062000103 | Nonghati Damehari | Anuppur | PWD | Road | 2006-03-01 | OIC | 202.56 | RIDF Loan upto 10 crore | Project completed upto 94.15%. Progress is slow.
6 | R062000017 | Sihoniya-Porsa | Morena | PWD | Road | 2006-02-27 | DDM | 53.97 | RIDF Loan upto 10 crore | BT peeled off at many places. NB board not displayed.
6 | R062000140 | Shamgarh Khajuri Panth | Mandsaur | PWD | Road | 2006-02-24 | DDM | 78.33 | RIDF Loan upto 10 crore | Project is completed and the road is being. Quality of construction is satisfactory.
6 | R062000079 | Lalpur | Dindori | WRD | MIS | 2006-02-22 | DDM | 45.46 | RIDF Loan upto 10 crore | Project completed. NABARD board displayed but removed by villagers. WUA formed.
6 | R062000022 | Sunera-Khoriya | Shajapur | PWD | Road | 2006-02-16 | DDM | 119.7 | RIDF Loan upto 10 crore | 600 m road from Km 3/2 to 3/6 from Sunera end of the road is held up due to land acquisition problem. BT is not smooth. NB board has not been displayed.
6 | R062000004 | Shajapur-Bijana-Chomo | Shajapur | PWD | Road | 2006-02-16 | DDM | 203.22 | RIDF Loan upto 10 crore | No work done in 900 m between Km 15 and 16 due to land acquisition problem. Progress is slow. Project likely to be completed by May 2006. NB board not displayed.
6 | R062000066 | Delchi-Gurariya | Ujjain | PWD | Road | 2006-02-03 | DDM | 75.13 | RIDF Loan upto 10 crore | Project completed.
6 | R062000068 | Kapeli-Karedi | Ujjain | PWD | Road | 2006-02-03 | DDM | 49.42 | RIDF Loan upto 10 crore | Road work except BT completed. CD works are in progress.
6 | R062000014 | Shobhapur-Machha-Pachalwa | Hoshangabad | PWD | Road | 2006-01-31 | DDM | 170.6 | RIDF Loan upto 10 crore | Progress is slow. 9 km out of 12 km sanctioned.
6 | R062000131 | Tonk Khurd Gandrupuri Pipatasa | Dewas | PWD | Road | 2006-01-31 | DDM | 500.92 | RIDF Loan upto 10 crore | Project is completed. Quality of works is not satisfactory.
6 | R062000010 | Kunwari-3/4 | Morena | PWD | Bridge | 2006-01-27 | DDM | 77.94 | RIDF Loan upto 10 crore | Project is completed. The approach road has been damaged. NB board not displayed.
6 | R062000016 | Samai-Vijaypur | Morena | PWD | Road | 2006-01-27 | DDM | 123.03 | RIDF Loan upto 10 crore | Quality of works is not satisfactory. On the road falling in Sheopur dist. construction of bridge is necessary to provide connectivity to Vijaypur.
6 | R062000112 | Ubhegaon Gondra Rajana Bichhua | Chhindwara | PWD | Road | 2006-01-25 | DDM | 187.77 | RIDF Loan upto 10 crore | Project completed. PCR yet to be submitted.
6 | R062000023 | Jobat | Alirajpur | NVDA | MIP | 2005-12-21 | DDM | 7653.31 | RIDF Loan 25 crore & above | Project is likely to be completed by June 2006
6 | r062000111 | Marud Itawa | Chhindwara | PWD | Road | 2005-12-16 | DDM | 163.56 | RIDF Loan upto 10 crore | Project is completed in all respects.
6 | R062000103 | Nonghati Damehari | Anuppur | PWD | Road | 2005-12-14 | DDM | 202.56 | RIDF Loan upto 10 crore | 1. WBM completed in 23 kms. 2. BT completed in 3 kms. 3. Work may be expedited.
6 | r062000013 | Manawar-Dehri | Dhar | PWD | Road | 2005-12-09 | DDM | 186.7 | RIDF Loan upto 10 crore | Project is completed. PCR is yet to be submitted. Damages to the road observed at many places.
6 | R062000086 | Barnagar-Nagda | Ujjain | PWD | Road | 2005-12-07 | DDM | 206.22 | RIDF Loan upto 10 crore | (1) Road on either side of the CD at 21/6 is damaged due to overflow of water and needs repair. The suitability of design of the CD may be examined.
6 | r062000056 | Tirodi-Khawasa | Balaghat | PWD | Road | 2005-12-01 | DDM | 98.25 | RIDF Loan upto 10 crore | Project has already been completed. NABARD Board not displayed.
6 | R062000154 | LBMC 72km-84km-with its dist. excl Deory dist. | Narsinghpur | NVDA | MJP | 2005-11-30 | DDM | 2169.3 | RIDF Loan 10.01-24.99 crore | (1) Lining is yet to be done in certain patches between RD 72 and RD 78 km. (2) Pace of execution slow and completion of the project by March 2006 as indicated by the department may not be possible.
6 | R062000107 | Deori Distributory | Narsinghpur | NVDA | MJP | 2005-11-22 | DDM | 634.65 | RIDF Loan upto 10 crore | Progress of work is slow
6 | R062000127 | LBMC 63.42-72.00 dist.sys | Narsinghpur | NVDA | MJP | 2005-11-18 | DDM | 1713.04 | RIDF Loan 10.01-24.99 crore | Work is in progress - Likely to be completed by March 2006
6 | R062000102 | Langha Tola Patana Karpa | Anuppur | PWD | Road | 2005-11-09 | DDM | 112.76 | RIDF Loan upto 10 crore | (1) Project was completed in May 2005 (2) Damage to the road observed at KM 24/8 which need be repaired
6 | R062000153 | Parwati 22/8 | Shajapur | PWD | Bridge | 2005-10-28 | DDM | 102.19 | RIDF Loan upto 10 crore | Project completed and PCR verified. Approach road needs strengthening. NB board not displayed.
6 | R062000152 | Kalisindh 2/4 | Shajapur | PWD | Bridge | 2005-10-28 | DDM | 142.26 | RIDF Loan upto 10 crore | Project completed. PCR verified. NB board not displayed.
6 | R062000150 | Kalisindh 19/8 | Rajgarh | PWD | Bridge | 2005-10-28 | DDM | 223.23 | RIDF Loan upto 10 crore | Project completed. PCR verified. Approach road needs improvement.
6 | R062000114 | Tendukheda Gadarwara | Narsinghpur | PWD | Road | 2005-10-07 | DDM | 108.51 | RIDF Loan upto 10 crore | The progress of work is slow and notices have issued to the contractor to expedite the work immediately. The quality of work is unsatisfactory as large sections of the road have been damaged due to rains/floods and particularly near cross drainage.
6 | R062000118 | Chitrangi Garwa | Singrauli | PWD | Road | 2005-10-06 | DDM | 283.48 | RIDF Loan upto 10 crore | Progress of implementation of work is slow. The work was held up since one and a half year. Bottleneck in the implementation was due to Fund allotment/ constraint due to revision in rates for items of work.
6 | R062000119 | Deogawan Nakajhar | Sidhi | PWD | Road | 2005-10-05 | DDM | 57.18 | RIDF Loan upto 10 crore | Progress is slow. There was no record of maintenance of Quality Control registe at the site. Due to rainy season there were some damages in the road. PWD is required to get the road repaired at the earliest. NABARD board has not been displayed.
6 | R062000120 | Kukaranwa Nakjhar | Sidhi | PWD | Road | 2005-10-05 | DDM | 70.44 | RIDF Loan upto 10 crore | Progress is slow. There was no Quality Control registe at the site. Due to rainy season there were some damages in the road. NABARD board not displayed. PWD is required to get the road repaired and arrange to get the board displayed at the earliest.
6 | r062000061 | Mundalaram-Riyawan-Ranayara-Bhatkheda | Ratlam | PWD | Road | 2005-10-05 | DDM | 203.69 | RIDF Loan upto 10 crore | Project is completed. Quality of works satisfactory.
6 | R062000139 | Dhabala Mohan Khadawada | Mandsaur | PWD | Road | 2005-09-30 | DDM | 206.95 | RIDF Loan upto 10 crore | The work has been completed. One end of CD located at 3/8 km is heavily damaged and needs to be attended to urgently so to avoid accidents and further damage to CD.
6 | R062000138 | Bardia Amra Balod | Mandsaur | PWD | Road | 2005-09-30 | DDM | 476.05 | RIDF Loan upto 10 crore | The Project work has been completed. NABARD board has been displayed but the board at Baloda end is damaged. The name is required to be displayed in bold letters. As the road is 2-3 years old, the surface is badly damaged at some places.
6 | R062000128 | Chandora | Betul | WRD | MIP | 2005-08-25 | DDM | 140.31 | RIDF Loan upto 10 crore | PCR verified.
6 | R062000149 | Tannor 69/10 | Balaghat | PWD | Bridge | 2005-07-01 | DDM | 115.97 | RIDF Loan upto 10 crore | Overall progress of work is satisfactory. NABARD board was not visible and the same was advised to the authorities concerned. The Bridge division does not have a vehicle and the same may be provided for monitoring and smooth functioning.
6 | R062000100 | Gourela Manikpur | Anuppur | PWD | Road | 2005-06-30 | DDM | 179.25 | RIDF Loan upto 10 crore | Implementation was not satisfactory.. The projected was completed on 30.06.04. The PWD should send the Project Completion Report.
6 | R062000143 | Nowgaon Amiliya Sagouni | Satna | PWD | Road | 2005-03-31 | DDM | 72.6 | RIDF Loan upto 10 crore | NABARD Board not displayed. At many places road has sunk. BT has come out. The scheduled date of completion of road is alreay over. Regular monitoring system at district level by SE or EE should be introduced. About one km. road is in very bad shape.
6 | R062000146 | Kedarpur Dhanwahi | Seoni | PWD | Road | 2005-03-27 | DDM | 77.52 | RIDF Loan upto 10 crore | WBM was completed in 10 km. and BT in 4.80 km. was ongoing.
6 | R062000021 | Ghisi-Pandiya-Chhapara | Seoni | PWD | Road | 2005-03-25 | DDM | 131.71 | RIDF Loan upto 10 crore | Project was completed in July 2004. Rain cuts were seen. Kilometer stones were not fixed.
6 | R062000068 | Kapeli-Karedi | Ujjain | PWD | Road | 2005-03-22 | DDM | 49.42 | RIDF Loan upto 10 crore | Work quality extremely poor. WBM done but has come out. BT work has not commenced. Contractor has backed out from the project and has given notice under clause 14 to surrender the project. NABARD Board was not displayed.
6 | R062000066 | Delchi-Gurariya | Ujjain | PWD | Road | 2005-03-22 | DDM | 75.13 | RIDF Loan upto 10 crore | The project has been completed. NABARD Board was not displayed.
6 | R062000015 | Jeeran-Kangetti | Mandsaur | PWD | Road | 2005-03-22 | DDM | 94.06 | RIDF Loan upto 10 crore | The progress of implementation is tardy and likely to be completed by june 2005. Delay in land acquisition was major hurdle in completion of the work. NABARD Board was not displayed.
6 | R062000142 | Lhodar Jhingodar | Satna | PWD | Road | 2005-03-19 | DDM | 53.78 | RIDF Loan upto 10 crore | Project is completed. However, in some portion WBM and BT is not done
6 | R062000117 | Balpur Dhanora-Kachi Budhawara Agaria Ghogharima | Seoni | PWD | Road | 2005-03-18 | DDM | 170.05 | RIDF Loan upto 10 crore | Total 2.5 Km road not constructed and 1 CD work is to be constructed. Overall 75& work has been completed. Despite the fact that actual expenditure incurred was more than NABARD sanction, the road was incomplete.
6 | R062000145 | Ghagharimal Khamaria | Seoni | PWD | Road | 2005-03-18 | DDM | 193 | RIDF Loan upto 10 crore | Out of the sanctioned 18 km, 16 Km WBM road was completed. Balance 2.6 Km was left unattended due to inaduate funds. Quality of BT road was poor. CDs completed were 25 as against 29 sanctioned. NABARD sanction was utilised fully but road was incomplete.
6 | R062000086 | Barnagar-Nagda | Ujjain | PWD | Road | 2005-03-10 | DDM | 206.22 | RIDF Loan upto 10 crore | The quality is very poor. WBM and BT has done only on 16.5 Km. out of total sanctioned 29.6 Km.WBM done on some part of balance portion has come out.Non allocation of funds for the project was major bottleneck.NABARD Board was not displayed.
6 | R062000136 | Rudharpura Rairu | Gwalior | PWD | Road | 2005-02-19 | DDM | 18.49 | RIDF Loan upto 10 crore | work in 2.1 km towards Rudrapura and 0.3km towards Rairu completed. A number of small pits/pot-holes appear on the surface of the road. Land acquisition in the village area (0.33 km.) was the main problem. NABARD board was not displayed.
6 | R062000127 | LBMC 63.42-72.00 dist.sys | Narsinghpur | NVDA | MJP | 2005-02-19 | DDM | 1713.04 | RIDF Loan 10.01-24.99 crore | The progress is slow. Earlier tender was approved with dynamite which was not possible due to ground reality. Tender for rock cutting is finalised and work has started.
6 | R062000118 | Chitrangi Garwa | Singrauli | PWD | Road | 2005-02-16 | DDM | 283.48 | RIDF Loan upto 10 crore | The progress of implementation is very slow. No record of visits by EE/CE and also Quality Control register was maintained at site. NABARD Board is not displayed in revised format.
6 | R062000004 | Shajapur-Bijana-Chomo | Shajapur | PWD | Road | 2005-01-19 | DDM | 203.22 | RIDF Loan upto 10 crore | Time overrun, work likely to be completed by 30.06.05 as against the due date of 31.03.04. Contractor problem, single contractor executing work slowly, contract period expired on 15.03.2004, extension sought upto 31.05.05.
6 | R062000058 | Bhoura-Phophaliya | Betul | PWD | Road | 2005-01-18 | DDM | 302.58 | RIDF Loan upto 10 crore | Slow progress due to contractor's problem
6 | R062000083 | Ambah-Roli | Morena | PWD | Road | 2005-01-13 | DDM | 185.24 | RIDF Loan upto 10 crore | No progress in work after Feb. 2004. PWD has already utilised the funds. PWD has given revised estimates to construct 1 km. road from Daljeet ka pura and other works. But no sanction received so far.
6 | r062000154 | LBMC 72km-84km-with its dist. excl Deory dist. | Narsinghpur | NVDA | MJP | 2004-12-31 | DDM | 2169.3 | RIDF Loan 10.01-24.99 crore | The progress of the work appears to be satisfactory. The work is likely to be completed by 30-06-2005.
6 | R062000006 | Hathini-1/8 | Alirajpur | PWD | Bridge | 2004-12-28 | DDM | 58.73 | RIDF Loan upto 10 crore | Only pillars have been erected. NABARD Board not displayed. Maintenance arrangement should be made.
6 | R062000061 | Mundalaram-Riyawan-Ranayara-Bhatkheda | Ratlam | PWD | Road | 2004-12-17 | DDM | 203.69 | RIDF Loan upto 10 crore | Work completed. Patch work has been in about 25-30 places. Patchwork still requires in about 25-30 places. The road didnot to be as good as other nearby roads.
6 | R062000159 | Hirapur Tank | Alirajpur | WRD | MIS | 2004-12-10 | DDM | 61.1 | RIDF Loan upto 10 crore | Only 90% of the earthwork and 95% of the canal work has been completed so far. WUA not formed so far. NABARD Board not displayed. Maintenance arrangement should be made.
6 | R062000079 | Lalpur | Dindori | WRD | MIS | 2004-12-08 | DDM | 45.46 | RIDF Loan upto 10 crore | The work was completed in June2003. WUA not formed so far. Fields water linings will have to be prepared for irrigation to save the waste.
6 | R062000080 | Madrawal | Rewa | WRD | MIS | 2004-12-04 | DDM | 121.06 | RIDF Loan upto 10 crore | The progress is very slow. NABARD Board was not displayed. Stone patchng work on east side 100 ft. west side nearly 150 ft. is yet to be done.
6 | R062000112 | Ubhegaon Gondra Rajana Bichhua | Chhindwara | PWD | Road | 2004-12-01 | DDM | 187.77 | RIDF Loan upto 10 crore | Road construction was completed except 500 mtr. inside village road at Bchua end. Road width was less than 6 mtrs. at some places. No senior officer has visited the project site.
6 | R062000139 | Dhabala Mohan Khadawada | Mandsaur | PWD | Road | 2004-11-06 | DDM | 206.95 | RIDF Loan upto 10 crore | The work has been completed. CD located at 3/8 Km. was damaged.
6 | R062000140 | Shamgarh Khajuri Panth | Mandsaur | PWD | Road | 2004-11-06 | DDM | 78.33 | RIDF Loan upto 10 crore | The WBM work of entire 10 km. road was over. Black topping of 8.75 km. is done. The road has been opened to the public.
6 | R062000057 | Betul-Khandala-Barsali-Amla | Betul | PWD | Road | 2004-10-23 | DDM | 390.5 | RIDF Loan upto 10 crore | The progress of the work is very slow. Land aquisition problem. NABARD Board not displayed.
6 | R062000105 | Nagna Sub Distributory | Jabalpur | NVDA | MJP | 2004-10-19 | DDM | 663.43 | RIDF Loan upto 10 crore | Overall progress about 40%. There was delay in fixation of work agency.
6 | R062000104 | Patan Branch (9.86 - 18.74) | Jabalpur | NVDA | MJP | 2004-10-19 | DDM | 638.91 | RIDF Loan upto 10 crore | Lining work not yet started due to rainy season.
6 | R062000111 | Marud Itawa | Chhindwara | PWD | Road | 2004-10-19 | DDM | 163.56 | RIDF Loan upto 10 crore | Overall progress was satisfactory. No senior officer has visited the project.
6 | R062000114 | Tendukheda Gadarwara | Narsinghpur | PWD | Road | 2004-10-08 | DDM | 108.51 | RIDF Loan upto 10 crore | The progress of the work is very slow. Budgetary allocation is not available.NABARD Board was not displayed.
6 | R062000038 | Jamunziri Tank No1 | Dhar | WRD | MIS | 2004-10-07 | DDM | 89.32 | RIDF Loan upto 10 crore | The work is behind the schedule. Out of 3 kms. canal from RD 90 to RD 225 work is balance.
6 | R062000106 | LBC Lining RD 51 to 63.4 | Jabalpur | NVDA | MJP | 2004-10-06 | DDM | 1380.96 | RIDF Loan 10.01-24.99 crore | More than 91% of the work has been completed. The progress of the work is satisfactory. Agreement period of S N Thakur ( Agency) had expired on 30.06.2004.
6 | R062000156 | Birpur Tank | Dhar | WRD | MIS | 2004-10-06 | DDM | 15.67 | RIDF Loan upto 10 crore | The work is behind the schedule. NABARD Board not displayed. Only 4 culverts have been constructed as against estimated number of 21 culverts.
6 | R062000155 | Kawatiapura Tank | Dhar | WRD | MIS | 2004-10-06 | DDM | 14.84 | RIDF Loan upto 10 crore | The work is behind the schedule. NABARD Board not displyed. Site note visit register was not made available.
6 | R062000014 | Shobhapur-Machha-Pachalwa | Hoshangabad | PWD | Road | 2004-10-04 | DDM | 170.6 | RIDF Loan upto 10 crore | Soil work completed for 10 kms. Sub base work completed of 8 kms. CDs completed 11 numbers. Gade I & II work completed 5 kms. Tar work done on 2 kms.
6 | R062000138 | Bardia Amra Balod | Mandsaur | PWD | Road | 2004-09-22 | DDM | 476.05 | RIDF Loan upto 10 crore | The subgrade, subbase, WBM and black topping work of the entire road is completed. All 21 CDs were laid. Two junctions at 7 & 8 Kms. respectively needs improvement. LA compensation to the extent of Rs. 72 lakhs is yet to be made.
6 | R062000069 | Tondiya-1/8 | Balaghat | PWD | Bridge | 2004-09-04 | DDM | 75.55 | RIDF Loan upto 10 crore | Project already completed on 30/04/2003. NABARD Board not displayed.
6 | R062000134 | Kariyawati Bhangarh | Gwalior | PWD | Road | 2004-09-03 | DDM | 40.48 | RIDF Loan upto 10 crore | the progress is very slow.The actual length of the road is reduced from 6.5 Kms. to 5.625 Kms.No. of CD works reduced from 6 to 4.Black topping work not yet started. there is time and cost overrun.
6 | R062000149 | Tannor 69/10 | Balaghat | PWD | Bridge | 2004-09-03 | DDM | 115.97 | RIDF Loan upto 10 crore | Progress is satisfactory however due to mansoon presently work is at hault. NABARD Board was not visible.
6 | R062000008 | Nogaon-24/6 | Jhabua | PWD | Bridge | 2004-08-27 | DDM | 69.04 | RIDF Loan upto 10 crore | Maintainance arrangements should be made. NABARD Board not displayed
6 | r062000007 | Anas-10/2 | Jhabua | PWD | Bridge | 2004-08-27 | DDM | 141.41 | RIDF Loan upto 10 crore | Maintenance arrangements sahould be made. NABARD Board not displayed.
6 | R062000013 | Manawar-Dehri | Dhar | PWD | Road | 2004-08-04 | DDM | 186.7 | RIDF Loan upto 10 crore | The progress is slow. The work was held up on account of budgetary provision. NABARD Board not displyed. Overall work of the project is not upto the mark.
6 | R062000113 | Kusmania Harangaon Deepgaon | Dewas | PWD | Road | 2004-07-27 | DDM | 699.58 | RIDF Loan upto 10 crore | No progress in the work as there is no budget provision during the year 2003-04.NABARD Board not displayed.
6 | R062000128 | Chandora | Betul | WRD | MIP | 2004-07-10 | DDM | 140.31 | RIDF Loan upto 10 crore | Headworks:99%, Canal:95%. Utilisation during last crop season 03-04:2200ha. Benefits accrued:1148ha. 3 WUAs formed. Maintenance of Headwork carried out as per funds availability and that of canals through WUAs. Lining of main canal is required.
6 | R062000100 | Gourela Manikpur | Anuppur | PWD | Road | 2004-07-01 | DDM | 179.25 | RIDF Loan upto 10 crore | 1. Project completed.
6 | R062000154 | LBMC 72km-84km-with its dist. excl Deory dist. | Narsinghpur | NVDA | MJP | 2004-05-28 | DDM | 2169.3 | RIDF Loan 10.01-24.99 crore | 1) Tendering for Unit II complete 2) Contractor is not able to keep up with schedule.3) Unit II - Prel : 88.33%, LA : 100%, Masonry : 64.28%, Earthwork / Lining : 99.84% / 55.08%
6 | R062000127 | LBMC 63.42-72.00 dist.sys | Narsinghpur | NVDA | MJP | 2004-05-26 | DDM | 1713.04 | RIDF Loan 10.01-24.99 crore | 1) Tendering for Unit II complete. 2) The contractor has not yet started the work for minors. Deptt is pursuing the matter. 3) Unit II - Prel : 100%, Masonry : 20%, Earthwork : 18%
6 | R062000092 | Betul Athner | Betul | PWD | Road | 2004-05-19 | DDM | 35.96 | RIDF Loan upto 10 crore | 1) One bridge is still not complete. 2) Farmers could carry their products to market.
6 | R062000018 | Bina-Agasod-Kanjiya | Sagar | PWD | Road | 2004-03-27 | DDM | 129.31 | RIDF Loan upto 10 crore | Slow progress-from km8/6 to km13/4 BT & two CDs work not do NB board not displayed.
6 | R062000134 | Kariyawati Bhangarh | Gwalior | PWD | Road | 2004-03-25 | DDM | 40.48 | RIDF Loan upto 10 crore | Slow progress- delay in tendering process & commencement of work.No physical progress during August 02 to December 03.WBM & CD work not completed.BT not done.Time overrun- Project likely to be completed by June 04 as against March 04.
6 | R062000132 | Bandha Baijnath Dham | Gwalior | PWD | Road | 2004-03-24 | DDM | 68.14 | RIDF Loan upto 10 crore | Project completed.
6 | R062000086 | Barnagar-Nagda | Ujjain | PWD | Road | 2004-03-17 | DDM | 206.22 | RIDF Loan upto 10 crore | Slow progress-Physical progress of WBM,BT & CD works is 32%,32% &22% respectively.NB board not displayed.
6 | R062000131 | Tonk Khurd Gandrupuri Pipatasa | Dewas | PWD | Road | 2004-03-17 | DDM | 500.92 | RIDF Loan upto 10 crore | 1) Tender for Road and CD works complete. 2) Work on 840m. patch in village Sekhli pending due to LA payment. 3) Work on 2.5km stretch affected due to land compensation dispute. 4) 560 m of road, including a bridge, falling in submergence area.
6 | R062000066 | Delchi-Gurariya | Ujjain | PWD | Road | 2004-03-16 | DDM | 75.13 | RIDF Loan upto 10 crore | NB board not displayed.
6 | R062000067 | Delchi-Kapeli | Ujjain | PWD | Road | 2004-03-16 | DDM | 45.59 | RIDF Loan upto 10 crore | Poor maintainance- Road at Kapeli side damagwd at several places. NB board not displayed.
6 | R062000068 | Kapeli-Karedi | Ujjain | PWD | Road | 2004-03-16 | DDM | 49.42 | RIDF Loan upto 10 crore | Slow progress-WBM work progress is 20% .CD & BT work not done. Contractor problem.
6 | R062000100 | Gourela Manikpur | Anuppur | PWD | Road | 2004-03-12 | DDM | 179.25 | RIDF Loan upto 10 crore | Slow progress-sub base yet to be completed.BT not done. Time overrun- project likely to be completed by June 2004 as against March 2004.
6 | R062000103 | Nonghati Damehari | Anuppur | PWD | Road | 2004-03-12 | DDM | 202.56 | RIDF Loan upto 10 crore | Slow progress-overall progress is 9%. Retendering to be done due to contractor problem.
6 | R062000106 | LBC Lining RD 51 to 63.4 | Jabalpur | NVDA | MJP | 2004-03-09 | DDM | 1380.96 | RIDF Loan 10.01-24.99 crore | More than 62% of the worrk has been completed
6 | R062000080 | Madrawal | Rewa | WRD | MIS | 2004-02-26 | DDM | 121.06 | RIDF Loan upto 10 crore | Progress in implementation is slow.NB board not displayed. Further finishing in stone patching work is needed .
6 | R062000139 | Dhabala Mohan Khadawada | Mandsaur | PWD | Road | 2004-02-20 | DDM | 206.95 | RIDF Loan upto 10 crore | Funds constraints-BT work on 3.5 kms portion of the road pending for want of funds.LA payment amounting to Rs.40 lakhs to the affected farmers.
6 | R062000138 | Bardia Amra Balod | Mandsaur | PWD | Road | 2004-02-20 | DDM | 476.05 | RIDF Loan upto 10 crore | LA payment amounting to Rs.72 lakhs not payed to the affected farmers.
6 | R062000118 | Chitrangi Garwa | Singrauli | PWD | Road | 2004-02-19 | Consultant | 283.48 | RIDF Loan upto 10 crore | Slow progress- BT yet to be completed
6 | R062000020 | Dobi-Khowa-Murari | Sehore | PWD | Road | 2004-02-17 | Consultant | 33.05 | RIDF Loan upto 10 crore | culvert found in very shabby condition.G-iii renewal coated road would profile correction before BT done.The workmanship was found to be poor.
6 | R062000019 | Amon-Bansgahen-Khiriya-Kurmi | Sehore | PWD | Road | 2004-02-17 | Consultant | 41.67 | RIDF Loan upto 10 crore | There is a little progress of work .
6 | R062000121 | Nakjhar Lauyar | Sidhi | PWD | Road | 2004-02-17 | Consultant | 119.13 | RIDF Loan upto 10 crore | No deviation observed.
6 | R062000120 | Kukaranwa Nakjhar | Sidhi | PWD | Road | 2004-02-17 | Consultant | 70.44 | RIDF Loan upto 10 crore | Slow progress-CD & BT work yet to be completed
6 | R062000010 | Kunwari-3/4 | Morena | PWD | Bridge | 2004-02-16 | DDM | 77.94 | RIDF Loan upto 10 crore | The bridge construction has been completed.Approach road work not completed .
6 | R062000119 | Deogawan Nakajhar | Sidhi | PWD | Road | 2004-02-16 | Consultant | 57.18 | RIDF Loan upto 10 crore | Project completed.Records not made available at site for inspection.
6 | R062000010 | Kunwari-3/4 | Morena | PWD | Bridge | 2004-02-16 | DDM | 77.94 | RIDF Loan upto 10 crore | The bridge construction work has been completed. NABARD Board has not displayed.
6 | R062000150 | Kalisindh 19/8 | Rajgarh | PWD | Bridge | 2004-02-14 | Consultant | 223.23 | RIDF Loan upto 10 crore | BT yet to be done on approach road.Records not made available at site for inspection.
6 | R062000131 | Tonk Khurd Gandrupuri Pipatasa | Dewas | PWD | Road | 2004-02-14 | DDM | 500.92 | RIDF Loan upto 10 crore | 2-1/2 km alignment of road project is coming in submergence of the irrigation project PWD should sort out the issue with WRD. Slow progress- overall progress is 57%. NB board not displayed.
6 | R062000028 | Parsora | Raisen | WRD | MIS | 2004-02-13 | Consultant | 95.86 | RIDF Loan upto 10 crore | the work is in progress.
6 | R062000013 | Manawar-Dehri | Dhar | PWD | Road | 2004-02-13 | DDM | 186.7 | RIDF Loan upto 10 crore | LA problem- no work done at 6/8 km & 6/10 km due to LA of 18 cases(1.792 ha).NB board not put installed.
6 | R062000125 | Br. on Padariya Rd-km 23/6 | Raisen | PWD | Bridge | 2004-02-12 | Consultant | 61.59 | RIDF Loan upto 10 crore | The work is completed .Only protection work remains.
6 | R062000124 | Br. on Khamaria Rd-km 20/6 | Raisen | PWD | Bridge | 2004-02-12 | Consultant | 53.52 | RIDF Loan upto 10 crore | The work is completed .Only protection work remains.
6 | R062000126 | Br. on Salaiya Rd-km 26/4 | Raisen | PWD | Bridge | 2004-02-12 | Consultant | 26.35 | RIDF Loan upto 10 crore | The work is completed .Only protection work remains.
6 | R062000069 | Tondiya-1/8 | Balaghat | PWD | Bridge | 2004-02-11 | Consultant | 75.55 | RIDF Loan upto 10 crore | the work has been completed.
6 | R062000122 | Br. on Kharpadia Rd-km 6/8 | Balaghat | PWD | Bridge | 2004-02-11 | Consultant | 67.5 | RIDF Loan upto 10 crore | Prima facei no deficiency appeared.
6 | R062000156 | Birpur Tank | Dhar | WRD | MIS | 2004-02-11 | DDM | 15.67 | RIDF Loan upto 10 crore | Canal work started .Land acquisition is over.NB board not displayed.
6 | R062000155 | Kawatiapura Tank | Dhar | WRD | MIS | 2004-02-11 | DDM | 14.84 | RIDF Loan upto 10 crore | NB board as per new guidelines not installed .WUA not formed so far.
6 | R062000108 | Shahpura Distributory | Jabalpur | NVDA | MJP | 2004-02-11 | DDM | 1163.34 | RIDF Loan 10.01-24.99 crore | Time overrun-project likely to be completed by June 04 as against March 04. Slow progress-Physical progress of masonary & earthwork is 8% & 43% respectively.Delay in LA process.
6 | R062000149 | Tannor 69/10 | Balaghat | PWD | Bridge | 2004-02-10 | Consultant | 115.97 | RIDF Loan upto 10 crore | The work is under execution ,the foundation and piers have been constructed.One side abetment is also completed.
6 | R062000098 | Bhilkheri Kunwar Kothari Dhabla | Rajgarh | PWD | Road | 2004-02-09 | Consultant | 106.23 | RIDF Loan upto 10 crore | Time overrun- project likely to be completed by June 04 as against March 04.Poor quality of work-Bern at many places not as per specification & no seal coat applied in BT covered road .
6 | R062000083 | Ambah-Roli | Morena | PWD | Road | 2004-02-06 | DDM | 185.24 | RIDF Loan upto 10 crore | At present the construction work has stopped due to cost overrun. No drainage facility so water will overrun on the road.
6 | R062000083 | Ambah-Roli | Morena | PWD | Road | 2004-02-06 | DDM | 185.24 | RIDF Loan upto 10 crore | Word delayed due to termination of contractor and cost overrun. No provision for CDs when the road is passing through villages. Undulations observed, no provision for surface dressing. The road construction work should stop at Daljeet ka pura village.
6 | r062000057 | Betul-Khandala-Barsali-Amla | Betul | PWD | Road | 2004-01-30 | DDM | 390.5 | RIDF Loan upto 10 crore | Slow progress, physical progress of sub-grade, sub-base, WBM & CD is 81%, 74%,9% & 91% respectively. BT not done. Contractor not paying full attention to the work.
6 | r062000014 | Shobhapur-Machha-Pachalwa | Hoshangabad | PWD | Road | 2004-01-28 | DDM | 170.6 | RIDF Loan upto 10 crore | Slow progress- physical progress of WBM & CD works is 25% & 90% respectively.Overall progress is 44%.
6 | r062000143 | Nowgaon Amiliya Sagouni | Satna | PWD | Road | 2004-01-21 | DDM | 72.6 | RIDF Loan upto 10 crore | Slow progress, WBM and BT yet to be completed, out of 12CD 3CD yet to be completed, technical problems - necessary measures not taken by department as 2-3 KM of road in low lying area, NB Biard not displayed.
6 | r062000015 | Jeeran-Kangetti | Mandsaur | PWD | Road | 2004-01-21 | DDM | 94.06 | RIDF Loan upto 10 crore | Funds constraints , contractor hasn't completed the work due to non-receipt of payment.
6 | R062000113 | Kusmania Harangaon Deepgaon | Dewas | PWD | Road | 2004-01-15 | DDM | 699.58 | RIDF Loan upto 10 crore | Slow progress-overall progress of the project is 27% . No budgetary provision during the year 2003-04. Due to fund shortage LA process is slow.
6 | r062000105 | Nagna Sub Distributory | Jabalpur | NVDA | MJP | 2004-01-09 | DDM | 663.43 | RIDF Loan upto 10 crore | Time overrun - project likely to be completed by October 04 as against March 04. Tendering problem- delay in fixation of work agency Slow progress- mesonary work not started,earth work done 13.5%.
6 | r062000104 | Patan Branch (9.86 - 18.74) | Jabalpur | NVDA | MJP | 2004-01-08 | DDM | 638.91 | RIDF Loan upto 10 crore | Time overrun- project likely to be completed by October 04 as against by March 04.Tendering problem- delay in fixation of work agency.Physical progress of masonary & earth work is Nil & 11% respectively.
6 | R062000130 | Aghera Dhabala Khalsa | Dewas | PWD | Road | 2004-01-08 | DDM | 209.18 | RIDF Loan upto 10 crore | LA problem between 11/8 to 13/8 kms. Pot holes observed at 6/0km,8/0km & 8/2km.Slow progress- overall progress is 71%.
6 | r062000140 | Shamgarh Khajuri Panth | Mandsaur | PWD | Road | 2004-01-07 | DDM | 78.33 | RIDF Loan upto 10 crore | Slowv progress - BT yet to be completed, funds constraints - contractor stopped the work.
6 | R062000158 | Chandwariya Tank | Dhar | WRD | MIS | 2004-01-06 | DDM | 25.82 | RIDF Loan upto 10 crore | Only drain is made .Proper slope was not made .Earth compection not done properly.Construction is not upto the mark.
6 | r062000154 | LBMC 72km-84km-with its dist. excl Deory dist. | Narsinghpur | NVDA | MJP | 2003-12-29 | DDM | 2169.3 | RIDF Loan 10.01-24.99 crore | Progress of mesonry, earthwork and lining is 62.5%, 99% and 41% respectively, time over-run and Contractor problem.Contractor is not able to maintain time schedule due to which project is likely to be completed in December'04 as against March'04.
6 | r062000127 | LBMC 63.42-72.00 dist.sys | Narsinghpur | NVDA | MJP | 2003-12-29 | DDM | 1713.04 | RIDF Loan 10.01-24.99 crore | Contractor problem - contractor not started the work of minor so far time over-run - project is likely to be completed by December'04 as against March'04.
6 | R062000065 | Madumar-Astone | Tikamgarh | PWD | Road | 2003-12-09 | RO Official | 65.99 | RIDF Loan upto 10 crore | BT to be done at CDs, some cuts were ovserbved at road corners at 6/4,6/6,6/8. At 6/10 KMs irrigation canal has covered the road length about 5 to 6 meteres, LA problem at 12/2 to 12/6 Kms NB board not displayed at Astone village site.
6 | R062000148 | Prithavipur Simra | Tikamgarh | PWD | Road | 2003-12-09 | RO Official | 30.13 | RIDF Loan upto 10 crore | BT to be done at 3/10 CD & 1/6-1/8KMs. LA problem at 1/6-1/8 KMs aat 4/6KM. Irigation canal had cut the road site at two places at 8/2 about 30feet BT to be done. Nabard board not displayed.
6 | R062000068 | Kapeli-Karedi | Ujjain | PWD | Road | 2003-12-06 | DDM | 49.42 | RIDF Loan upto 10 crore | 1. Slow progress. 2. Tendering problem, re-tendering process should be done fast, contractor problem. 3. NB board not displayed.
6 | R062000103 | Nonghati Damehari | Anuppur | PWD | Road | 2003-11-30 | DDM | 202.56 | RIDF Loan upto 10 crore | Tendering completed. Work not started.
6 | r062000023 | Jobat | Alirajpur | NVDA | MIP | 2003-11-25 | DDM | 7653.31 | RIDF Loan 25 crore & above | Slow progress, time overrun, project to be completed by December'04 as against March'04.
6 | R062000091 | Baretha Ghoradongari Ranipur | Betul | PWD | Road | 2003-11-17 | DDM | 41.11 | RIDF Loan upto 10 crore | 1. BT to be done at approach road of minor bridges.
6 | R062000085 | Nagda-Ghinoda | Ujjain | PWD | Road | 2003-11-15 | DDM | 150.09 | RIDF Loan upto 10 crore | The project has been completed .Minor repair works are being undertaken by the contractor.
6 | R062000135 | Purani Jail Sanichara | Gwalior | PWD | Road | 2003-11-11 | RO Official | 24.56 | RIDF Loan upto 10 crore | Slow progress.
6 | R062000106 | LBC Lining RD 51 to 63.4 | Jabalpur | NVDA | MJP | 2003-11-05 | DDM | 1380.96 | RIDF Loan 10.01-24.99 crore | 1. Delay in tendering. 2. Slow progress. Progress of Lining is only 34 percent.
6 | R062000151 | Wainganga 14/10 | Seoni | PWD | Bridge | 2003-10-17 | RO Official | 88.94 | RIDF Loan upto 10 crore | Project is completed. NB Board not displyed.
6 | R062000021 | Ghisi-Pandiya-Chhapara | Seoni | PWD | Road | 2003-10-16 | RO Official | 131.71 | RIDF Loan upto 10 crore | Work Completed
6 | R062000061 | Mundalaram-Riyawan-Ranayara-Bhatkheda | Ratlam | PWD | Road | 2003-10-15 | DDM | 203.69 | RIDF Loan upto 10 crore | Slow progress due to non availability of fund
6 | R062000005 | Khamkheda-Bamankheda-Bans | Vidisha | PWD | Road | 2003-09-03 | DDM | 58.34 | RIDF Loan upto 10 crore | Span of 1 Km road from 4 to 5 is badly damaged.
6 | R062000061 | Mundalaram-Riyawan-Ranayara-Bhatkheda | Ratlam | PWD | Road | 2003-07-25 | DDM | 203.69 | RIDF Loan upto 10 crore | NABARD board not displayed.
6 | R062000154 | LBMC 72km-84km-with its dist. excl Deory dist. | Narsinghpur | NVDA | MJP | 2003-06-25 | DDM | 2169.3 | RIDF Loan 10.01-24.99 crore | Time overrun - likely date of completion is 31-12-04 instead of 31-3-04.
6 | R062000017 | Sihoniya-Porsa | Morena | PWD | Road | 2003-06-25 | DDM | 53.97 | RIDF Loan upto 10 crore | Black topping work is not completed.Road work is not good.
6 | R062000114 | Tendukheda Gadarwara | Narsinghpur | PWD | Road | 2003-06-19 | DDM | 108.51 | RIDF Loan upto 10 crore | Progress of implementation is slow as WBM achievement was 40% on 7-6-02 and on 19-6-03, it was only 45%.NB board not displayed.
6 | R062000094 | Rasara Sarod | Jabalpur | PWD | Road | 2003-05-13 | DDM | 64.47 | RIDF Loan upto 10 crore | Tendering problem-agreement with the agency expired on 31-3-03 which has not been extended till anticipatory date of completion, poor maintenance-small patch of BT damaged at 7/2 km which may be repaired.
6 | R062000008 | Nogaon-24/6 | Jhabua | PWD | Bridge | 2003-04-30 | DDM | 69.04 | RIDF Loan upto 10 crore | No arrangement for maintenance. NB board not displayed.
6 | R062000007 | Anas-10/2 | Jhabua | PWD | Bridge | 2003-04-25 | DDM | 141.41 | RIDF Loan upto 10 crore | NB board not displayed. Arrangement for maintenance of project not made.
6 | R062000033 | Baledi | Dhar | WRD | MIS | 2003-03-31 | DDM | 27.53 | RIDF Loan upto 10 crore | NB board not displayed in proper format.
6 | R062000106 | LBC Lining RD 51 to 63.4 | Jabalpur | NVDA | MJP | 2003-03-31 | DDM | 1380.96 | RIDF Loan 10.01-24.99 crore | Time overrun, likely date of completion of project is June 2004 as against stipulated March 2004. Slow progress. The overall progress of lining is just 19%. Delay in tendering.
6 | R062000108 | Shahpura Distributory | Jabalpur | NVDA | MJP | 2003-03-29 | DDM | 1163.34 | RIDF Loan 10.01-24.99 crore | Slow progress. The overall progress of work is 9%. Delay in tendering. Time overrun - likely date of completion of the project is June 2004 as against stipulated completion date March 2004. change in technical design without intimating to NB.
6 | R062000147 | Niwar Tigeli Gidkhiri Pipara | Tikamgarh | PWD | Road | 2003-03-11 | RO Official | 28.35 | RIDF Loan upto 10 crore | Change in technical design (due to non-availability of land papers of Teela village road has been diverted inside village (1/10-150m & 2/2-2/4 km = 400 m as per proposal of Gram Panchayat,Teela,Chief Engineer,PWD,Sagar zone permitted above diversion.
6 | R062000107 | Deori Distributory | Narsinghpur | NVDA | MJP | 2003-02-19 | DDM | 634.65 | RIDF Loan upto 10 crore | Land of 10.564 ha not acquired for 7 minors, delay in tendering , Time overrun (project is likely to be completed by September 2004 as against the completion date March 2004). NB board not displayed in proper format.
6 | R062000010 | Kunwari-3/4 | Morena | PWD | Bridge | 2003-02-08 | DDM | 77.94 | RIDF Loan upto 10 crore | Funds constraint, the progress of approach road is tardy, contractor is finding it difficult to execute the work due to funds shortage, the EE informed that there is ban on release of funds as per state govt. instructions, NB board not displayed.
6 | R062000016 | Samai-Vijaypur | Morena | PWD | Road | 2003-02-08 | DDM | 123.03 | RIDF Loan upto 10 crore | Time overrun, slow progress of work, BT done for 3 km only, since more than one year has lapsed after completing the WBM work, the same has come out at many places, contractor problem (not ready to do the blacktopping work).
6 | R062000130 | Aghera Dhabala Khalsa | Dewas | PWD | Road | 2003-01-13 | DDM | 209.18 | RIDF Loan upto 10 crore | Land acquisition problem (Land acquisition problem between 11/8 to 13/8 km). Slow progress (physical progress was only 51%), unsatisfactory quality of work (finished road surface is uneven at several places). NB board not displayed in proper format.
6 | R062000023 | Jobat | Alirajpur | NVDA | MIP | 2003-01-02 | OIC+RO Officials | 7653.31 | RIDF Loan 25 crore & above | Time overrun (likely date of completion June 2004), agencies for various work namely construction of non-overflow masonry dam (block No. 3 to 13), construction of block no. 1 of non-overflow dam, fixation of instru in block no. 2 & 1.
6 | R062000061 | Mundalaram-Riyawan-Ranayara-Bhatkheda | Ratlam | PWD | Road | 2002-12-28 | DDM | 203.69 | RIDF Loan upto 10 crore | Satisfactory.
6 | R062000057 | Betul-Khandala-Barsali-Amla | Betul | PWD | Road | 2002-11-30 | DDM | 390.5 | RIDF Loan upto 10 crore | Slow progress ofwork due to LA and laxy contractor
6 | R062000008 | Nogaon-24/6 | Jhabua | PWD | Bridge | 2002-11-29 | DDM | 69.04 | RIDF Loan upto 10 crore | NB board not displayed.
6 | R062000094 | Rasara Sarod | Jabalpur | PWD | Road | 2002-11-29 | DDM | 64.47 | RIDF Loan upto 10 crore | Old CDs at Km 3/10 & 2/10 have cracks. Agreement with the agency may be extended till anticipated date of completion. QC register not maintained at site. Monitoring being not done properly. The road may be extended upto Belkhedu for full connectivity.
6 | R062000007 | Anas-10/2 | Jhabua | PWD | Bridge | 2002-11-28 | DDM | 141.41 | RIDF Loan upto 10 crore | NB board not displayed.
6 | R062000018 | Bina-Agasod-Kanjiya | Sagar | PWD | Road | 2002-11-27 | DDM | 129.31 | RIDF Loan upto 10 crore | NB board not displayed. Toe shoulders need to be provided. Contractor insisiting on black topping the road. Cost overrun likely.
6 | R062000085 | Nagda-Ghinoda | Ujjain | PWD | Road | 2002-11-15 | DDM | 150.09 | RIDF Loan upto 10 crore | Small potholes at several places have come up.
6 | R062000080 | Madrawal | Rewa | WRD | MIS | 2002-10-30 | DDM | 121.06 | RIDF Loan upto 10 crore | Delay in Land Acquisition, Monitoring by Dept. not satisfactory, NB board not displayed.
6 | R062000100 | Gourela Manikpur | Anuppur | PWD | Road | 2002-10-17 | DDM | 179.25 | RIDF Loan upto 10 crore | No proper monitoring and supervision at site. Required quantity of material for construction as per manual is not ensured. NB board not displayed. Slow progress.
6 | R062000101 | Jaithri Seoni Semerwar | Anuppur | PWD | Road | 2002-10-17 | DDM | 132.16 | RIDF Loan upto 10 crore | Slow progress. NB board not displayed.
6 | R062000102 | Langha Tola Patana Karpa | Anuppur | PWD | Road | 2002-10-05 | DDM | 112.76 | RIDF Loan upto 10 crore | Slow progress.
6 | R062000143 | Nowgaon Amiliya Sagouni | Satna | PWD | Road | 2002-08-22 | DDM | 72.6 | RIDF Loan upto 10 crore | Delay in tendering, likely cost overrun (estimate does not provide for required earthwork for emabankment in low lying stretches for a length of about 2-3km)
6 | R062000083 | Ambah-Roli | Morena | PWD | Road | 2002-07-17 | DDM | 185.24 | RIDF Loan upto 10 crore | Slow progress(tender rejected), In village portion, water is flowing over the road, In some villages, pucca houses have been constructed on the road, NABARD board not displayed.
6 | R062000095 | Bamhni Dhenko | Mandla | PWD | Road | 2002-07-13 | DDM | 39.7 | RIDF Loan upto 10 crore | Completed.
6 | R062000004 | Shajapur-Bijana-Chomo | Shajapur | PWD | Road | 2002-07-04 | RO Official | 203.22 | RIDF Loan upto 10 crore | Likely cost overrun (due to LA, inclusion of Gr II WBM in Km 7 to 14), NB board not displayed, Others (In Shajapur Bijana road section, work has not been executed in Km 7 to 14 and the same may be taken up to complete the project in time)
6 | R062000062 | Bhooriya-Khajuria-Fard-Berchhadatar | Shajapur | PWD | Road | 2002-07-03 | RO Official | 182.21 | RIDF Loan upto 10 crore | LA problem (LA process to be expedited), NB board not displayed
6 | R062000025 | Kubrakhedi | Hoshangabad | WRD | MIS | 2002-06-21 | DDM | 27.2 | RIDF Loan upto 10 crore | NB board not displayed, Canal work to be completed
6 | R062000034 | Bildaj | Dhar | WRD | MIS | 2002-06-14 | DDM | 28.15 | RIDF Loan upto 10 crore | Pitching approximately 10 ft at left side appears to be inferior. Progress of work is not satisfactory.
6 | R062000035 | Chhotibildari | Dhar | WRD | MIS | 2002-06-14 | DDM | 30.4 | RIDF Loan upto 10 crore | Work pertaining to canal excavation not started.
6 | R062000037 | Jhamli Tank No2 | Dhar | WRD | MIS | 2002-06-14 | DDM | 20.43 | RIDF Loan upto 10 crore | Contractor is not taking adequate interest in completion of work.
6 | R062000114 | Tendukheda Gadarwara | Narsinghpur | PWD | Road | 2002-06-07 | DDM | 108.51 | RIDF Loan upto 10 crore | NB board not displayed. Slow progress (only 25% of work is done since it was sanctioned in 2000).
6 | R062000084 | Sukhakheri-Barha | Narsinghpur | PWD | Road | 2002-06-06 | DDM | 84.44 | RIDF Loan upto 10 crore | Likely cost overrun (due to design changes). NB board not displayed.
6 | R062000093 | Batakakhapa Ozaldhana | Chhindwara | PWD | Road | 2002-06-04 | DDM | 99.48 | RIDF Loan upto 10 crore | NB board not displayed
6 | R062000116 | Saijawata Bangrod Jadawasa | Ratlam | PWD | Road | 2002-05-30 | DDM | 65.09 | RIDF Loan upto 10 crore | In progress.
6 | R062000061 | Mundalaram-Riyawan-Ranayara-Bhatkheda | Ratlam | PWD | Road | 2002-05-29 | DDM | 203.69 | RIDF Loan upto 10 crore | In progress
6 | R062000026 | Gadigaltar | Khargone | WRD | MIS | 2002-05-24 | DDM | 135.62 | RIDF Loan upto 10 crore | Spill work to be completed
6 | R062000038 | Jamunziri Tank No1 | Dhar | WRD | MIS | 2002-05-16 | DDM | 89.32 | RIDF Loan upto 10 crore | After 4-4-02 EE not visited.
6 | R062000036 | Dedali | Dhar | WRD | MIS | 2002-05-15 | DDM | 39.79 | RIDF Loan upto 10 crore | Detail report not given.
6 | R062000100 | Gourela Manikpur | Anuppur | PWD | Road | 2002-05-15 | DDM | 179.25 | RIDF Loan upto 10 crore | Slow progress (delay in tendering), NB board not displayed.
6 | R062000101 | Jaithri Seoni Semerwar | Anuppur | PWD | Road | 2002-05-15 | DDM | 132.16 | RIDF Loan upto 10 crore | Slow progress (delay in tendering), NB board not displayed.
6 | R062000133 | Jaurasi Antri | Gwalior | PWD | Road | 2002-05-15 | DDM | 23.12 | RIDF Loan upto 10 crore | Contractor problem (work order cancelled once and extension givn to new contractor).
6 | R062000132 | Bandha Baijnath Dham | Gwalior | PWD | Road | 2002-05-14 | DDM | 68.14 | RIDF Loan upto 10 crore | Slow progress (flank work and BT/WBM in balance portion to be done).
6 | R062000135 | Purani Jail Sanichara | Gwalior | PWD | Road | 2002-05-13 | DDM | 24.56 | RIDF Loan upto 10 crore | Slow progress (flank work for entire reach is not done still. Project was to be completed by Oct 01).
6 | R062000136 | Rudharpura Rairu | Gwalior | PWD | Road | 2002-05-13 | DDM | 18.49 | RIDF Loan upto 10 crore | Slow progress (only 75% work done although it was to be completed by Mar 02). Contractor problem (work order cancelled and fresh tenders settled)
6 | R062000005 | Khamkheda-Bamankheda-Bans | Vidisha | PWD | Road | 2002-05-08 | DDM | 58.34 | RIDF Loan upto 10 crore | Others (inadequate attention from dept. staff).
6 | R062000006 | Hathini-1/8 | Alirajpur | PWD | Bridge | 2002-04-30 | DDM | 58.73 | RIDF Loan upto 10 crore | NB board to be displayed. Slow progress (work started one year after sanction).
6 | R062000111 | Marud Itawa | Chhindwara | PWD | Road | 2002-04-30 | DDM | 163.56 | RIDF Loan upto 10 crore | NB board to be displayed.
6 | R062000082 | Sendhwa-Niwal-Khetai | Badwani | PWD | Road | 2002-04-29 | RO Official+C | 502.63 | RIDF Loan upto 10 crore | Report as per Annexure.
6 | R062000094 | Rasara Sarod | Jabalpur | PWD | Road | 2002-04-29 | DDM | 64.47 | RIDF Loan upto 10 crore | Material - non leasing of quarry resultng in higher leads for metal. NB boad not displayed. Road level is lower than fields in Km 3. CD works at Km 3/10 & 2/10 have cracks. QC register not maintained. Records of visits by senior officers not maintained.
6 | R062000056 | Tirodi-Khawasa | Balaghat | PWD | Road | 2002-04-27 | RO Official | 98.25 | RIDF Loan upto 10 crore | Stretch falling in Seoni division also should be brought to BT standards under A/R as envisaged by PWD for full connectivity.
6 | R062000109 | Kukarra Boda | Balaghat | PWD | Road | 2002-04-27 | RO Official | 32.92 | RIDF Loan upto 10 crore | Watering and compaction of shoulders to be done. Part of the road falling in Mandla division also to be developed to BT standards for proper connectivity.
6 | R062000008 | Nogaon-24/6 | Jhabua | PWD | Bridge | 2002-04-26 | DDM | 69.04 | RIDF Loan upto 10 crore | NB board to be displayed. Slow progress (work started one year after sanction).
6 | R062000007 | Anas-10/2 | Jhabua | PWD | Bridge | 2002-04-19 | DDM | 141.41 | RIDF Loan upto 10 crore | NB board to be displayed
6 | R062000159 | Hirapur Tank | Alirajpur | WRD | MIS | 2002-04-17 | DDM | 61.1 | RIDF Loan upto 10 crore | Slow progress (canal work yet to be started). NB board to be displayed
6 | R062000089 | Umar 19/4 | Narsinghpur | PWD | Bridge | 2002-04-12 | DDM | 43.66 | RIDF Loan upto 10 crore | Approach road black topping is delayed.
6 | R062000092 | Betul Athner | Betul | PWD | Road | 2002-04-09 | DDM | 35.96 | RIDF Loan upto 10 crore | NB board not displayed.
6 | R062000134 | Kariyawati Bhangarh | Gwalior | PWD | Road | 2002-03-28 | DDM | 40.48 | RIDF Loan upto 10 crore | Delay in tendering (delay at sub-committee of Zilla Sarkar).
6 | R062000017 | Sihoniya-Porsa | Morena | PWD | Road | 2002-03-27 | DDM | 53.97 | RIDF Loan upto 10 crore | Report awaited
6 | R062000017 | Sihoniya-Porsa | Morena | PWD | Road | 2002-03-27 | DDM | 53.97 | RIDF Loan upto 10 crore | NB board to be displayed, Poor quality (road width is less at many places, BT edge lacks protection)
6 | R062000100 | Gourela Manikpur | Anuppur | PWD | Road | 2002-03-26 | DDM | 179.25 | RIDF Loan upto 10 crore | Metal collection in progrss. NB board not displayed.
6 | R062000101 | Jaithri Seoni Semerwar | Anuppur | PWD | Road | 2002-03-26 | DDM | 132.16 | RIDF Loan upto 10 crore | Metal collection in progrss. NB board not displayed.
6 | R062000118 | Chitrangi Garwa | Singrauli | PWD | Road | 2002-03-21 | RO Official | 283.48 | RIDF Loan upto 10 crore | Report as per Annexure.
6 | R062000025 | Kubrakhedi | Hoshangabad | WRD | MIS | 2002-03-14 | DDM | 27.2 | RIDF Loan upto 10 crore | Work not started yet, NABARD board not displayed.
6 | R062000112 | Ubhegaon Gondra Rajana Bichhua | Chhindwara | PWD | Road | 2002-01-24 | DDM | 187.77 | RIDF Loan upto 10 crore | NB board not displayed.
6 | R062000129 | Sukri Umreth | Chhindwara | PWD | Road | 2002-01-23 | DDM | 53.34 | RIDF Loan upto 10 crore | QC tests not done. Work commenced one month after issue of work order. NB board not displayed.
6 | R062000114 | Tendukheda Gadarwara | Narsinghpur | PWD | Road | 2002-01-18 | DDM | 108.51 | RIDF Loan upto 10 crore | NB board not displayed, contractor problem (started the work late)
6 | R062000091 | Baretha Ghoradongari Ranipur | Betul | PWD | Road | 2002-01-15 | DDM | 41.11 | RIDF Loan upto 10 crore | Work is yet to commence. Camber correction required.
6 | R062000066 | Delchi-Gurariya | Ujjain | PWD | Road | 2002-01-11 | DDM | 75.13 | RIDF Loan upto 10 crore | Slow progress (progress is only 29%, the scheduled date of completion is 3/2002).
6 | R062000067 | Delchi-Kapeli | Ujjain | PWD | Road | 2002-01-11 | DDM | 45.59 | RIDF Loan upto 10 crore | Slow progress (delay in fixing agency).
6 | R062000068 | Kapeli-Karedi | Ujjain | PWD | Road | 2002-01-11 | DDM | 49.42 | RIDF Loan upto 10 crore | Slow progress (delay in fixing agency, only material collection has been done so far)
6 | R062000014 | Shobhapur-Machha-Pachalwa | Hoshangabad | PWD | Road | 2002-01-09 | DDM | 170.6 | RIDF Loan upto 10 crore | Slow progress (work not started), delay in tendering (tender was to be opened on 8.6.01, but process is still incomplete)
6 | R062000016 | Samai-Vijaypur | Morena | PWD | Road | 2002-01-09 | DDM | 123.03 | RIDF Loan upto 10 crore | NB board not displayed, WBM undulating
6 | R062000079 | Lalpur | Dindori | WRD | MIS | 2002-01-09 | RO Official | 45.46 | RIDF Loan upto 10 crore | Being executed under ITDP and proposed to be withdrawn.
6 | R062000084 | Sukhakheri-Barha | Narsinghpur | PWD | Road | 2002-01-03 | DDM | 84.44 | RIDF Loan upto 10 crore | Slow progress (only sub-grade and CD works have been partly executed so far. Balance items not commenced as yet).
6 | R062000096 | Maharajpur Ghaga | Mandla | PWD | Road | 2002-01-02 | DDM | 93.44 | RIDF Loan upto 10 crore | About 2-3 km work stoppped due to objection by Forest Dept. - to be resolved.
6 | R062000135 | Purani Jail Sanichara | Gwalior | PWD | Road | 2001-12-31 | DDM | 24.56 | RIDF Loan upto 10 crore | NB board not displayed. Slow progress (not completed within scheduled date of 3-10-01).
6 | R062000134 | Kariyawati Bhangarh | Gwalior | PWD | Road | 2001-12-14 | DDM | 40.48 | RIDF Loan upto 10 crore | Slow progress (delay in grounding due to delay in approval by Sub-committee).
6 | R062000102 | Langha Tola Patana Karpa | Anuppur | PWD | Road | 2001-12-13 | DDM | 112.76 | RIDF Loan upto 10 crore | Slow progress (late tendering).
6 | R062000111 | Marud Itawa | Chhindwara | PWD | Road | 2001-11-30 | DDM | 163.56 | RIDF Loan upto 10 crore | NB board not displayed
6 | R062000144 | Tikuririmari Hariharpur | Satna | PWD | Road | 2001-11-22 | DDM | 28.65 | RIDF Loan upto 10 crore | Work not yet commenced, Inadequate monitoring by the department (progress of implementation not being reviewed regulary by EE/SE/CE), Observation of technical nature (1. a few parts of original road which were shown as complete.
6 | R062000142 | Lhodar Jhingodar | Satna | PWD | Road | 2001-11-21 | DDM | 53.78 | RIDF Loan upto 10 crore | Work not yet commenced, Inadequate monitoring by the department (progress of implementation not being reviewed regulary by EE/SE/CE), NB board not displayed, Observation of technical nature (1. a few parts of original road which were shown as complete.
6 | R062000005 | Khamkheda-Bamankheda-Bans | Vidisha | PWD | Road | 2001-11-08 | DDM | 58.34 | RIDF Loan upto 10 crore | Progress of implementation satisfactory (only two items of work viz. 16.7% WBM and 72.2% BT remained incomplete)
6 | R062000003 | Agra-Newari-Atawada | Indore | PWD | Road | 2001-11-07 | DDM | 66.92 | RIDF Loan upto 10 crore | Slow progress of work, NB board not displayed
6 | R062000130 | Aghera Dhabala Khalsa | Dewas | PWD | Road | 2001-11-06 | DDM+C | 209.18 | RIDF Loan upto 10 crore | Slow progress of work (work not yet commenced), Time overrun likely (project likely to be completed only by March 04 as against the completion due date of 31/3/03), Delay in tendering (although the project was sanctioned in 2000-01.
6 | R062000131 | Tonk Khurd Gandrupuri Pipatasa | Dewas | PWD | Road | 2001-11-06 | DDM+C | 500.92 | RIDF Loan upto 10 crore | No physical work commenced at site, Delay in tendering (although the project was sanctioned during 2000-01, the tender was called and approved only recently), Any delay in tendering defeats the very purpose of project management.
6 | R062000113 | Kusmania Harangaon Deepgaon | Dewas | PWD | Road | 2001-11-05 | DDM+C | 699.58 | RIDF Loan upto 10 crore | No physical work commenced at site, Delay in tendering (although the project was sanctioned during 2000-01, the tender was called and approved only recently), Any delay in tendering defeats the very purpose of project management.
6 | R062000082 | Sendhwa-Niwal-Khetai | Badwani | PWD | Road | 2001-10-31 | RO Official+C | 502.63 | RIDF Loan upto 10 crore | Progress of work on road part was by and large as per the time schedule, In case of CDs however, the work was in progress for 24 CDs only out of 62 which needed to be accelerated, BT surface for the road length from Km 19/2 to 20/4 in Sendhwa city.
6 | R062000023 | Jobat | Alirajpur | NVDA | MIP | 2001-10-30 | DDM+C | 7653.31 | RIDF Loan 25 crore & above | Slow progress, project likely to be completed by June 04 as against the completion due date of 31/3/03, Delay in land acquisition, rehabilitation work, tendering, General (project staff is often engaged in other works).
6 | R062000110 | Balwadi Deoli Dhawli | Badwani | PWD | Road | 2001-10-30 | RO Official+C | 155.33 | RIDF Loan upto 10 crore | Report received
6 | R062000026 | Gadigaltar | Khargone | WRD | MIS | 2001-10-29 | DDM | 135.62 | RIDF Loan upto 10 crore | Work in progress
6 | R062000094 | Rasara Sarod | Jabalpur | PWD | Road | 2001-10-29 | DDM | 64.47 | RIDF Loan upto 10 crore | Work not yet commenced (although tendering for road and CDs has been over and the agencies are finalised), NB board not displayed.
6 | R062000089 | Umar 19/4 | Narsinghpur | PWD | Bridge | 2001-10-23 | DDM+C | 43.66 | RIDF Loan upto 10 crore | Work on fixing of railing should be taken up, Joints at plates in concrete need to be finished smooth, Action point suggested (work on approach roads should be taken up earlier), NB board displayed earlier needs to be refixed
6 | R062000093 | Batakakhapa Ozaldhana | Chhindwara | PWD | Road | 2001-10-23 | DDM | 99.48 | RIDF Loan upto 10 crore | Slow progress of work (work regarding sub-base, WBM, BT not yet commenced), Contractor problem (inadequate capacity, slow execution of work), Delay in tendering (tendering for WBM and BT was not initiated), Inadequate monitoring.
6 | R062000114 | Tendukheda Gadarwara | Narsinghpur | PWD | Road | 2001-10-18 | DDM | 108.51 | RIDF Loan upto 10 crore | Work order is yet to be issued. Dept may expedite implementation
6 | R062000116 | Saijawata Bangrod Jadawasa | Ratlam | PWD | Road | 2001-10-18 | DDM | 65.09 | RIDF Loan upto 10 crore | Delay in tendering, Work not yet commenced.
6 | R062000133 | Jaurasi Antri | Gwalior | PWD | Road | 2001-10-18 | DDM | 23.12 | RIDF Loan upto 10 crore | The agency, however, did not complete the work by due date and was terminated on 5/10/01), Delay in tendering (tender accepted on 4/6/01 had to be cancelled subsequently as it was 30% below the CSR and the agency abondoned the work).
6 | R062000132 | Bandha Baijnath Dham | Gwalior | PWD | Road | 2001-10-17 | DDM | 68.14 | RIDF Loan upto 10 crore | Division received intimation of sanction of project on 31/3/01 and the work has commenced from 21/7/01.
6 | R062000136 | Rudharpura Rairu | Gwalior | PWD | Road | 2001-10-17 | DDM | 18.49 | RIDF Loan upto 10 crore | Delay in tendering (tender accepted on 26/5/01 had to be cancelled as the rates quoted were 34.1% below the CSR and the agency fixed subsequently abondoned the work).
6 | R062000061 | Mundalaram-Riyawan-Ranayara-Bhatkheda | Ratlam | PWD | Road | 2001-10-16 | DDM | 203.69 | RIDF Loan upto 10 crore | Delay in tendering, Work not yet commenced
6 | R062000089 | Umar 19/4 | Narsinghpur | PWD | Bridge | 2001-10-16 | DDM | 43.66 | RIDF Loan upto 10 crore | Slow work progress (due to discharge of water from Bargi Dam and non-availability of raw material locally), NB board not displayed.
6 | R062000102 | Langha Tola Patana Karpa | Anuppur | PWD | Road | 2001-09-27 | DDM | 112.76 | RIDF Loan upto 10 crore | Slow progress of work (work not yet commenced), Delay in tendering (tendering for road and CD work not yet initiated),
6 | R062000081 | Semaria | Shahdol | WRD | MIS | 2001-09-19 | DDM | 50.17 | RIDF Loan upto 10 crore | Slow progress of work (work not yet commenced), Delay in tendering (tendering for Unit I under process and for Unit II not yet initiated), NB board not displayed
6 | R062000013 | Manawar-Dehri | Dhar | PWD | Road | 2001-05-03 | DDM | 186.7 | RIDF Loan upto 10 crore | NB board not displayed, WBM completed for 16.6 km out of the sanctioned road length of 19.2 km, 13 CDs of the 19 CDs sanctioned were pending.
6 | R062000084 | Sukhakheri-Barha | Narsinghpur | PWD | Road | 2001-05-03 | DDM | 84.44 | RIDF Loan upto 10 crore | Delay in tendering(draft NIT-both for road & CD work awaiting approval of the CE-Jabalpur),work not yet commenced, observations of technical nature(condition of the sub-grade II is very bad for the road length of 4.6 kms already completed.
6 | R062000003 | Agra-Newari-Atawada | Indore | PWD | Road | 2001-04-28 | DDM | 66.92 | RIDF Loan upto 10 crore | Slow progress of work owing to scarcity of water for drought conditions in the district, NB board not displayed, earthwork and CDs in progress, road work prior to NB sanction was damaged in patches and required rectification.
6 | R062000013 | Manawar-Dehri | Dhar | PWD | Road | 2001-03-14 | DDM | 186.7 | RIDF Loan upto 10 crore | Agency fixed and work in progress,NB board not displayed
6 | R062000081 | Semaria | Shahdol | WRD | MIS | 2001-01-09 | DDM | 50.17 | RIDF Loan upto 10 crore | Tendering still in progress. Need to be finalised soon. So, WRD should look into the matter immediately.
6 | R062000001 | Taradeh-Bansi-Sarra | Damoh | PWD | Road |  |  | 86.24 | RIDF Loan upto 10 crore
6 | R062000002 | Tejgarh-Kalera | Damoh | PWD | Road |  |  | 77.89 | RIDF Loan upto 10 crore
6 | R062000009 | Sonar-4/9 | Damoh | PWD | Bridge |  |  | 164.48 | RIDF Loan upto 10 crore
6 | R062000011 | Barsuri-10/2 | Sheopur | PWD | Bridge |  |  | 85.98 | RIDF Loan upto 10 crore
6 | R062000012 | Taradehi-Maharajpur | Damoh | PWD | Road |  |  | 42.84 | RIDF Loan upto 10 crore
6 | R062000045 | Bhaliwara | Seoni | WRD | MIS |  |  | 76.47 | RIDF Loan upto 10 crore
6 | R062000059 | Pathariya-Kindroh-Jerath | Damoh | PWD | Road |  |  | 199.2 | RIDF Loan upto 10 crore
6 | R062000063 | Jeron-Baswan | Tikamgarh | PWD | Road |  |  | 184.2 | RIDF Loan upto 10 crore
6 | R062000064 | Kari-Mabai | Tikamgarh | PWD | Road |  |  | 48.45 | RIDF Loan upto 10 crore
6 | R062000072 | Tem-2/8 | Guna | PWD | Bridge |  |  | 72.86 | RIDF Loan upto 10 crore
6 | R062000097 | Manasa Badal | Neemuch | PWD | Road |  |  | 43.81 | RIDF Loan upto 10 crore
6 | R062000099 | Patadia Dhakad Budanpur | Rajgarh | PWD | Road |  |  | 118.87 | RIDF Loan upto 10 crore
6 | R062000115 | Neemuch Baghana Darududarsi | Neemuch | PWD | Road |  |  | 149.54 | RIDF Loan upto 10 crore
6 | R062000123 | Br. on Wardha Rd-km 5/10 | Betul | PWD | Bridge |  |  | 123.89 | RIDF Loan upto 10 crore
6 | R062000137 | Thandla Sutreti Mahuda | Jhabua | PWD | Road |  |  | 18.86 | RIDF Loan upto 10 crore
6 | R062000141 | Khoi Chuwa Bhiyamau | Satna | PWD | Road |  |  | 79.04 | RIDF Loan upto 10 crore
6 | R062000157 | Jamunziri Tank No.2 | Dhar | WRD | MIS |  |  | 14.98 | RIDF Loan upto 10 crore
7 | r072000095 | Tawa Left Bank Main Canal | Hoshangabad | WRD | MJP | 2007-12-13 | RO Officer | 1321.21 | RIDF Loan 10.01-24.99 crore | The project has been completed and PCR submitted. No cost overrun. All test records maintained. WRD is well equipped with technical staff and looks after maintenance of the project after completion.
7 | r072000012 | Kaka Sahab Gadgil Sagar (Chaldu) Tank | Mandsaur | WRD | MIS | 2007-12-11 | Mandsaur DDM | 2257.66 | RIDF Loan 10.01-24.99 crore | PCR VERIFICATION.NABARD board not displayed. Water does not reach the tail end of canal. WUA not formed. The project is completed and the Dept. should submit PCR.
7 | r072000057 | Small Hydro Electric Power Project of 10 MW | Jabalpur | NVDA | Power | 2007-09-26 | Jabalpur (Katni) DDM | 3771.27 | RIDF Loan 25 crore & above
7 | r072000057 | Small Hydro Electric Power Project of 10 MW | Jabalpur | NVDA | Power | 2007-09-26 | Jabalpur DDM | 3771.27 | RIDF Loan 25 crore & above | Time overrun. The power house is complete in all respects.
7 | r072000055 | Bargi Diversion Project-RABC fm (-)43 m to 8.0 km | Jabalpur | NVDA | MJP | 2007-09-25 | Jabalpur (Katni) DDM | 6518.07 | RIDF Loan 25 crore & above
7 | r072000056 | Bargi Diversion Project-RABC fm 8.0 km to 16.0 km - Package 2 | Jabalpur | NVDA | MJP | 2007-09-25 | Jabalpur (Katni) DDM | 5450.53 | RIDF Loan 25 crore & above
7 | r072000055 | Bargi Diversion Project-RABC fm (-)43 m to 8.0 km | Jabalpur | NVDA | MJP | 2007-09-25 | Jabalpur DDM | 6518.07 | RIDF Loan 25 crore & above | NABARD board has not been displayed. The canal needs to be cleaned since lot of mud and shrubs have grown all over before release of water in canal.
7 | r072000056 | Bargi Diversion Project-RABC fm 8.0 km to 16.0 km - Package 2 | Jabalpur | NVDA | MJP | 2007-09-25 | Jabalpur DDM | 5450.53 | RIDF Loan 25 crore & above | NABARD board has not been displayed. The canal needs to be cleaned urgently before release of water.
7 | r072000056 | Bargi Diversion Project-RABC fm 8.0 km to 16.0 km - Package 2 | Jabalpur | NVDA | MJP | 2007-03-19 | Jabalpur DDM | 5450.53 | RIDF Loan 25 crore & above | Cleaning of the canal site was in progress. The project is expected to be completed by March 07. NABARD board has been displayed.
7 | r072000022 | Banjar 1/4 | Mandla | PWD | Bridge | 2007-03-07 | Mandla DDM | 228.46 | RIDF Loan upto 10 crore | NABARD board has not been displayed. Work has restarted in January 2007.
7 | r072000026 | Samarboh Surangi khamarpani | Chhindwara | PWD | Road | 2007-01-29 | Chindwara DDM | 260.72 | RIDF Loan upto 10 crore | Project has been completed. NABARD board has been displayed.
7 | r072000015 | Dola Panjara Gumtara | Chhindwara | PWD | Road | 2007-01-29 | Chindwara DDM | 201.07 | RIDF Loan upto 10 crore | Project has been completed. EE visited the project. NABARD board has been displayed. 200 metre road is yet to be completed as they were not allowed to construct as the farmer's compensation is yet to be paid.
7 | r072000002 | Ramnagar | Dindori | WRD | MIS | 2007-01-19 | Mandla DDM | 203.75 | RIDF Loan upto 10 crore | Tank is completed. Water is also stored but utilisation is lower due to incomplete canal since December 05. Large pile of hard rock is lying at site. NABARD board has been displayed.
7 | r072000064 | Kathotiya Linga | Narsinghpur | PWD | Road | 2007-01-16 | Narsinghpur DDM | 146.52 | RIDF Loan upto 10 crore | The milestones and shoulders are not there. A bridge on the nulla/river in place of existing causeway will be required for making the road perennially operational.
7 | r072000065 | Singpur Khura | Narsinghpur | PWD | Road | 2007-01-12 | Narsinghpur DDM | 84.4 | RIDF Loan upto 10 crore | The compaction of the road constructed in phases does not appear proper. The road has developed depressions at a number of places. Deep ruts and potholes have developed on the road.
7 | r072000051 | Semlipura Tank | Dhar | WRD | MIS | 2006-11-17 | Dhar DDM | 61.19 | RIDF Loan upto 10 crore | Before construction of the tank irrigation was dependant on monsoon only. The project has been completed in March 2006. NABARD board has not been displayed.
7 | R072000079 | Satner Dehgud Mandvi | Betul | PWD | Road | 2006-11-02 | Betul DDM | 101.21 | RIDF Loan upto 10 crore | NABARD board displayed on both sides. Condition of road is satisfactory. Work completed. Around 25 villages benefited.
7 | r072000082 | Rajola Bhokai | Chhindwara | PWD | Road | 2006-10-18 | Chindwara DDM | 68.4 | RIDF Loan upto 10 crore | Quality of work was not satisfactory. Department to take up repairs and maintenance. Road has increased connectivity of villages. NABARD board has been displayed on both the ends. Connecting roads to the present road is in bad condition.
7 | r072000081 | Mothar Approach | Chhindwara | PWD | Road | 2006-10-18 | Chindwara DDM | 51.9 | RIDF Loan upto 10 crore | Quality of work was not satisfactory. Department to take up repairs and maintenance. Road has increased connectivity of villages. NABARD board has been displayed on both the ends. Connecting roads to the present road is in bad condition.
7 | r072000004 | Kosami Kaparwadi | Chhindwara | PWD | Road | 2006-10-18 | Chindwara DDM | 264.48 | RIDF Loan upto 10 crore | Quality of work is satisfactory. Department to take up repairs and maintenance. Road has increased connectivity of villages. NABARD board has been displayed on both the ends.
7 | R072000074 | Mahigaon Tank | Dewas | WRD | MIS | 2006-10-10 | Dewas DDM | 402.36 | RIDF Loan upto 10 crore | Project yet to be completed. In canal work seepage has been noticed for which work has to be done, ramp and railing has to be made, bunding work has not been completed. NB board not displayed.
7 | R072000013 | Manpur Katangi | Balaghat | PWD | Road | 2006-09-15 | Balaghat DDM | 194.57 | RIDF Loan upto 10 crore | Project has already been completed. Condition of road not proper. Nos. of potholes observed. One vental causeway fully damaged, approach on another causeway washed out. Repair work to be taken up shortly by the contractor.
7 | R072000013 | Manpur Katangi | Balaghat | PWD | Road | 2006-09-15 | RO Officer | 194.57 | RIDF Loan upto 10 crore | The initial stretch of 2 kms in bad shape not considered. the width of the road was only 6' with no shoulders either way in long stretches. Survey not done. Approach road to vented causeway at 21/4 washed out.
7 | r072000015 | Dola Panjara Gumtara | Chhindwara | PWD | Road | 2006-09-14 | Chindwara DDM | 201.07 | RIDF Loan upto 10 crore | NABARD board displayed. Road users satisfied.
7 | R072000057 | Small Hydro Electric Power Project of 10 MW | Jabalpur | NVDA | Power | 2006-07-25 | Jabalpur DDM | 3771.27 | RIDF Loan 25 crore & above | Project has been completed. Agreement between NVDA and Power Trading Co. have not been entered so far.
7 | r072000057 | Small Hydro Electric Power Project of 10 MW | Jabalpur | NVDA | Power | 2006-07-24 | OIC | 3771.27 | RIDF Loan 25 crore & above | Project has been completed. Agreement between NVDA and Power Trading Co. have not been entered so far.
7 | R072000057 | Small Hydro Electric Power Project of 10 MW | Jabalpur | NVDA | Power | 2006-06-01 | Jabalpur DDM | 3771.27 | RIDF Loan 25 crore & above | Project has been completed. Agreement between NVDA and Power Trading Co. has not been entered into so far.
7 | R072000012 | Kaka Sahab Gadgil Sagar (Chaldu) Tank | Mandsaur | WRD | MIS | 2006-05-04 | Mandsaur DDM | 2257.66 | RIDF Loan 10.01-24.99 crore | NABARD board not displayed. Due to land acquisition problem construction of minors delayed.
7 | r072000059 | Nissani Tank | Neemuch | WRD | MIS | 2006-04-04 | Mandsaur DDM | 76.4 | RIDF Loan upto 10 crore | PCR verification. Many substations have got relief from overlaod problem. Voltage supply and temporary connections have increased.
7 | R072000011 | Bankri 5/8 | Sagar | PWD | Bridge | 2006-03-28 | DDM | 108.71 | RIDF Loan upto 10 crore | Project except some portion of approach road completed. NABARD board not displayed.
7 | R072000093 | Chakhla Tank | Chhindwara | WRD | MIS | 2006-03-07 | DDM | 372.16 | RIDF Loan upto 10 crore | Project completed. WUA formed and functioning.
7 | R072000063 | Pattan Nasod | Betul | PWD | Road | 2006-03-02 | DDM | 82.66 | RIDF Loan upto 10 crore | PCR verified. Quality of works satisfactory.
7 | r072000089 | Danmarhi Tank | Vidisha | WRD | MIS | 2006-02-27 | DDM | 404.07 | RIDF Loan upto 10 crore | Work is in progress. Forest clearance not recd. Project likely to be completed by 31-12-06.
7 | R072000002 | Ramnagar | Dindori | WRD | MIS | 2006-02-22 | DDM | 203.75 | RIDF Loan upto 10 crore | Project completed upto 95%. NABARD board displayed but removed by villagers. One WUA formed.
7 | R072000001 | Thanwar | Mandla | WRD | MJP | 2006-02-21 | DDM | 357.16 | RIDF Loan upto 10 crore | Headworks completed. Canal work is in progress.
7 | R072000074 | Mahigaon Tank | Dewas | WRD | MIS | 2006-02-02 | OIC+DDM | 402.36 | RIDF Loan upto 10 crore | 80% Headworks and Canal completed. Work stopped since Feb 2004 due to resistance of local farmers on issue of payment of registration charges by Govt. Now the farmers have agreed to allow the work to start. The work is likely to start from 15 Feb 2004.
7 | r072000019 | Panihar Pagara | Gwalior | PWD | Road | 2006-01-16 | DDM | 198.16 | RIDF Loan upto 10 crore | Retendering is reportedly in progress as the earlier contract has been cancelled.
7 | R072000026 | Samarboh Surangi khamarpani | Chhindwara | PWD | Road | 2006-01-13 | DDM | 260.72 | RIDF Loan upto 10 crore | Project completed except for BT in 6 km.
7 | R072000015 | Dola Panjara Gumtara | Chhindwara | PWD | Road | 2006-01-11 | DDM | 201.07 | RIDF Loan upto 10 crore | Work completed upto 70%. The road between Km 9 and 13 has been covered under PMGSY.
7 | r072000075 | Doli Tank | Jabalpur | WRD | MIS | 2005-12-29 | DDM | 199.99 | RIDF Loan upto 10 crore | Project completed on 31-8-2005 and PCR is verified. Irrigation potential of 181 ha in Kharif and 216 ha in Rabi is created. WUA is yet to be formed.
7 | r072000075 | Doli Tank | Jabalpur | WRD | MIS | 2005-12-13 | DDM | 199.99 | RIDF Loan upto 10 crore | Work is in progress
7 | R072000071 | Bagini 6/6 | Dhar | PWD | Bridge | 2005-12-13 | DDM | 93.24 | RIDF Loan upto 10 crore | Works completed. PCR is yet to be submitted. NABARD board is not displayed.
7 | r072000012 | Kaka Sahab Gadgil Sagar (Chaldu) Tank | Mandsaur | WRD | MIS | 2005-12-10 | DDM | 2257.66 | RIDF Loan 10.01-24.99 crore | Headworks is completed. Excepting for a railway crossing at RD 3680 km the main canal is also completed. Work is in progress in minor canals. Project is likely to be completed by March 2007.
7 | r072000082 | Rajola Bhokai | Chhindwara | PWD | Road | 2005-12-02 | DDM | 68.4 | RIDF Loan upto 10 crore | Works have been completed. Maintenance is poor.
7 | r072000081 | Mothar Approach | Chhindwara | PWD | Road | 2005-12-01 | DDM | 51.9 | RIDF Loan upto 10 crore | Project is completed. Adequate maintenance need be ensured.
7 | r072000004 | Kosami Kaparwadi | Chhindwara | PWD | Road | 2005-12-01 | DDM | 264.48 | RIDF Loan upto 10 crore | Project is completed. Proper maintenance of the road and shoulders need be ensured.
7 | R072000001 | Thanwar | Mandla | WRD | MJP | 2005-11-15 | DDM | 357.16 | RIDF Loan upto 10 crore | (1) Headworks completed. (2) Canal work is under progress (3) Likely date of completion June 2006
7 | R072000059 | Nissani Tank | Neemuch | WRD | MIS | 2005-10-21 | DDM | 76.4 | RIDF Loan upto 10 crore | 1. Project is completed and irrigation to 75 ha provided during last season. 2. WUA is yet to be formed
7 | R072000009 | Khaira Mishirgawan | Singrauli | PWD | Road | 2005-10-06 | DDM | 203.08 | RIDF Loan upto 10 crore | Progress of implementation of work is slow, and, is almost complete. The quality of work is satisfactory. There was no record of maintenance of Quality Control register at the site. The bottleneck was due to escalation in cost.
7 | R072000079 | Satner Dehgud Mandvi | Betul | PWD | Road | 2005-10-05 | DDM | 101.21 | RIDF Loan upto 10 crore | The work has been completed and the quality is good.
7 | R072000064 | Kathotiya Linga | Narsinghpur | PWD | Road | 2005-10-04 | DDM | 146.52 | RIDF Loan upto 10 crore | progress slow. Notices issued to contractor by department to expedilte the work, potholes and damages observed , PWD should ensure to get the repair work done before expiry of the guarantee period. NABARD board has not been displayed.
7 | R072000065 | Singpur Khura | Narsinghpur | PWD | Road | 2005-10-03 | DDM | 84.4 | RIDF Loan upto 10 crore | The construction of the road was scheduled to be completed by 11/12/02. The project has been delayed due to bottlenecks/litigations in acquisiton of land which has since been solved. There are several potholes and other types of damages.
7 | R072000053 | Jamanya Naka Tank | Dhar | WRD | MIS | 2005-09-29 | DDM | 43.62 | RIDF Loan upto 10 crore | Headworks completed. Canal portion requires to be repaired.
7 | R072000012 | Kaka Sahab Gadgil Sagar (Chaldu) Tank | Mandsaur | WRD | MIS | 2005-07-22 | OIC+C | 2257.66 | RIDF Loan 10.01-24.99 crore | The head works have been completed. Except for the railway crossing at RD 3.68 km, the remaining length of the main canal work with structures have been completed. This part of the work has to be executed by the Railway Department.
7 | R072000101 | Narmada 1/4 | Mandla | PWD | Bridge | 2005-07-02 | DDM | 411.79 | RIDF Loan upto 10 crore | project not yet started. There are bottlenecks which the EE is not revealing and he says that the department is pursuing with the Govt. The project cost has been revised twice and the proposal has been sent by department to State HQ on 11/05/05.
7 | R072000022 | Banjar 1/4 | Mandla | PWD | Bridge | 2005-06-30 | DDM | 228.46 | RIDF Loan upto 10 crore | The work is in progress. Likely date of completion is June 2006. NABARD board is not displayed.
7 | R072000041 | Belkheda Kataighat Barman | Jabalpur | PWD | Road | 2005-06-03 | DDM | 84.91 | RIDF Loan upto 10 crore | Slow progress. Construction covered under PMGSY from Km 9/4 to 10/6. About 1 km of the road from NH to Belkheda is badly damaged which need to be repaired. The work may be extended upto NH to provide full conectivity. NABARD board was not displayed.
7 | R072000036 | Behpur Nandwel | Mandsaur | PWD | Road | 2005-05-26 | DDM | 165.94 | RIDF Loan upto 10 crore | The work is completed. It was observed that the board on Nandvel side has been removed by miscreants.
7 | R072000055 | Bargi Diversion Project-RABC fm (-)43 m to 8.0 km | Jabalpur | NVDA | MJP | 2005-04-12 | DDM | 6518.07 | RIDF Loan 25 crore & above | New work agencies were fixed. work on RBC main canal as well as distributaries were in full swing. lining work was in progress.
7 | R072000056 | Bargi Diversion Project-RABC fm 8.0 km to 16.0 km - Package 2 | Jabalpur | NVDA | MJP | 2005-04-12 | DDM | 5450.53 | RIDF Loan 25 crore & above | New work agencies were fixed. The work was in full swing both on RBC main canal as well as distriburories. NABARD Board was not displayed.
7 | R072000057 | Small Hydro Electric Power Project of 10 MW | Jabalpur | NVDA | Power | 2005-04-08 | DDM | 3771.27 | RIDF Loan 25 crore & above | Civil work was in nearing completion. The progress was satisfactory.
7 | R072000093 | Chakhla Tank | Chhindwara | WRD | MIS | 2005-03-29 | DDM | 372.16 | RIDF Loan upto 10 crore | Project was completed.
7 | R072000040 | Keolari Khapa bazar | Seoni | PWD | Road | 2005-03-22 | DDM | 319.7 | RIDF Loan upto 10 crore | There was overlapping of 2.6 Km. road sanctioned under PMGSY and NABARD. G1 was completed in 10.20 km. inside village roads, balance work was awaiting instructions from higher offices. A few settlements were seen first two kms. and a few other spots.
7 | R072000017 | Daloda Digaon mali | Mandsaur | PWD | Road | 2005-03-22 | DDM | 161.39 | RIDF Loan upto 10 crore | NABARD Board was not displayed,.There was problem of land acquisition near 1/8 km. point. The same was pending for long time. of the total 11.4 km., black topping is done on about 9 km. length.
7 | R072000037 | Kyampur Nataram sitamau | Mandsaur | PWD | Road | 2005-03-22 | DDM | 191.8 | RIDF Loan upto 10 crore | sub grade work of almost 2/3rd road length is over. Sub base work has been done upto almost 905 level. WBM is over on entire road. Black topping is yet to start. total 21 CDs have to be laid, of which 14 have been laid. NABARD Board was not displayed.
7 | R072000067 | Gangwariya Umari Karahiya Praswara | Satna | PWD | Road | 2005-03-19 | DDM | 80.05 | RIDF Loan upto 10 crore | Due to the contractors problem, work is slow. NABARD board not displayed
7 | R072000039 | Semri Fatehpur katan | Satna | PWD | Road | 2005-03-19 | DDM | 78.01 | RIDF Loan upto 10 crore | Project is completed in all respect
7 | R072000069 | Nagod Rahikwara Surdaha | Satna | PWD | Road | 2005-03-19 | DDM | 46.56 | RIDF Loan upto 10 crore | The work is slow. Contrctor's problem. NABARD Board not displayed. Regular monitoring system at district level by SE or EE should be introduced and progress of implementation of NABARD projects should be monitered.
7 | R072000070 | Pipariya Dhapara | Seoni | PWD | Road | 2005-03-19 | DDM | 46.89 | RIDF Loan upto 10 crore | Road construction was completed. Road width was less than 6 meters at some places.
7 | R072000012 | Kaka Sahab Gadgil Sagar (Chaldu) Tank | Mandsaur | WRD | MIS | 2005-03-11 | DDM | 2257.66 | RIDF Loan 10.01-24.99 crore | LA problem. One CD at railway crossing yet to be constructed. NABARD Board not displayed. Most of the sections of main canal needs dressing. Two-three corves in the main canal across Mhow-Neemuch highway be pitched before release of water in the canal.
7 | R072000012 | Kaka Sahab Gadgil Sagar (Chaldu) Tank | Mandsaur | WRD | MIS | 2005-03-11 | DDM | 2257.66 | RIDF Loan 10.01-24.99 crore | The work is delayed to some extent. Construction of minors delayed due to the problem of of land acuisition. One CD at railway crossing is yet to be constructed by the Railway Dept. NABARD Board was not displayed.
7 | R072000028 | Charkha Gadajer itama | Gwalior | PWD | Road | 2005-03-05 | DDM | 53.4 | RIDF Loan upto 10 crore | Work completed in March 2003. The quality of the work appears to be satisfactory however there was no proper system for maintenance of road.
7 | R072000027 | Adampura Joura Shyampura | Gwalior | PWD | Road | 2005-03-05 | DDM | 35.38 | RIDF Loan upto 10 crore | Work was completed in Nov. 2002. The quality of the work appears to be satisfactory however there was no proper system of maintenance of road.
7 | R072000049 | Churia Tank | Jabalpur | WRD | MIS | 2005-03-03 | DDM | 38.43 | RIDF Loan upto 10 crore | Overall 98% works has been completed. Progress and quality of works is satisfactory. Canal being dug from RD 0-200 meters. NABARD board be displayed at project site.
7 | R072000075 | Doli Tank | Jabalpur | WRD | MIS | 2005-03-02 | DDM | 199.99 | RIDF Loan upto 10 crore | Overall 81% of work has been completed. NABARD board be displayed at project site.
7 | R072000031 | Jamahar Approach | Gwalior | PWD | Road | 2005-02-19 | DDM | 36.92 | RIDF Loan upto 10 crore | Approach roads and parapet wall on both the sides of the bridge are yet to be constructed. Grade III and asphalting is yet to be done. The contractor stopped the work for almost one year due to non-cooperation from the farmers.
7 | R072000066 | Bhadanpur Bhatura | Satna | PWD | Road | 2005-02-17 | DDM | 127.21 | RIDF Loan upto 10 crore | The work is stalled. Dept. is not able to supervise the work and Contractor has let out works to petty contractor who neither have the efficiency nor resources to complete the work.
7 | R072000009 | Khaira Mishirgawan | Singrauli | PWD | Road | 2005-02-16 | DDM | 203.08 | RIDF Loan upto 10 crore | The progress of implementation is very slow.Delay in clearance from Forest Dept. for Bridge and culvert. No record of visits by EE/CE and also Quality Control register was maintained at site. NABARD Board is not displayed in revised format.
7 | R072000036 | Behpur Nandwel | Mandsaur | PWD | Road | 2005-02-14 | DDM | 165.94 | RIDF Loan upto 10 crore | The construction of the road is completed. The surface of CD at 6/4 km. was found to be damaged. Dept. should arrange for display of NABARD board at Nandvel end of the road.
7 | R072000068 | Jaitwara Dagdiha Sohas Kothak Pawaiya | Satna | PWD | Road | 2005-02-05 | DDM | 132.64 | RIDF Loan upto 10 crore | The progress is slow. Work relating to 12 CDs is nearing completion. At the time of visit the WBM work was in progress. The original agreement was terminated and new work order issued to on the basis of retendering.
7 | R072000083 | Nayagaon Sabhapur | Satna | PWD | Road | 2005-02-05 | DDM | 46.55 | RIDF Loan upto 10 crore | The progress is slow. Work relating to one CD is half done. NABARD Board was not displayed. The contract is taken up by some contractor who cannot execute the work in the area without taking into confidence the local contractor or muscleman.
7 | R072000059 | Nissani Tank | Neemuch | WRD | MIS | 2005-02-04 | DDM | 76.4 | RIDF Loan upto 10 crore | The work of Unit I is completed. Some amount of work of Unit II was yet to be completed. Cotractor problem in case of Unit II. Proposal for formation of WUA has been submitted to the CE, Indore.
7 | R072000011 | Bankri 5/8 | Sagar | PWD | Bridge | 2005-01-09 | DDM | 108.71 | RIDF Loan upto 10 crore | The work pertaining to approach road is in arrears. PWD has aleady deposited the LA money with Dist.Admn. However LA order has not passed by the Admn. NABARD board has not displayed.
7 | R072000024 | Sajli 17/8 | Sagar | PWD | Bridge | 2005-01-09 | DDM | 62.21 | RIDF Loan upto 10 crore | The bridge is complete in all respect. NABARD Board has not displayed. Dept. may submit PCR with appropriate expenditure details.
7 | R072000015 | Dola Panjara Gumtara | Chhindwara | PWD | Road | 2004-12-12 | DDM | 201.07 | RIDF Loan upto 10 crore | There was overlaping of 4 Km. road length ( between 9-13 Km) under PMGSY and NABARD, Dept. decided not to cover 4 Km under NABARD. The road work has stopped in 0.2 Km. on account of non receipt of compensation of LA to farmer.
7 | R072000098 | Chanuwa Joona Jamghat | Sagar | PWD | Road | 2004-12-09 | DDM | 181.84 | RIDF Loan upto 10 crore | The earlier contract has been cancelled by the Dept. New contractor has been assigned the work on 28 Oct. 2004. The work is likely to be completed by 30 June 2005. the original road sanctioned was Jamghat-Joona-Channouwa.
7 | R072000098 | Chanuwa Joona Jamghat | Sagar | PWD | Road | 2004-12-09 | RO Official | 181.84 | RIDF Loan upto 10 crore | Report received
7 | R072000082 | Rajola Bhokai | Chhindwara | PWD | Road | 2004-12-08 | DDM | 68.4 | RIDF Loan upto 10 crore | Road construction quality was poor.Out of 8 km, 4 km was reported poor and therefore no payment was made to the agency. Due to this balance work was not taken up by the contractor.
7 | R072000081 | Mothar Approach | Chhindwara | PWD | Road | 2004-12-08 | DDM | 51.9 | RIDF Loan upto 10 crore | Construction work was completed. Before issue of completion certificate department should ensure maintenance of minor repairing.
7 | R072000004 | Kosami Kaparwadi | Chhindwara | PWD | Road | 2004-12-08 | DDM | 264.48 | RIDF Loan upto 10 crore | Project was completed except 5 meter road connection with cement concrete road constructed in one village. No officer above the rank of EE has visited the site so far.
7 | R072000002 | Ramnagar | Dindori | WRD | MIS | 2004-12-08 | DDM | 203.75 | RIDF Loan upto 10 crore | The work was completed in June 2003. Canal work has not started . Visit register not kept at sight.Fields water linings will have to be prepared for irrigation to save the waste.
7 | R072000026 | Samarboh Surangi khamarpani | Chhindwara | PWD | Road | 2004-12-07 | DDM | 260.72 | RIDF Loan upto 10 crore | Orignal date for project completion date was Aug. 03. The dept. had submittedproposal for exension upto 30 June 05. No senior officer has visited the project.
7 | R072000064 | Kathotiya Linga | Narsinghpur | PWD | Road | 2004-11-17 | DDM | 146.52 | RIDF Loan upto 10 crore | The progress is very slow. The major bottleneck is budgetory allocation. NABARD Board not displayed.
7 | R072000053 | Jamanya Naka Tank | Dhar | WRD | MIS | 2004-11-17 | DDM | 43.62 | RIDF Loan upto 10 crore | There is delay in implementation of the project. NABARD Board not displayed.
7 | R072000071 | Bagini 6/6 | Dhar | PWD | Bridge | 2004-11-10 | DDM | 93.24 | RIDF Loan upto 10 crore | Project is completed however completion report has not so far submitted. NABARD Board not displayed. Work quality is not upto the mark.
7 | R072000001 | Thanwar | Mandla | WRD | MJP | 2004-11-04 | DDM | 357.16 | RIDF Loan upto 10 crore | The progress has been delayed due to continuous water flow for irrigation. The project is likely to be completed by June 2005.
7 | R072000048 | Banas 54/10 | Sidhi | PWD | Bridge | 2004-10-20 | DDM | 174.13 | RIDF Loan upto 10 crore | The bridge work was in progress. Approach road work is yet to commence including calling of tenders. NABARD Board not displayed.
7 | R072000038 | Barethia Hilondha katkon | Satna | PWD | Road | 2004-10-12 | DDM | 95.88 | RIDF Loan upto 10 crore | The work has been completed.Quality of the work is satisfactory. NABARD Board not displayed.
7 | R072000061 | Maraiya Gond Tank | Sagar | WRD | MIS | 2004-09-26 | DDM | 96.2 | RIDF Loan upto 10 crore | The work relating to Unit I and Unit II are almost completed except small finishing touches remaining. NABARD Board not displayed.
7 | R072000014 | Seonda Pandri Tehamgaon Sados | Bhind | PWD | Road | 2004-09-25 | DDM | 384.35 | RIDF Loan upto 10 crore | Out of 5 slab culverts cause ways 4 were good. Concerete railings of one of the culverts was a bit more wide on one side. WBM work was under progress. NABARD Board was not displayed.
7 | R072000046 | Tamus 26/4 | Rewa | PWD | Bridge | 2004-09-24 | DDM | 89.83 | RIDF Loan upto 10 crore | The progress of the work was very slow. The delay in the bridge work was reported on account of delay in the designing and drawing and change in the design of the bridge. Approach road is yet to commence.NABARD Board was not displayed.
7 | R072000012 | Kaka Sahab Gadgil Sagar (Chaldu) Tank | Mandsaur | WRD | MIS | 2004-09-21 | DDM | 2257.66 | RIDF Loan 10.01-24.99 crore | The work is delayed. It is likely to be completed by Dec. 2004.
7 | R072000100 | Turar 200/2 | Dindori | PWD | Bridge | 2004-09-16 | DDM | 107.13 | RIDF Loan upto 10 crore | The bridge work is completed. Control testing register was maintained at site. NABARD Board was not displayed.
7 | R072000072 | Padmavati 8/10 | Jhabua | PWD | Bridge | 2004-08-31 | DDM | 75.19 | RIDF Loan upto 10 crore | Maintenance arrangements should be made. NABARD Board not displyed.
7 | R072000057 | Small Hydro Electric Power Project of 10 MW | Jabalpur | NVDA | Power | 2004-08-28 | DDM | 3771.27 | RIDF Loan 25 crore & above | Civil work is in full swing. The progress of the work is satisfactory.
7 | R072000074 | Mahigaon Tank | Dewas | WRD | MIS | 2004-07-27 | DDM | 402.36 | RIDF Loan upto 10 crore | Headwork is complete but for small portion of Nalla closure. However the villagers are demanding waiver of registration charges. NABARD Board not displayed.
7 | R072000022 | Banjar 1/4 | Mandla | PWD | Bridge | 2004-06-28 | DDM | 228.46 | RIDF Loan upto 10 crore | Very slow progress.NABARD Board not displayed.
7 | r072000089 | Danmarhi Tank | Vidisha | WRD | MIS | 2004-06-17 | DDM | 404.07 | RIDF Loan upto 10 crore | 1 )Work is not initiated so far 2 ) Problem of land acquisition, Forest dept. has to clear the same.
7 | R072000057 | Small Hydro Electric Power Project of 10 MW | Jabalpur | NVDA | Power | 2004-06-04 | DDM | 3771.27 | RIDF Loan 25 crore & above | Work agency has been fixed and the execution of civil work is in progress.
7 | R072000055 | Bargi Diversion Project-RABC fm (-)43 m to 8.0 km | Jabalpur | NVDA | MJP | 2004-06-03 | DDM | 6518.07 | RIDF Loan 25 crore & above | Work incomplete and the agencies were terminated by NVDA in Feb 2004. Fresh tenders were called.
7 | R072000056 | Bargi Diversion Project-RABC fm 8.0 km to 16.0 km - Package 2 | Jabalpur | NVDA | MJP | 2004-06-03 | DDM | 5450.53 | RIDF Loan 25 crore & above | Work was incomplete and the agencies were terminated by NVDA. Fresh tenders were called.
7 | R072000101 | Narmada 1/4 | Mandla | PWD | Bridge | 2004-05-21 | DDM | 411.79 | RIDF Loan upto 10 crore | 1) Tendering of bridge structure and approach road under process. 2) Work yet to commence. 3) Possibility of estimate to be revised to appx Rs. 800.00 Lakhs and efforts are being made to cover this project under Central Govt projects.
7 | R072000079 | Satner Dehgud Mandvi | Betul | PWD | Road | 2004-05-18 | DDM | 101.21 | RIDF Loan upto 10 crore | 1) Slow progress. 2)LA of 2.8km still pending.3) Farmers are now able to carry their farm products to market.
7 | R072000041 | Belkheda Kataighat Barman | Jabalpur | PWD | Road | 2004-04-23 | DDM | 84.91 | RIDF Loan upto 10 crore | 1) Constr of proposed road from Km9/4 to 10/6 covered under PMGSY. 2) About 1 Km of the road from NH to Belkheda is badly damaged. 3) NB board not displayed. 4)Sub-grade:35.4% Sub-base:65.6% WBM:20.3%
7 | R072000031 | Jamahar Approach | Gwalior | PWD | Road | 2004-03-29 | DDM | 36.92 | RIDF Loan upto 10 crore | Slow progress- Delay in tendering,no physical progress since March 03 . BT not done.Time overrun-project likely to be completed by May 04 as against March 04.
7 | R072000087 | Chhoti Kalisindh 3/10 | Ujjain | PWD | Bridge | 2004-03-19 | DDM | 67.11 | RIDF Loan upto 10 crore | Approach road work for 40m remains to be done.NB board not displayed.
7 | R072000088 | Bichhrod nalla 13/2 | Ujjain | PWD | Bridge | 2004-03-19 | DDM | 41.42 | RIDF Loan upto 10 crore | NB board not displayed.
7 | R072000071 | Bagini 6/6 | Dhar | PWD | Bridge | 2004-03-17 | DDM | 93.24 | RIDF Loan upto 10 crore | Slow progress-cap work of pillers P1 P2 P3 not completed,approach slab of Ghatyadeo side abutment yet to be completed. No progress in approach road.NB board not displayed.
7 | R072000012 | Kaka Sahab Gadgil Sagar (Chaldu) Tank | Mandsaur | WRD | MIS | 2004-03-13 | DDM | 2257.66 | RIDF Loan 10.01-24.99 crore | Masonry work yet to be completed in case of Unit-I &II.
7 | R072000055 | Bargi Diversion Project-RABC fm (-)43 m to 8.0 km | Jabalpur | NVDA | MJP | 2004-03-12 | DDM | 6518.07 | RIDF Loan 25 crore & above | NABARD Board not displayed The project is likely to be completed by 30.06.2004.
7 | R072000056 | Bargi Diversion Project-RABC fm 8.0 km to 16.0 km - Package 2 | Jabalpur | NVDA | MJP | 2004-03-12 | DDM | 5450.53 | RIDF Loan 25 crore & above | NABARD Board is not displayed. The project is likely to be completed by 30.06.2004.
7 | R072000074 | Mahigaon Tank | Dewas | WRD | MIS | 2004-03-11 | DDM | 402.36 | RIDF Loan upto 10 crore | Slow progress- Unit-II work not commenced. Masonry & earthwork yet to be completed.Department should try to slove the problem of electricity poles which come under submergence.NB board not displayed.
7 | R072000001 | Thanwar | Mandla | WRD | MJP | 2004-03-11 | DDM | 357.16 | RIDF Loan upto 10 crore | LA problem- payment not made to the farmers.Time overrun- project likely to be completed by June 2005 as against March 2004. Slow progress-masonry & earthwork not completed.
7 | R072000101 | Narmada 1/4 | Mandla | PWD | Bridge | 2004-03-09 | DDM | 411.79 | RIDF Loan upto 10 crore | Project likely to be withdrawn.
7 | R072000098 | Chanuwa Joona Jamghat | Sagar | PWD | Road | 2004-02-25 | DDM | 181.84 | RIDF Loan upto 10 crore | Contractor is asking additional budget for raising of the road above the field level in certain packets.This issue is affecting the progess of the work.
7 | R072000014 | Seonda Pandri Tehamgaon Sados | Bhind | PWD | Road | 2004-02-24 | Consultant | 384.35 | RIDF Loan upto 10 crore | Mandatory soil test not carried out. Slow progress-out 56 CDs only 10 have been constructed.Time overrun-likely date of completion is December 04 as against March 04.
7 | R072000076 | Jhikari | Sehore | WRD | MIS | 2004-02-21 | Consultant | 168.74 | RIDF Loan upto 10 crore | land acquisition for unit 1 has been completed .Dam is under construction covering two nalas.Works on excabvation and filling of puddle trench on one nala is in progress,construction of filter drains also under construction.
7 | R072000048 | Banas 54/10 | Sidhi | PWD | Bridge | 2004-02-21 | Consultant | 174.13 | RIDF Loan upto 10 crore | Delay in tendering. Work not commensed.Due to slow progress project completion will be delayed.
7 | R072000009 | Khaira Mishirgawan | Singrauli | PWD | Road | 2004-02-20 | Consultant | 203.08 | RIDF Loan upto 10 crore | Slow progress-farmers not allowing to work .
7 | R072000091 | Barka Tank | Singrauli | WRD | MIS | 2004-02-18 | Consultant | 165.26 | RIDF Loan upto 10 crore | Slow progress-masonry & earthwork yet to be completed. Time overrun- project likely to be completed by June 04 as against March 04.
7 | R072000008 | Harphari Dhani khaira | Singrauli | PWD | Road | 2004-02-17 | Consultant | 191.68 | RIDF Loan upto 10 crore | Slow progress- farmers not permitting to work as they demand land compensation for drains.Timeoverrun- project likely to be completed by June 04 as against March 04.
7 | R072000084 | Kumdawada Maina | Sehore | PWD | Road | 2004-02-16 | Consultant | 84.24 | RIDF Loan upto 10 crore | slow progress in the work for want of payment.poor work metal have dispersed.
7 | R072000060 | Padariya Tank | Raisen | WRD | MIS | 2004-02-13 | Consultant | 166.29 | RIDF Loan upto 10 crore | The work is almost in completion stage.
7 | R072000003 | Katedara Zhaliwada | Balaghat | PWD | Road | 2004-02-09 | Consultant | 87.45 | RIDF Loan upto 10 crore | There is no deficiency noticed.
7 | R072000013 | Manpur Katangi | Balaghat | PWD | Road | 2004-02-09 | Consultant | 194.57 | RIDF Loan upto 10 crore | As such there is no remarkable deficiency noticed.
7 | R072000066 | Bhadanpur Bhatura | Satna | PWD | Road | 2004-02-07 | DDM | 127.21 | RIDF Loan upto 10 crore | Progress of the implementation is stalled for contractors problem.
7 | r072000038 | Barethia Hilondha katkon | Satna | PWD | Road | 2004-02-03 | DDM | 95.88 | RIDF Loan upto 10 crore | Time overrun - project likely to be completed by Jun '04 as against March '04. slow progress - physical progress of WBM, BT and CD is 76%, 34% and 68% respectively. NB board not displayed.
7 | R072000057 | Small Hydro Electric Power Project of 10 MW | Jabalpur | NVDA | Power | 2004-02-03 | OIC+RO Officials | 3771.27 | RIDF Loan 25 crore & above | Delay in fixation of work agency.
7 | r072000042 | Aajnala 2/10 | Harda | PWD | Bridge | 2004-01-30 | Consultant | 55.54 | RIDF Loan upto 10 crore | Slow progress, the approach road not constructed, the flowing during the rains in the river has cut/eroded, the down stream embarkment towards village Rubi paredia .
7 | r072000089 | Danmarhi Tank | Vidisha | WRD | MIS | 2004-01-29 | DDM | 404.07 | RIDF Loan upto 10 crore | Tendering problem - Tendering process not initiated for unit II, LA problem, forest deptt. has not cleared the land, monitoring mechanism - no officer above the rank of EE has visited the site.
7 | r072000096 | Chhirari Guda Baleh | Sagar | PWD | Road | 2004-01-28 | DDM | 113.62 | RIDF Loan upto 10 crore | Time overrun- project likely to be completed by December 04 as against March 04.Slow progress-physical progress of sub-grade,sub- base& WBM is 80%, 35% &27% respectively.Wheras BT not done at all.NB board not displayed.
7 | R072000097 | Barkheda Sikandar | Sagar | PWD | Road | 2004-01-28 | DDM | 182.11 | RIDF Loan upto 10 crore | Time overrun- project is likely to be completed by December 04 as against March 04.Slow progress - physical progress of sub- grade,sub-base & WBM is 80%, 35% &23% respectively.CD (HP,RCC slab culverts& Med. bridge )work not completed.
7 | r072000099 | Roan Chhulla Baleh | Sagar | PWD | Road | 2004-01-28 | DDM | 138.87 | RIDF Loan upto 10 crore | Time overrun- project is likely to be completed by December 04as against March 04.Slow progress-Physical progress of sub-grade &sub-base is 87% & 36% respectively.WBM not done.RCC slab culverts & medium bridges work not started.NB board not displayed.
7 | r072000065 | Singpur Khura | Narsinghpur | PWD | Road | 2004-01-22 | DDM | 84.4 | RIDF Loan upto 10 crore | Time overrun- project likely to be completed by March 05 as against March 04. In adequate budgetary allocation. NB Board not displayed.
7 | r072000064 | Kathotiya Linga | Narsinghpur | PWD | Road | 2004-01-22 | DDM | 146.52 | RIDF Loan upto 10 crore | NB Board not displayed. Slow progress- CD work yet to be completed.
7 | r072000037 | Kyampur Nataram sitamau | Mandsaur | PWD | Road | 2004-01-21 | DDM | 191.8 | RIDF Loan upto 10 crore | Fund constraints - contractor has not received the payment for completed work - slow progress - physical progress of sub-base, WBM & CD in 81%,44% & 43% respectively, BT not done. NB Board not displayed.
7 | r072000017 | Daloda Digaon mali | Mandsaur | PWD | Road | 2004-01-21 | DDM | 161.39 | RIDF Loan upto 10 crore | LA problem at 1/8 KM, slow progress - physical progress of WBM, CD & BT is 92%,88% & 90% respectively. NB Board not displayed.
7 | r072000095 | Tawa Left Bank Main Canal | Hoshangabad | WRD | MJP | 2004-01-20 | DDM | 1321.21 | RIDF Loan 10.01-24.99 crore | Slow progress-physical progress of earth work is 10%. Murram & WBM over service road yet to be completed. Masonry work not started so far.
7 | r072000036 | Behpur Nandwel | Mandsaur | PWD | Road | 2004-01-19 | DDM | 165.94 | RIDF Loan upto 10 crore | Slow progress - physical progress of WBM & BT is 90% & 59% respectively. Funds constraints & budgetery allocation problems.
7 | r072000026 | Samarboh Surangi khamarpani | Chhindwara | PWD | Road | 2004-01-18 | DDM | 260.72 | RIDF Loan upto 10 crore | Slow progress. BTnot done.
7 | r072000022 | Banjar 1/4 | Mandla | PWD | Bridge | 2004-01-16 | DDM | 228.46 | RIDF Loan upto 10 crore | Slow progress & time overrun- peroject likely to be completed by June 05,delay in execution of work ( actual work started on 14/11/03).NB board not displayed.
7 | r072000015 | Dola Panjara Gumtara | Chhindwara | PWD | Road | 2004-01-14 | DDM | 201.07 | RIDF Loan upto 10 crore | Conpensation not paid to the farmers for LA, width of the road is less than specification, BT washed away at some places.
7 | R072000052 | Maphipura | Dhar | WRD | MIS | 2004-01-14 | DDM | 42.74 | RIDF Loan upto 10 crore | Sluice gate found broken.NB board not installed.
7 | r072000004 | Kosami Kaparwadi | Chhindwara | PWD | Road | 2004-01-13 | DDM | 264.48 | RIDF Loan upto 10 crore | Slow progress, sub-grade, sub-base done for 13 KMs as against 15KMs, BT and CD work yet to be completed, delay in LA
7 | r072000058 | Junapani Tank | Mandsaur | WRD | MIS | 2004-01-09 | DDM | 162.3 | RIDF Loan upto 10 crore | WUA not formed.
7 | R072000053 | Jamanya Naka Tank | Dhar | WRD | MIS | 2004-01-06 | DDM | 43.62 | RIDF Loan upto 10 crore | Work is in progress.Nabard board indicating finance not installed.
7 | r072000043 | Pakadiyar 2/4 | Rewa | PWD | Bridge | 2003-12-21 | DDM | 21.47 | RIDF Loan upto 10 crore | Slow progress, approach road not completed, earth work on Jorhat site upto 10meters damaged, NB board not displayed.
7 | r072000044 | Pakadiyar 4/4 | Rewa | PWD | Bridge | 2003-12-21 | DDM | 21.54 | RIDF Loan upto 10 crore | NB board not displayed as per specified proforma
7 | R072000006 | Amangang Lunhargaon | Panna | PWD | Road | 2003-12-12 | RO Official | 126.38 | RIDF Loan upto 10 crore | 1. Slow progress, BT to be done at 14/2-15/6 & 15/8-16/10 KMs. 2. WBM & BT to be done at 12/10 to 2/0 & 26/10 to 30/0 KMs.
7 | R072000094 | Jeron Tank | Tikamgarh | WRD | MIS | 2003-12-09 | RO Official | 49.06 | RIDF Loan upto 10 crore | Slow progress ,Work not started, delay in tendering .
7 | R072000077 | Feeder to Barana Bamhori Tank | Tikamgarh | WRD | MIS | 2003-12-09 | RO Official | 11.85 | RIDF Loan upto 10 crore | Earthwork for Lining to be done.
7 | R072000068 | Jaitwara Dagdiha Sohas Kothak Pawaiya | Satna | PWD | Road | 2003-12-06 | DDM | 132.64 | RIDF Loan upto 10 crore | 1. Slow progress. 2. Tendering problem. 3. NB board not displayed.
7 | R072000062 | Deori | Shahdol | WRD | MIS | 2003-11-28 | DDM | 75.81 | RIDF Loan upto 10 crore | NB Board not displayed. Work is completed
7 | R072000016 | Chachoda Panchi | Guna | PWD | Road | 2003-11-15 | DDM | 44.66 | RIDF Loan upto 10 crore | 1. NB board not displayed in proper format.
7 | R072000073 | Sarari 1/2-4 | Sheopur | PWD | Bridge | 2003-11-14 | RO Official | 132.52 | RIDF Loan upto 10 crore | Approach road is proposed to be handed over to PMRY road which is inder construction. NB board is not displayed. Slow progress due to contractor's problem.
7 | R072000086 | Uddakhand nalla 21/4 | Sheopur | PWD | Bridge | 2003-11-14 | RO Official | 31.09 | RIDF Loan upto 10 crore | Work is delay due to contractors problem. NB Board is not displayed.
7 | R072000001 | Thanwar | Mandla | WRD | MJP | 2003-11-14 | DDM | 357.16 | RIDF Loan upto 10 crore | 1. Delay in LA for 6.263 ha of unit II. 2. Project completed, department should sent PCR immediate. 2. Slow progress in mesonry work of unit I & unit ii and canal lining.
7 | r072000047 | Bina 9/6 | Sagar | PWD | Bridge | 2003-11-10 | DDM | 158.72 | RIDF Loan upto 10 crore | Slow prohress, overall progress is only 43%, LA problems, Time0overrun - Project to be completed by june 04 as against March' 04.
7 | r072000072 | Padmavati 8/10 | Jhabua | PWD | Bridge | 2003-11-05 | DDM | 75.19 | RIDF Loan upto 10 crore | Slow progress, construction work of roofing not started,NB board not displayed.
7 | R072000074 | Mahigaon Tank | Dewas | WRD | MIS | 2003-10-31 | DDM | 402.36 | RIDF Loan upto 10 crore | Funds constraints, slow progress - earth work not completed, NB Board not displayed
7 | r072000089 | Danmarhi Tank | Vidisha | WRD | MIS | 2003-10-18 | DDM | 404.07 | RIDF Loan upto 10 crore | Delay in tendering (tendering not initiated for Unit I, II & III ) NB Board not displayed.
7 | R072000057 | Small Hydro Electric Power Project of 10 MW | Jabalpur | NVDA | Power | 2003-10-10 | DDM | 3771.27 | RIDF Loan 25 crore & above | Slow progress-civil works & power plant /electric system not started. Delay in fixation of work agency.
7 | R072000026 | Samarboh Surangi khamarpani | Chhindwara | PWD | Road | 2003-10-08 | DDM | 260.72 | RIDF Loan upto 10 crore | Slow Prgress.
7 | R072000015 | Dola Panjara Gumtara | Chhindwara | PWD | Road | 2003-10-07 | DDM | 201.07 | RIDF Loan upto 10 crore | Land acquisition problem
7 | R072000012 | Kaka Sahab Gadgil Sagar (Chaldu) Tank | Mandsaur | WRD | MIS | 2003-09-19 | DDM | 2257.66 | RIDF Loan 10.01-24.99 crore | Work is in progress.
7 | R072000022 | Banjar 1/4 | Mandla | PWD | Bridge | 2003-09-06 | DDM | 228.46 | RIDF Loan upto 10 crore | Slow Progress due to delay in tendering. Work order issued. NABARD Board not displayed
7 | r072000101 | Narmada 1/4 | Mandla | PWD | Bridge | 2003-09-06 | DDM | 411.79 | RIDF Loan upto 10 crore | Slow progress due to delay in tendering, NB Board not displayed.
7 | R072000018 | Laxmipura(Alot barod) to Borkedi | Ratlam | PWD | Road | 2003-07-23 | DDM | 41.65 | RIDF Loan upto 10 crore | NABARD board not displayed.
7 | R072000090 | Ukawad Tank | Guna | WRD | MIS | 2003-06-24 | DDM | 161.59 | RIDF Loan upto 10 crore | Monitoring mechanism - no officer above the rank of EE has visited the project. LA problem - farmers have not received compensation for land. NB board not displayed.
7 | R072000028 | Charkha Gadajer itama | Gwalior | PWD | Road | 2003-06-23 | DDM | 53.4 | RIDF Loan upto 10 crore | Flank work on both sides of work is to be done.
7 | r072000089 | Danmarhi Tank | Vidisha | WRD | MIS | 2003-06-18 | DDM | 404.07 | RIDF Loan upto 10 crore | Tendering problem - tendering for Unit II not initiated. Contractor problem, work going on site is very slow due to contractor. Monitoring mechanism - no officer above the rank of EE has visited the site.
7 | R072000019 | Panihar Pagara | Gwalior | PWD | Road | 2003-06-17 | DDM | 198.16 | RIDF Loan upto 10 crore | funds constraint, Work on project not progressing since Feb '03. There is a dispute on payment of contractor bill. No record of the progress of work has been maintained since Nov'02. NB board not displayed.
7 | R072000004 | Kosami Kaparwadi | Chhindwara | PWD | Road | 2003-05-24 | DDM | 264.48 | RIDF Loan upto 10 crore | LA problem-due to delay in settlement of compensation, people from concerned villages are not cooperating
7 | R072000082 | Rajola Bhokai | Chhindwara | PWD | Road | 2003-05-21 | DDM | 68.4 | RIDF Loan upto 10 crore | Land acquisition problem-farmers have not received the payment
7 | R072000081 | Mothar Approach | Chhindwara | PWD | Road | 2003-05-20 | DDM | 51.9 | RIDF Loan upto 10 crore | Monitoring mechanism (no officer above the rank of EE has visited the site).
7 | R072000011 | Bankri 5/8 | Sagar | PWD | Bridge | 2003-03-21 | DDM | 108.71 | RIDF Loan upto 10 crore | Land acquisition problem (land owner brought stay from local court). NB not displayed in proper format.
7 | R072000022 | Banjar 1/4 | Mandla | PWD | Bridge | 2003-02-22 | DDM | 228.46 | RIDF Loan upto 10 crore | Tendering problem (tenders have been called and cancelled twice), project not started.
7 | R072000079 | Satner Dehgud Mandvi | Betul | PWD | Road | 2003-02-22 | DDM | 101.21 | RIDF Loan upto 10 crore | Satisfactory
7 | R072000101 | Narmada 1/4 | Mandla | PWD | Bridge | 2003-02-22 | DDM | 411.79 | RIDF Loan upto 10 crore | Tendering problem (only pre-qualification tenders have been called), project not started.
7 | R072000011 | Bankri 5/8 | Sagar | PWD | Bridge | 2003-02-07 | RO Official | 108.71 | RIDF Loan upto 10 crore | Land acquisition problem (delay in land acquisition for approach road, award pending with LAO since Oct'01)
7 | R072000061 | Maraiya Gond Tank | Sagar | WRD | MIS | 2003-02-06 | RO Official | 96.2 | RIDF Loan upto 10 crore | Unsatisfactory quality of work (quality control tests were not being done and no records were made available at site). NB board not displayed in proper format.
7 | R072000063 | Pattan Nasod | Betul | PWD | Road | 2003-02-05 | DDM | 82.66 | RIDF Loan upto 10 crore | BT to be done on 2 CDs.
7 | R072000080 | Teelakhedi Ratibad | Bhopal | PWD | Road | 2003-01-22 | RO Official | 214.74 | RIDF Loan upto 10 crore | No payment made against LA. some trees and electric poles coming within the road width . Fund allocation to the project may be ensured. Change in design is required due to site problem. This has led to 10% cost escalation. NB board not displayed.
7 | R072000091 | Barka Tank | Singrauli | WRD | MIS | 2003-01-22 | DDM | 165.26 | RIDF Loan upto 10 crore | Project to be completed by June '03.
7 | R072000026 | Samarboh Surangi khamarpani | Chhindwara | PWD | Road | 2003-01-16 | DDM | 260.72 | RIDF Loan upto 10 crore | Contractor problem at initial stage. Likely date of completion is Dec '03.
7 | R072000046 | Tamus 26/4 | Rewa | PWD | Bridge | 2003-01-15 | DDM | 89.83 | RIDF Loan upto 10 crore | Contractor problem, not taking interest. Delay in work, Actual work not started.
7 | R072000015 | Dola Panjara Gumtara | Chhindwara | PWD | Road | 2002-12-24 | DDM | 201.07 | RIDF Loan upto 10 crore | Patch of 4 km has been left unattended due to dispute of coverage under Prime Minister's Sadak Yojna. Local MLA insisted that overlapping patch be covered under PMSY only.
7 | R072000004 | Kosami Kaparwadi | Chhindwara | PWD | Road | 2002-12-23 | DDM | 264.48 | RIDF Loan upto 10 crore | Work delayed due to land acquisition and court cases filed by farmers. Poor progress.
7 | R072000078 | Bhaisdehi Nanda Bhimpur | Betul | PWD | Road | 2002-12-14 | DDM | 154.61 | RIDF Loan upto 10 crore | Tarring of approach road of minor bridges is to be completed.
7 | R072000001 | Thanwar | Mandla | WRD | MJP | 2002-12-12 | DDM | 357.16 | RIDF Loan upto 10 crore | LA case of 25.96 ha pending with LAO. Water courses have not been covered under NB sanction, though considered under CADA.
7 | R072000041 | Belkheda Kataighat Barman | Jabalpur | PWD | Road | 2002-11-29 | DDM | 84.91 | RIDF Loan upto 10 crore | Work not yet started. NB board not displayed.
7 | R072000027 | Adampura Joura Shyampura | Gwalior | PWD | Road | 2002-10-18 | DDM | 35.38 | RIDF Loan upto 10 crore | Progress in implementation is very poor
7 | R072000023 | Sitarewa 2/8 | Narsinghpur | PWD | Bridge | 2002-06-29 | DDM | 81.82 | RIDF Loan upto 10 crore | Completed
7 | R072000064 | Kathotiya Linga | Narsinghpur | PWD | Road | 2002-06-07 | DDM | 146.52 | RIDF Loan upto 10 crore | NB board not displayed.
7 | R072000080 | Teelakhedi Ratibad | Bhopal | PWD | Road | 2002-05-07 | HO Official | 214.74 | RIDF Loan upto 10 crore | BT not done, trees and electric poles coming within the road width should be removed / shifted.
7 | r072000012 | Kaka Sahab Gadgil Sagar (Chaldu) Tank | Mandsaur | WRD | MIS |  |  | 2257.66 | RIDF Loan 10.01-24.99 crore
7 | r072000012 | Kaka Sahab Gadgil Sagar (Chaldu) Tank | Mandsaur | WRD | MIS |  |  | 2257.66 | RIDF Loan 10.01-24.99 crore
7 | R072000005 | Kuanbadla Nandia | Chhindwara | PWD | Road |  |  | 40.45 | RIDF Loan upto 10 crore
7 | R072000010 | Biranj 12/6 | Narsinghpur | PWD | Bridge |  |  | 87.9 | RIDF Loan upto 10 crore
7 | R072000020 | Lakanwada Hathanapur | Seoni | PWD | Road |  |  | 61.47 | RIDF Loan upto 10 crore
7 | R072000021 | Choti Mahanadi 11/4 | Katni | PWD | Bridge |  |  | 56.3 | RIDF Loan upto 10 crore
7 | R072000025 | Bairagarh Bhilapar | Chhindwara | PWD | Road |  |  | 10.26 | RIDF Loan upto 10 crore
7 | R072000029 | Dubaha Approach | Gwalior | PWD | Road |  |  | 16.15 | RIDF Loan upto 10 crore
7 | R072000030 | Dubaha Dubahi | Gwalior | PWD | Road |  |  | 16.04 | RIDF Loan upto 10 crore
7 | R072000032 | Kachhua Badki sarai | Gwalior | PWD | Road |  |  | 12.87 | RIDF Loan upto 10 crore
7 | R072000033 | Kaitha approach | Gwalior | PWD | Road |  |  | 23.79 | RIDF Loan upto 10 crore
7 | R072000034 | Samoodan Sekra | Gwalior | PWD | Road |  |  | 13.62 | RIDF Loan upto 10 crore
7 | R072000035 | Shankarpur Jigsoli | Gwalior | PWD | Road |  |  | 15.83 | RIDF Loan upto 10 crore
7 | R072000045 | Sukad 10/4 | Rewa | PWD | Bridge |  |  | 30.03 | RIDF Loan upto 10 crore
7 | R072000050 | Prempura Tank | Khargone | WRD | MIS |  |  | 35.58 | RIDF Loan upto 10 crore
7 | R072000054 | Bhagliyapura Tank | Dhar | WRD | MIS |  |  | 43 | RIDF Loan upto 10 crore
7 | R072000085 | Narmada 1/4 | Dindori | PWD | Bridge |  |  | 92.72 | RIDF Loan upto 10 crore
7 | R072000092 | Mundia Kheda Tank | Raisen | WRD | MIS |  |  | 453.66 | RIDF Loan upto 10 crore
7 | R072000102 | Dhatuni 8/4 | Sheopur | PWD | Bridge |  |  | 49.36 | RIDF Loan upto 10 crore
8 | R082000108 | Jaliyapani Tank | Badwani | WRD | MIS | 2009-03-16 | DDM | 377.83 | RIDF Loan upto 10 crore | HW,SW<HR >76% ciompleted MC 51-75% completed CD 51-75% completed. Sr engineers visited . quality control put in place Test records maintained Assistance displayed. Due to delay in LA , there is impending TOR
8 | R082000110 | Bhainsakhedi Tank | Dewas | WRD | MIS | 2009-03-14 | DDM | 321.94 | RIDF Loan upto 10 crore | HW, spill ways, HR, MC, BC, lining of canal,distri, minors and sub minors have been more than 76% completed.COR due to LA, material.TOR due to delay in tender. Lining done under NREGs except one Cd work over r en visited rec maintd Assistance not display
8 | R082000122 | Kandeli Distributory | Narsinghpur | NVDA | MJP | 2009-02-11 | DDM | 1547.66 | RIDF Loan 10.01-24.99 crore | Distributary works like prelim, LA, Masonry and lining >76 % completed. Visit records not maintained. Tests records not maintainned Assistance displayedSiliting of canal breacches in lining of the canal Bush growth in canal Bad condition of canal and min
8 | R082000057 | Paramhansi | Narsinghpur | WRD | MIS | 2009-02-06 | DDM | 107.51 | RIDF Loan upto 10 crore | HW,SW,HR and MC >76% completed tests carried ; visit records not shownAsistance not displayed Pitching on us , rolling on ds,railing workon sluice and dressing of canal are yet to be completed
8 | R082000053 | Rabs-Lbc From Km 84 To 97 | Narsinghpur | NVDA | MJP | 2009-01-13 | DDM | 3782.63 | RIDF Loan 25 crore & above | MC,Distri minors is mor than 76% completed. Minors and sub minors 26-50% completed TOR due to delay in CD, Contractors LA and Hard rock in main canal. Visit record not maintained tests records not maintained. Board displayed
8 | R082000120 | Bhadgawan Branch Canal | Narsinghpur | NVDA | MJP | 2009-01-06 | DDM | 4518.07 | RIDF Loan 25 crore & above | LA ,EW,masnry main more than 76% LA Ew Msnry ling of distri mor than 76% completed. Minors and sub minors LA,EW,MSnry more than 76% completed ,lining 51-75% complTOR La Se dis COR lAEw Records NM Board displ
8 | R082000002 | NARMADA RIVER - 1/8 | Mandla | PWD | Bridge | 2008-12-12 | DDM | 364.66 | RIDF Loan upto 10 crore | Foundation, pier(22) nos,abut, super more than 76% completed. Approach Road is yet to be laid.Absence of hard rock in riverbed led to change in design of 3 piers. Contracto's dispute with the dept delayed. Time overrun by 2-3 years. NAB assist displayed
8 | R082000070 | Bageri | Dhar | WRD | MIS | 2008-12-06 | DDM | 966.44 | RIDF Loan upto 10 crore | Main canal and CD works 51-75% complete. Tim eover run Due to failure of contractor, new contractor is instated work will be completed by Dec 08. Cost orr La cost, extar item and debitable tender Assitance displayed Aqueduct 4170m t05325m to be tested
8 | R082000118 | Bargolia Tank | Rajgarh | WRD | MIS | 2008-12-04 | DDM | 723.56 | RIDF Loan upto 10 crore | Head work, spill way, Fhead regulator >765 completed, main canal and CD 51-75% Time overrun LA, tech sanctionCost or incre in cost oof LA for canal.No visit by Se tests done records maintainecd no board.
8 | R082000107 | Extension of Tawa LBC | Harda | WRD | MJP | 2008-12-02 | DDM | 2345.95 | RIDF Loan 10.01-24.99 crore | Minor and sub minor upto 25% CD works 26-50% distributaries,HR, minors more than 76% completed COr revised estimates, TOR due to LA Silting in canal 0 t 57 chg.Lining of canal to prvt slippage board stolen tssts done visited by Sr Eng
8 | R082000081 | RABS-Balkhedi Tail Minor | Jabalpur | NVDA | MJP | 2008-11-10 | DDM | 761.26 | RIDF Loan upto 10 crore | Time nover run due to increase in LA Cost escalation due to incease in number of structures .Visit records not shown tests carried out and records maintained. NABARD assistance not displayed. Poor maintenance of canals
8 | R082000080 | RABS-Pipariya SD | Jabalpur | NVDA | MJP | 2008-11-08 | DDM | 1646.5 | RIDF Loan 10.01-24.99 crore | Time oveerun due to delay in LA. Cost escalation due to increase in number of structureas on sub distributary.No follow up by NVDA. Quality tests carried out. Records maintained.EW at 0.8-1.6 Km incomplete.Poor maint Astace not displayed
8 | R082000121 | Surgi Distributory | Narsinghpur | NVDA | MJP | 2008-09-30 | RO Officer | 1422.73 | RIDF Loan 10.01-24.99 crore | Time over run; Actual expenditure is Rs.1604.02Lakh ;Distributray work almosdt complete;30m work at railway crossing to be completed;NVDA Technical staff carried out quality tests;problems-land acquisition high court stay order
8 | R082000123 | Andia Distributory | Narsinghpur | NVDA | MJP | 2008-09-29 | RO Officer | 1029.69 | RIDF Loan 10.01-24.99 crore | Time over run; work of distributary complete Actual exp Rs.1140.70 Lakh; Adequate technical staff for NVDA to take care of quality test;Problems- Land acquisition High court stayl;work at 12.4Km railway crosing yet to be done;NAB disp board not install
8 | R082000054 | Rabs-Lbc From Km 97 To 111 | Narsinghpur | NVDA | MJP | 2008-09-29 | RO Officer | 2414.1 | RIDF Loan 10.01-24.99 crore | Time over run; Actual expe Rs.2049.48 Lakh;Main canal work almost complete; quality tests conducted problems- land acquisitiopn ;high court stay order;work at NH6 106m to be completed; NAB bord not displayed
8 | R082000055 | Navalpura | Khargone | WRD | MIS | 2008-09-09 | DDM | 634.31 | RIDF Loan upto 10 crore | Headwotrks ,spill ways, Head Regulator100%Main canal 90% ;Branch canal,minors and cross drainage >75% Lining of canal 25% Sought extension upto 31 Mar 09 Time over run -delay in land acquisition;Engineers monitor quality control test;NABARD board display
8 | R082000053 | Rabs-Lbc From Km 84 To 97 | Narsinghpur | NVDA | MJP | 2008-06-19 | DDM | 3782.63 | RIDF Loan 25 crore & above | Field visits by engineers are not documented.Test records are not maintained.NABARD assistance not displayed. Though major work in canal,distributaries minors sub-minors completed, CADA work has been neglected.
8 | R082000133 | Upper Beda | Khargone | NVDA | MIP | 2008-06-06 | DDM | 8032.42 | RIDF Loan 25 crore & above | Time overrun opposition oustees under NBA Cost overrun change in compensation values of land.Quality control tests are conducted and records maintained. Head work by june 08 Canal work in 2 years.Due to closure of VIII trAIBP fund.SG wants RIDF 10%AIB
8 | R082000120 | Bhadgawan Branch Canal | Narsinghpur | NVDA | MJP | 2008-05-14 | DDM | 4518.07 | RIDF Loan 25 crore & above | Time overrun -delay in land acquisition, shifting of electric poldes,Constrcution of bridge across railway line;Cost overrun -increase in rate of earth work. Though work in main canal is over, farmers are not benefited due to non- execution of CADA
8 | r082000126 | Satkinala | Chhindwara | WRD | MIS | 2008-03-03 | Chindwara DDM | 519.91 | RIDF Loan upto 10 crore | NABARD board is displayed. Project has been completed. PCR to be submitted.
8 | r082000016 | Bilidar | Khargone | WRD | MIS | 2008-02-29 | Khargone DDM | 109.2 | RIDF Loan upto 10 crore | PCR VERIFICATION. The physical and financial details are found to be correct. Seepages have been observed in canal due to permeable strata which needs lining at some places. PCR to be accepted.
8 | r082000133 | Upper Beda | Khargone | NVDA | MIP | 2008-01-29 | Khargone DDM | 8032.42 | RIDF Loan 25 crore & above | NABARD board displayed. Records maintained. The canal work is expected to start very soon and will be completed in 2 years period.
8 | r082000053 | Rabs-Lbc From Km 84 To 97 | Narsinghpur | NVDA | MJP | 2007-12-18 | Narsinghpur DDM | 3782.63 | RIDF Loan 25 crore & above | The major bottleneck is construction of two CDs in the main canal. The work progress is very slow because of the contractor. NABARD board has been displayed.
8 | r082000002 | NARMADA RIVER - 1/8 | Mandla | PWD | Bridge | 2007-12-15 | Mandla DDM | 364.66 | RIDF Loan upto 10 crore | In the board ASSISTED BY NABARD is missing. Dispute with contractors in bridge project. Foundation level surveys through experts/latest technology not used.
8 | r082000081 | RABS-Balkhedi Tail Minor | Jabalpur | NVDA | MJP | 2007-12-14 | Jabalpur DDM | 761.26 | RIDF Loan upto 10 crore | NABARD board not displayed. Cleaning of the canal and maintenance has become necessary. No records are available at project site.
8 | R082000080 | RABS-Pipariya SD | Jabalpur | NVDA | MJP | 2007-12-14 | Jabalpur DDM | 1646.5 | RIDF Loan 10.01-24.99 crore | NABARD board not displayed. Cracks at some places of the lining. Cleaning of canal to be done at regular intervals. WUA has been formed but not functioning. No maintenance of distributory.
8 | r082000118 | Bargolia Tank | Rajgarh | WRD | MIS | 2007-11-30 | Shajapur DDM | 723.56 | RIDF Loan upto 10 crore | Only the head work was complete. Construction of canal has not begun. Cost overrun. Site to be heavily guarded. NABARD board has not been displayed.
8 | R082000118 | Bargolia Tank | Rajgarh | WRD | MIS | 2007-11-30 | Shajapur DDM | 723.56 | RIDF Loan upto 10 crore | Slow progress. delay in according technical sanction, delay in land acquisition of land, delay in tendering, delay in fixing agency for canal work, NABARD board not displayed, SE/CE not visited to monitor the work, watch & ward to guard the site.
8 | r082000070 | Bageri | Dhar | WRD | MIS | 2007-09-28 | Dhar DDM | 966.44 | RIDF Loan upto 10 crore | NABARD BOARD has been displayed.
8 | r082000132 | Simrol No. 1 | Shajapur | WRD | MIS | 2007-06-26 | Shajapur DDM | 289.02 | RIDF Loan upto 10 crore | The project has been completed and PCRto be submitted. NABARD board to be erected at prominent place.
8 | r082000107 | Extension of Tawa LBC | Harda | WRD | MJP | 2007-06-22 | Hoshangabad DDM | 2345.95 | RIDF Loan 10.01-24.99 crore | NABARD board has been displayed. There was bottleneck in land acquisition which has been completed in main canals and some is remaining in minors.
8 | r082000021 | Upper Jamla | Khargone | WRD | MIS | 2007-06-15 | Khargone DDM | 35.98 | RIDF Loan upto 10 crore | The contractor could not execute the construction work on time. NABARD board has been displayed. Headwork has been completed. The canal work has not been executed.
8 | r082000113 | Ruplaziri Tank | Khargone | WRD | MIS | 2007-06-11 | Khargone DDM | 62.75 | RIDF Loan upto 10 crore | Delay in land acquisition.NABARD board has been displayed.
8 | r082000120 | Bhadgawan Branch Canal | Narsinghpur | NVDA | MJP | 2007-06-01 | Narsinghpur DDM | 4518.07 | RIDF Loan 25 crore & above | NABARD board has been displayed. Delay in land acquisition. Shifting of poles in the bed/on the bank of canal/distribution/minor by MPSEB.
8 | r082000122 | Kandeli Distributory | Narsinghpur | NVDA | MJP | 2007-05-24 | Narsinghpur DDM | 1547.66 | RIDF Loan 10.01-24.99 crore | The lining of the canal damaged. Bushes and trees have grown in canal. There is large scale silting in the canal. Minor at 3.6 as per design a VRB is to be provided instead a syphon like structure is reportedly constructed.
8 | r082000121 | Surgi Distributory | Narsinghpur | NVDA | MJP | 2007-05-23 | Narsinghpur DDM | 1422.73 | RIDF Loan 10.01-24.99 crore | NABARD board has not been displayed. The lining of the canal has been damaged at several places. There is large scale silting in the canal. Bushes and trees have grown in the canal. There is need for making the canal operational.
8 | r082000123 | Andia Distributory | Narsinghpur | NVDA | MJP | 2007-05-21 | Narsinghpur DDM | 1029.69 | RIDF Loan 10.01-24.99 crore | NABARD board has been displayed. The lining of the canal has been damaged at several places. There is large scale silting in the canal. Bushes and trees have grown in the canale. There is need for making the canal operational.
8 | r082000110 | Bhainsakhedi Tank | Dewas | WRD | MIS | 2007-05-18 | Dewas DDM | 321.94 | RIDF Loan upto 10 crore | Delay in LA. Delay in passing the tender of work related to canal etc. Visit by officials to the site is very rare. 76% of Work is completed in headway, spillways and headregulator. Canal work yet to begin. NABARD board has not been displayed.
8 | r082000054 | Rabs-Lbc From Km 97 To 111 | Narsinghpur | NVDA | MJP | 2007-05-18 | Narsinghpur DDM | 2414.1 | RIDF Loan 10.01-24.99 crore | Delay in construction of two CDs. NABARD board has not been displayed.
8 | r082000053 | Rabs-Lbc From Km 84 To 97 | Narsinghpur | NVDA | MJP | 2007-05-11 | Narsinghpur DDM | 3782.63 | RIDF Loan 25 crore & above | The major bottle neck has been delay in construction of two CDS in the main canal. The delay is attributed to the very slow progress on the part of the contractor. NABARD board has been displayed.
8 | r082000108 | Jaliyapani Tank | Badwani | WRD | MIS | 2007-05-08 | Khargone DDM | 377.83 | RIDF Loan upto 10 crore | Time and cost overrun, agitation by Adiwasi Mukti Sanghatan, LA problem. NABARD board has been displayed. Monitoring is being done regularly. Due to delay in land acquisition another six months time may be required to complete the project.
8 | r082000018 | Basantpura | Khargone | WRD | MIS | 2007-04-11 | Khargone DDM | 376.03 | RIDF Loan upto 10 crore | Forest clearance is awaited. NABARD board has been displayed. The nala closure work is stopped for last one year. To be expedited.
8 | r082000073 | Chandanpura | Khargone | WRD | MIS | 2007-04-10 | Khargone DDM | 334.21 | RIDF Loan upto 10 crore | Project work is completed. NABARD board has been displayed. All records are maintained.
8 | r082000055 | Navalpura | Khargone | WRD | MIS | 2007-04-05 | Khargone DDM | 634.31 | RIDF Loan upto 10 crore | There was delay in land acquisition and forest clearance. NABARD board has been displayed. All records are maintained at site.
8 | r082000133 | Upper Beda | Khargone | NVDA | MIP | 2007-04-03 | Khargone DDM | 8032.42 | RIDF Loan 25 crore & above | NABARD board has been displayed. The records for various tests conducted are maintained.
8 | r082000004 | RAILWAY BRIDGE NO.- 193 - 1/2 KM | Ratlam | PWD | Bridge | 2007-03-21 | Ratlam DDM | 343.89 | RIDF Loan upto 10 crore | More than 76% of work has been completed. NABARD board has been displayed. The progress is very slow. Because of little work to be completed on both the sides of the bridge it has not been opened for public.
8 | r082000107 | Extension of Tawa LBC | Harda | WRD | MJP | 2007-02-15 | Hoshangabad DDM | 2345.95 | RIDF Loan 10.01-24.99 crore | Due to delay in land acquisition the construction of distributory and minors are held up. Canal gate at zero chainage HR/CR on both sides are still to be constructed. It appears that the project will not be completed within the sanctioned period.
8 | r082000087 | Parron nalla 13/8 | Datia | PWD | Bridge | 2007-02-08 | Gwalior DDM | 62.86 | RIDF Loan upto 10 crore | Project completed in Dec-2005. Board not displayed. Railing on both the sides not provided. The earth on both the sides of the bridge has been flown away with rain water and the spot has become accident prone. Immediate attention to be paid.
8 | r082000087 | Parron nalla 13/8 | Datia | PWD | Bridge | 2007-02-08 | Gwalior DDM | 62.86 | RIDF Loan upto 10 crore | Work completed. Railings not provided as the structure is submersible. Earth on both the sides has flown away forming huge pits. The spot has become accident prone.
8 | R082000057 | Paramhansi | Narsinghpur | WRD | MIS | 2007-02-07 | Narsinghpur DDM | 107.51 | RIDF Loan upto 10 crore | NABARD board has not been displayed. Land acquisition work delayed due to non-cooperation of cultivators.
8 | r082000119 | Amanala Tank | Seoni | WRD | MIS | 2007-01-22 | Chindwara DDM | 222.81 | RIDF Loan upto 10 crore | PCR VERIFICATION. The farmers have expressed satisfaction over construction of dam. WUA formed and is functioning properly. The overall utilisation is 100%. Quality of crops has improved and farmers are also planning diversification of crops.
8 | r082000130 | Lohara | Chhindwara | WRD | MIS | 2007-01-22 | Chindwara DDM | 326.06 | RIDF Loan upto 10 crore | Project has been completed. EE has visited the project regularly during construction period. Site order book has been maintained. NABARD board has been displayed.
8 | r082000129 | Dhadgawan Branch | Chhindwara | WRD | MIS | 2007-01-22 | Chindwara DDM | 195.42 | RIDF Loan upto 10 crore | Major portion (above 76%) of the project has been completed. EE has visited the project during construction period. Site order book has been maintained. NABARD board has been displayed.
8 | r082000131 | Khairipaika | Chhindwara | WRD | MIS | 2007-01-19 | Chindwara DDM | 183.99 | RIDF Loan upto 10 crore | Project has been completed. EE has visited the project frequently during construction period. Site order book has been maintained. NABARD board has been displayed.
8 | r082000128 | Mohkhedi | Chhindwara | WRD | MIS | 2007-01-19 | Chindwara DDM | 436 | RIDF Loan upto 10 crore | Head work has been completed. EE has visited the site frequently. Contractors problem. Site book maintained at site. NABARD board has been displayed.
8 | r082000079 | Rudaheda | Ujjain | WRD | MIS | 2007-01-17 | Ujjain DDM | 338.35 | RIDF Loan upto 10 crore | NABARD board has not been displayed. On account of breach of bund in the nala portion a department enquiry is in progress.
8 | r082000118 | Bargolia Tank | Rajgarh | WRD | MIS | 2007-01-12 | Shajapur DDM | 723.56 | RIDF Loan upto 10 crore | Slow progress, delay in LA, delay in tendering, delay in fixing agency for canal work. There will be time overrun and cost overrun. SE/CE concerned has not visited the site to monitor the project. NABARD board has not been displayed.
8 | r082000070 | Bageri | Dhar | WRD | MIS | 2007-01-12 | Dhar DDM | 966.44 | RIDF Loan upto 10 crore | NABARD board has been displayed. WUA has not been formed. The ground water table has improved. The project is very useful to the villagers and it will provide irrigation facility to 6 villages.
8 | r082000120 | Bhadgawan Branch Canal | Narsinghpur | NVDA | MJP | 2007-01-09 | Narsinghpur DDM | 4518.07 | RIDF Loan 25 crore & above | Slow work pace. The work relating to earthwork of minors in machchwara, supla, pipria and Rani pindarai villages is held up on account of complications viz., lack of title deeds, dispute of share in property, compensation, land acquisition process etc.
8 | R082000125 | Ghoghra | Chhindwara | WRD | MIS | 2007-01-05 | Chindwara DDM | 251.56 | RIDF Loan upto 10 crore | NABARD board has been displayed. Project has been comploeted. The project has been visited by CE and EE and SDO visit on regular basis.
8 | r082000127 | Sakarwara | Chhindwara | WRD | MIS | 2007-01-05 | Chindwara DDM | 521.3 | RIDF Loan upto 10 crore | NABARD board has been displayed. The overall progress is satisfactory.
8 | r082000040 | Kotma S/s | Shahdol | MPSEB | Power | 2007-01-03 | Shahdol DDM | 369.7 | RIDF Loan upto 10 crore | PCR VERIFICATION. The DDM has done PCR verification of the above project.
8 | R082000067 | Deopur-Mugalsarai | Vidisha | PWD | Road | 2006-12-14 | Vidisha DDM | 296.32 | RIDF Loan upto 10 crore | The quality of work appeared to be satisfactory except some minor defects like shrinking of shoulders due to wild plants/shrubs, cutting of edges of carriage way at a few placed etc. The width of the road is inadequate.
8 | r082000053 | Rabs-Lbc From Km 84 To 97 | Narsinghpur | NVDA | MJP | 2006-11-30 | Narsinghpur DDM | 3782.63 | RIDF Loan 25 crore & above | Very slow progress.
8 | r082000054 | Rabs-Lbc From Km 97 To 111 | Narsinghpur | NVDA | MJP | 2006-11-28 | Narsinghpur DDM | 2414.1 | RIDF Loan 10.01-24.99 crore | Work is in progress. The project is likely to be completed by March 2007.
8 | R082000010 | Mahavir Pavitra Sarovar(Dhamela) | Dhar | WRD | MIS | 2006-11-16 | Dhar DDM | 458.6 | RIDF Loan upto 10 crore | Quality of work is good. NABARD board not found. The project will be useful and it will provide irrigation facility to 3 villages. The ground water level has also increased in the surrounding areas.
8 | r082000071 | Govindpura | Dhar | WRD | MIS | 2006-11-16 | Dhar DDM | 541.27 | RIDF Loan upto 10 crore | Quality of work is good. The project is good and it will provide irrigation facility to 5 villages. The ground water table in the surrounding area has improved. NABARD board not displayed.
8 | r082000046 | Umaria S/s | Umaria | MPSEB | Power | 2006-11-15 | Shahdol DDM | 309.7 | RIDF Loan upto 10 crore | Work has been completed. Quality of work is good. NABARD board has been displayed.
8 | r082000002 | NARMADA RIVER - 1/8 | Mandla | PWD | Bridge | 2006-11-10 | Mandla DDM | 364.66 | RIDF Loan upto 10 crore | Work is in progress. Approval of revised designs for remaining 4 spans to be expedited and forest clearance for approach road to be vigorously pursued.
8 | r082000100 | Tallar 1/4 | Shajapur | PWD | Bridge | 2006-11-09 | Shajapur DDM | 49.85 | RIDF Loan upto 10 crore | Approaches of about 250 mtres and 200 mtrs on its two sides remained incomplete. They require metal coat and black topping. NABARD board has not been displayed. The dept. should finish the work before the date of closure of the tranche VIII.
8 | R082000103 | Narkuin 7/10 | Sidhi | PWD | Bridge | 2006-10-29 | Rewa DDM | 60.77 | RIDF Loan upto 10 crore | NABARD board not displayed. Work appears to be okay. No visits are being made by officers above the rank of EE. Maintenance/repairs work to be done.
8 | r082000102 | Jokaha 17/6 | Sidhi | PWD | Bridge | 2006-10-29 | Rewa DDM | 48.28 | RIDF Loan upto 10 crore | NABARD board not displayed. Work in progress. Quality appears to be okay. Dept. may speed up the work.
8 | R082000082 | Sarrathi 2/8 | Balaghat | PWD | Bridge | 2006-10-18 | OIC | 114.14 | RIDF Loan upto 10 crore | Distance between villages has been reduced by 10 km. 21 villages connected. NABARD board displayed. Quality of work satisfactory.
8 | R082000082 | Sarrathi 2/8 | Balaghat | PWD | Bridge | 2006-10-17 | Balaghat DDM | 114.14 | RIDF Loan upto 10 crore | Project already completed. NABARD board displayed. Quality of work satisfactory. Distance between Khari and Kharghat villages has been reduced by 10 kms. 21 villages benefited.
8 | R082000110 | Bhainsakhedi Tank | Dewas | WRD | MIS | 2006-10-09 | Dewas DDM | 321.94 | RIDF Loan upto 10 crore | The project is yet to be completed. Water committee will be formed after the completion of the project. Water recharge level has increased in the villages. Canal work yet to be started. Tenders yet to be passed. NB board not displayed.
8 | R082000069 | Chhayanmaina | Dewas | WRD | MIS | 2006-10-09 | Dewas DDM | 157.28 | RIDF Loan upto 10 crore | The project is yet to be completed. Water committee will be formed after the completion of the project. Water recharge level has increased in the villages. Canal work yet to be started.
8 | R082000068 | Orni | Dewas | WRD | MIS | 2006-10-09 | Dewas DDM | 123.99 | RIDF Loan upto 10 crore | The project is yet to be completed. Water committee will be formed after the completion of the project. Water recharge level has increased in the villages. Canal work yet to be started. NB board not displayed.
8 | r082000095 | Gangli 51/10 | Neemuch | PWD | Bridge | 2006-06-06 | Mandsaur DDM | 88 | RIDF Loan upto 10 crore | Bridge is yet to be completed. NABARD board not displayed.
8 | R082000104 | Kharri 3/10 | Sidhi | PWD | Bridge | 2006-06-06 | Rewa DDM | 49.21 | RIDF Loan upto 10 crore | Progress is very slow. There is contractor problem. NABARD board has not been displayed. The work is already delayed and requires to be completed at the earliest.
8 | r082000011 | Chhapri | Jhabua | WRD | MIS | 2006-05-26 | Jhabua DDM | 75.16 | RIDF Loan upto 10 crore | Project completed. NABARD board is displayed very far from the site. As per discussions with the Engineer completion of the project is doubtful.
8 | R082000057 | Paramhansi | Narsinghpur | WRD | MIS | 2006-05-19 | Narsinghpur DDM | 107.51 | RIDF Loan upto 10 crore | NABARD board not displayed.
8 | r082000022 | Richhai | Narsinghpur | WRD | MIS | 2006-05-18 | Narsinghpur DDM | 365.87 | RIDF Loan upto 10 crore | NABARD board not displayed.
8 | R082000053 | Rabs-Lbc From Km 84 To 97 | Narsinghpur | NVDA | MJP | 2006-05-10 | Narsinghpur DDM | 3782.63 | RIDF Loan 25 crore & above | Structures are getting damaged and degenerated due to non-use. Work should be expedited. Implementation is reportedly very poor.
8 | r082000122 | Kandeli Distributory | Narsinghpur | NVDA | MJP | 2006-05-05 | Narsinghpur DDM | 1547.66 | RIDF Loan 10.01-24.99 crore | NABARD board displayed at few places. Dept. should take effective steps to expedite the work.
8 | R082000123 | Andia Distributory | Narsinghpur | NVDA | MJP | 2006-04-27 | Narsinghpur DDM | 1029.69 | RIDF Loan 10.01-24.99 crore | NABARD board displayed at few places. Progress is very slow.
8 | R082000121 | Surgi Distributory | Narsinghpur | NVDA | MJP | 2006-04-25 | Narsinghpur DDM | 1422.73 | RIDF Loan 10.01-24.99 crore | Work needs to be speeded up. NABARD board not displayed.
8 | R082000054 | Rabs-Lbc From Km 97 To 111 | Narsinghpur | NVDA | MJP | 2006-04-24 | Narsinghpur DDM | 2414.1 | RIDF Loan 10.01-24.99 crore | Work order not issued. NABARD board displayed at some places but should be painted.
8 | r082000094 | Tumbar 11/6 | Mandsaur | PWD | Bridge | 2006-04-13 | Mandsaur DDM | 48.47 | RIDF Loan upto 10 crore | Land acquisition problem, NABARD board not displayed.
8 | r082000033 | Tap on Satna-Rewa | Satna | MPSEB | Power | 2006-04-03 | Satna DDM | 10.32 | RIDF Loan upto 10 crore | PCR Verification. The bridge has provided connectivity to 33 surrounding villages benefitting 0.56 lakh people. The villages are connected by a good all weather road. NABARD board not displayed.
8 | R082000039 | Sironj S/s | Vidisha | MPSEB | Power | 2006-03-29 | DDM | 294.7 | RIDF Loan upto 10 crore | PCR verified. Project is complete in all respects.
8 | R082000049 | Basoda S/s | Vidisha | MPSEB | Power | 2006-03-29 | DDM | 309.7 | RIDF Loan upto 10 crore | PCR verified. Project is complete in all respects.
8 | R082000082 | Sarrathi 2/8 | Balaghat | PWD | Bridge | 2006-03-25 | DDM | 114.14 | RIDF Loan upto 10 crore | Project completed. PCR submitted. NABARD board not displayed.
8 | R082000119 | Amanala Tank | Seoni | WRD | MIS | 2006-03-10 | DDM | 222.81 | RIDF Loan upto 10 crore | Project completed.
8 | R082000108 | Jaliyapani Tank | Badwani | WRD | MIS | 2006-03-09 | Khargone DDM | 377.83 | RIDF Loan upto 10 crore | Work of main structure completed. Work was stopped for one year due to interruption of Adiwasi Mukti Sangathan. Now the problem is sorted out and work is progressing.
8 | R082000086 | Sapra 2/8 | Chhindwara | PWD | Bridge | 2006-03-08 | DDM | 48.04 | RIDF Loan upto 10 crore | Project is complete. NABARD board not displayed.
8 | R082000048 | Garoth S/s | Mandsaur | MPSEB | Power | 2006-03-03 | DDM | 369.7 | RIDF Loan upto 10 crore | PCR verified. Project complete in all respects.
8 | R082000046 | Umaria S/s | Umaria | MPSEB | Power | 2006-03-02 | DDM | 309.7 | RIDF Loan upto 10 crore | Civil work and structures completed upto 85%. There is delay due to untimely supply of material.
8 | R082000046 | Umaria S/s | Umaria | MPSEB | Power | 2006-03-02 | OIC | 309.7 | RIDF Loan upto 10 crore | Civil works completed in all respects. Installation of transformer bays in progress. Project is likely to be completed by March 2006.
8 | R082000009 | Dhamariya | Badwani | WRD | MIS | 2006-03-01 | DDM | 57.79 | RIDF Loan upto 10 crore | RA
8 | R082000009 | Dhamariya | Badwani | WRD | MIS | 2006-02-28 | DDM | 57.79 | RIDF Loan upto 10 crore | Headwork completed. Project likely to be completed by June 2006. There is problem in land acquisition under canal work.
8 | R082000132 | Simrol No. 1 | Shajapur | WRD | MIS | 2006-02-18 | DDM | 289.02 | RIDF Loan upto 10 crore | Slow work progress. NB board not displayed.
8 | R082000117 | Hanmantiya Tank | Mandsaur | WRD | MIS | 2006-02-08 | DDM | 103.84 | RIDF Loan upto 10 crore | Head works completed. In Unit II Canals, progress is slow on account of delay in completion of LA.
8 | R082000045 | Katangi S/s | Balaghat | MPSEB | Power | 2006-02-07 | DDM | 309.7 | RIDF Loan upto 10 crore | Sub station is completed in all respects. Improvement in the quality of power supply in the areas serviced by the sub-station reported.
8 | r082000098 | Semarwai 7/6 | Satna | PWD | Bridge | 2006-01-18 | DDM | 53.57 | RIDF Loan upto 10 crore | About 60% work completed in foundation and substructure. Work is in progress and the project is likely to be completed by June 2006.
8 | r082000057 | Paramhansi | Narsinghpur | WRD | MIS | 2005-12-27 | DDM | 107.51 | RIDF Loan upto 10 crore | Headworks completed. LBC completed upto 90% and RBC is completed upto 10%. Likely to be completed by June 2006.
8 | r082000022 | Richhai | Narsinghpur | WRD | MIS | 2005-12-26 | DDM | 365.87 | RIDF Loan upto 10 crore | Work is in progress. 25 out of 83 structures on the canal are completed. Likely to be completed by March 2006.
8 | r082000092 | Kaveri 6/10 | Khandwa | PWD | Bridge | 2005-12-17 | DDM | 69.58 | RIDF Loan upto 10 crore | Project is completed.
8 | r082000123 | Andia Distributory | Narsinghpur | NVDA | MJP | 2005-12-14 | DDM | 1029.69 | RIDF Loan 10.01-24.99 crore | Progress is hampered due to prolonged monsoon. Work is in progress.
8 | r082000111 | Bandhi Tank | Jabalpur | WRD | MIS | 2005-12-14 | DDM | 138.44 | RIDF Loan upto 10 crore | Work is in progress
8 | r082000044 | Lakhnadaun S/s | Seoni | MPSEB | Power | 2005-12-13 | DDM | 369.7 | RIDF Loan upto 10 crore | Project visited by DDM, Chhindwara. Project completed in May 2003. Improvement in the quality of power supply observed.
8 | R082000088 | Kukshi 6/16 | Dhar | PWD | Bridge | 2005-12-13 | DDM | 136.11 | RIDF Loan upto 10 crore | Work is completed. PCR is yet to be submitted. Quality of works is satisfactory. NABARD board not displayed.
8 | R082000004 | RAILWAY BRIDGE NO.- 193 - 1/2 KM | Ratlam | PWD | Bridge | 2005-12-09 | DDM | 343.89 | RIDF Loan upto 10 crore | Work completed in foundation & substructure. Work is in progress in respect of super structure. Quality of works is satisfactory.
8 | R082000122 | Kandeli Distributory | Narsinghpur | NVDA | MJP | 2005-12-08 | DDM | 1547.66 | RIDF Loan 10.01-24.99 crore | Pace of implementation is poor. Tenders have been finalised. Work delayed due to monsoon.
8 | r082000121 | Surgi Distributory | Narsinghpur | NVDA | MJP | 2005-12-02 | DDM | 1422.73 | RIDF Loan 10.01-24.99 crore | Work is in progress at RS 11.4 to RD 12 KM.
8 | R082000072 | Mohana | Indore | WRD | MIS | 2005-11-30 | DDM | 68.34 | RIDF Loan upto 10 crore | (1) Project is completed (2) Irrigation provided to 27 ha during last season (3) WUA is yet to be formed
8 | R082000109 | Khamthi Tank | Chhindwara | WRD | MIS | 2005-11-24 | DDM | 94.15 | RIDF Loan upto 10 crore | 1. Work is completed. 2. WUA not yet formed.
8 | R082000043 | Amarwada S/s | Chhindwara | MPSEB | Power | 2005-11-16 | DDM | 369.7 | RIDF Loan upto 10 crore | 1. Work is complete in all respects.
8 | R082000120 | Bhadgawan Branch Canal | Narsinghpur | NVDA | MJP | 2005-11-10 | DDM | 4518.07 | RIDF Loan 25 crore & above | Work is in progress and the project is likely to be completed by March 2006
8 | R082000053 | Rabs-Lbc From Km 84 To 97 | Narsinghpur | NVDA | MJP | 2005-11-09 | DDM | 3782.63 | RIDF Loan 25 crore & above | The portion of canal falling between RD 85.43 to 86.055 km and RD 87.9 to 88.11 km requires removal of hardrock. As blasting is being opposed by the residents re-tendering may be required for this work. NABARD Board not displayed.
8 | R082000046 | Umaria S/s | Umaria | MPSEB | Power | 2005-10-01 | DDM | 309.7 | RIDF Loan upto 10 crore | The progress of work is slow as the phasing of the project was for 2 years i.e., 2002-03 and 2003-04. NABARD Board has not been displayed. MPEB is required to take steps to complete the project early ( within 6 months ).
8 | R082000094 | Tumbar 11/6 | Mandsaur | PWD | Bridge | 2005-10-01 | DDM | 48.47 | RIDF Loan upto 10 crore | 1. Project is completed in all respects. 2. NABARD Board is not displayed
8 | R082000045 | Katangi S/s | Balaghat | MPSEB | Power | 2005-09-30 | DDM | 309.7 | RIDF Loan upto 10 crore | Report yet to be submitted.
8 | r082000045 | Katangi S/s | Balaghat | MPSEB | Power | 2005-09-30 | DDM | 309.7 | RIDF Loan upto 10 crore | Improvement in power supply in the substation found. Project is completed.
8 | R082000010 | Mahavir Pavitra Sarovar(Dhamela) | Dhar | WRD | MIS | 2005-09-27 | DDM | 458.6 | RIDF Loan upto 10 crore | 1. Project is completed. 2. Scattered material from cut-off dumped at RD 1300 m need be removed
8 | R082000071 | Govindpura | Dhar | WRD | MIS | 2005-09-27 | DDM | 541.27 | RIDF Loan upto 10 crore | 1. Project is nearing completion. 2. Out of 7.5 km right bank canal 6.5 km has been constructured.
8 | R082000073 | Chandanpura | Khargone | WRD | MIS | 2005-09-01 | OIC+RO Officials | 334.21 | RIDF Loan upto 10 crore | Unit-I comprising of Head work of the project and Unit-II-Canals alignment and exacavation are almost complete. Out of 33 structures proposed in canals 8 structures have been completed. Work on the remaining structures is in progress.
8 | R082000002 | NARMADA RIVER - 1/8 | Mandla | PWD | Bridge | 2005-07-01 | DDM | 364.66 | RIDF Loan upto 10 crore | The work is in progress. Likely date of completion of the project is June 2006.
8 | R082000054 | Rabs-Lbc From Km 97 To 111 | Narsinghpur | NVDA | MJP | 2005-06-29 | DDM | 2414.1 | RIDF Loan 10.01-24.99 crore | The canal cuts through National Highway No.26 and a bridge is to be built over the canal. The approval for desilgn of the bridge is waited frokm the National Highway Authority (NHA). 7 MPEB electrical poles in the area of canal are yet to be shifted.
8 | R082000021 | Upper Jamla | Khargone | WRD | MIS | 2005-06-25 | DDM | 35.98 | RIDF Loan upto 10 crore | The progress of work is satisfactory. The project work is likely to be completed by 30.06.2005.
8 | r082000021 | Upper Jamla | Khargone | WRD | MIS | 2005-06-25 | DDM | 35.98 | RIDF Loan upto 10 crore | Head work is almost completed and canal works are under progress. Progress in implementation is satisfactory.
8 | R082000068 | Orni | Dewas | WRD | MIS | 2005-06-22 | OIC | 123.99 | RIDF Loan upto 10 crore | Headwork has been completed. Farmers are benefitting through sluice and percolation of water. Canal work is going to be completed by next year.
8 | R082000069 | Chhayanmaina | Dewas | WRD | MIS | 2005-06-22 | OIC | 157.28 | RIDF Loan upto 10 crore | Project is going to be completed by March 2006. Headworks has been completed.
8 | r082000068 | Orni | Dewas | WRD | MIS | 2005-06-22 | DDM | 123.99 | RIDF Loan upto 10 crore | Project visited alongwith CGM. Project is likely to be completed by March 2006.
8 | r082000069 | Chhayanmaina | Dewas | WRD | MIS | 2005-06-22 | DDM | 157.28 | RIDF Loan upto 10 crore | Project visited along with CGM. Project is likely to be completed by March 2006.
8 | R082000095 | Gangli 51/10 | Neemuch | PWD | Bridge | 2005-06-16 | DDM | 88 | RIDF Loan upto 10 crore | The quality of is satisfactory. NABARD baord is yet to be displayed. The project is yet to be completed which is expected to be completed by the end of June 2005
8 | R082000025 | Marhikheda-Karera DCDS Line | Jabalpur | MPSEB | Power | 2005-05-18 | DDM | 608.46 | RIDF Loan upto 10 crore | Overall progress is satisfactory and NABARD board is displayed.
8 | R082000067 | Deopur-Mugalsarai | Vidisha | PWD | Road | 2005-04-13 | DDM | 296.32 | RIDF Loan upto 10 crore | Progress is slow. Presently no work is going on at the site in absence of labour since holi festival.
8 | R082000066 | 33/11 KV Sub-Station(MVA) | Ujjain | MPSEB | Power | 2005-04-01 | DDM | 1400.77 | RIDF Loan 10.01-24.99 crore | Visited by DDM Dewas. Bairagarh S/s-completed on 31-5-02 Expenditure 43.73 Lakh. Donta S/s-completed on 22-4-01 Expenditure 6.38 Lakh. Enabad S/s-completed in 2002 Expenditure 24.70 Lakh. Panda jangir S/s- completed on 30-5-02 Expenditure 59.47 Lakh.
8 | r082000066 | 33/11 KV Sub-Station(MVA) | Ujjain | MPSEB | Power | 2005-04-01 | DDM | 1400.77 | RIDF Loan 10.01-24.99 crore | Donta Sub-station visited. Work completed on 22 April 2001.
8 | r082000066 | 33/11 KV Sub-Station(MVA) | Ujjain | MPSEB | Power | 2005-04-01 | DDM | 1400.77 | RIDF Loan 10.01-24.99 crore | Anabad Sub-station visited. Work completed in 2002.
8 | r082000066 | 33/11 KV Sub-Station(MVA) | Ujjain | MPSEB | Power | 2005-04-01 | DDM | 1400.77 | RIDF Loan 10.01-24.99 crore | Panda Jagir Sub-station visited. Work completed on 30 May 2002.
8 | R082000004 | RAILWAY BRIDGE NO.- 193 - 1/2 KM | Ratlam | PWD | Bridge | 2005-03-24 | DDM | 343.89 | RIDF Loan upto 10 crore | The work is in progress and likely to be completed by june 05.
8 | R082000019 | Gawlan | Khargone | WRD | MIS | 2005-03-22 | DDM | 584.29 | RIDF Loan upto 10 crore | Report yet to be submitted.
8 | R082000058 | Tulsipura | Rajgarh | WRD | MIS | 2005-03-19 | DDM | 180.95 | RIDF Loan upto 10 crore | Report yet to be submitted.
8 | R082000077 | Kudali | Rajgarh | WRD | MIS | 2005-03-19 | DDM | 113.6 | RIDF Loan upto 10 crore | Report yet to be submitted.
8 | R082000016 | Bilidar | Khargone | WRD | MIS | 2005-03-18 | DDM | 109.2 | RIDF Loan upto 10 crore | Report yet to be submitted.
8 | R082000130 | Lohara | Chhindwara | WRD | MIS | 2005-03-16 | DDM | 326.06 | RIDF Loan upto 10 crore | Head work was completed in June. Slab at the top of sluice was not provided. Canal excavation was not taken up.
8 | R082000118 | Bargolia Tank | Rajgarh | WRD | MIS | 2005-03-16 | DDM | 723.56 | RIDF Loan upto 10 crore | Report yet to be submitted.
8 | R082000015 | Ambadar | Khargone | WRD | MIS | 2005-03-09 | DDM | 109.95 | RIDF Loan upto 10 crore | Report yet to be submitted.
8 | R082000093 | Dalki 89/8 | Khargone | PWD | Bridge | 2005-03-08 | DDM | 97.46 | RIDF Loan upto 10 crore | Report yet to be submitted.
8 | R082000074 | Ramathan | Khargone | WRD | MIS | 2005-03-08 | DDM | 68.21 | RIDF Loan upto 10 crore | Land acquisition process is yet to be completed and Irrigation department has taken up the matter with the Revenue Authorities advising to expedite the matter. Likely date of completion of the project is June 2005.
8 | R082000116 | Dhavali Tank | Khargone | WRD | MIS | 2005-03-07 | DDM | 66.42 | RIDF Loan upto 10 crore | Report yet to be submitted.
8 | R082000113 | Ruplaziri Tank | Khargone | WRD | MIS | 2005-03-04 | DDM | 62.75 | RIDF Loan upto 10 crore | Report yet to be submitted.
8 | R082000111 | Bandhi Tank | Jabalpur | WRD | MIS | 2005-03-03 | DDM | 138.44 | RIDF Loan upto 10 crore | Overall 50% works has been completed. Progress and quality of the work is satisfactory. NABARD board be displayed at project site.
8 | R082000114 | Devla No. 1 Tank | Khargone | WRD | MIS | 2005-03-03 | DDM | 62.26 | RIDF Loan upto 10 crore | Report yet to be submitted.
8 | R082000129 | Dhadgawan Branch | Chhindwara | WRD | MIS | 2005-03-02 | DDM | 195.42 | RIDF Loan upto 10 crore | Head work was completed. Pithing was in progress. Sluice was constructed, however, slab was yet to be put on sluice. Excavation/construction for spill was in progress. Canal work was not done so far.
8 | R082000011 | Chhapri | Jhabua | WRD | MIS | 2005-03-02 | DDM | 75.16 | RIDF Loan upto 10 crore | The project has been completed and the PCR is being submitted. WUA should be formed immediately. NABARD board should be displayed.
8 | R082000011 | Chhapri | Jhabua | WRD | MIS | 2005-03-02 | DDM | 75.16 | RIDF Loan upto 10 crore | The project has been completed and the PCR is being subamitted. WUA should be formed immediately. NABARD board should be displayed.
8 | R082000128 | Mohkhedi | Chhindwara | WRD | MIS | 2005-03-01 | DDM | 436 | RIDF Loan upto 10 crore | Work in all fronts was progressing well. Excavation/construction for sluice, spill and nalla closure was in progress.
8 | R082000112 | Balkhadiya Tank | Khargone | WRD | MIS | 2005-02-26 | DDM | 51.91 | RIDF Loan upto 10 crore | Report yet to be submitted.
8 | R082000073 | Chandanpura | Khargone | WRD | MIS | 2005-02-26 | DDM | 334.21 | RIDF Loan upto 10 crore | Report yet to be submitted.
8 | R082000014 | Temarni | Khargone | WRD | MIS | 2005-02-24 | DDM | 68.05 | RIDF Loan upto 10 crore | Report yet to be submitted.
8 | R082000125 | Ghoghra | Chhindwara | WRD | MIS | 2005-02-23 | DDM | 251.56 | RIDF Loan upto 10 crore | Nalla closure is completed and excavation and construction of suit fall is in progress
8 | R082000021 | Upper Jamla | Khargone | WRD | MIS | 2005-02-23 | DDM | 35.98 | RIDF Loan upto 10 crore | Report yet to be submitted.
8 | R082000120 | Bhadgawan Branch Canal | Narsinghpur | NVDA | MJP | 2005-02-18 | DDM | 4518.07 | RIDF Loan 25 crore & above | The progress is very slow. Land acquisition and shifting of MPSEB poles are the major bottlenecks in implementation of the project.
8 | R082000086 | Sapra 2/8 | Chhindwara | PWD | Bridge | 2005-02-16 | DDM | 48.04 | RIDF Loan upto 10 crore | Bridge work is completed. Tendering for approach road is in progress. NABARD Board was not displayed.
8 | R082000090 | Indra 19/8 | Hoshangabad | PWD | Bridge | 2005-02-12 | DDM | 52.79 | RIDF Loan upto 10 crore | Overall physical progress was 20%. due to perennial water in the river Indra and due to sandy stata even at 5 mt. depth, the difficulties are faced by the Contractor for foundation work. The project is likely to be completed by 30.06.2005.
8 | R082000098 | Semarwai 7/6 | Satna | PWD | Bridge | 2005-02-10 | DDM | 53.57 | RIDF Loan upto 10 crore | Construction of pier and abutments was in progress at the time of visit. NABARD Board was not displayed. Land acquisition of 0.26 ha. was not done. Award yet to be passed, pending with Collector.
8 | R082000012 | Dhaba | Khargone | WRD | MIS | 2005-02-09 | DDM | 58.49 | RIDF Loan upto 10 crore | Report yet to be submitted.
8 | R082000104 | Kharri 3/10 | Sidhi | PWD | Bridge | 2005-01-23 | DDM | 49.21 | RIDF Loan upto 10 crore | Progress is very slow. In case of bridge, foundation work was completed and only sub structure work of 3 piers below the cap level and some work of 2 abutments was done. Approach road work was yet to commence. At the time of visit no work was going on.
8 | R082000017 | Jaljyoti | Khargone | WRD | MIS | 2005-01-22 | DDM | 121.06 | RIDF Loan upto 10 crore | Report yet to be submitted.
8 | R082000018 | Basantpura | Khargone | WRD | MIS | 2005-01-20 | DDM | 376.03 | RIDF Loan upto 10 crore | Report yet to be submitted.
8 | R082000018 | Basantpura | Khargone | WRD | MIS | 2005-01-20 | DDM | 376.03 | RIDF Loan upto 10 crore | Progress is satisfactory. Likely date of completion of the project work is 30.06.2005.
8 | R082000080 | RABS-Pipariya SD | Jabalpur | NVDA | MJP | 2005-01-19 | OIC+C | 1646.5 | RIDF Loan 10.01-24.99 crore | Overall progress is more than 58%. About 80% land acqisition completed. E/W & CNS completed in the entire 12 Kms. length. Lining work completed from 0 to 2 Kms. and is in progress between 2 to 5 Kms. The major bottleneck is nonavailability of good CNS.
8 | R082000081 | RABS-Balkhedi Tail Minor | Jabalpur | NVDA | MJP | 2005-01-19 | OIC+C | 761.26 | RIDF Loan upto 10 crore | Overall 35% work has been completed. Land acquisition is mostly completed.E/W and filling of CNS is also completed. Lining completed from 4.0 to 8.0 Kms. 12 Nos. structures completed. Balance lining and structures are in progress.
8 | R082000076 | Kaldha | Khargone | WRD | MIS | 2005-01-12 | DDM | 208.96 | RIDF Loan upto 10 crore | Report yet to be submitted.
8 | R082000076 | Kaldha | Khargone | WRD | MIS | 2005-01-12 | DDM | 208.96 | RIDF Loan upto 10 crore | The progress of the project is satisfactory and the work is expected to be completed by June 2005.
8 | R082000022 | Richhai | Narsinghpur | WRD | MIS | 2005-01-11 | DDM | 365.87 | RIDF Loan upto 10 crore | The progress of the wcrk is very slow. The decision on closure of nalla is yet to be taken by the Dept. Dozar was not provided to the contractor by the Dept due to this the project may be delayed..
8 | R082000055 | Navalpura | Khargone | WRD | MIS | 2005-01-11 | DDM | 634.31 | RIDF Loan upto 10 crore | Report yet to be submitted.
8 | R082000055 | Navalpura | Khargone | WRD | MIS | 2005-01-11 | DDM | 634.31 | RIDF Loan upto 10 crore | The progress of work is satisfactory and the project would be completed within the scheduled period.
8 | R082000095 | Gangli 51/10 | Neemuch | PWD | Bridge | 2005-01-10 | DDM | 88 | RIDF Loan upto 10 crore | All the four piers, sub-structure and one abutment completed. Approach road on one side is completed except BT. The work hampered due to contractor. The bridge will be completed by March 05. CE not visited the site so far. NABARD Board not displayed.
8 | R082000109 | Khamthi Tank | Chhindwara | WRD | MIS | 2005-01-07 | DDM | 94.15 | RIDF Loan upto 10 crore | Project likely to be completed by March 2005. Head work completed in last June and water storage was about 30% of the capacity. About 20 submerged trees were visible in tank. Dept may take up the matter with the concerned to remove the decayed trees.
8 | R082000043 | Amarwada S/s | Chhindwara | MPSEB | Power | 2005-01-04 | DDM | 369.7 | RIDF Loan upto 10 crore | The work was completed in all respects and sub station was charged. Test certificates were not available at sight.
8 | R082000094 | Tumbar 11/6 | Mandsaur | PWD | Bridge | 2005-01-02 | DDM | 48.47 | RIDF Loan upto 10 crore | bridge and approach road completed except BT. The work likely to be completed by Jan 2005. NABARD Board not displayed. The pitching of the abutment walls may be raised by another two ft. so that flood water may not damage the walls.
8 | r082000053 | Rabs-Lbc From Km 84 To 97 | Narsinghpur | NVDA | MJP | 2004-12-31 | DDM | 3782.63 | RIDF Loan 25 crore & above | Rock portion consists from Kms. 85.5 to 86.00. During last 6 months tenders were invited by NVDA on 5 occasions for the blasting of rock portion. However, due to higher bidding of rates NVDA could not finalised the tender.
8 | R082000126 | Satkinala | Chhindwara | WRD | MIS | 2004-12-28 | DDM | 519.91 | RIDF Loan upto 10 crore | Physical progress was satisfactory. Nalla closure work was in progress. The work is likely to be completed by June 2005.
8 | R082000131 | Khairipaika | Chhindwara | WRD | MIS | 2004-12-27 | DDM | 183.99 | RIDF Loan upto 10 crore | Pysical work was satisfactory. CE has not visited the project so far. The work is likely to be completed by June 2005.
8 | r082000123 | Andia Distributory | Narsinghpur | NVDA | MJP | 2004-12-24 | DDM | 1029.69 | RIDF Loan 10.01-24.99 crore | Some electric polls are to be removed. NVDA has already paid amount for shifting of polls to MPSEB. However so far polls were not removed. This may result in delay in completion of project. The progress appears to be satisfactory.
8 | r082000122 | Kandeli Distributory | Narsinghpur | NVDA | MJP | 2004-12-24 | DDM | 1547.66 | RIDF Loan 10.01-24.99 crore | Some electric polls are to be removed. NVDA has already paid amount for shifting of polls to MPSEB. However so far polls were not removed. This may result in delay in completion of the project. The progress appears to be satisfactory.
8 | R082000132 | Simrol No. 1 | Shajapur | WRD | MIS | 2004-12-24 | DDM | 289.02 | RIDF Loan upto 10 crore | Report yet to be submitted.
8 | r082000121 | Surgi Distributory | Narsinghpur | NVDA | MJP | 2004-12-22 | DDM | 1422.73 | RIDF Loan 10.01-24.99 crore | Some electric polls are to be removed. NVDA has already paid amount for shifting of polls to MPSEB. However so far polls were not removed. The progress appears to be satisfactory.
8 | r082000054 | Rabs-Lbc From Km 97 To 111 | Narsinghpur | NVDA | MJP | 2004-12-22 | DDM | 2414.1 | RIDF Loan 10.01-24.99 crore | Seven electric polls are to be shifted by MPSEB for which NVDA has already paid Rs.3.87 lacs to MPSEB. However MPSEB has not initiated any action in this regard. This may result in delay in completion of the project.
8 | r082000060 | 33/11 KV Sub-Station(MVA) | Jabalpur | MPSEB | Power | 2004-12-16 | DDM | 761.43 | RIDF Loan upto 10 crore | Bar chart was not prepared. There was delay in receipt of material. No insurance was taken for installation of equipments at local level. The overall quality of workmanship appears to be satisfactory.
8 | R082000060 | 33/11 KV Sub-Station(MVA) | Jabalpur | MPSEB | Power | 2004-12-08 | DDM | 761.43 | RIDF Loan upto 10 crore | Visit by Narsingpur DDM to Piparpani Substation - Bar chart was not prepared. Late receipt of required material. No insurance was taken for installation at local level. NABARD Board was not displayed.
8 | R082000044 | Lakhnadaun S/s | Seoni | MPSEB | Power | 2004-12-02 | DDM | 369.7 | RIDF Loan upto 10 crore | Project completed. Test certificates were not available at sight.
8 | r082000040 | Kotma S/s | Shahdol | MPSEB | Power | 2004-11-29 | DDM | 369.7 | RIDF Loan upto 10 crore | Most of the work has completed. Civil work is under progress.
8 | R082000009 | Dhamariya | Badwani | WRD | MIS | 2004-11-25 | DDM | 57.79 | RIDF Loan upto 10 crore | The progress of work is satisfactory and would be completed within 3-4 months.
8 | R082000117 | Hanmantiya Tank | Mandsaur | WRD | MIS | 2004-11-22 | DDM | 103.84 | RIDF Loan upto 10 crore | The work is progressing satisfactorily. The work is likely to be completed by March 2005.
8 | R082000070 | Bageri | Dhar | WRD | MIS | 2004-11-17 | DDM | 966.44 | RIDF Loan upto 10 crore | Likely to be delayed. Revenue Dept. not taking enough interest in the matter. NABARD Board not displayed.
8 | R082000108 | Jaliyapani Tank | Badwani | WRD | MIS | 2004-11-17 | DDM | 377.83 | RIDF Loan upto 10 crore | The nala closure yet to be done due to demand of additional compensation by Adivasi Mukti Sangthan. Likely date of completion of the project is December 2005.
8 | R082000106 | Pilliyakhal 20/4 | Ujjain | PWD | Bridge | 2004-11-04 | DDM | 150.59 | RIDF Loan upto 10 crore | Approach roads on both sides to be completed. NABARD Board was not displayed.
8 | R082000080 | RABS-Pipariya SD | Jabalpur | NVDA | MJP | 2004-10-21 | DDM | 1646.5 | RIDF Loan 10.01-24.99 crore | Overall progress is more than 50%. About 79% of land aquisition and 92% of earthwork is completed. NABARD Board not displayed.
8 | R082000081 | RABS-Balkhedi Tail Minor | Jabalpur | NVDA | MJP | 2004-10-21 | DDM | 761.26 | RIDF Loan upto 10 crore | Overall 58% of works have been completed. The progress of the work is satisfactory. 71% of earthwork and filling of CNS material is completed.
8 | R082000119 | Amanala Tank | Seoni | WRD | MIS | 2004-10-21 | DDM | 222.81 | RIDF Loan upto 10 crore | More than 60% of the work was completed. Balance work was under progress. Project is likely to be completed by March 2005. NABARD Board not displayed.
8 | R082000069 | Chhayanmaina | Dewas | WRD | MIS | 2004-10-21 | DDM | 157.28 | RIDF Loan upto 10 crore | Work commenced on 19 October 2004. There was delay due to delay n fixing up the agency. L. A. is pending. NABARD Board was not displayed.
8 | R082000110 | Bhainsakhedi Tank | Dewas | WRD | MIS | 2004-10-21 | DDM | 321.94 | RIDF Loan upto 10 crore | Dam seat almost completed. Sluice upstream completed, downstream to be completed. Delay n distribution of land compensation. NABARD Board was not displayed.
8 | R082000068 | Orni | Dewas | WRD | MIS | 2004-10-21 | DDM | 123.99 | RIDF Loan upto 10 crore | Dam earthwork completed. Pitching work is in partially balance. L.A. is pending. NABARD Board was not displayed.
8 | R082000046 | Umaria S/s | Umaria | MPSEB | Power | 2004-10-19 | DDM | 309.7 | RIDF Loan upto 10 crore | 80% of the civil & structure work has been completed.Quality test certificates were not available at site. The progress of the work is very slow.
8 | R082000127 | Sakarwara | Chhindwara | WRD | MIS | 2004-10-12 | DDM | 521.3 | RIDF Loan upto 10 crore | Nalla closure was in progress. The work is likely to be completed by 31 March 2005.
8 | R082000088 | Kukshi 6/16 | Dhar | PWD | Bridge | 2004-10-05 | DDM | 136.11 | RIDF Loan upto 10 crore | The work is behind the schedule. NABARD Board not displayed. Finishing work is not proper.
8 | r082000108 | Jaliyapani Tank | Badwani | WRD | MIS | 2004-09-30 | DDM | 377.83 | RIDF Loan upto 10 crore | Report yet to be submitted.
8 | r082000009 | Dhamariya | Badwani | WRD | MIS | 2004-09-23 | DDM | 57.79 | RIDF Loan upto 10 crore | Report yet to be submitted.
8 | R082000067 | Deopur-Mugalsarai | Vidisha | PWD | Road | 2004-09-22 | DDM | 296.32 | RIDF Loan upto 10 crore | The progress was very slow. Department has to take keen interest to start the work with full stream.
8 | R082000102 | Jokaha 17/6 | Sidhi | PWD | Bridge | 2004-09-04 | DDM | 48.28 | RIDF Loan upto 10 crore | Progress is very slow. NABARD Board not displayed. As per our recod the length of the bridge is 80 Mtrs. however the length of the bridge being constructed is only 60 Mtrs.
8 | R082000103 | Narkuin 7/10 | Sidhi | PWD | Bridge | 2004-09-04 | DDM | 60.77 | RIDF Loan upto 10 crore | Progress is very slow. NABARD Board not displayed. Although as per our records the length of the bridge is 84 Mtrs., the length of the the bridge is being constructed is only 60 Mtrs.
8 | R082000082 | Sarrathi 2/8 | Balaghat | PWD | Bridge | 2004-09-04 | DDM | 114.14 | RIDF Loan upto 10 crore | The progress of the work was satisfactory. However the work was stopped due to mansoon season. NABARD Board was not displayed.
8 | R082000001 | BANJAR RIVER - 11/4 | Balaghat | PWD | Bridge | 2004-09-03 | DDM | 86.9 | RIDF Loan upto 10 crore | Project already completed on 10/07/03. NABARD Board not displayed.
8 | R082000051 | 132 kV Feeder bays | Jabalpur | MPSEB | Power | 2004-07-15 | DDM | 544.54 | RIDF Loan upto 10 crore | Erection of new 1X3.15 MVA Substation at Lathgaon- Approved procedure was adopted. Late receipt of required material.
8 | R082000051 | 132 kV Feeder bays | Jabalpur | MPSEB | Power | 2004-07-13 | DDM | 544.54 | RIDF Loan upto 10 crore | Erection of new 1x3.15MVA Sub Station at Mugali - Approved procedure was adopted by the Division. Late receipt of required material.
8 | R082000051 | 132 kV Feeder bays | Jabalpur | MPSEB | Power | 2004-07-13 | DDM | 544.54 | RIDF Loan upto 10 crore | Erection of new 1X3.15 MVA Sub-station at Berhatta- Approved proecdure was adopted. Late receipt of material.
8 | R082000048 | Garoth S/s | Mandsaur | MPSEB | Power | 2004-07-03 | DDM | 369.7 | RIDF Loan upto 10 crore | Project delayed as Gandhisagar-Suwasara HTL was reserved for power supply to Ujjain for Kumbh fair. Papers relating to project are maintained at DE office at Nagda
8 | r082000002 | NARMADA RIVER - 1/8 | Mandla | PWD | Bridge | 2004-06-28 | DDM | 364.66 | RIDF Loan upto 10 crore | LA to be finalised.Permission from Forest Dept.is pending.
8 | r082000049 | Basoda S/s | Vidisha | MPSEB | Power | 2004-06-18 | DDM | 309.7 | RIDF Loan upto 10 crore | 1) the work has been completed in all respects. 2) the unit is functioning from 05 May 2003. 3) the balance fund is to be utilised for construction of staff quarters and water tank.
8 | r082000039 | Sironj S/s | Vidisha | MPSEB | Power | 2004-06-18 | DDM | 294.7 | RIDF Loan upto 10 crore | 1) Replacement of transformer from 20 MVA to 40 MVA yet to be completed. The unit is functioning from 19.10.02
8 | R082000122 | Kandeli Distributory | Narsinghpur | NVDA | MJP | 2004-06-09 | DDM | 1547.66 | RIDF Loan 10.01-24.99 crore | Tendering of unit II completed.Project is likely to be completed by 31.03.05
8 | R082000121 | Surgi Distributory | Narsinghpur | NVDA | MJP | 2004-06-09 | DDM | 1422.73 | RIDF Loan 10.01-24.99 crore | Tendering of unit II completed.The project is likely to be completed by 30.06.05
8 | R082000047 | Rampur Bagelaon S/s | Satna | MPSEB | Power | 2004-06-02 | DDM | 309.7 | RIDF Loan upto 10 crore | Work is in progress .Road making to be done.
8 | R082000047 | Rampur Bagelaon S/s | Satna | MPSEB | Power | 2004-06-02 | DDM | 309.7 | RIDF Loan upto 10 crore | 33KV Switchyard - All structures were erected. Cable laying is under progress. 132 KV Switchyard - Steps making for 3 Nos. Circuit Breaker,yard metalling and finishing work to be done.
8 | R082000054 | Rabs-Lbc From Km 97 To 111 | Narsinghpur | NVDA | MJP | 2004-06-02 | DDM | 2414.1 | RIDF Loan 10.01-24.99 crore | The progress of the implmentation of the project was satisfactory and likely to be completed by 31.03.2005.
8 | R082000123 | Andia Distributory | Narsinghpur | NVDA | MJP | 2004-06-02 | DDM | 1029.69 | RIDF Loan 10.01-24.99 crore | Tendering of unit II completed.Progress is slow due to land acquisition problem.
8 | R082000022 | Richhai | Narsinghpur | WRD | MIS | 2004-06-01 | DDM | 365.87 | RIDF Loan upto 10 crore | 1) Delay in LA. 2) Unit I - Prel : 100%, Masonry : 20%, Earthwork (Dam/Spill) : 30% / 55% Unit II - Prel : 100%, LA : 91.13%, Earthwork : 11%
8 | R082000053 | Rabs-Lbc From Km 84 To 97 | Narsinghpur | NVDA | MJP | 2004-05-28 | DDM | 3782.63 | RIDF Loan 25 crore & above | 1) Tendering for Unit II complete. 2) Prel : 40.53, LA : 80.43, Masonry : 12.57, Earthwork / Lining : 60.96% / 34.06%
8 | R082000120 | Bhadgawan Branch Canal | Narsinghpur | NVDA | MJP | 2004-05-26 | DDM | 4518.07 | RIDF Loan 25 crore & above | 1)Tendering for Unit II completed. 2) Prel : 85%, LA : 93.12%, Masonry : 21%, Earthwork/Lining : 40% / 10%
8 | R082000003 | BUDHNER RIVER - 4/4 | Mandla | PWD | Bridge | 2004-05-21 | DDM | 199.53 | RIDF Loan upto 10 crore | 1) Tender delayed : tendering for approach road is under process. 2) Work has not commenced yet. 3) E/E office is at Jabalpur and thus planning of visits is difficult.
8 | r082000079 | Rudaheda | Ujjain | WRD | MIS | 2004-05-01 | DDM | 338.35 | RIDF Loan upto 10 crore | Report received.
8 | R082000079 | Rudaheda | Ujjain | WRD | MIS | 2004-05-01 | OIC | 338.35 | RIDF Loan upto 10 crore | Report received.
8 | R082000098 | Semarwai 7/6 | Satna | PWD | Bridge | 2004-04-29 | DDM | 53.57 | RIDF Loan upto 10 crore | LA Award to be passed by collector. 15% retention money to be kept by deptt for 5 yrs after completion of project yet to be settled between contractor and deptt. No work done. Deptt has issued two notices to the contractor.
8 | R082000068 | Orni | Dewas | WRD | MIS | 2004-03-26 | DDM | 123.99 | RIDF Loan upto 10 crore | Tender: Unit I-complete. Unit II-submitted with C.E. LA case for dam is submitted for approval at Commissioner's office. Canal LA is under scrutiny in the C.E. office. NB board not displayed. Unit I: Prel-18%, LA-97%, Earthwork(Dam)-40%.
8 | R082000110 | Bhainsakhedi Tank | Dewas | WRD | MIS | 2004-03-26 | DDM | 321.94 | RIDF Loan upto 10 crore | 1) Tender completed for Unit I, yet to be floated for Unit II. 2) Excavation of sluice is under progress and likely to be completed shortly. 3) LA case is under progress. Dhara 4,6 and 7 completed for major portion. Payments yet to be made.
8 | R082000056 | Naidar | Khargone | WRD | MIS | 2004-03-24 | DDM | 50.93 | RIDF Loan upto 10 crore | Delay in LA procress for canal work .Time overrun- project likely to be completed by June 2005 as against March 2005.
8 | R082000117 | Hanmantiya Tank | Mandsaur | WRD | MIS | 2004-03-23 | DDM | 103.84 | RIDF Loan upto 10 crore | Delay in LA for Unit-I & Unit-II.Slow progress of Masonry & earthwork.
8 | R082000016 | Bilidar | Khargone | WRD | MIS | 2004-03-23 | DDM | 109.2 | RIDF Loan upto 10 crore | Delay in LA process for canal work
8 | R082000092 | Kaveri 6/10 | Khandwa | PWD | Bridge | 2004-03-19 | DDM | 69.58 | RIDF Loan upto 10 crore | Delay in tendering-tendering process not initiated for approach road.
8 | R082000125 | Ghoghra | Chhindwara | WRD | MIS | 2004-03-17 | DDM | 251.56 | RIDF Loan upto 10 crore | Masonry work in case of Unit-I & Unit-II not started.Earthwork yet to be commenced for Unit-I.
8 | R082000106 | Pilliyakhal 20/4 | Ujjain | PWD | Bridge | 2004-03-16 | DDM | 150.59 | RIDF Loan upto 10 crore | Slow progress- Physical progress of foundation , sub structure,super structure work is 66%,66% & 20%respectively.Approach road work not strated.NB board displayed.
8 | R082000094 | Tumbar 11/6 | Mandsaur | PWD | Bridge | 2004-03-15 | DDM | 48.47 | RIDF Loan upto 10 crore | Slow progress- physical progress of foundation & sub- structure work is 29% & 20% respectively.Super structure & approach road work not started.
8 | R082000040 | Kotma S/s | Shahdol | MPSEB | Power | 2004-03-11 | DDM | 369.7 | RIDF Loan upto 10 crore | Civil work yet to be completed .
8 | R082000116 | Dhavali Tank | Khargone | WRD | MIS | 2004-03-11 | DDM | 66.42 | RIDF Loan upto 10 crore | Delay in .LA process
8 | R082000064 | 33/11 KV Sub-Station(MVA) | Gwalior | MPSEB | Power | 2004-03-10 | DDM | 443.72 | RIDF Loan upto 10 crore | No insurance cover taken for labour & equipment.NB board not displayed.
8 | R082000113 | Ruplaziri Tank | Khargone | WRD | MIS | 2004-03-10 | DDM | 62.75 | RIDF Loan upto 10 crore | Slow progress-earth work not completed.The compaction density test not done after puddling work.
8 | R082000003 | BUDHNER RIVER - 4/4 | Mandla | PWD | Bridge | 2004-03-09 | DDM | 199.53 | RIDF Loan upto 10 crore | Slow progress in tendering.Work not commenced . NB board not displayed.
8 | R082000072 | Mohana | Indore | WRD | MIS | 2004-03-03 | DDM | 68.34 | RIDF Loan upto 10 crore | Physical progress is 70%.Canal work not started so far.Earth work not completed.NB board not displayed.
8 | R082000098 | Semarwai 7/6 | Satna | PWD | Bridge | 2004-02-29 | DDM | 53.57 | RIDF Loan upto 10 crore | It was informed that the contractor is corresponding with the authorities on the issue of 15% retention money controversy. NB board not displayed.
8 | R082000132 | Simrol No. 1 | Shajapur | WRD | MIS | 2004-02-29 | DDM | 289.02 | RIDF Loan upto 10 crore | Work was not yet started. Department has issued two notices to the contractor for starting the work.NABARD Board not displayed.
8 | R082000064 | 33/11 KV Sub-Station(MVA) | Gwalior | MPSEB | Power | 2004-02-27 | DDM | 443.72 | RIDF Loan upto 10 crore | No CPM/Bar chart is prepared .Payment to labour contractor is done .Project completed in time.
8 | R082000015 | Ambadar | Khargone | WRD | MIS | 2004-02-26 | DDM | 109.95 | RIDF Loan upto 10 crore | Canal work yet to be taken up.
8 | R082000074 | Ramathan | Khargone | WRD | MIS | 2004-02-25 | DDM | 68.21 | RIDF Loan upto 10 crore | LA process yet to be completed . Masonry & earth work of Unit-I & Unit-II not completed.
8 | R082000013 | Jalkhan Tank 2 | Khargone | WRD | MIS | 2004-02-23 | DDM | 35.94 | RIDF Loan upto 10 crore | Progress of implemention is as per schdule.
8 | R082000048 | Garoth S/s | Mandsaur | MPSEB | Power | 2004-02-19 | DDM | 369.7 | RIDF Loan upto 10 crore | The work is in progress slightly delayed because of late supply of transformer and towers by the Dept.
8 | R082000118 | Bargolia Tank | Rajgarh | WRD | MIS | 2004-02-15 | Consultant | 723.56 | RIDF Loan upto 10 crore | Slow progress-earth work in case of head works not started.canal work not commenced so far.Delay in tendering for Unit II. LA problem- land to be acquired -164.64 ha & 48 ha in case of head work & canal work respectively.
8 | R082000045 | Katangi S/s | Balaghat | MPSEB | Power | 2004-02-14 | Consultant | 309.7 | RIDF Loan upto 10 crore | Civil work for control room already completed .70% of the civil formation works has been completed and remaining will be done at the availabilty of structures.
8 | r082000127 | Sakarwara | Chhindwara | WRD | MIS | 2004-02-13 | DDM | 521.3 | RIDF Loan upto 10 crore | Masonary & work work not completed.LA for unit-I & IInot completed.
8 | R082000077 | Kudali | Rajgarh | WRD | MIS | 2004-02-13 | Consultant | 113.6 | RIDF Loan upto 10 crore | LA problem-land to be acquired 40.14 ha & 4.185 ha in case of head & canal work.Time overrun- project likely to be completed by June 05 as against June 04.
8 | R082000096 | Newaj 14/4 | Rajgarh | PWD | Bridge | 2004-02-13 | Consultant | 152.47 | RIDF Loan upto 10 crore | Delay in commencement of work. Records not made available at site for inspection.
8 | R082000080 | RABS-Pipariya SD | Jabalpur | NVDA | MJP | 2004-02-13 | DDM | 1646.5 | RIDF Loan 10.01-24.99 crore | LA process delayed. Slow progress-no work done for preliminary & masonary . NB board not displayed.
8 | R082000081 | RABS-Balkhedi Tail Minor | Jabalpur | NVDA | MJP | 2004-02-12 | DDM | 761.26 | RIDF Loan upto 10 crore | Slow progress-no work done for preliminary and masonary .
8 | R082000058 | Tulsipura | Rajgarh | WRD | MIS | 2004-02-11 | Consultant | 180.95 | RIDF Loan upto 10 crore | Time overrun- project likely to be completed by June 05 as against March 05.Slow progress- earthwork & masonry work yet to be comleted in case of Unit- I & II.
8 | R082000068 | Orni | Dewas | WRD | MIS | 2004-02-11 | DDM | 123.99 | RIDF Loan upto 10 crore | Delay in tendering for Unit-II.NB board not displayed.
8 | R082000110 | Bhainsakhedi Tank | Dewas | WRD | MIS | 2004-02-11 | DDM | 321.94 | RIDF Loan upto 10 crore | Delay in tendering for Unit-II . NBboard not displayed.
8 | R082000001 | BANJAR RIVER - 11/4 | Balaghat | PWD | Bridge | 2004-02-10 | Consultant | 86.9 | RIDF Loan upto 10 crore | The execution of work appeared to be of good quality.
8 | R082000047 | Rampur Bagelaon S/s | Satna | MPSEB | Power | 2004-02-06 | DDM | 309.7 | RIDF Loan upto 10 crore | Yard metalling ,circuit breakers and finishing work to be done.Cable lying junction ,two wave traps and their jumpering under progress.
8 | R082000069 | Chhayanmaina | Dewas | WRD | MIS | 2004-02-06 | DDM | 157.28 | RIDF Loan upto 10 crore | Delay in commencement of work- work not srarted so far.NB board not displayed.
8 | r082000107 | Extension of Tawa LBC | Harda | WRD | MJP | 2004-01-31 | Consultant | 2345.95 | RIDF Loan 10.01-24.99 crore | Time over run, project to be completed by June'06 as against March'05, delay in tendering - tenders for two major structures Viz, aquaducts at Machak and Sayani river not accepted so for, tenders for minors not initiated so for.
8 | r082000125 | Ghoghra | Chhindwara | WRD | MIS | 2004-01-30 | DDM | 251.56 | RIDF Loan upto 10 crore | Mesonery work and earth work of unit I and Unit II not completed, LA for unit II to be done.
8 | R082000021 | Upper Jamla | Khargone | WRD | MIS | 2004-01-28 | DDM | 35.98 | RIDF Loan upto 10 crore | Slow progress- Unit- I preliminary, masonry & earth work yet to be completed. Unit-II work not commenced.LA yet to be done.
8 | R082000020 | Ahilyapura | Khargone | WRD | MIS | 2004-01-24 | DDM | 80.4 | RIDF Loan upto 10 crore | Progress of implementation is as per schdule.
8 | R082000014 | Temarni | Khargone | WRD | MIS | 2004-01-23 | DDM | 68.05 | RIDF Loan upto 10 crore | Progress of implementation is slow due to LA.
8 | R082000114 | Devla No. 1 Tank | Khargone | WRD | MIS | 2004-01-22 | DDM | 62.26 | RIDF Loan upto 10 crore | LA problem - LA process yet to be completed . Physical progress - Slow progress Unit-I- Masonry & earth work work yet to be completed. Unit-II-Delay in commancement of work.
8 | R082000017 | Jaljyoti | Khargone | WRD | MIS | 2004-01-21 | DDM | 121.06 | RIDF Loan upto 10 crore | LA problem -commancement of the project delayed due to LA process.
8 | R082000075 | Jamniya | Khargone | WRD | MIS | 2004-01-19 | DDM | 44.42 | RIDF Loan upto 10 crore | Contractor problem-work stopped by contractor. Physical progress- canal work yet to be intiated.
8 | R082000019 | Gawlan | Khargone | WRD | MIS | 2004-01-17 | DDM | 584.29 | RIDF Loan upto 10 crore | Work in progress.
8 | r082000002 | NARMADA RIVER - 1/8 | Mandla | PWD | Bridge | 2004-01-16 | DDM | 364.66 | RIDF Loan upto 10 crore | Slow progress- tendering problem- tendering process not completed for approach road. super structure work not started.
8 | r082000043 | Amarwada S/s | Chhindwara | MPSEB | Power | 2004-01-15 | DDM | 369.7 | RIDF Loan upto 10 crore | Overall quality of workmanship is satisfactory.
8 | R082000088 | Kukshi 6/16 | Dhar | PWD | Bridge | 2004-01-15 | DDM | 136.11 | RIDF Loan upto 10 crore | Slow progress- work progress is behind schedule.NB board not displayed.
8 | R082000043 | Amarwada S/s | Chhindwara | MPSEB | Power | 2004-01-15 | DDM | 369.7 | RIDF Loan upto 10 crore | Cost overrun due to increase in cost of material.43 out of 110 towers were erected. Work at sight was in full swing.
8 | R082000112 | Balkhadiya Tank | Khargone | WRD | MIS | 2004-01-14 | DDM | 51.91 | RIDF Loan upto 10 crore | LA problem- Department to pursue with Revenue Department for completion of LA process for timely completion of the project.
8 | r082000022 | Richhai | Narsinghpur | WRD | MIS | 2004-01-08 | DDM | 365.87 | RIDF Loan upto 10 crore | Slow progress- there is no physical progress for preliminary, LA & mesonary work in Unit- I .As regards Unit-II except LA no progress in other item.
8 | R082000010 | Mahavir Pavitra Sarovar(Dhamela) | Dhar | WRD | MIS | 2004-01-07 | DDM | 458.6 | RIDF Loan upto 10 crore | Work is in progress.Foundation is completed.
8 | R082000071 | Govindpura | Dhar | WRD | MIS | 2004-01-07 | DDM | 541.27 | RIDF Loan upto 10 crore | Work is in progress .Foundation is completed ,Two suize gate work is in progress.NB board not displayed.
8 | R082000070 | Bageri | Dhar | WRD | MIS | 2004-01-06 | DDM | 966.44 | RIDF Loan upto 10 crore | Problem in land acquisition .NB board not installed.
8 | r082000130 | Lohara | Chhindwara | WRD | MIS | 2004-01-05 | DDM | 326.06 | RIDF Loan upto 10 crore | Earth work for unit I yet to be completed, masonery, earth work and LA for unit II not commenced.
8 | r082000053 | Rabs-Lbc From Km 84 To 97 | Narsinghpur | NVDA | MJP | 2004-01-02 | DDM | 3782.63 | RIDF Loan 25 crore & above | Slow progress - physical progress of preliminary, LA, mesonry and earth work is 41%, 80%, 6% AND 41% respectively.
8 | r082000120 | Bhadgawan Branch Canal | Narsinghpur | NVDA | MJP | 2004-01-02 | DDM | 4518.07 | RIDF Loan 25 crore & above | Slow progress - physical progress of preliminary, LA, mesonry and earth work is 49%, 61%, 10% and 7% respectively.
8 | R082000048 | Garoth S/s | Mandsaur | MPSEB | Power | 2003-12-19 | DDM | 369.7 | RIDF Loan upto 10 crore | 1. Insurance cover for equipment at S/S site has expired on November 03. The department please insure the stock.
8 | r082000054 | Rabs-Lbc From Km 97 To 111 | Narsinghpur | NVDA | MJP | 2003-12-16 | DDM | 2414.1 | RIDF Loan 10.01-24.99 crore | Slow progress, physical achievement of preliminary is 2 KM, 111.50 ha and earth work is 240 CUM. Mesonary work not started.
8 | r082000123 | Andia Distributory | Narsinghpur | NVDA | MJP | 2003-12-16 | DDM | 1029.69 | RIDF Loan 10.01-24.99 crore | Slow progress. Physical progress of LA, mesonary and earth work is 38%, 1%, 12% respectively.
8 | r082000122 | Kandeli Distributory | Narsinghpur | NVDA | MJP | 2003-12-11 | DDM | 1547.66 | RIDF Loan 10.01-24.99 crore | Slow progress for masonary & earth work , LA done for 128.62 ha as against 167.72 ha
8 | r082000121 | Surgi Distributory | Narsinghpur | NVDA | MJP | 2003-12-11 | DDM | 1422.73 | RIDF Loan 10.01-24.99 crore | Slow progress, physical progress of LA, mesonry and earth work is 60%, 2% and 4% respectively.
8 | R082000078 | Aston Chandela | Tikamgarh | WRD | MIS | 2003-12-09 | RO Official | 26.87 | RIDF Loan upto 10 crore | Slow progress, work not started. LA to be done for head work 1.897 ha & Canal work 0.644 ha
8 | R082000127 | Sakarwara | Chhindwara | WRD | MIS | 2003-11-21 | DDM | 521.3 | RIDF Loan upto 10 crore | 1. NB board not displayed at dam site.
8 | r082000060 | 33/11 KV Sub-Station(MVA) | Jabalpur | MPSEB | Power | 2003-11-12 | DDM | 761.43 | RIDF Loan upto 10 crore | New 33/11 KV 1X3.15 MVA substation at Bankheda Narsinghpur. Visited by DDM Narsinghpur.material not received .work has not started only fencing is completed.
8 | r082000060 | 33/11 KV Sub-Station(MVA) | Jabalpur | MPSEB | Power | 2003-11-12 | DDM | 761.43 | RIDF Loan upto 10 crore | 1x3.15MVA33/11KV s/s at Khulari Dist Narsinghpur .Visited by DDMNarsinghpur.Quality control tests were not undertaken .CPM/Bar chart was not prepared .
8 | r082000060 | 33/11 KV Sub-Station(MVA) | Jabalpur | MPSEB | Power | 2003-11-11 | DDM | 761.43 | RIDF Loan upto 10 crore | 1x3.15MVA33/11KV s/s at Tendukheda Dist Narsinghpur .Vi8sited by DDM Narsinghpur.CPM/Bar chart was not prepared .Quality tests were not undertaken .
8 | r082000060 | 33/11 KV Sub-Station(MVA) | Jabalpur | MPSEB | Power | 2003-11-10 | DDM | 761.43 | RIDF Loan upto 10 crore | 33/11KV 1x1.6MVA s/s at Madanpur Dist Narsinghpur .Visited by DDM .Project is completed .Quality control tests were not undertaken .
8 | R082000060 | 33/11 KV Sub-Station(MVA) | Jabalpur | MPSEB | Power | 2003-11-10 | DDM | 761.43 | RIDF Loan upto 10 crore | 1x3.15MVA33/11KV s/s at Piparwani Dist Narsinghpur .Visited by DDM Narsinghpur .No progress at all .Place is not yet decided .Material is not available.
8 | R082000039 | Sironj S/s | Vidisha | MPSEB | Power | 2003-11-04 | DDM | 294.7 | RIDF Loan upto 10 crore | Work is completed except replacement of transformer.
8 | R082000043 | Amarwada S/s | Chhindwara | MPSEB | Power | 2003-11-04 | DDM | 369.7 | RIDF Loan upto 10 crore | Work in progress
8 | R082000049 | Basoda S/s | Vidisha | MPSEB | Power | 2003-11-04 | DDM | 309.7 | RIDF Loan upto 10 crore | Project is completed.
8 | r082000060 | 33/11 KV Sub-Station(MVA) | Jabalpur | MPSEB | Power | 2003-11-03 | DDM | 761.43 | RIDF Loan upto 10 crore | 1x3.15MVA33KV s/s at Badhaiyakheda Dist Narsinghpur .Visited by DDM Narsinghpur.Quality control tests were not undertaken .
8 | r082000060 | 33/11 KV Sub-Station(MVA) | Jabalpur | MPSEB | Power | 2003-11-03 | DDM | 761.43 | RIDF Loan upto 10 crore | 1x3.15MVA additional tranformer at 33/11KV s/s at Dangidhua Dist Narsinghpur .Visited by DDM Narsinghpur .VCB is to be received
8 | r082000060 | 33/11 KV Sub-Station(MVA) | Jabalpur | MPSEB | Power | 2003-11-01 | DDM | 761.43 | RIDF Loan upto 10 crore | 1x3.15MVA33/11KVs/s at Lathgaon Dist Narsinghpur.visited by DDM Narsinghpur.Structure is ready since last 2yrs but VCB,transformer and conductor is yet to be provided by Dept E.E.
8 | R082000060 | 33/11 KV Sub-Station(MVA) | Jabalpur | MPSEB | Power | 2003-11-01 | DDM | 761.43 | RIDF Loan upto 10 crore | 1X3.15MVA33/11S/S at Berhata Dist Narsinghpur .Visited by DDM Narsinghpur .Structure is ready since last 2yrs but Transformer and VCB is yet to be provided by the Dept E.E.
8 | r082000060 | 33/11 KV Sub-Station(MVA) | Jabalpur | MPSEB | Power | 2003-10-31 | DDM | 761.43 | RIDF Loan upto 10 crore | 1x3.15MVA33/11KVs/s at Naktua Dist Narsinghpur .Visited by DDM Narsinghpur .Inadequate fund allocation for control room .Now adequate funds have been releasd and it would be completed by 30.11.03
8 | r082000060 | 33/11 KV Sub-Station(MVA) | Jabalpur | MPSEB | Power | 2003-10-31 | DDM | 761.43 | RIDF Loan upto 10 crore | 1x3.15MVA33/11KV s/s at Mugoli Dist Narsinghpur .Visited by DDM Narsinghpur .Power tranformer ,conductor ,VCB,steel structure material is not made available to the division
8 | R082000047 | Rampur Bagelaon S/s | Satna | MPSEB | Power | 2003-10-18 | DDM | 309.7 | RIDF Loan upto 10 crore | Work in progress
8 | R082000044 | Lakhnadaun S/s | Seoni | MPSEB | Power | 2003-10-17 | RO Official | 369.7 | RIDF Loan upto 10 crore | Work is in progress.
8 | R082000060 | 33/11 KV Sub-Station(MVA) | Jabalpur | MPSEB | Power | 2003-10-15 | DDM | 761.43 | RIDF Loan upto 10 crore | Quality control tests were not undertaken. No insurance is made for installation
8 | R082000040 | Kotma S/s | Shahdol | MPSEB | Power | 2003-09-26 | DDM | 369.7 | RIDF Loan upto 10 crore | Almost work is completed. Balance work is in progress.Equipment are not insuranced.
8 | R082000067 | Deopur-Mugalsarai | Vidisha | PWD | Road | 2003-09-18 | DDM | 296.32 | RIDF Loan upto 10 crore | Slow progress due to contractors' problem
8 | R082000003 | BUDHNER RIVER - 4/4 | Mandla | PWD | Bridge | 2003-09-06 | DDM | 199.53 | RIDF Loan upto 10 crore | Progress is very slow due todelay in tendering. Work order not issued. NABARD Board not displayed.
8 | R082000002 | NARMADA RIVER - 1/8 | Mandla | PWD | Bridge | 2003-08-26 | DDM | 364.66 | RIDF Loan upto 10 crore | Progress is slow due to delay in tendering. NABARD Board not displayed.
8 | R082000040 | Kotma S/s | Shahdol | MPSEB | Power | 2003-08-26 | OIC | 369.7 | RIDF Loan upto 10 crore | Equipments have not been insured.
8 | R082000040 | Kotma S/s | Shahdol | MPSEB | Power | 2003-08-26 | DDM | 369.7 | RIDF Loan upto 10 crore | Almost work is completed. Balance civil work is under progress.Equipment not insuranced.
8 | R082000120 | Bhadgawan Branch Canal | Narsinghpur | NVDA | MJP | 2003-06-27 | DDM | 4518.07 | RIDF Loan 25 crore & above | LA problem - physical achievement only 10.25%.
8 | R082000054 | Rabs-Lbc From Km 97 To 111 | Narsinghpur | NVDA | MJP | 2003-06-26 | DDM | 2414.1 | RIDF Loan 10.01-24.99 crore | LA problem - physical achievement is merely 33%. NB board not displayed.
8 | R082000053 | Rabs-Lbc From Km 84 To 97 | Narsinghpur | NVDA | MJP | 2003-06-25 | DDM | 3782.63 | RIDF Loan 25 crore & above | Tendering problem - delay in tendering. NB board not displayed.
8 | R082000039 | Sironj S/s | Vidisha | MPSEB | Power | 2003-06-24 | DDM | 294.7 | RIDF Loan upto 10 crore | Project completed
8 | R082000049 | Basoda S/s | Vidisha | MPSEB | Power | 2003-06-24 | DDM | 309.7 | RIDF Loan upto 10 crore | Project completed.
8 | R082000067 | Deopur-Mugalsarai | Vidisha | PWD | Road | 2003-05-27 | DDM | 296.32 | RIDF Loan upto 10 crore | Delay in tendering
8 | R082000073 | Chandanpura | Khargone | WRD | MIS | 2003-05-15 | OIC | 334.21 | RIDF Loan upto 10 crore | Satisfactory.
8 | r082000131 | Khairipaika | Chhindwara | WRD | MIS |  |  | 183.99 | RIDF Loan upto 10 crore
8 | R082000064 | 33/11 KV Sub-Station(MVA) | Gwalior | MPSEB | Power |  |  | 443.72 | RIDF Loan upto 10 crore
8 | R082000129 | Dhadgawan Branch | Chhindwara | WRD | MIS |  |  | 195.42 | RIDF Loan upto 10 crore
8 | R082000005 | THEL RIVER - 18/2KM | Seoni | PWD | Bridge |  |  | 67.15 | RIDF Loan upto 10 crore
8 | R082000006 | THEL RIVER -3/6KM | Seoni | PWD | Bridge |  |  | 60.12 | RIDF Loan upto 10 crore
8 | R082000007 | BIJNA ROAD - 21/8 KM | Seoni | PWD | Bridge |  |  | 40.59 | RIDF Loan upto 10 crore
8 | R082000008 | Panwa | Badwani | WRD | MIS |  |  | 27.7 | RIDF Loan upto 10 crore
8 | R082000023 | Dunda | Tikamgarh | WRD | MIS |  |  | 63.13 | RIDF Loan upto 10 crore
8 | R082000024 | Bhitari LIS | Tikamgarh | WRD | MIS |  |  | 144.81 | RIDF Loan upto 10 crore
8 | R082000026 | LILO Amarkantak-Manendragarh | Jabalpur | MPSEB | Power |  |  | 13.4 | RIDF Loan upto 10 crore
8 | R082000027 | Handia-Nasrullaganj DCSS | Sehore | MPSEB | Power |  |  | 524.9 | RIDF Loan upto 10 crore
8 | R082000028 | LILO Itarsi-Harda | Hoshangabad | MPSEB | Power |  |  | 93.82 | RIDF Loan upto 10 crore
8 | R082000029 | LILO Seoni-Chhindwara | Jabalpur | MPSEB | Power |  |  | 353.94 | RIDF Loan upto 10 crore
8 | R082000030 | LILO Jabalpur-Seoni | Jabalpur | MPSEB | Power |  |  | 26.8 | RIDF Loan upto 10 crore
8 | R082000031 | Tap on Balaghat-Seoni | Jabalpur | MPSEB | Power |  |  | 361.46 | RIDF Loan upto 10 crore
8 | R082000032 | Katni-Umaria DCSS | Jabalpur | MPSEB | Power |  |  | 600.48 | RIDF Loan upto 10 crore
8 | R082000034 | LILO Gandhisagar-Suwasara | Jabalpur | MPSEB | Power |  |  | 26.8 | RIDF Loan upto 10 crore
8 | R082000035 | Handia-Harda DCDS | Hoshangabad | MPSEB | Power |  |  | 227.84 | RIDF Loan upto 10 crore
8 | R082000036 | Handia-Kannod DCSS | Jabalpur | MPSEB | Power |  |  | 402.78 | RIDF Loan upto 10 crore
8 | R082000037 | LILO Panwadi | Shajapur | MPSEB | Power |  |  | 80.42 | RIDF Loan upto 10 crore
8 | R082000038 | Susner S/s | Shajapur | MPSEB | Power |  |  | 162.94 | RIDF Loan upto 10 crore
8 | R082000041 | Nasrullaganj S/s | Sehore | MPSEB | Power |  |  | 309.7 | RIDF Loan upto 10 crore
8 | R082000042 | Seonimalwa S/s | Hoshangabad | MPSEB | Power |  |  | 369.7 | RIDF Loan upto 10 crore
8 | R082000050 | Panwadi S/s | Shajapur | MPSEB | Power |  |  | 369.7 | RIDF Loan upto 10 crore
8 | R082000059 | Kutmeli | Seoni | WRD | MIS |  |  | 90.6 | RIDF Loan upto 10 crore
8 | R082000061 | 33/11 KV Sub-Station(MVA) | Sagar | MPSEB | Power |  |  | 3.69 | RIDF Loan upto 10 crore
8 | R082000062 | 33/11 KV Sub-Station(MVA) | Rewa | MPSEB | Power |  |  | 215.48 | RIDF Loan upto 10 crore
8 | R082000063 | 33/11 KV Sub-Station(MVA) | Bhopal | MPSEB | Power |  |  | 62.97 | RIDF Loan upto 10 crore
8 | R082000065 | 33/11 KV Sub-Station(MVA) | Indore | MPSEB | Power |  |  | 149.13 | RIDF Loan upto 10 crore
8 | R082000083 | Chandan 7/2 | Balaghat | PWD | Bridge |  |  | 119.18 | RIDF Loan upto 10 crore
8 | R082000084 | Goi 3/10 | Badwani | PWD | Bridge |  |  | 112.22 | RIDF Loan upto 10 crore
8 | R082000085 | Halali 11/8 | Bhopal | PWD | Bridge |  |  | 47.2 | RIDF Loan upto 10 crore
8 | R082000089 | Bamuriya nalla 15/2 | Ashoknagar | PWD | Bridge |  |  | 27.78 | RIDF Loan upto 10 crore
8 | R082000091 | Patpara 8/6 | Katni | PWD | Bridge |  |  | 29.39 | RIDF Loan upto 10 crore
8 | R082000097 | Maleni 7/2 | Ratlam | PWD | Bridge |  |  | 76.9 | RIDF Loan upto 10 crore
8 | R082000099 | Kalisindh 1/2 | Shajapur | PWD | Bridge |  |  | 116.09 | RIDF Loan upto 10 crore
8 | R082000101 | Kalisindh 10/2 | Shajapur | PWD | Bridge |  |  | 170.26 | RIDF Loan upto 10 crore
8 | R082000105 | Chamla 1/6 | Ujjain | PWD | Bridge |  |  | 76.97 | RIDF Loan upto 10 crore
8 | R082000115 | Bagaimata Tank | Khargone | WRD | MIS |  |  | 79.84 | RIDF Loan upto 10 crore
9 | R092000088 | Saroth | Chhindwara | WRD | MIS | 2009-03-19 | DDM | 832.46 | RIDF Loan upto 10 crore | Main canal is 51-75% complete.H.W.,spillways,H.R. are more than 76% complete.TOR was due to L.A..COR was due to revision in La cost.Senior engineers of WRD visited the projects.Test were carried out,records were maintained,NABARD assistance displayed.
9 | R092000025 | Holinal | Khargone | WRD | MIS | 2009-03-18 | DDM | 140.97 | RIDF Loan upto 10 crore | HW,SW,HR >76% completed MC, BC upto 25% completed Problems in lA dur to mismatch of record Sr engineers visited. Records maintained Assistance displayed. Contractor problem is leading to retendering
9 | R092000022 | Dehri No. 2 | Khargone | WRD | MIS | 2009-03-04 | DDM | 605.78 | RIDF Loan upto 10 crore | HW,SW,HR 100% completed MC 80% completed CD 21% completed Sr engi visited Tests carried Records maintained LA due to standing Kharif crops leading to TOR 1.7Km MC to be crops.Tendering for minor canals to completed Ass diplayed
9 | R092000128 | Sonar 42/8 | Sagar | PWD | Bridge | 2009-02-05 | DDM | 151.7 | RIDF Loan upto 10 crore | FOund, Pier, abut Super struc appr rosd >76% completed Tests carried out.NABARD assistance not displayed. The bridge facilitated all weather connectivity
9 | R092000135 | Janar 47/2 | Umaria | PWD | Bridge | 2009-01-22 | DDM | 48.67 | RIDF Loan upto 10 crore | Foundation >75% Super stru & sub struc 51-75% Appr Rd >75% contractor repalced 2 piers reanmining tests carried out test records maintained .NABARD assistance not displayed
9 | R092000019 | Shivsagar | Jhabua | WRD | MIS | 2009-01-20 | DDM | 528.16 | RIDF Loan upto 10 crore | Work is more than 75 % completed.TOR due to LA and contrcators problems. ZSr engineers visiting the project. Test records maintained NABARD assistance displayed
9 | R092000136 | Lbc Canal Rd 111-130 Km | Narsinghpur | NVDA | MJP | 2009-01-13 | DDM | 5835.2 | RIDF Loan 25 crore & above | Diastri sun minors > 76% Masnry lining of Main canal 25-50%Prel LA and EW of MCmore than 76% completedTOr due to dely Forest land shifting of poles COr due to LA incre cost. Visit records not shown, tests records not maintained Sl prog Board not displaye
9 | R092000097 | Kushalpura | RAJGARH | WRD | MIP | 2009-01-06 | DDM | 5269.29 | RIDF Loan 25 crore & above | TOR likly 30 June 10 COr likely, contrcators problem quality tests carried out rexcords maintained delay ion LA land for canal yet to be acquired Multiplicy of agencies to execute works. Inadequate monmitoring Board not displayed
9 | R092000086 | Rajdongri | Chhindwara | WRD | MIS | 2008-12-29 | DDM | 296.51 | RIDF Loan upto 10 crore | Time over run due to delayed LA, Cost over run due to structural changes.Senior engineers visit records maintainedNABARD assistance displayed. Canal works yet to be tested. Construction work completed
9 | R092000034 | Mohanpura | Rajgarh | WRD | MIS | 2008-12-04 | DDM | 219.94 | RIDF Loan upto 10 crore | Head way,spill way and head regulator completed, main canal ,branch canal and minor26-50%CD upto 25%Time overun due to o/s canal work, Tech sanc delay,delay in LA. Cost overrun due to LA and incre canal no visits No board pilfering by villagers
9 | R092000010 | Mohanpur | Ashoknagar | WRD | MIS | 2008-10-22 | DDM | 49.97 | RIDF Loan upto 10 crore | Time overrun due to LA.Cost overrun due to change design incr EW. Change in strata of spill way Mon by senior officials of WRd. Quality tests done. recordd maintained NABARD brd not displayed.WUA not formed. No provison for maintenanc Pot 58 ha
9 | R092000011 | Sumeri | Guna | WRD | MIS | 2008-09-24 | DDM | 517.06 | RIDF Loan upto 10 crore | Time overrun minor and sub minor LA release of water in rabi05-06,06-07 ,07-08 Cost overrun change in design of dam section, increase in length of canal. Montrg by sen officers of WRD quality tests done NABARD brd not in format.Rem wrk in Mar09
9 | R092000108 | Parasatola Jatta Mohgaon | Balaghat | PWD | Road | 2008-08-05 | DDM | 51.9 | RIDF Loan upto 10 crore | Time over run due to naxalite problem and dispute with contrcator.Regular tests have been carried out and records maibtained. NABARD asistance displayed. Though the project was completed , it had path holes; Rs.12 Lakh payable to contractor is with held.
9 | R092000097 | Kushalpura | RAJGARH | WRD | MIP | 2008-07-15 | DDM | 5269.29 | RIDF Loan 25 crore & above | Slow progress due multiple agencies implementing the various sectors Time over frun ; The project si unlikely to be completed by 31-12-08; Delay in land acquisition for RBC and LBC; NABARD board not displayed
9 | R092000136 | Lbc Canal Rd 111-130 Km | Narsinghpur | NVDA | MJP | 2008-06-18 | DDM | 5835.2 | RIDF Loan 25 crore & above | Visit to 111 to 126.19 Km.Time overrun on account of acquisition of forest land.This has since been sorted out.Documentation of visits by engineers is not available.Test records are not maintained.NABARD asistance is not displayed
9 | R092000103 | Ramkund | Mandsaur | WRD | MIS | 2008-05-28 | DDM | 427.43 | RIDF Loan upto 10 crore | Irrigation from the tank started during the year 2007.WUA is yet to be formed. NABARD assistance is yet to be displayed.
9 | R092000104 | Satalkhedi | Mandsaur | WRD | MIS | 2008-05-21 | DDM | 68.67 | RIDF Loan upto 10 crore | Due to scanty rainfall , there is underutilization of storage capacity. WUA is to be formed . NABARD board is not displayed
9 | R092000136 | Lbc Canal Rd 111-130 Km | Narsinghpur | NVDA | MJP | 2008-05-06 | DDM | 5835.2 | RIDF Loan 25 crore & above | There was time overrun due to delay in land acquisition; delay in shifting of poles; System for quality control was introduced by the department. About 95 tests have been conducted between 01 April 2007 and 31 March 2008.NABARD assistance is not displaye
9 | r092000037 | Ghenghi | sehore | WRD | MIS | 2008-02-25 | RO Officer | 183.72 | RIDF Loan upto 10 crore | Land acquisition problem. Contents of NABARD board not visible. Needs to be repainted. Project likely to be completed by March 2008. Test records maintained in file. All tests carried out.
9 | r092000134 | Gajra 2/2 | Umaria | PWD | Bridge | 2008-02-12 | Shahdol DDM | 18.95 | RIDF Loan upto 10 crore | PCR VERIFICATION. NABARD board not put up. The dimensions and other technical details of the bridge of the PCR were verified and found correct. The bridge is open for public and serves 15 villages.
9 | r092000097 | Kushalpura | RAJGARH | WRD | MIP | 2007-12-21 | Shajapur DDM | 5269.29 | RIDF Loan 25 crore & above | NABARD board not displayed. Time and cost overrun. Delay in land acquisition, fixing agency. Slow progress. Monitoring to be done regularly.
9 | r092000022 | Dehri No. 2 | Khargone | WRD | MIS | 2007-12-19 | Khargone DDM | 605.78 | RIDF Loan upto 10 crore | Delay due to land acquisition. NABARD board displayed.
9 | r092000088 | Saroth | Chhindwara | WRD | MIS | 2007-11-22 | Chindwara DDM | 832.46 | RIDF Loan upto 10 crore | NABARD board displayed but not at site. Test records maintained. Delay in land acquisition.
9 | r092000122 | Onai 15/2 | Bhind | PWD | Bridge | 2007-06-13 | Morena DDM | 27.82 | RIDF Loan upto 10 crore | NABARD board has been displayed. Land acquisition problem. Frequent visits are taking place.
9 | r092000027 | Jhunapani | Khargone | WRD | MIS | 2007-06-06 | Khargone DDM | 198.82 | RIDF Loan upto 10 crore | NABARD board has been displayed. There is contractors problem.
9 | r092000136 | Lbc Canal Rd 111-130 Km | Narsinghpur | NVDA | MJP | 2007-05-17 | Narsinghpur DDM | 5835.2 | RIDF Loan 25 crore & above | NABARD board has not been displayed. Delay on account of acquisition of forest land.
9 | r092000025 | Holinal | Khargone | WRD | MIS | 2007-05-16 | Khargone DDM | 140.97 | RIDF Loan upto 10 crore | Time overrun because of delay in land acquisition for canals. NABARD board has been displayed. Monitoring is regular.
9 | r092000026 | Selda | Khargone | WRD | MIS | 2007-05-15 | Khargone DDM | 50.83 | RIDF Loan upto 10 crore | There is time overrun because the contractor couldn't execute the construction work on time. Dept. may take necessary steps to expedite the canal work by retendering the process.
9 | r092000001 | Ralawati | Badwani | WRD | MIP | 2007-05-14 | Khargone DDM | 1320.29 | RIDF Loan 10.01-24.99 crore | Delay in land acquisition. Increase in land cost. NABARD board has been displayed. Monitoring visits are regular.
9 | R092000135 | Janar 47/2 | Umaria | PWD | Bridge | 2007-05-11 | Shahdol DDM | 48.67 | RIDF Loan upto 10 crore | Progress is very slow. Contractor is not active. NABARD board has not been displayed. As the bridge will reduce nearly 30 KMs from Shahdol to Manpur early completion will benefit the people. Quality is satisfactory.
9 | r092000019 | Shivsagar | Jhabua | WRD | MIS | 2007-04-18 | Jhabua DDM | 528.16 | RIDF Loan upto 10 crore | Slow progress. Due to slow progress of canal work, contractor could not complete the work in stipulated time. NABARD board has been displayed. More than 75% of the work is the progress.
9 | r092000011 | Sumeri | Guna | WRD | MIS | 2007-04-17 | RO Officer | 517.06 | RIDF Loan upto 10 crore | More than 76% of the work has been completed under all items of work. NABARD board has been displayed but in the prescribed format. Due to delay in acquisition of land there is time overrun.
9 | R092000136 | Lbc Canal Rd 111-130 Km | Narsinghpur | NVDA | MJP | 2007-04-17 | Narsinghpur DDM | 5835.2 | RIDF Loan 25 crore & above | Time overrun because of delay in land acquisition. Documentation of visits carried out by EE and CE not available. NABARD board has not been displayed.
9 | r092000040 | Rusalli Sahu | Vidisha | WRD | MIS | 2007-03-21 | Vidisha DDM | 100.95 | RIDF Loan upto 10 crore | No physicalf work was going on in the site. Records are maintained. NABARD board has not been displayed. Supt. Engineer and Executive Engineers visit the site.
9 | r092000041 | Rusia | Vidisha | WRD | MIS | 2007-03-21 | Vidisha DDM | 277.91 | RIDF Loan upto 10 crore | No physical work was going on in the site. No pucca approach raod has been constructed by the Dept. for approaching the project.
9 | r092000115 | Karahal Sarai | Sheopur | PWD | Road | 2007-02-21 | Shivpuri DDM | 63.86 | RIDF Loan upto 10 crore | 85% work is completed. Rectification of defects has to be carried out. At present work is completely stopped. NABARD board has not been displayed.
9 | r092000007 | Jhirlinga | Chhindwara | WRD | MIS | 2007-01-31 | Chindwara DDM | 128.66 | RIDF Loan upto 10 crore | Major portion of the work has been completed. Delay because of land acquisition. NABARD board has been displayed. EE has visited the project regularly.
9 | r092000008 | Dhanora | Chhindwara | WRD | MIS | 2007-01-31 | Chindwara DDM | 131.94 | RIDF Loan upto 10 crore | Major portion of the work has been completed. Delay because of land acquisition problem. NABARD board has been displayed.
9 | r092000048 | Silgi 13/8 | Dindori | PWD | Bridge | 2007-01-18 | Mandla DDM | 76.38 | RIDF Loan upto 10 crore | Project has been completed in February 2006. There is regular system of supervision & monitoring of contractors work at regular intervals by JE and EE. NABARD board has not been displayed. Only 3 out of 7 culverts have been done.
9 | r092000068 | Sengari 2/4 | Rewa | PWD | Bridge | 2007-01-17 | Rewa DDM | 23.03 | RIDF Loan upto 10 crore | NABARD board not displayed. The work is delayed. No officer above EE visited the project. Delay in LA. Completion of project is expected by 30/6/07. Bridge work is completed. Approach on Managawa side not commenced so far.
9 | r092000067 | Bihar 12/2-4 | Rewa | PWD | Bridge | 2007-01-17 | Rewa DDM | 49.94 | RIDF Loan upto 10 crore | Progress slow. In case of bridge nearly 90% foundation work is complete. No officer above the rank of EE has visited the site. The project is likely to be completed by 31-3-2008. NABARD board has not been displayed.
9 | r092000034 | Mohanpura | Rajgarh | WRD | MIS | 2007-01-12 | Shajapur DDM | 219.94 | RIDF Loan upto 10 crore | Slow progress, delay in LA, technical sanction, fixing agency for canal work. likely time overrun and cost overun. SE/CE has not visited the site . NABARD board has not been displayed.
9 | R092000050 | Siltiya 4/4 | Khandwa | PWD | Bridge | 2007-01-10 | Khandwa DDM | 58.4 | RIDF Loan upto 10 crore | NABARD board has been displayed. Quality of work is satisfactory. Happiness observed in the locals as road blocking will be over during rainy season. Slow progress. Work to be speeded up.
9 | r092000051 | Ghorwa 3/6 | Khandwa | PWD | Bridge | 2007-01-10 | Khandwa DDM | 61.11 | RIDF Loan upto 10 crore | Quality is satisfactory. Locals are happy. NABARD board has been displayed.
9 | r092000097 | Kushalpura | RAJGARH | WRD | MIP | 2007-01-09 | Shajapur DDM | 5269.29 | RIDF Loan 25 crore & above | Progress is very slow. Only head work has been completed. There is delay in land acquisition, fixing agency. NABARD board has not been displayed. No monitoring visit by SE/CE. The project will suffer from time overrun.
9 | r092000088 | Saroth | Chhindwara | WRD | MIS | 2006-12-07 | RO Officer | 832.46 | RIDF Loan upto 10 crore | Due to delay in land acquisition and payment of compensation there was delay in start of work. The left bank canal work at dam site is almost complete and about 50% of the right bank completed. No other problems are foreseen for completing the works.
9 | r092000086 | Rajdongri | Chhindwara | WRD | MIS | 2006-12-07 | RO Officer | 296.51 | RIDF Loan upto 10 crore | The trees uprooted in the dam area were lying in the site pending permission from the Forest Dept. for their removal. No cost overrun except in the case of land acquisition as the value as per award was more than the estimates.
9 | r092000082 | Janakpura | Indore | WRD | MIS | 2006-12-01 | Indore DDM | 125.97 | RIDF Loan upto 10 crore | Due to delay in land acquisition work has been delayed and there is increase in cost. NABARD board has been displayed.
9 | R092000071 | Bihar 5/6 | Satna | PWD | Bridge | 2006-11-28 | DDM | 29.56 | RIDF Loan upto 10 crore | The bridge has been completed. The villagers are happy as they are in a position to take their produce to the nearest town. It has reduced a distance of 10 Kms from the nearest town. NABARD board has been displayed on one side of the bridge.
9 | r092000071 | Bihar 5/6 | Satna | PWD | Bridge | 2006-11-28 | Satna DDM | 29.56 | RIDF Loan upto 10 crore | PCR VERIFICATION. The bridge has been completed. The villagers are very happy as it has reduced a distance of 10 Kms. The villagers are happy as they are in a position to take their produce for marketing to the nearest town easily.
9 | r092000071 | Bihar 5/6 | Satna | PWD | Bridge | 2006-11-28 | Satna DDM | 29.56 | RIDF Loan upto 10 crore | The bridge is useful and has reduced 10 km distance to the nearest town. Quality of work is satisfactory.
9 | r092000075 | Khan 1/2 | Ujjain | PWD | Bridge | 2006-11-09 | Ujjain DDM | 60.46 | RIDF Loan upto 10 crore | Approach road work was going on. The work is satisfactory.
9 | r092000109 | Khapa Amla | Chhindwara | PWD | Road | 2006-09-11 | Chindwara DDM | 11.94 | RIDF Loan upto 10 crore | NABARD board displayed. 2 KM old road was in poor condition, could have been included in the project. Quality of work satisfactory.
9 | R092000104 | Satalkhedi | Mandsaur | WRD | MIS | 2006-08-10 | Mandsaur DDM | 68.67 | RIDF Loan upto 10 crore | Project has been completed. NABARD board not displayed. WUA yet to be formed. PCR yet to be submitted.
9 | r092000135 | Janar 47/2 | Umaria | PWD | Bridge | 2006-07-27 | Shahdol DDM | 48.67 | RIDF Loan upto 10 crore | Contractor not active. Very slow progress. NABARD board not displayed.
9 | R092000134 | Gajra 2/2 | Umaria | PWD | Bridge | 2006-07-27 | Shahdol DDM | 18.95 | RIDF Loan upto 10 crore | Quality of work was satisfactory. NABARD board not displayed.
9 | r092000050 | Siltiya 4/4 | Khandwa | PWD | Bridge | 2006-07-21 | Khandwa DDM | 58.4 | RIDF Loan upto 10 crore | Slow progress. No monitoring. Work since halted. Contractor is daily based and not turning up.
9 | R092000129 | Dhasan 1/2-4 | Sagar | PWD | Bridge | 2006-07-14 | Sagar DDM | 90.62 | RIDF Loan upto 10 crore | Quality of work appears to be satisfactory. NABARD board not displayed. Work delayed due to land acquisition.
9 | R092000088 | Saroth | Chhindwara | WRD | MIS | 2006-06-13 | Chindwara DDM | 832.46 | RIDF Loan upto 10 crore | NABARD board displayed. Site visited regularly.
9 | R092000073 | Mahan 2/6 | Sidhi | PWD | Bridge | 2006-06-06 | Rewa DDM | 59.08 | RIDF Loan upto 10 crore | NABARD board is not displayed. Work is being done very slowly by contractor.
9 | r092000052 | Rewa 2/4 | Mandsaur | PWD | Bridge | 2006-06-02 | Mandsaur DDM | 34.07 | RIDF Loan upto 10 crore | NABARD board not displayed. Work delayed. Early completion to be pursued.
9 | r092000015 | Patbardi | Alirajpur | WRD | MIS | 2006-05-26 | Jhabua DDM | 69.07 | RIDF Loan upto 10 crore | The project has been completed. NABARD board has been displayed. Farmers have been benefitted.
9 | R092000103 | Ramkund | Mandsaur | WRD | MIS | 2006-05-01 | Mandsaur DDM | 427.43 | RIDF Loan upto 10 crore | Delay in land acquisition is hindering the pace of progress. NABARD board is not displayed.
9 | R092000100 | Viramkho | GUNA | WRD | MIS | 2006-04-26 | Guna DDM | 41.3 | RIDF Loan upto 10 crore | NABARD board not displayed. Land acquisition compensation to be paid.
9 | R092000079 | Ambeh | Guna | WRD | MIS | 2006-04-26 | Guna DDM | 94.68 | RIDF Loan upto 10 crore | CCA is not plain area. NABARD board not displayed.
9 | R092000001 | Ralawati | Badwani | WRD | MIP | 2006-04-25 | Khargone DDM | 1320.29 | RIDF Loan 10.01-24.99 crore | Work was stopped due to agitation by Adiwasi Sangathan.
9 | R092000136 | Lbc Canal Rd 111-130 Km | Narsinghpur | NVDA | MJP | 2006-04-21 | Narsinghpur DDM | 5835.2 | RIDF Loan 25 crore & above | Project not yet complete. Progress is very slow. NABARD board not displayed.
9 | r092000010 | Mohanpur | Ashoknagar | WRD | MIS | 2006-04-18 | Guna DDM | 49.97 | RIDF Loan upto 10 crore | NABARD board not displayed.
9 | r092000087 | Kadwaya Feeder | Ashoknagar | WRD | MIS | 2006-04-18 | Guna DDM | 99.8 | RIDF Loan upto 10 crore | NABARD board not displayed. Quality of work is satisfactory.
9 | r092000065 | Awana 2/2 | Mandsaur | PWD | Bridge | 2006-04-08 | Mandsaur DDM | 35.81 | RIDF Loan upto 10 crore | NABARD board not displayed. Slow progress
9 | r092000126 | Chambal 13/6 | Mandsaur | PWD | Bridge | 2006-04-08 | Mandsaur DDM | 203.58 | RIDF Loan upto 10 crore | The progress is very slow because of land acquisition problem.
9 | R092000136 | Lbc Canal Rd 111-130 Km | Narsinghpur | NVDA | MJP | 2006-04-04 | Narsinghpur DDM | 5835.2 | RIDF Loan 25 crore & above | No work is in progress as the contractor is being replaced.
9 | R092000046 | Katanga 3/8 | Balaghat | PWD | Bridge | 2006-03-25 | DDM | 46.7 | RIDF Loan upto 10 crore | Project completed and PCR submitted. NABARD board not displayed.
9 | R092000092 | Bhajipani | Chhindwara | WRD | MIS | 2006-03-23 | DDM | 63.05 | RIDF Loan upto 10 crore | Project completed.
9 | R092000031 | Lopiya | neemuch | WRD | MIS | 2006-03-22 |  | 38.22 | RIDF Loan upto 10 crore
9 | R092000095 | Thaori | Chhindwara | WRD | MIS | 2006-03-14 | DDM | 312.26 | RIDF Loan upto 10 crore | Headwork in progress.
9 | R092000003 | Kekra | Chhindwara | WRD | MIS | 2006-03-13 | DDM | 349.53 | RIDF Loan upto 10 crore | Project completed.
9 | R092000088 | Saroth | Chhindwara | WRD | MIS | 2006-03-07 | DDM | 832.46 | RIDF Loan upto 10 crore | Unit I Headwork 35% complete. Project likely to be completed by June 2006.
9 | R092000101 | Jateri | GUNA | WRD | MIS | 2006-03-04 | DDM | 96.13 | RIDF Loan upto 10 crore | Headworks completed. Work is in progress in canal system.
9 | R092000076 | Pipliya Khushal | Guna | WRD | MIS | 2006-03-04 | DDM | 165.45 | RIDF Loan upto 10 crore | Project completed excepting 2 CD works. Delay in Land acquisition and payment to farmers observed.
9 | R092000077 | Umarthana | Guna | WRD | MIS | 2006-03-04 | DDM | 85.67 | RIDF Loan upto 10 crore | Project is completed in all respects. LA of submergence land is under progress.
9 | R092000035 | Pagara | Rajgarh | WRD | MIS | 2006-03-03 | DDM | 96.69 | RIDF Loan upto 10 crore | Headworks completed. 11 out of 13 CD works completed. Work is in progress
9 | R092000032 | Shankarpura | Rajgarh | WRD | MIS | 2006-03-03 | DDM | 113.72 | RIDF Loan upto 10 crore | Except for the puddle on the right flank, work is yet to start. Progress is slow.
9 | R092000097 | Kushalpura | RAJGARH | WRD | MIP | 2006-03-03 | DDM | 5269.29 | RIDF Loan 25 crore & above | Progress is slow. Land for canal works acquired and land for canals is yet to be acquired. Project is likely to be completed by 31-3-2008 due to delayed start.
9 | R092000031 | Lopiya | neemuch | WRD | MIS | 2006-03-02 | DDM | 38.22 | RIDF Loan upto 10 crore | PCR verified. Project is complete in all respect.
9 | R092000033 | Dhanwas Kalan | Rajgarh | WRD | MIS | 2006-03-01 | DDM | 211.52 | RIDF Loan upto 10 crore | Delay in land acquisition . Slow work progress. Project likely to be completed by 30-6-06. NB board not displayed.
9 | R092000102 | Gangapat | Khandwa | WRD | MIS | 2006-02-15 | DDM | 69.69 | RIDF Loan upto 10 crore | Headwork completed. Filling to be done in the down portion. Canal work has been completed.
9 | R092000020 | Mirpur | khandwa | WRD | MIS | 2006-02-15 | DDM | 58.77 | RIDF Loan upto 10 crore | Headwork competed. Land acquired for canal but work has not been started. Re-tendering has been done.
9 | R092000098 | Karidongri | Chhindwara | WRD | MIS | 2006-02-14 | DDM | 214.04 | RIDF Loan upto 10 crore | Progress in Unit I 75% and in Unit II 65%. Work is in progress.
9 | R092000073 | Mahan 2/6 | Sidhi | PWD | Bridge | 2006-02-04 | DDM | 59.08 | RIDF Loan upto 10 crore | Foundation work is in progress. Project is likely to be completed by Mar 2007. NABARD Board is not displayed.
9 | R092000042 | Tarana Limbadit | Ujjain | PWD | Road | 2006-02-03 | DDM | 117.66 | RIDF Loan upto 10 crore | Work is in progress. Progress was slow due to non availability of water for compacting.
9 | R092000071 | Bihar 5/6 | Satna | PWD | Bridge | 2006-02-02 | DDM | 29.56 | RIDF Loan upto 10 crore | Bridge is completed. Approach road is yet to be completed as LA on Padaha side is yet to be done.
9 | R092000071 | Bihar 5/6 | Satna | PWD | Bridge | 2006-02-02 | DDM | 29.56 | RIDF Loan upto 10 crore | Foundation, sub structure and super structure completed. Construction of approach road is yet to be completed. Delay due to land acquisition.
9 | R092000116 | Sukha Amkheda Satpada Hat | Vidisha | PWD | Road | 2006-01-28 | DDM | 73.01 | RIDF Loan upto 10 crore | 5.2 km out of 5.5 km sanctioned road length is completed. All CD works are completed. Likely to be completed by March 2006.
9 | R092000117 | Golana Satapada Hat | Vidisha | PWD | Road | 2006-01-28 | DDM | 43.09 | RIDF Loan upto 10 crore | WBM and BT completed in 4.5 km out of 5 km sanctioned length. Project is likely to be completed by March 2006.
9 | R092000118 | Gurod Pipabadhar To Sukh Amkheda Ro | Vidisha | PWD | Road | 2006-01-28 | DDM | 61.83 | RIDF Loan upto 10 crore | All works are completed excepting BT in 1 km length. Project is likely to be completed by March 2006.
9 | r092000063 | Ajnal 14/4 | Khandwa | PWD | Bridge | 2005-12-17 | DDM | 56.22 | RIDF Loan upto 10 crore | 3 out of 5 piers completed. However, contractor has stopped work. Dept. may iniatite necessary action for completing the project in time.
9 | r092000109 | Khapa Amla | Chhindwara | PWD | Road | 2005-12-15 | DDM | 11.94 | RIDF Loan upto 10 crore | Project is completed.
9 | r092000014 | Tilsani | jabalpur | WRD | MIS | 2005-12-13 | DDM | 39.08 | RIDF Loan upto 10 crore | Work is in progress
9 | R092000019 | Shivsagar | Jhabua | WRD | MIS | 2005-12-09 | DDM | 528.16 | RIDF Loan upto 10 crore | 1. Project is nearing completion. 2. Implementation satisfactory.
9 | R092000054 | Kurel 12/8 | Ratlam | PWD | Bridge | 2005-12-09 | DDM | 70.35 | RIDF Loan upto 10 crore | Work is in progress. Likely to be completed by March 2006.
9 | r092000052 | Rewa 2/4 | Mandsaur | PWD | Bridge | 2005-12-08 | DDM | 34.07 | RIDF Loan upto 10 crore | Tendering completed. As per agreement the work is to be completed by August 2005. However, present progress is only 30%.
9 | r092000051 | Ghorwa 3/6 | Khandwa | PWD | Bridge | 2005-12-06 | DDM | 61.11 | RIDF Loan upto 10 crore | Structure of the bridge is completed. Approach on Diwal side of the bridge needs improvement.
9 | r092000050 | Siltiya 4/4 | Khandwa | PWD | Bridge | 2005-12-06 | DDM | 58.4 | RIDF Loan upto 10 crore | Foundation work completed upto 50%. Contractor stopped the work for the last 6 months.
9 | R092000012 | Rampuriya Buzurg | indore | WRD | MIS | 2005-12-01 | DDM | 115.84 | RIDF Loan upto 10 crore | (1) Project is complete in all respects. (2) Irrigation provided to 110 ha during the last season. (3) WUA is yet to be formed.
9 | R092000013 | Khedisihod | Indore | WRD | MIS | 2005-12-01 | DDM | 104.94 | RIDF Loan upto 10 crore | (1) Project is completed. (2) Irrigation already provided to 68 ha. (3) WUA is yet to be formed.
9 | R092000016 | Kobra Nalla Storage | Alirajpur | WRD | MIS | 2005-12-01 | DDM | 71.85 | RIDF Loan upto 10 crore | (1) Work under progress and is likely to be completed by June 2006. (2) NABARD board not displayed.
9 | R092000070 | Tons 10/4 | Satna | PWD | Bridge | 2005-11-30 | DDM | 64.9 | RIDF Loan upto 10 crore | Foundation is completed. Work on sub structure and super structures is in progress. Likely to be completed by June 2006.
9 | R092000136 | Lbc Canal Rd 111-130 Km | Narsinghpur | NVDA | MJP | 2005-11-29 | DDM | 5835.2 | RIDF Loan 25 crore & above | (1) Preliminary and Land acquisition completed (2) Earthwork completed upto 47% (3) Likely date of completion 18 May 2006
9 | R092000040 | Rusalli Sahu | Vidisha | WRD | MIS | 2005-11-16 | DDM | 100.95 | RIDF Loan upto 10 crore | (1) Agency for Unit II is yet to be fixed.
9 | R092000056 | Gopad 12/4 | Sidhi | PWD | Bridge | 2005-11-12 | DDM | 71.82 | RIDF Loan upto 10 crore | 1. Pace of implementation is slow - As per agreement the work should have been completed by February 2005, but due to slow progress it is likely to be completed in March 2006. 2. NABARD board is not displayed
9 | R092000104 | Satalkhedi | Mandsaur | WRD | MIS | 2005-11-08 | DDM | 68.67 | RIDF Loan upto 10 crore | (1) Unit I completed. (2) 75% of masonry structures and 85% of excavation completed in respect of Unit II. (3) Likely to be completed by March 2006. (4) NABARD board not displayed.
9 | R092000089 | Kiradia | Dhar | WRD | MIS | 2005-10-05 | DDM | 193.1 | RIDF Loan upto 10 crore | 1. Progress is slow. 2. NABARD Board is not displayed.
9 | R092000031 | Lopiya | neemuch | WRD | MIS | 2005-10-03 | DDM | 38.22 | RIDF Loan upto 10 crore | 1. Project is completed and irrigation provided to 63 ha during last season. 2. WUA yet to be formed. 3. NABARD Board is not displayed
9 | R092000009 | Gawala | Dhar | WRD | MIS | 2005-09-30 | DDM | 83.01 | RIDF Loan upto 10 crore | 1. Headworks completed upto 80%. 2. Canal work is in progress. 3. NABARD Board is not displayed
9 | r092000045 | Rakoda Maukheri Riyawa | Ratlam | PWD | Road | 2005-09-27 | DDM | 30.75 | RIDF Loan upto 10 crore | Collection of material is in progress. NABARD Board not displayed.
9 | r092000044 | Bargar Uparwara BS | Ratlam | PWD | Road | 2005-09-23 | DDM | 6.5 | RIDF Loan upto 10 crore | Works have been completed. NABARD board is not displayed.
9 | R092000103 | Ramkund | Mandsaur | WRD | MIS | 2005-09-20 | DDM | 427.43 | RIDF Loan upto 10 crore | The progress of work under Unit-II is slow due to problems in land acquisition. The department has to closely follow up with the revenue authorities to solve the land acquisitlion problems.
9 | R092000126 | Chambal 13/6 | Mandsaur | PWD | Bridge | 2005-09-09 | DDM | 203.58 | RIDF Loan upto 10 crore | The project is expected to be completed in February 2006 and quality of work is satisfactory. NABARD board has not been displayed and the department should arrange to display the same.
9 | R092000068 | Sengari 2/4 | Rewa | PWD | Bridge | 2005-06-29 | DDM | 23.03 | RIDF Loan upto 10 crore | 1)Progress in imlplentation is slow. Nearly 80% work is complete. Approach road work on Managawa side has not commenced so far. 20 No visits were undertaken by any Officer above the rank of EE and no such records were maintained at the site.
9 | R092000080 | Roopkheda | Khargone | WRD | MIS | 2005-06-24 | DDM | 55.8 | RIDF Loan upto 10 crore | The progress of the project work is satisfactory and is likely to be completed by 30.06.2005.
9 | R092000026 | Selda | Khargone | WRD | MIS | 2005-06-23 | DDM | 50.83 | RIDF Loan upto 10 crore | The nala closure and canal work was yet to be completed. The contractor was not willing to work. Irrigation department is pursuing with the contractor. Likely date of completion of the project is 31.12.2005.
9 | R092000013 | Khedisihod | Indore | WRD | MIS | 2005-06-07 | OIC+RO Officials | 104.94 | RIDF Loan upto 10 crore | Entire head works have been completed. Work is going on in respect of 2 falls on spillway and syphon on the canal. The structures proposed on the right bank canal are : 1 syphon at RD 315 mt, 1 VRB at RD 405 mt, 1 syphon on nala at RD 705.
9 | R092000012 | Rampuriya Buzurg | indore | WRD | MIS | 2005-06-07 | OIC+RO Officials | 115.84 | RIDF Loan upto 10 crore | Headworks have been completed and the canal works have also been completed by December 2004. The irrigation benefits have already started flowing in. Recharging of groundwater structures have been reported in the upstream of the project.
9 | R092000082 | Janakpura | Indore | WRD | MIS | 2005-06-06 | OIC+RO Officials | 125.97 | RIDF Loan upto 10 crore | Excavation of earthwork in progress. Rs. 68.94 lakhs deposited with the LA Officers for acquiring the land for headworks and canals. Rs. 7.50 lakhs has been spent on the project work so far. The works are scheduled to be completed by Dec. 2005.
9 | R092000072 | Indar 1/2 | Shivpuri | PWD | Bridge | 2005-06-04 | DDM | 31.94 | RIDF Loan upto 10 crore | Bridge work is completed. NABARD board is not displayed. The EE has not so far given the the details of physical and financial achievement.
9 | R092000096 | Dabia Govind Tank | Shivpuri | WRD | MIS | 2005-04-20 | DDM | 85.86 | RIDF Loan upto 10 crore | The progress is slow. There is no continuity in work. NABARD Board was displayed but not as per specification.
9 | R092000065 | Awana 2/2 | Mandsaur | PWD | Bridge | 2005-03-31 | DDM | 35.81 | RIDF Loan upto 10 crore | The boring work for pier has been completed. NABARD Board was not displayed.
9 | R092000095 | Thaori | Chhindwara | WRD | MIS | 2005-03-30 | DDM | 312.26 | RIDF Loan upto 10 crore | Work was just started. Excavation for puddle, sluice and filters was in progress.
9 | R092000028 | Main Gaon Guwadi | Khargone | WRD | MIS | 2005-03-28 | DDM | 270.4 | RIDF Loan upto 10 crore | Report yet to be submitted.
9 | R092000052 | Rewa 2/4 | Mandsaur | PWD | Bridge | 2005-03-28 | DDM | 34.07 | RIDF Loan upto 10 crore | The work on the bridge has just commenced. design work is in progress. NABARD Board was not displayed.
9 | R092000054 | Kurel 12/8 | Ratlam | PWD | Bridge | 2005-03-24 | DDM | 70.35 | RIDF Loan upto 10 crore | The work is in progress and likely to be completed by June 05. NABARD Board was not displayed.
9 | R092000132 | Chhoti Kalisindh 3/10 | Ujjain | PWD | Bridge | 2005-03-22 | DDM | 73.15 | RIDF Loan upto 10 crore | The work has been recently started. Only excavation work has done. NABARD Board was not displayed.
9 | R092000042 | Tarana Limbadit | Ujjain | PWD | Road | 2005-03-22 | DDM | 117.66 | RIDF Loan upto 10 crore | The work has recently started. Non allocation of funds was the major bottleneck. NABARD Board was not displayed.
9 | R092000091 | Ramgarhi | Chhindwara | WRD | MIS | 2005-03-21 | DDM | 74.64 | RIDF Loan upto 10 crore | Work is in progress. WRD should take appropriate action against the contractor/stop making payments in case instructions issued by Engineers not followed. Senior officers should visit the project frequently.
9 | R092000032 | Shankarpura | Rajgarh | WRD | MIS | 2005-03-19 | DDM | 113.72 | RIDF Loan upto 10 crore | Report yet to be submitted.
9 | R092000097 | Kushalpura | RAJGARH | WRD | MIP | 2005-03-19 | DDM | 5269.29 | RIDF Loan 25 crore & above | Report yet to be submitted.
9 | R092000022 | Dehri No. 2 | Khargone | WRD | MIS | 2005-03-19 | DDM | 605.78 | RIDF Loan upto 10 crore | Report yet to be submitted.
9 | R092000126 | Chambal 13/6 | Mandsaur | PWD | Bridge | 2005-03-18 | DDM | 203.58 | RIDF Loan upto 10 crore | The work on the bridge has just commenced. Excavation of one abuttment and one pier has started. NABARD Board was not displyed.
9 | R092000106 | Shankarpura | Rajgarh | WRD | MIS | 2005-03-16 | DDM | 160.9 | RIDF Loan upto 10 crore | Report yet to be submitted.
9 | R092000034 | Mohanpura | Rajgarh | WRD | MIS | 2005-03-16 | DDM | 219.94 | RIDF Loan upto 10 crore | Report yet to be submitted.
9 | R092000033 | Dhanwas Kalan | Rajgarh | WRD | MIS | 2005-03-16 | DDM | 211.52 | RIDF Loan upto 10 crore | Report yet to be submitted.
9 | R092000109 | Khapa Amla | Chhindwara | PWD | Road | 2005-03-15 | DDM | 11.94 | RIDF Loan upto 10 crore | Construction was in progress. Shoulders were cleaned before consolidation and hard murram was filled up. BT work was started within a day or two. NABARD Board was not displayed.
9 | R092000014 | Tilsani | jabalpur | WRD | MIS | 2005-03-02 | DDM | 39.08 | RIDF Loan upto 10 crore | The earthwork on the dam has been started during Feb.2005. Construction of structures is under progress. The progress of the work is satisfactory. NABARD board was not displayed.
9 | R092000020 | Mirpur | khandwa | WRD | MIS | 2005-03-01 | DDM | 58.77 | RIDF Loan upto 10 crore | Head work is completed. Work on spill way is in progress. Work of canal is not started due to land aquisition. Overall 85 % work is completed.
9 | R092000102 | Gangapat | Khandwa | WRD | MIS | 2005-03-01 | DDM | 69.69 | RIDF Loan upto 10 crore | Head work and dam work are completed to the extend of 35%.
9 | R092000005 | Dolapanjara | Chhindwara | WRD | MIS | 2005-02-28 | DDM | 128.52 | RIDF Loan upto 10 crore | Work started from 22 Jan. 2004. and major work was completed at sight. Balance work were (1) Murram topping on dam (2) small cracks on the top of the sluice and (3) pitching was to be done here and there.
9 | R092000026 | Selda | Khargone | WRD | MIS | 2005-02-26 | DDM | 50.83 | RIDF Loan upto 10 crore | Report yet to be submitted.
9 | R092000081 | Gujari No. 2 | Khargone | WRD | MIS | 2005-02-25 | DDM | 53.35 | RIDF Loan upto 10 crore | Report yet to be submitted.
9 | R092000127 | Umar 18/8 | Narsinghpur | PWD | Bridge | 2005-02-23 | DDM | 68.96 | RIDF Loan upto 10 crore | The progress is slow. The contractor is new and he has never constructed any bridge. NABARD board was not displayed.
9 | R092000051 | Ghorwa 3/6 | Khandwa | PWD | Bridge | 2005-02-19 | DDM | 61.11 | RIDF Loan upto 10 crore | Tendering is completed. The work of approach road is in progress
9 | R092000031 | Lopiya | neemuch | WRD | MIS | 2005-02-19 | DDM | 38.22 | RIDF Loan upto 10 crore | NABARD Board not displayed. Overall 90% work is completed
9 | R092000050 | Siltiya 4/4 | Khandwa | PWD | Bridge | 2005-02-19 | DDM | 58.4 | RIDF Loan upto 10 crore | Tendering is completed. The work of foundation is in progress.
9 | R092000023 | Bahadpura | Khargone | WRD | MIS | 2005-02-18 | DDM | 97.48 | RIDF Loan upto 10 crore | Report yet to be submitted.
9 | R092000024 | Hirapur | Khargone | WRD | MIS | 2005-02-14 | DDM | 70.11 | RIDF Loan upto 10 crore | Report yet to be submitted.
9 | R092000049 | Morand 1/2 | Hoshangabad | PWD | Bridge | 2005-02-12 | DDM | 129.76 | RIDF Loan upto 10 crore | No progress was made so far as the design is yet to be approved by the Department. NABARD board was not displayed. The project is likely to be completed by 30.06.2006.
9 | R092000059 | Vaisely 9/10 | Bhind | PWD | Bridge | 2005-02-12 | DDM | 40.58 | RIDF Loan upto 10 crore | Project is Completed. NABARD board was not displayed.
9 | R092000123 | Kunwari 12/6 | Bhind | PWD | Bridge | 2005-02-12 | DDM | 142.86 | RIDF Loan upto 10 crore | Tendering is completed.Work of construction of bridge has not yet initiated.
9 | r092000090 | Umaria | Khargone | WRD | MIS | 2005-02-12 | DDM | 34.46 | RIDF Loan upto 10 crore | Report yet to be submitted.
9 | R092000070 | Tons 10/4 | Satna | PWD | Bridge | 2005-02-10 | DDM | 64.9 | RIDF Loan upto 10 crore | Cement Concrete work of piers and excavation of abutments was in progress. NABARD Board was not displayed. Award in regard to land acquisition of 0.864 ha was yet to be passed by Collector Office.
9 | R092000071 | Bihar 5/6 | Satna | PWD | Bridge | 2005-02-10 | DDM | 29.56 | RIDF Loan upto 10 crore | Excavation work of piers and abutments was in progress.As per Contractor, the design was received in August 2004. Land acquisition of 0.31 ha. was not done. Award yet to be passed by Collector. NABARD Board was not displayed.
9 | R092000007 | Jhirlinga | Chhindwara | WRD | MIS | 2005-02-08 | DDM | 128.66 | RIDF Loan upto 10 crore | Tendering is completed. Dam construction was completed, however, supplementary work like pitching , murram tapping and canal work was in progress.
9 | R092000130 | Wainganga 11/4 | Seoni | PWD | Bridge | 2005-01-28 | DDM | 86.77 | RIDF Loan upto 10 crore | About 30% of the work was completed, however, no payment was made to the Contractor as on the date of visit. NABARD Board was not displayed.
9 | R092000098 | Karidongri | Chhindwara | WRD | MIS | 2005-01-27 | DDM | 214.04 | RIDF Loan upto 10 crore | The barrage( cross trench across the river) filling with black soil, filling of filters with garvels, boulders etc. and right hand sluice-gate work was in progress.
9 | R092000056 | Gopad 12/4 | Sidhi | PWD | Bridge | 2005-01-23 | DDM | 71.82 | RIDF Loan upto 10 crore | Progress is very slow. In case of bridge, foundation work and sub structure work except cap work of 11 piers and sub structure work of 13 slabs was completed. Approach road work is yet to commence.
9 | R092000044 | Bargar Uparwara BS | Ratlam | PWD | Road | 2005-01-14 | DDM | 6.5 | RIDF Loan upto 10 crore | Work completed. Patch work required at many places. NABARD Board was not displayed.
9 | R092000068 | Sengari 2/4 | Rewa | PWD | Bridge | 2005-01-09 | DDM | 23.03 | RIDF Loan upto 10 crore | The progress is very slow. In case of bridge, only 31% foundation work ( for 1 unit of 2 boxes ) was completed and sub-structure work of one abutment and 2 boxes was in progress. As regards approach road only some earthwork was done on Budawa side.
9 | R092000104 | Satalkhedi | Mandsaur | WRD | MIS | 2005-01-09 | DDM | 68.67 | RIDF Loan upto 10 crore | The progress is hampered due to the problem of land acquisition. Dept. may closely follow up the matter of land acquisition with revenue authorities.
9 | R092000103 | Ramkund | Mandsaur | WRD | MIS | 2004-12-24 | DDM | 427.43 | RIDF Loan upto 10 crore | No progress could be made so far in Unit II due to land acquisition problem. NABARD Board not displayed.
9 | R092000039 | Suwagaon | shajapur | WRD | MIS | 2004-12-23 | DDM | 113.62 | RIDF Loan upto 10 crore | Report yet to be submitted.
9 | R092000016 | Kobra Nalla Storage | Alirajpur | WRD | MIS | 2004-12-09 | DDM | 71.85 | RIDF Loan upto 10 crore | Only 80% of the earthwork has been completed. The tank is without canals in the estimation. WUA has not formed so far. NABARD Board not displayed. Maintenance arrangement should be made.
9 | R092000128 | Sonar 42/8 | Sagar | PWD | Bridge | 2004-12-09 | DDM | 151.7 | RIDF Loan upto 10 crore | The work has just started and likely to be completed by December 2005. NABARD Board has not displayed.
9 | R092000128 | Sonar 42/8 | Sagar | PWD | Bridge | 2004-12-09 | RO Official | 151.7 | RIDF Loan upto 10 crore | Report submitted
9 | R092000015 | Patbardi | Alirajpur | WRD | MIS | 2004-12-08 | DDM | 69.07 | RIDF Loan upto 10 crore | Only 6% of the earthwork has been completed. The contractor has left the work during the month of June2004. WUA not formed so far. NABARD Board not displayed. Maintenance arrangement should be made.
9 | R092000017 | Guneri | Alirajpur | WRD | MIS | 2004-12-07 | DDM | 73.72 | RIDF Loan upto 10 crore | 95% of the earthwork and 55 % of the canalwork has been completed. WUA has not formed so far. NABARD Board not displayed. Maintenance arrangement should be made.
9 | r092000085 | Jhamiya | Mandsaur | WRD | MIS | 2004-12-02 | DDM | 96.12 | RIDF Loan upto 10 crore | The work in progress is satisfactory. NABARD Board not displayed.
9 | R092000092 | Bhajipani | Chhindwara | WRD | MIS | 2004-11-24 | DDM | 63.05 | RIDF Loan upto 10 crore | 95 % of the work was completed. Canal work was in progress, which s likely to be completed by the end of Dec. 04.
9 | R092000003 | Kekra | Chhindwara | WRD | MIS | 2004-11-19 | DDM | 349.53 | RIDF Loan upto 10 crore | Work started recently. However the work was in full swing. The project is likely to be completed by March 2005.
9 | R092000101 | Jateri | GUNA | WRD | MIS | 2004-10-20 | DDM | 96.13 | RIDF Loan upto 10 crore | The progress of the work is satisfactory. 70% of dam work is completed. NABARD Board not displayed. LA compensation not passed to the farmers till date.
9 | R092000077 | Umarthana | Guna | WRD | MIS | 2004-10-20 | DDM | 85.67 | RIDF Loan upto 10 crore | The main construction of water tank is almost completed. The construction of canal work is not yet started. NABARD Board not displayed.
9 | R092000076 | Pipliya Khushal | Guna | WRD | MIS | 2004-10-20 | DDM | 165.45 | RIDF Loan upto 10 crore | 30% of the dam work is completed. The legal process of land aquisition and payment of compensation amount is not initiated. NABARD Board is not displayed.
9 | R092000004 | Heorasani | Chhindwara | WRD | MIS | 2004-10-12 | DDM | 105.46 | RIDF Loan upto 10 crore | The work of puddle execavation and filling was in progress. Exacavation work for filters and sluce was in progress. Overall progress was good.
9 | R092000012 | Rampuriya Buzurg | indore | WRD | MIS | 2004-09-30 | DDM | 115.84 | RIDF Loan upto 10 crore | Most of the work has been cmopleted but only a part and some approach road yet to be done.
9 | R092000013 | Khedisihod | Indore | WRD | MIS | 2004-09-30 | DDM | 104.94 | RIDF Loan upto 10 crore | Work was in progress.
9 | R092000008 | Dhanora | Chhindwara | WRD | MIS | 2004-09-12 | DDM | 131.94 | RIDF Loan upto 10 crore | During the dicussions it was revealed that original contractor M/S R.K.Jain has awarded sub contractto some other contractor. There was no proper coordination between cotractor and department. The quality of sand used in filters was poor.
9 | R092000069 | Sukhchen 1/8 | Sagar | PWD | Bridge | 2004-09-08 | DDM | 47.16 | RIDF Loan upto 10 crore | Tendering has been completed a year back. Agreement with the contractor has been executed. Work order has been issued.
9 | R092000128 | Sonar 42/8 | Sagar | PWD | Bridge | 2004-09-08 | DDM | 151.7 | RIDF Loan upto 10 crore | Work order has been issued. No major progress so far due to mansoon.
9 | R092000046 | Katanga 3/8 | Balaghat | PWD | Bridge | 2004-09-04 | DDM | 46.7 | RIDF Loan upto 10 crore | The progress of the work was satisfactory. Work was stopped due to mansoon season. NABARD Board was not displayed.
9 | R092000118 | Gurod Pipabadhar To Sukh Amkheda Ro | Vidisha | PWD | Road | 2004-08-03 | DDM | 61.83 | RIDF Loan upto 10 crore | An amount of Rs. 18.55 lakhs disbursed by NABARD,has not received by the Dept. from the State Govt. The tendering work has not been initiated .
9 | R092000043 | Namali Semaliya Gunwad | Ratlam | PWD | Road | 2004-07-05 | DDM | 9.78 | RIDF Loan upto 10 crore | PWD is treating the project as completed despite a stretch of 330m yet to be laid down. Sarpanch want this stretch to be done in concrete. PWD took up the matter with local MLA but the sarpanch is adamant. NB board not displayed. WBM:100.72%, BT:91.2%
9 | r092000040 | Rusalli Sahu | Vidisha | WRD | MIS | 2004-06-08 | DDM | 100.95 | RIDF Loan upto 10 crore | 1) Tendering for Unit I in process, for Unit II not initiated. 2) Agency for undertaking work related to Unit II has not been fixed so far. 3) NB board not displayed. 4) Prel : 83%, LA : 35%, Masonry : 50%, Earthwork : 40%
9 | r092000041 | Rusia | Vidisha | WRD | MIS | 2004-06-08 | DDM | 277.91 | RIDF Loan upto 10 crore | 1) Tendering for Unit I under process, for Unit II not initiated. 2) Agency for Unit II works has not been fixed yet. 3) Prel : 76%, LA : 41%, Masonry : 50%, Earthwork : 45%.
9 | R092000011 | Sumeri | Guna | WRD | MIS | 2004-04-24 | DDM | 517.06 | RIDF Loan upto 10 crore | NB board not displayed. WUA not formed. Rehabilitation of villagers under progress. Farmers' complaint regarding compensation not being at par with prevailing market rates of land in their areas. LA:100%,Earthwork: 5%, Masonry:80%,20%, Dam:61%,Spill:70%
9 | R092000090 | Umaria | Khargone | WRD | MIS | 2004-04-15 | DDM | 34.46 | RIDF Loan upto 10 crore | 1) LA in submergence to be completed. 2) Excavation of puddle trench over, filling in progress. Construction of filter, seepage drains and boulder toe in progress.
9 | R092000063 | Ajnal 14/4 | Khandwa | PWD | Bridge | 2004-03-19 | DDM | 56.22 | RIDF Loan upto 10 crore | Delay in tendering - tendering process yet to srart for bridge structure & not intiated for approach road.NB board not displayed.
9 | R092000022 | Dehri No. 2 | Khargone | WRD | MIS | 2004-03-12 | DDM | 605.78 | RIDF Loan upto 10 crore | Funds constraints- funds not released by Govt.due to which contractor stopped the work.
9 | R092000061 | Kalisindh 13/10 | Dewas | PWD | Bridge | 2004-03-11 | DDM | 142.42 | RIDF Loan upto 10 crore | Delay in tendering process. Work not commenced. NB board not displayed.
9 | R092000005 | Dolapanjara | Chhindwara | WRD | MIS | 2004-02-23 | DDM | 128.52 | RIDF Loan upto 10 crore | Work at sight was going on very fast .Work likely to be completed before june 04.
9 | R092000015 | Patbardi | Alirajpur | WRD | MIS | 2004-02-03 | DDM | 69.07 | RIDF Loan upto 10 crore | NB board not displayed.
9 | R092000028 | Main Gaon Guwadi | Khargone | WRD | MIS | 2004-01-24 | DDM | 270.4 | RIDF Loan upto 10 crore | Progress of implementation is as per schedule.
9 | r092000041 | Rusia | Vidisha | WRD | MIS | 2004-01-16 | DDM | 277.91 | RIDF Loan upto 10 crore | Tendering process not intiated.
9 | r092000040 | Rusalli Sahu | Vidisha | WRD | MIS | 2004-01-16 | DDM | 100.95 | RIDF Loan upto 10 crore | Tendering process not intiated. NB board not displayed.
9 | R092000023 | Bahadpura | Khargone | WRD | MIS | 2004-01-16 | DDM | 97.48 | RIDF Loan upto 10 crore | LA problem- LA process yet to be completed
9 | R092000090 | Umaria | Khargone | WRD | MIS | 2004-01-15 | DDM | 34.46 | RIDF Loan upto 10 crore | Delay in LA for Unit-I & II.
9 | R092000020 | Mirpur | khandwa | WRD | MIS | 2004-01-07 | DDM | 58.77 | RIDF Loan upto 10 crore | LA problem-the acqusition of land is yet to be approvedby Govt. Dept. has not deposited the amount to the LAO in advance.
9 | R092000002 | Kekdiya | Badwani | WRD | MIS |  |  | 55.41 | RIDF Loan upto 10 crore
9 | R092000006 | Pipariya Guwani | Chhindwara | WRD | MIS |  |  | 187.15 | RIDF Loan upto 10 crore
9 | R092000018 | Bhavpura | Jhabua | WRD | MIS |  |  | 76.86 | RIDF Loan upto 10 crore
9 | R092000029 | Dada Gaon Stop Dam | Khargone | WRD | MIS |  |  | 52.78 | RIDF Loan upto 10 crore
9 | R092000036 | Dhobipura | Rajgarh | WRD | MIS |  |  | 102.08 | RIDF Loan upto 10 crore
9 | R092000038 | Gorakhpur | seoni | WRD | MIS |  |  | 185.8 | RIDF Loan upto 10 crore
9 | R092000047 | Sendhla 1/2 | Dewas | PWD | Bridge |  |  | 38.71 | RIDF Loan upto 10 crore
9 | R092000053 | Ajnar 2/10 | Rajgarh | PWD | Bridge |  |  | 46.4 | RIDF Loan upto 10 crore
9 | R092000055 | Kaliyadeo 6/2 | Sehore | PWD | Bridge |  |  | 54.89 | RIDF Loan upto 10 crore
9 | R092000057 | Pankhi 1/10 | Tikamgarh | PWD | Bridge |  |  | 52.12 | RIDF Loan upto 10 crore
9 | R092000058 | Kshipra 3/4 | Ujjain | PWD | Bridge |  |  | 59.89 | RIDF Loan upto 10 crore
9 | R092000060 | Bairma 88/4 | Damoh | PWD | Bridge |  |  | 145.55 | RIDF Loan upto 10 crore
9 | R092000062 | Rehanda 1/4 | Jhabua | PWD | Bridge |  |  | 31.16 | RIDF Loan upto 10 crore
9 | R092000064 | Kunda 15/8 | Khargone | PWD | Bridge |  |  | 175.17 | RIDF Loan upto 10 crore
9 | R092000066 | Utaoli 1/2 | Rajgarh | PWD | Bridge |  |  | 27.22 | RIDF Loan upto 10 crore
9 | R092000074 | Sadhni 1/2 | Tikamgarh | PWD | Bridge |  |  | 64.4 | RIDF Loan upto 10 crore
9 | R092000078 | Sironji | Rajgarh | WRD | MIS |  |  | 150.04 | RIDF Loan upto 10 crore
9 | R092000083 | Keolari | Raisen | WRD | MIS |  |  | 318.83 | RIDF Loan upto 10 crore
9 | R092000084 | Dhankala | Khargone | WRD | MIS |  |  | 86.75 | RIDF Loan upto 10 crore
9 | R092000093 | Ghutna | Seoni | WRD | MIS |  |  | 209.38 | RIDF Loan upto 10 crore
9 | R092000094 | Burha Feeder | Chattarpur | WRD | MIS |  |  | 94.95 | RIDF Loan upto 10 crore
9 | R092000099 | Banka Naganpur | Chhindwara | WRD | MIS |  |  | 150.2 | RIDF Loan upto 10 crore
9 | R092000105 | Khar Kheda | RAJGARH | WRD | MIS |  |  | 71.86 | RIDF Loan upto 10 crore
9 | R092000107 | Atariya | SEONI | WRD | MIS |  |  | 171.95 | RIDF Loan upto 10 crore
9 | R092000110 | Penchi Murela | Guna | PWD | Road |  |  | 32.87 | RIDF Loan upto 10 crore
9 | R092000111 | Katangi Pola Majholi Abhana Bachaiy | Jabalpur | PWD | Road |  |  | 283.18 | RIDF Loan upto 10 crore
9 | R092000119 | Mata Mundra To Satguru Nagar | Vidisha | PWD | Road |  |  | 117.23 | RIDF Loan upto 10 crore
9 | R092000120 | Deo 7/10 | Balaghat | PWD | Bridge |  |  | 139.32 | RIDF Loan upto 10 crore
9 | R092000121 | Machna 2/6 | Betul | PWD | Bridge |  |  | 45.06 | RIDF Loan upto 10 crore
9 | R092000124 | Kanar 13./8 | Dewas | PWD | Bridge |  |  | 45.52 | RIDF Loan upto 10 crore
9 | R092000125 | Devnalia 13/8 | Dewas | PWD | Bridge |  |  | 24.06 | RIDF Loan upto 10 crore
9 | R092000133 | Gambhir 22/4 | Ujjain | PWD | Bridge |  |  | 77.51 | RIDF Loan upto 10 crore
10 | r102000020 | Pahargaon Tank | Chattarpur | WRD | MIS | 2011-03-08 | DDM | 180.77 | RIDF Loan upto 10 crore | HW,MC,CD,sluice gate wrks more than 76% complete.TOR & COR due to non clearence frm forest dept.LA,labour problem,conflict between cntrctr nd villagers & poor fund flow.NB board nt displayed.
10 | R102000049 | Deb 14/4 | Badwani | PWD | Bridge | 2010-03-31 | DDM | 113.07 | RIDF Loan upto 10 crore | The proje t has been conmpleted LA and Fund flow were the problems faced. Records
10 | R102000292 | Bakud Tank | Betul | WRD | MIS | 2010-03-30 | DDM | 937.59 | RIDF Loan upto 10 crore | HW,SW and HR >76% completed MC is 26-50% completesd. Delay in comp for LA is hampering canal work.Tests carried out . Records maintained. Assistance displayed.
10 | r102000291 | Bistan-Tensemali | Khargone | PWD | Road | 2010-03-30 | DDM | 684.09 | RIDF Loan upto 10 crore | Of the 50 Km Road, 33 Km is completed.Records maintained . Tests done Board displaying NABARD assistance was not displayed.
10 | R102000293 | Godhna Tank | Betul | WRD | MIS | 2010-03-29 | DDM | 717.73 | RIDF Loan upto 10 crore | Head work, Spill way and head regulator were more than 76% completed.Main canal 51-75% completed.Branch canal 26-50% completed. Pyment for lA is yet to be made. Monitored by the WRD. Records were maintained. Board displaying NB assistance was not displa
10 | R102000315 | Tawa 2/4 | Hoshangabad | PWD | Bridge | 2010-03-24 | DDM | 766.93 | RIDF Loan upto 10 crore | Barring appr rd project is complete.TOR in appr road LA is over new contrcator will completed by sep 10.COR - >SOR and delayed LA. Supervised, tests done rec ain . Displaced board needs to be re installed.
10 | R102000294 | Bambhera Tank | Burhanpur | WRD | MIS | 2010-03-11 | DDM | 88.54 | RIDF Loan upto 10 crore | Project is completed TOR due to delay in LA and shifting of electric pole. Quality control insatlled. Records maintained.Visit registers maintained
10 | R102000025 | Khamaria Chandora Tank | Raisen | WRD | MIS | 2010-03-10 | RO Official | 252.99 | RIDF Loan upto 10 crore | Dam, spill way,sluice completed. Canal system is yet to be complted.LA delayed the project and consequent COR. Tests carried out. Recotrds maintained. Installation of concrete borad is needed.Aapr road to canal and WUA are yet to be done.
10 | r102000026 | Umarkhoh Tank | Raisen | WRD | MIS | 2010-03-10 | RO Official | 204.04 | RIDF Loan upto 10 crore | Dam, spill way,sluice completed.One structure canal system is yet to be complted.LA delayed the project and consequent COR. Tests carried out. Recotrds maintained. Installation of concrete borad is needed.Aapr road to canal and WUA & watch be done.
10 | r102000016 | Parasthani Tank | Betul | WRD | MIS | 2009-12-23 | DDM | 150.19 | RIDF Loan upto 10 crore | Head work and Spill way are more than 76% completed.. Main canal, branch canal and distributaries 51-75% completed. LA cases have delayed canal works and would be completed by March 2010. CoR change in SOR. Inspected by Dept, rec mai NAB ass not disp
10 | R102000295 | Bijepani Tank | Chhindwara | WRD | MIS | 2009-12-23 | DDM | 159.64 | RIDF Loan upto 10 crore | HW,SW,MC,BC more than 76% completed. TOR due to La delay in payment of com pensation. Testsv done Test records and visit records maintained.NABARD assitance displayed. Likely to be completed by 31 December 09
10 | R102000063 | Sone 3/2 | Satna | PWD | Bridge | 2009-09-24 | DDM | 364.17 | RIDF Loan upto 10 crore | LA Found >75% completed. Piers Super Struc 51-75% completed;Abut Appr Rd 26-50% completed.Env related case hampered the project.After apex court's permission, work is under progress.LA for appr road iled toTOR. NABARD assistance not displayed
10 | R102000001 | Jaleshwar | Ashoknagar | WRD | MIS | 2009-06-19 | DDM | 87.75 | RIDF Loan upto 10 crore | Work on HW,HR,MC 100% completed.Monitoing done by the WRd. Tests catrtried out,records not shown. NABARD assistance displayed. WUA is yet to be formed. The project would benefit 20 Ha during Kharif and 80 ha during Rabi.
10 | R102000306 | Abdullapura Tank | Dhar | WRD | MIS | 2009-06-03 | DDM | 263.1 | RIDF Loan upto 10 crore | Wrk on HW,SW,HR,MC,BC is cmpltd.Minors,subminors, CD R cmpltd.TOR was due 2 LA & relloctn of habitats falling in the dam inundationn area.COR: delay in execution of work & LA.Sr engs visit.Rec mntnd.Test dun,NB brd dsplyd,lkly t b cmpltd by 15 Jun 09.
10 | R102000134 | Morena (171 New-PS) | Morena | RSK | School | 2009-03-27 | DDM | 72.68 | RIDF Loan upto 10 crore | Recd in April 09. Construction of new primary school is completed
10 | R102000168 | Bhind (10 OG-MS) | Bhind | RSK | School | 2009-03-18 | DDM | 7.5 | RIDF Loan upto 10 crore | Recd in April 09 construction of midle school is completed Visit records were not shown. Quality control test records were not maintained . NABARD assistance not displayed
10 | R102000079 | Bhind (197 OG-PS) | Bhind | RSK | School | 2009-03-18 | DDM | 83.73 | RIDF Loan upto 10 crore | Recd in April 09 . Construction of Primary school is completed.Visit records were not shown. Quality control test records were not maintained . NABARD assistance not displayed
10 | R102000135 | Sheopur (150 New-PS) | Sheopur | RSK | School | 2009-03-06 | DDM | 63.75 | RIDF Loan upto 10 crore | Scholl infrastructure construction is completed. The PMS has class rooms, kitchen and varanda. Ks is used for MDMS Hand pump wurk in Ward No 10 Block Sheopur is yet yo be completed
10 | R102000018 | Maika Sarra Tank | Betul | WRD | MIS | 2009-02-27 | DDM | 65.43 | RIDF Loan upto 10 crore | HW, SW HR >76% compl MC 26-50% CD works >76% MC is in progress. Low rainfall lead to poor inflow command area did not get suffiecient water visist conducted tests done records maintained NAb ass not disply .Lining of canal is yet to be done
10 | R102000063 | Sone 3/2 | Satna | PWD | Bridge | 2009-02-04 | DDM | 364.17 | RIDF Loan upto 10 crore | LA Found 25-50% completedPier 51-75% completed Abutment26-50% completed Appr Road 26-50% completed Super structure upto 25% completed TOR due Supreme court case forest dpat Sr en visited tests caried out records maintained. Assistance not displayed
10 | R102000058 | Narmada 3/10 | Jabalpur | PWD | Bridge | 2009-02-03 | DDM | 85.71 | RIDF Loan upto 10 crore | Found pier,Abut SupStrand Apprc Rd >76% TOR- La for approach Rd and high water level in Narmada. Records not shown. NABARd assistance not displayed
10 | R102000057 | Hiran 2/8 | Jabalpur | PWD | Bridge | 2009-02-03 | DDM | 89.3 | RIDF Loan upto 10 crore | Foun > 76%Pier 51-75% Abut 26-50% Super Appr ropad yet to start.TOR - work started in June 08, rainy season difficulties in bringing material.Rec not shown Connecting rd required Assit not displayed
10 | R102000319 | LBC Dongariya 5.00-23 km | Narsinghpur | NVDA | MIP | 2009-01-28 | DDM | 2811.11 | RIDF Loan 25 crore & above | MC, distri more than 76% completed In case of nminors and sub LA EW >76% Masonry 25-50% lining <25%Bridges by rail NAHAI to be doneVisit records not available Tests done and records not shown NAB assist not displayed
10 | R102000067 | Johilla 42/6 | Umaria | PWD | Bridge | 2009-01-22 | DDM | 116.87 | RIDF Loan upto 10 crore | Foundation >75% Super stru 25% sub struc 26-50% Appr Rd 51-75% Rocky layer at great depth led to cost esc Sr eng visited. Quality control taken care of Test records maintained.NABARD board not displayed
10 | R102000042 | Hardi Tank | Shahdol | WRD | MIS | 2009-01-16 | DDM | 65.64 | RIDF Loan upto 10 crore | Work completed Engineers visited qaulity control taken care of Tests conducted Tests records mainrained. NABARd assistance displayed. Weeds have choked some of the structures
10 | R102000043 | Mithouri Tank | Shahdol | WRD | MIS | 2009-01-16 | DDM | 87.78 | RIDF Loan upto 10 crore | Survey and LA completed. Masonry and Earth work 70% completed. Contractor is yet to sign for the balance work. Qaulity control ensured test records maintained. NABARD assistance displayed.
10 | R102000321 | Sadumar Br.Canal RD.9-21 | Narsinghpur | NVDA | MIP | 2009-01-16 | DDM | 3136.73 | RIDF Loan 25 crore & above | Preli La for main canal and minors is >75% completed. Masonry and lining yet to start. Tenders tussle with railways leading to TOR vsist records not shown tests done assist displayed
10 | R102000323 | Birahi Tank | Bhopal | WRD | MIS | 2009-01-15 | RO Officer | 989.64 | RIDF Loan upto 10 crore | Head works, spill way 51-75% completed; haed regulator more than 76%. Time overrun due to delay in LA and contractor's problem. ost overrun incre in land rates and change in waste weir design.Sr eng visited.recs maintianed.Board displayed
10 | R102000320 | Sadumar Br.canal RD 4.5 | Narsinghpur | NVDA | MIP | 2009-01-10 | DDM | 3987.09 | RIDF Loan 25 crore & above | EW LA for head distri and minors is >76% Masonry lining of canal is less than 25% Tussle with railays Visit records and quality tests records not shown. assistance not displayed
10 | R102000317 | Narmada 8/8 | Sehore | PWD | Bridge | 2008-12-26 | RO Officer | 812.42 | RIDF Loan upto 10 crore | Found and Sub Stru > than 76%;SS 51-75%;CD 26-50% ;LA and approach Road upto 25% LA, int dep tussl,poor fund flow are problems.TO LA,changeg in design, CO cost of raw material,LA and labour charges Visits by Sen Off, tests recorded board displayed
10 | R102000298 | Dholankhapa Tank | Chhindwara | WRD | MIS | 2008-09-29 | DDM | 107.07 | RIDF Loan upto 10 crore | Time overrun due to delay in LA. Cost overrun due to structural changes.WRD engineers visit the project. Records maintained. NABARD assistance displayed. Due to low rainfall, canal testing could not be done by leeting water from tank
10 | R102000265 | Gwalior (190 KS) | Gwalior | RSK | School | 2008-09-29 | DDM | 10.09 | RIDF Loan upto 10 crore | Work was carried uot by GPs. There is no consistency in the quality of work under costing in view of the increase in pricr of raw material.No supervision over GPs. Records were not shown. NABARD assistance not displayed. PCR to be furnished.
10 | R102000299 | Hivra Sebadwar Tank | Chhindwara | WRD | MIS | 2008-09-28 | DDM | 270.13 | RIDF Loan upto 10 crore | Time over run delay in LA Cost over run due to structural changes,contractor problem poor fund flows Senior engineers regularly visit. Quality control system installed. NABARD assistance displayed.
10 | R102000320 | Sadumar Br.canal RD 4.5 | Narsinghpur | NVDA | MIP | 2008-06-17 | DDM | 3987.09 | RIDF Loan 25 crore & above | Part 4.5 -9 Km monitored.The About 15 tests have been carried between 01 April 08 and 15 June 08.Documentation of Field visits by engineeers is not available.Test records are not available. The work has reportedly commenced on 25 March 08
10 | R102000055 | Hathed 25/8 | Hoshangabad | PWD | Bridge | 2008-05-27 | DDM | 98.61 | RIDF Loan upto 10 crore | Original contractor executed 30% of the work and left. The incumbent contractor is incapable of executing the work, hence the progress is tardy.The PWD is taking action. There is time overrun. Due to initial stages of work, cost overrun doesnot arise.
10 | R102000320 | Sadumar Br.canal RD 4.5 | Narsinghpur | NVDA | MIP | 2008-05-23 | DDM | 3987.09 | RIDF Loan 25 crore & above | Time overrun due to dealy in finalizing tenders. The agreement has been executedf on 07 March 08.A separate division is monitoring quality control aspects. Works ahve commenced recently. NABARD assistance is not displayed.
10 | R102000319 | LBC Dongariya 5.00-23 km | Narsinghpur | NVDA | MIP | 2008-05-22 | DDM | 2811.11 | RIDF Loan 25 crore & above | No cost and time overrun. A separate divison is monitoring quality aspect. About 1483 tests have been done between 01 April 07 and 31 March 08. Test records are reportedly maintained with quality control sub division. NABARD assistance not displayed.
10 | R102000306 | Abdullapura Tank | Dhar | WRD | MIS | 2008-05-16 | DDM | 263.1 | RIDF Loan upto 10 crore | There were cost and time over run due to delay in execution of work, landacquisition and reloacation of villages coming under dam alignment. Dispaly borad does not indicate financial assistance from NABARD.
10 | R102000321 | Sadumar Br.Canal RD.9-21 | Narsinghpur | NVDA | MIP | 2008-05-15 | DDM | 3136.73 | RIDF Loan 25 crore & above | Time overrun due to delay in finalizing tenders. A separate division is monitoring quality control. About 25 tests have been conducted bet 01 Apr 07 and 31 Mar08. NABARD assistance is not displayed.
10 | r102000292 | Bakud Tank | Betul | WRD | MIS | 2008-03-12 | Betul DDM | 937.59 | RIDF Loan upto 10 crore | NABARD board displayed. Progress of work affected due to land acquisition problem.
10 | r102000133 | Dindori (69 New-PS) | Dindori | RSK | School | 2008-03-10 | Mandla DDM | 29.33 | RIDF Loan upto 10 crore | PS at Prachin Dindori, Block: Dindori.NABARD board not displayed. There is no boundary and stray cattle and dogs create nuisance.
10 | R102000177 | Dindori (5 OG-MS) | Dindori | RSK | School | 2008-03-10 | Mandla DDM | 3.85 | RIDF Loan upto 10 crore | Subarwar Madhyamik Shala, Subarwar panchayat. Dindori. NABARD board not displayed. There was no compound wall.
10 | r102000212 | Dindori (119 New-MS) | Dindori | RSK | School | 2008-03-10 | Mandla DDM | 101.15 | RIDF Loan upto 10 crore | Prachin Dindori Madhyamik Shala. Land levelling in front of classroom not done. NABARD board not displayed. Compound wall not constructed.
10 | r102000315 | Tawa 2/4 | Hoshangabad | PWD | Bridge | 2008-03-07 | Hoshangabad DDM | 766.93 | RIDF Loan upto 10 crore | NABARD board has been displayed. The project period and cost is likely to overrun. The approach road work is only 20% done.
10 | r102000329 | Nawali Tank | Mandsaur | WRD | MIS | 2008-03-04 | Mandsaur DDM | 258.64 | RIDF Loan upto 10 crore | NABARD board not displayed. The bund damaged during monsoon needs to be dressed. WUA should be formed.
10 | r102000330 | Tungi Tank | Mandsaur | WRD | MIS | 2008-03-04 | Mandsaur DDM | 138.86 | RIDF Loan upto 10 crore | NABARD board not displayed. WUA to be formed after the project is completed.
10 | r102000293 | Godhna Tank | Betul | WRD | MIS | 2008-02-28 | Betul DDM | 717.73 | RIDF Loan upto 10 crore | NABARD board has not been displayed. More than 50% of construction of RBC work is over. Some litigation has been filed.
10 | r102000169 | Damoh (52 OG-MS) | Damoh | RSK | School | 2008-02-28 | Sagar DDM | 37.76 | RIDF Loan upto 10 crore | NABARD board has not been displayed. 100% work is completed but PCR has not been submitted.
10 | r102000013 | Vinayakpura Tank | Sehore | WRD | MIS | 2008-02-25 | RO Officer | 164.53 | RIDF Loan upto 10 crore | NABARD board displayed but was stolen. WUA yet to be formed. Project likely to be completed by March 08. Monitoring by Dept. is being done. Records are maintained in file.
10 | r102000026 | Umarkhoh Tank | Raisen | WRD | MIS | 2008-02-13 | RO Officer | 204.04 | RIDF Loan upto 10 crore | Board displayed without mention of NABARD. The dam work is complete only upto 90%. 75% of second waste weir has been submerged in sand. Senior officers above EE do not visit the site.
10 | r102000285 | Nisarpur-Padiyal-Ali | Dhar | PWD | Road | 2008-02-12 | Dhar DDM | 578.29 | RIDF Loan upto 10 crore | NABARD board displayed. Cost overrun. Regular tests and maintenance of test record is in order. 200 metres of road inbetween is pending because of court case.
10 | r102000014 | Khanota Tank | Shajapur | WRD | MIS | 2008-01-03 | Shajapur DDM | 104.3 | RIDF Loan upto 10 crore | NABARD board displayed. CE/SE/EE to visit regularly the site for qood quality work.
10 | r102000014 | Khanota Tank | Shajapur | WRD | MIS | 2008-01-03 | Shajapur DDM | 104.3 | RIDF Loan upto 10 crore | CE/SE/EE to make regular visit to the site to ensure good quality of work.
10 | r102000132 | Mandla (358 New-PS) | Mandla | RSK | School | 2008-01-01 | Mandla DDM | 152.15 | RIDF Loan upto 10 crore | Shiksha Guarantee Shala, Katra Tola, Palasundar, Block-Nainpur,NABARD board has not been displayed. Kitchen roof is of tin and not concrete. Cracks have developed below the slab in all classrooms.
10 | r102000211 | Mandla (228 New-MS) | Mandla | RSK | School | 2008-01-01 | Mandla DDM | 193.8 | RIDF Loan upto 10 crore | Naveen Madhyamik Shala,Khir Khiri Village, Nainpur Block. Plastering to be completed. Toilets not constructed. No compound.
10 | r102000319 | LBC Dongariya 5.00-23 km | Narsinghpur | NVDA | MIP | 2007-12-28 | Narsinghpur DDM | 2811.11 | RIDF Loan 25 crore & above | NABARD board has not been displayed. Documentation of site visits not maintained.
10 | r102000318 | LBC RD 130.67-136.87 km | Narsinghpur | NVDA | MIP | 2007-12-28 | Narsinghpur DDM | 3352.26 | RIDF Loan 25 crore & above | NABARD board has not been displayed. Documentation of visits by CE and EE not made.
10 | r102000321 | Sadumar Br.Canal RD.9-21 | Narsinghpur | NVDA | MIP | 2007-12-28 | Narsinghpur DDM | 3136.73 | RIDF Loan 25 crore & above | Project not yet commenced. Agreement yet to be executed. The process of finalisation of tender and execution of agreement appears to be unduly delayed.
10 | r102000291 | Bistan-Tensemali | Khargone | PWD | Road | 2007-12-27 | Khargone DDM | 684.09 | RIDF Loan upto 10 crore | NABARD board has been displayed. Land acquisition problem. Tussle between forest dept and PWD. Out of 48.80 KM only 8 Kms have been tarred.
10 | R102000290 | Jobat-Bori-Para | Alirajpur | PWD | Road | 2007-12-26 | Jhabua DDM | 616.9 | RIDF Loan upto 10 crore | The work has been completed on 29.6.2007 and the department has been advised to submit PCR.
10 | r102000134 | Morena (171 New-PS) | Morena | RSK | School | 2007-09-27 | Morena DDM | 72.68 | RIDF Loan upto 10 crore | Jivajiganj P.S (girls) No quality control system has been introduced. NABARD board not displayed.
10 | r102000134 | Morena (171 New-PS) | Morena | RSK | School | 2007-09-27 | Morena DDM | 72.68 | RIDF Loan upto 10 crore | Deekhat Pura P.S.No quality control system. NABARD board to be displayed.
10 | r102000134 | Morena (171 New-PS) | Morena | RSK | School | 2007-09-27 | Morena DDM | 72.68 | RIDF Loan upto 10 crore | Dattapura PS girls. NABARD board to be displayed. No quality control.
10 | r102000134 | Morena (171 New-PS) | Morena | RSK | School | 2007-09-27 | Morena DDM | 72.68 | RIDF Loan upto 10 crore | Ganeshpura PS Buniyadi. No quality control. NABARD board to be displayed.
10 | r102000317 | Narmada 8/8 | Sehore | PWD | Bridge | 2007-09-18 | RO Officer | 812.42 | RIDF Loan upto 10 crore | Land acquisition problem. Likely date of completion of the project is June 2008 as against March 2007. NABARD board has not been displayed. There was delay in finalisation of agency.
10 | r102000323 | Birahi Tank | Bhopal | WRD | MIS | 2007-09-13 | RO Officer | 989.64 | RIDF Loan upto 10 crore | Problem in land acquisition. Work has not started in Unit II. NABARD board has not been displayed.
10 | r102000025 | Khamaria Chandora Tank | Raisen | WRD | MIS | 2007-09-11 | RO | 252.99 | RIDF Loan upto 10 crore | NABARD board has not been displayed. The railings in the sluice gate has been cut and stolen. Masonory work in the sluice gate has been damaged.
10 | r102000044 | Birgod Motakhora Tank | Shajapur | WRD | MIS | 2007-06-26 | Shajapur DDM | 126 | RIDF Loan upto 10 crore | NABARD boards to be erected at the highway at the point of deviation leading to the da site and also at the dam site. Senior officials other than EE to also frequently visit the site to monitor the work progress.
10 | r102000023 | Chapna LIS | Katni | WRD | MIS | 2007-06-22 | Jabalpur DDM | 286.79 | RIDF Loan upto 10 crore | Slow progress of work both in construction of rising main and canals. Inordinate delay in sanction of MPEB connection. NABARD board not displayed. Farmers are creating problems for digging the canal due to non-payment of compensation to the farmers.
10 | r102000015 | Semalkhedi Tank | Vidisha | WRD | MIS | 2007-06-22 | Vidisha DDM | 142.99 | RIDF Loan upto 10 crore | Only 45% of the work has been completed. The work is likely to recommence from October/November 2007.
10 | r102000231 | Rajgarh (315 New-MS) | Rajgarh | RSK | School | 2007-06-21 | Shajapur DDM | 267.75 | RIDF Loan upto 10 crore | Khuri Middle School. The school building stands completed. Construction appears to be satisfactory.
10 | r102000231 | Rajgarh (315 New-MS) | Rajgarh | RSK | School | 2007-06-21 | Shajapur DDM | 267.75 | RIDF Loan upto 10 crore | Mau Middle School. The school building stands completed. Construction appears to be satisfactory.
10 | r102000325 | Shanti Nagar | Katni | WRD | MIS | 2007-06-19 | Jabalpur DDM | 326.09 | RIDF Loan upto 10 crore | NABARD board has not been displayed. The progress was very slow. Due to delay in commencement of construction of headwork by the contractor the work had suffered.
10 | R102000219 | Balaghat (190 New-MS) | Balaghat | RSK | School | 2007-06-07 | Balaghat DDM | 161.5 | RIDF Loan upto 10 crore | Thanegaon M.S. NABARD board has not been displayed as there was no such instructions from their controlling office.
10 | r102000219 | Balaghat (190 New-MS) | Balaghat | RSK | School | 2007-06-07 | Balaghat DDM | 161.5 | RIDF Loan upto 10 crore | DIET M.S., Balaghat. NABARD board has not been displayed as there was no such instructions from their controlling office.
10 | r102000219 | Balaghat (190 New-MS) | Balaghat | RSK | School | 2007-06-07 | Balaghat DDM | 161.5 | RIDF Loan upto 10 crore | Kanya M.S. NABARD board has not been displayed as there was no such instructions from their controlling office.
10 | r102000326 | Chhoti Oon Tank | Khargone | WRD | MIS | 2007-06-01 | Khargone DDM | 96.97 | RIDF Loan upto 10 crore | NABARD board has been displayed. It is being monitored regularly.
10 | r102000120 | Panna (250 New-PS) | Panna | RSK | School | 2007-05-22 | Satna DDM | 106.25 | RIDF Loan upto 10 crore | Shiksha Guarantee shala Devipura Kusedar, Gunnour Block. NABARD board has not been displayed. Toilet has not been constructed. External and internal plastering work not done. Ramp not constructed. Top officials have not visited the project.
10 | r102000120 | Panna (250 New-PS) | Panna | RSK | School | 2007-05-22 | Satna DDM | 106.25 | RIDF Loan upto 10 crore | Madhyamki Shala Bhavan, Gunnour block. There is contractor's problem. No monitoring visits are undertaken. NABARD support board has not been displayed. Toilet has not been constructed.
10 | R102000068 | Kadiya 16/2 | Umaria | PWD | Bridge | 2007-05-11 | Shahdol DDM | 50.93 | RIDF Loan upto 10 crore | Progress is very slow. Contractor is not active. NABARD board has not been displayed. Quality of work is satisfactory. Approach road to be constructed. PWD to ensure that work will be completed in time by 31 December 2007
10 | R102000067 | Johilla 42/6 | Umaria | PWD | Bridge | 2007-05-11 | Shahdol DDM | 116.87 | RIDF Loan upto 10 crore | Progress is very slow. Lot of delay in completion of work. Work should be started immediately. Likely date of completion is April 2008. NABARD board has not been displayed. Quality of work is satisfactory. Approach road to be constructed.
10 | r102000216 | Shajapur (313 New-MS) | Shajapur | RSK | School | 2007-05-10 | Shajapur DDM | 266.05 | RIDF Loan upto 10 crore | Mulikhed middle school. Drinking water facility is very close to the toilet block which may pose health hazard. NABARD board has not been displayed.
10 | r102000216 | Shajapur (313 New-MS) | Shajapur | RSK | School | 2007-05-10 | Shajapur DDM | 266.05 | RIDF Loan upto 10 crore | Construction of the school building stands completed. Ceiling and flooring may require a finishing cement coat. NABARD board has not been displayed.
10 | r102000216 | Shajapur (313 New-MS) | Shajapur | RSK | School | 2007-05-10 | Shajapur DDM | 266.05 | RIDF Loan upto 10 crore | Badanpur Middle school. The school building stands completed. Construction appears to be satisfactory. NABARD board has not been displayed.
10 | r102000308 | Kundiya Pada Tank | Jhabua | WRD | MIS | 2007-05-03 | Jhabua DDM | 74.86 | RIDF Loan upto 10 crore | NABARD board has been displayed. Frequent monitoring is done by WRD Engineers.
10 | r102000308 | Kundiya Pada Tank | Jhabua | WRD | MIS | 2007-05-03 | Jhabua DDM | 74.86 | RIDF Loan upto 10 crore | NABARD board has been displayed. Frequent monitoring is done by WRD engineers. More than 76% of work is completed.
10 | r102000283 | Sendhwa-Palsood-Silawad | Badwani | PWD | Road | 2007-05-01 | Khargone DDM | 222.16 | RIDF Loan upto 10 crore | There is time overrun and cost overrun. NABARD board has not been displayed. Regular monitoring is being done. All records have been maintained.
10 | r102000319 | LBC Dongariya 5.00-23 km | Narsinghpur | NVDA | MIP | 2007-04-18 | Narsinghpur DDM | 2811.11 | RIDF Loan 25 crore & above | The overall progress is only 25%. NABARD board has not been displayed. No documentation of visits by CE and EE is maintained at the site.
10 | r102000320 | Sadumar Br.canal RD 4.5 | Narsinghpur | NVDA | MIP | 2007-04-18 | Narsinghpur DDM | 3987.09 | RIDF Loan 25 crore & above | Project yet to commence.
10 | r102000321 | Sadumar Br.Canal RD.9-21 | Narsinghpur | NVDA | MIP | 2007-04-18 | Narsinghpur DDM | 3136.73 | RIDF Loan 25 crore & above | Project yet to commence.
10 | r102000318 | LBC RD 130.67-136.87 km | Narsinghpur | NVDA | MIP | 2007-04-18 | Narsinghpur DDM | 3352.26 | RIDF Loan 25 crore & above | Project yet to commence.
10 | r102000297 | Chircutagondi Tank | Chhindwara | WRD | MIS | 2007-03-26 | Chindwara DDM | 257.89 | RIDF Loan upto 10 crore | The physical progress in regard toheadworks, spillways and head regulator is upto 25%.NABARD board has been displayed.
10 | r102000030 | Vajpura Tank | Rajgarh | WRD | MIS | 2007-03-23 | Shajapur DDM | 262.45 | RIDF Loan upto 10 crore | Project likely to be completed by 30.6.08 as against the due date of 31.3.2007 due to delay in LA, tendering etc. NABARD board not displayed Cost escalation due to be high tendering.
10 | r102000309 | Rawatpura Tank | Rajgarh | WRD | MIS | 2007-03-23 | Shajapur DDM | 104.47 | RIDF Loan upto 10 crore | Project likely to be completed by 31.3.08 as against the due date of 31.3.2007 due to delay in LA, tendering etc. NABARD board to be erected at the highway at the point of deviation leading to the dam site and also at the dam site. Cost escalation .
10 | r102000034 | Ahmedabad Khilli Tank | Vidisha | WRD | MIS | 2007-03-21 | Vidisha DDM | 207.98 | RIDF Loan upto 10 crore | There is no pucca approach road for the project. No physical work was going on in the site. NABARD board has not been displayed.
10 | r102000029 | Bamlabeh Tank | Rajgarh | WRD | MIS | 2007-03-20 | Shajapur DDM | 192.86 | RIDF Loan upto 10 crore | Project likely to be completed by 31.3.08 as against the due date of 31.3.07 due to LA, delay in tendering. There has been cost escalation by 8% in headwork owing to higher tendering. NABARD boards to be erected at the highway and also at the dam site.
10 | r102000009 | Chandpura Tank | Rajgarh | WRD | MIS | 2007-03-20 | Shajapur DDM | 142.51 | RIDF Loan upto 10 crore | Likely date of completion 30.11.07 as against the due date of 31.3.07. Owing to high tendering likely cost escalation. NABARD boards to be erected at prominent places and also at the dam site.
10 | r102000010 | Maniyapura Tank | Rajgarh | WRD | MIS | 2007-03-20 | Shajapur DDM | 270.47 | RIDF Loan upto 10 crore | Project likely to be completed by 31.3.08 as against the due date of 31.3.07 due to delay in LA, fixing agency, tendering etc. NABARD board to be erected at the highway at the point of deviation leading to the dam site and also at the dam site.
10 | r102000301 | Khori Tank | Chhindwara | WRD | MIS | 2007-03-17 | Chindwara DDM | 208.09 | RIDF Loan upto 10 crore | NABARD board has been displayed. The physical progress of the work is upto 75% in regard to headworksf and spillways.
10 | r102000300 | Jamlapani Tank | Chhindwara | WRD | MIS | 2007-03-17 | Chindwara DDM | 139.28 | RIDF Loan upto 10 crore | NABARD board has been displayed. Physical progress is upto 50% inregard to spillways, main canal and 30% regarding branch canal.
10 | r102000136 | Seoni (422 New-PS) | Seoni | RSK | School | 2007-03-09 | Chindwara DDM | 179.35 | RIDF Loan upto 10 crore | PATRA TOFA P.S. NABARD board has not been displayed. Drinking water, boundary wall and kitchen shed to be provided.
10 | R102000136 | Seoni (422 New-PS) | Seoni | RSK | School | 2007-03-09 | Chindwara DDM | 179.35 | RIDF Loan upto 10 crore | BOTIA P.S. NABARD board has not been displayed. Drinking water, boundary wall and kitchen shed to be provided.
10 | r102000290 | Jobat-Bori-Para | Alirajpur | PWD | Road | 2007-03-07 | Jhabua DDM | 616.9 | RIDF Loan upto 10 crore | More than 75% of the project is completed. NABARD board has been displayed. There is poor fund flow.
10 | r102000290 | Jobat-Bori-Para | Alirajpur | PWD | Road | 2007-03-07 | Jhabua DDM | 616.9 | RIDF Loan upto 10 crore | NABARD board has been displayed. Maintenance of tests record/site visit/order books is maintained. Nearly 50-75% of work is the physical progress.
10 | r102000204 | Damoh (250 New-MS) | Damoh | RSK | School | 2007-02-23 | Sagar DDM | 212.5 | RIDF Loan upto 10 crore | Amkheda village - Middle School. There are 90 students and 03 teachers. Parent teachers association has been formed.
10 | r102000204 | Damoh (250 New-MS) | Damoh | RSK | School | 2007-02-23 | Sagar DDM | 212.5 | RIDF Loan upto 10 crore | Gunji Middle school - There are 174 students and 4 teachers. Parent teachers association has been formed.
10 | r102000204 | Damoh (250 New-MS) | Damoh | RSK | School | 2007-02-23 | Sagar DDM | 212.5 | RIDF Loan upto 10 crore | Luhana village - Middle school - 02 teachers - Cleanliness to be maintained.
10 | r102000080 | Damoh (158 OG-PS) | Damoh | RSK | School | 2007-02-23 | Sagar DDM | 40.92 | RIDF Loan upto 10 crore | Gunji - Indira Awas Colony. There are 49 students and 02 teachers. Parent teachers association has been formed.
10 | R102000033 | Morai Tank | Sheopur | WRD | MIS | 2007-02-20 | Shivpuri DDM | 78.55 | RIDF Loan upto 10 crore | Bund /earthwork is completed, canal work main and branch to be done. Land acquisition for canal work is under process. Contractor has left the work and new contractor to be identified.
10 | r102000284 | Sardarpur-Baloda | Dhar | PWD | Road | 2007-02-13 | Dhar DDM | 210.12 | RIDF Loan upto 10 crore | NABARD board not displayed. Sanctioned length of road completed but there are patches in between Baloda and Badveli, to be filled up for safety of the road.
10 | r102000285 | Nisarpur-Padiyal-Ali | Dhar | PWD | Road | 2007-02-12 | Dhar DDM | 578.29 | RIDF Loan upto 10 crore | NABARD board has been displayed. As the road passes through hilly portion protection walls to be constructed.
10 | r102000286 | Pankhedi-Digthan-Sagdi | Dhar | PWD | Road | 2007-01-29 | Dhar DDM | 286.52 | RIDF Loan upto 10 crore | Work is in progress. Sanctioned length of road is 21.40 KM of which 12.40 km road is completed. Digthan to Sakedi road work is in preliminary stage i.e. upto earth work only under some patches. NABARD board has been displayed.
10 | r102000079 | Bhind (197 OG-PS) | Bhind | RSK | School | 2007-01-19 | Morena DDM | 83.73 | RIDF Loan upto 10 crore | Bhind (197-OG-PS)68/Govt. P.S., Phooph. There are 460 students and 5 teachers. Construction and finishing of the building is good.
10 | r102000079 | Bhind (197 OG-PS) | Bhind | RSK | School | 2007-01-19 | Morena DDM | 83.73 | RIDF Loan upto 10 crore | Bhind (197 OG-PS)62/Govt. Primary School, Badi Didi. There are 136 students and 03 teachers. Construction and finishing is good. School building is ont the side of the main road (national highway). A boundary wall will avoid accidents.
10 | r102000079 | Bhind (197 OG-PS) | Bhind | RSK | School | 2007-01-19 | Morena DDM | 83.73 | RIDF Loan upto 10 crore | Bhind (197 OG - PS)70/Govt. Primary School, Gandhi Shala. Number of students is 238 and 04 teachers. Construction and finishing is good.
10 | r102000124 | Bhind (206 New-PS) | Bhind | RSK | School | 2007-01-19 | Morena DDM | 87.55 | RIDF Loan upto 10 crore | Govt. Primary SChool, Ranjana Nagar. Presently the school is being run under a tree. There are 105 students and 1 teacher. Construction and finishing is good.
10 | r102000168 | Bhind (10 OG-MS) | Bhind | RSK | School | 2007-01-19 | Morena DDM | 7.5 | RIDF Loan upto 10 crore | Govt. M.S., Arya Nagar. There are 160 students and 5 teachers. Building not completed, foundation and wall work completed. RCC roof work is being done.
10 | r102000162 | Rewa (14 OG-MS) | Rewa | RSK | School | 2007-01-18 | Rewa DDM | 7.25 | RIDF Loan upto 10 crore | Mahhigawan middle school. The work is delayed. Technical officers visit the building at various stages of construction. The work to be completed at the earliest.
10 | r102000162 | Rewa (14 OG-MS) | Rewa | RSK | School | 2007-01-18 | Rewa DDM | 7.25 | RIDF Loan upto 10 crore | Karariya middle school. Visits are paid at various stages of construction. The constructed school building is incomplete and not in use as there are no doors, windows and there is leakage.
10 | r102000117 | Rewa (664 New-PS) | Rewa | RSK | School | 2007-01-18 | Rewa DDM | 282.2 | RIDF Loan upto 10 crore | Mado primary school. Visits are made at various stages of construction. The school is constructed on the bank of village pond which is risky for students.
10 | r102000072 | Rewa (620 OG-PS) | Rewa | RSK | School | 2007-01-18 | Rewa DDM | 263.5 | RIDF Loan upto 10 crore | Baikunthpur. No visit record is being maintained. In the newly constructed building the rooms are very small and there is no proper ventilation. The school is being run in the old building.
10 | r102000117 | Rewa (664 New-PS) | Rewa | RSK | School | 2007-01-18 | Rewa DDM | 282.2 | RIDF Loan upto 10 crore | Palhan Boys primary school. 3-4 visits are made at various stages of construction but no record is being maintained. Ventilation window size is very big and rain water comes into the classroom. Necessary changes to be made.
10 | r102000072 | Rewa (620 OG-PS) | Rewa | RSK | School | 2007-01-18 | Rewa DDM | 263.5 | RIDF Loan upto 10 crore | Kharhan Boys primary school. 3-4 visits are paid at various stages of construction by technical officer. No records are being maintained. Size of ventilation is big and rain water comes into the classroom. Necessary changes to be made.
10 | r102000027 | Dendi Tank | Rajgarh | WRD | MIS | 2007-01-12 | Shajapur DDM | 195.77 | RIDF Loan upto 10 crore | The project is likely to be completed in March 2008.
10 | r102000028 | Dhablikhurd Tank | Rajgarh | WRD | MIS | 2007-01-12 | Shajapur DDM | 155.53 | RIDF Loan upto 10 crore | The project is likely to be completed by June 2008.
10 | r102000008 | Bhumaria Tank | Rajgarh | WRD | MIS | 2007-01-12 | Shajapur DDM | 218.28 | RIDF Loan upto 10 crore | The project is likely to be completed by June 2008
10 | r102000128 | Jhabua (400 New-PS) | Jhabua | RSK | School | 2007-01-07 | Jhabua DDM | 170 | RIDF Loan upto 10 crore | Meghnagar - Sarva Shiksha Abhiyan - Parents teachers association has been formed and meets once in a month.
10 | R102000075 | Panna (341 OG-PS) | Panna | RSK | School | 2007-01-04 | Satna DDM | 99 | RIDF Loan upto 10 crore | Bador village. Parent Teachers association has been formed. New building is under construction. School is being run in old building.
10 | r102000199 | Panna (250 New-MS) | Panna | RSK | School | 2007-01-04 | Satna DDM | 212.5 | RIDF Loan upto 10 crore | Baldev Mandir Panna. Presently the school is being run on rent in Mandir premises. Parent-teachers association formed. Details of expenditure not maintained. No record of monitoring maintained. No provision for seating like stone bench for students.
10 | r102000075 | Panna (341 OG-PS) | Panna | RSK | School | 2007-01-04 | Satna DDM | 99 | RIDF Loan upto 10 crore | Nai Basti, Lakshmipur village. Parent Teacher Association formed. School being run from old building. There are 112 students and one teacher. Platform has not been built in the kitchen.
10 | R102000294 | Bambhera Tank | Burhanpur | WRD | MIS | 2007-01-04 | Khandwa DDM | 88.54 | RIDF Loan upto 10 crore | NABARD board has not been displayed. Work halted at present. Contract period of 11 months is over. Contractor appears to be not interested in the work now. Work to speeded up.
10 | r102000299 | Hivra Sebadwar Tank | Chhindwara | WRD | MIS | 2006-12-07 | RO Officer | 270.13 | RIDF Loan upto 10 crore | No cost overrun except in the case of land acquisition as the value as per award was more than the estimates. The work is progressing satisfactorily. Likely date of completion June 2007.
10 | r102000151 | Sagar (183 New-PS) | Sagar | RSK | School | 2006-12-07 | Sagar DDM | 77.78 | RIDF Loan upto 10 crore | Shiksha Guarantee Primary School at Bidi Sharmik Colony, Karrapur. The number of students is 70 and there are two teachers.
10 | r102000151 | Sagar (183 New-PS) | Sagar | RSK | School | 2006-12-07 | Sagar DDM | 77.78 | RIDF Loan upto 10 crore | Primary school Sadar No.2, Sagar. School is running classes for Standard I to V. There are 123 students and 3 teachers.
10 | r102000230 | Sagar (291 New-MS) | Sagar | RSK | School | 2006-12-07 | Sagar DDM | 247.35 | RIDF Loan upto 10 crore | Kanya Madhyamik Shala, Subhash Nagar, Sagar. There are 324 students and 8 teachers.
10 | R102000318 | LBC RD 130.67-136.87 km | Narsinghpur | NVDA | MIP | 2006-11-29 | Narsinghpur DDM | 3352.26 | RIDF Loan 25 crore & above | Tenders called for the fifth time. Received on 25 May 2006 and yet to be approved. Work yet to commence.
10 | R102000319 | LBC Dongariya 5.00-23 km | Narsinghpur | NVDA | MIP | 2006-11-29 | Narsinghpur DDM | 2811.11 | RIDF Loan 25 crore & above | Work commenced recently. Likely date of completion 31 July 2008.
10 | R102000320 | Sadumar Br.canal RD 4.5 | Narsinghpur | NVDA | MIP | 2006-11-29 | Narsinghpur DDM | 3987.09 | RIDF Loan 25 crore & above | Tenders called for the fifth time. Received on 25 May 2006 and yet to be approved.
10 | r102000321 | Sadumar Br.Canal RD.9-21 | Narsinghpur | NVDA | MIP | 2006-11-29 | Narsinghpur DDM | 3136.73 | RIDF Loan 25 crore & above | Tenders reportedly received on 1.8.06. Tenders yet to be approved.
10 | R102000093 | Shivpuri (191 OG-PS) | Shivpuri | RSK | School | 2006-11-16 | Shivpuri DDM | 71.5 | RIDF Loan upto 10 crore | 2 class rooms and verandah completed, flooring and plastering work yet to start. Roof of verandah is bending down. Roof the classroom is slightly bent. The plastering and flooring work is expected to be completed within one month.
10 | r102000154 | Dhar (551 New-PS) | Dhar | RSK | School | 2006-11-15 | Dhar DDM | 234.18 | RIDF Loan upto 10 crore | Nandlayee village. No parents teachers association has been formed. School is already in existence. As the school is overcrowded loan given for additional classes. Classroom work is completed but work of toilet not yet started.
10 | r102000154 | Dhar (551 New-PS) | Dhar | RSK | School | 2006-11-15 | Dhar DDM | 234.18 | RIDF Loan upto 10 crore | Phool Gaonwadi village. Parent teacher association not formed. School was being run in Middle school building. Work is almost completed. Toilet work sanctioned but not yet started.
10 | r102000154 | Dhar (551 New-PS) | Dhar | RSK | School | 2006-11-15 | Dhar DDM | 234.18 | RIDF Loan upto 10 crore | Bhorkalee village. Parent teachers association not formed. School is being run in someone's house. 65-75% work completed. Flooring and plastering work in progress. Toilet work yet to be started.
10 | r102000154 | Dhar (551 New-PS) | Dhar | RSK | School | 2006-11-15 | Dhar DDM | 234.18 | RIDF Loan upto 10 crore | Nandlayee village. Parent teachers association not formed. School is already in existence. 2 additional classes and kitchen was sanctioned. Classroom work is completed but the kitchen work is yet to begin.
10 | r102000154 | Dhar (551 New-PS) | Dhar | RSK | School | 2006-11-15 | Dhar DDM | 234.18 | RIDF Loan upto 10 crore | Bodiya village. Parent teachers association not formed. School is in existence. Additional class sanctioned due to more number of students. 75-80% work completed. Flooring and plastering work in progress.
10 | r102000233 | Dhar (180 New-MS) | Dhar | RSK | School | 2006-11-15 | Dhar DDM | 153 | RIDF Loan upto 10 crore | Amzera village. Parent teachers association not formed. School is already in existence and is housed in old premises of Gram panchayat. Work is completed. CC to be issued.
10 | r102000233 | Dhar (180 New-MS) | Dhar | RSK | School | 2006-11-15 | Dhar DDM | 153 | RIDF Loan upto 10 crore | Rajpura village. Parent teachers association not formed. School was functioning in primary school. Work is completed and is functioning in the new premises. CC to be issued.
10 | R102000311 | Bhyana Bhudki Tank | Shajapur | WRD | MIS | 2006-11-10 | RO Officer+Consultant | 153.05 | RIDF Loan upto 10 crore | Progress found to be slow. Delay in implementation due to delay in land acquisition. Since land acquisition bottleneck has been overcome. NABARD board displayed. Advise to complete the project by March 2007.
10 | R102000044 | Birgod Motakhora Tank | Shajapur | WRD | MIS | 2006-11-09 | RO Officer+Consultant | 126 | RIDF Loan upto 10 crore | Progress found satisfactory. NABARD board displayed. Delay in work implementation due to shortage of water.
10 | R102000224 | Harda (143 New-MS) | Harda | RSK | School | 2006-11-09 | Hoshangabad DDM | 121.55 | RIDF Loan upto 10 crore | NABARD board not displayed. The construction is good. There was no provision for tubewell/handpump in the project for potable water.
10 | r102000062 | Kai 7/6 | Rajgarh | PWD | Bridge | 2006-11-09 | Shajapur DDM | 66.13 | RIDF Loan upto 10 crore | NABARD board has not been displayed. Quality of work is satisfactory. The bridge has been completed well before the due date of completion i.e. 31.3.2007.
10 | r102000233 | Dhar (180 New-MS) | Dhar | RSK | School | 2006-11-08 | Dhar DDM | 153 | RIDF Loan upto 10 crore | Brahmakundi village. Work is completed. CC to be issued
10 | r102000154 | Dhar (551 New-PS) | Dhar | RSK | School | 2006-11-08 | Dhar DDM | 234.18 | RIDF Loan upto 10 crore | Dedali village. School is in existence. Additional class sanctioned due to more no. of students. 75-80% work completed. Flooring and plastering work in progress.
10 | r102000337 | Marubadia Tank | Shajapur | WRD | MIS | 2006-11-08 | Shajapur DDM | 72.38 | RIDF Loan upto 10 crore | The project is likely to completed before the due date i.e. 31.3.2007. Quality of work appears to be satisfactory. NABARD board has not been displayed.
10 | r102000311 | Bhyana Bhudki Tank | Shajapur | WRD | MIS | 2006-11-08 | Shajapur DDM | 153.05 | RIDF Loan upto 10 crore | Only foundation work was in progress. The project is likely to overrun the project period. There is delay in land acquisition. No officer other than the EE has visited the site. NABARD board has not been displayed.
10 | r102000095 | Balaghat (371 OG-PS) | Balaghat | RSK | School | 2006-10-14 | Balaghat DDM | 157.68 | RIDF Loan upto 10 crore | School at village Jodapet Kayadi visited. Good school, involvement of teachers, students and parents noticed.
10 | r102000095 | Balaghat (371 OG-PS) | Balaghat | RSK | School | 2006-10-14 | Balaghat DDM | 157.68 | RIDF Loan upto 10 crore | Sindhi Govt. P.S., Varaseoni. School has reduced the commuting distance forthe children by 2-3 km. There is no electricity and furniture in the school.
10 | R102000032 | Richha Tank | Ratlam | WRD | MIS | 2006-10-05 | OIC | 284.59 | RIDF Loan upto 10 crore
10 | R102000031 | Moriya Tank | Ratlam | WRD | MIS | 2006-10-05 | OIC | 164.93 | RIDF Loan upto 10 crore
10 | R102000032 | Richha Tank | Ratlam | WRD | MIS | 2006-10-05 | Ratlam DDM | 284.59 | RIDF Loan upto 10 crore
10 | R102000031 | Moriya Tank | Ratlam | WRD | MIS | 2006-10-05 | Ratlam DDM | 164.93 | RIDF Loan upto 10 crore
10 | R102000164 | Umaria (11 OG-MS) | Umaria | RSK | School | 2006-09-15 | Shahdol DDM | 9.12 | RIDF Loan upto 10 crore | Middle School at village Uphari, block Karkeli visited. Borewell work not done. Building is quite useful for the students of the nearby villages.
10 | R102000095 | Balaghat (371 OG-PS) | Balaghat | RSK | School | 2006-09-14 | Balaghat DDM | 157.68 | RIDF Loan upto 10 crore | Jhadu Girls PS at village Mahendiwada visited. Existing structure of two rooms and varendah, toilets not sufficient for the strength of 100 students. Work completed in June 06.
10 | R102000095 | Balaghat (371 OG-PS) | Balaghat | RSK | School | 2006-09-14 | Balaghat DDM | 157.68 | RIDF Loan upto 10 crore | PS at village Jodapat Kayadi and Sindhi Shaskiya PS at village Varaseoni visited. No electricity and furnitures in the school. Prior to establishment of the schools the children had to commute 2-3 kms for schooling.
10 | r102000095 | Balaghat (371 OG-PS) | Balaghat | RSK | School | 2006-09-14 | RO Officer | 157.68 | RIDF Loan upto 10 crore | Sindhi Govt. P.S., Baraseoni. School is badly constructed and badly maintained. Vigorous efforts required by all concerned for proper upkeep of the school.
10 | r102000095 | Balaghat (371 OG-PS) | Balaghat | RSK | School | 2006-09-14 | RO Officer | 157.68 | RIDF Loan upto 10 crore | Kanya Primary School, Mahendiwada, Baraseoni. Elementary pictorial computer education being given by the two teachers. Though 6 other private schools exist in the village the attendance of students is regular.
10 | R102000164 | Umaria (11 OG-MS) | Umaria | RSK | School | 2006-09-13 | Shahdol DDM | 9.12 | RIDF Loan upto 10 crore | Building is quite useful for students of the nearby villages. There was delay in construction of the building.
10 | R102000074 | Umaria (59 OG-PS) | Umaria | RSK | School | 2006-09-13 | Shahdol DDM | 20.62 | RIDF Loan upto 10 crore | PS at village Bharolla, block Karkeli visited. Single coat colour painting observed. Building quite useful for students of nearby vilalges.
10 | R102000074 | Umaria (59 OG-PS) | Umaria | RSK | School | 2006-09-13 | Shahdol DDM | 20.62 | RIDF Loan upto 10 crore | Primary EGS school at village Karkeli, block Karkeli visited. Single coat colour painting was observed. Building useful for students of the nearby villages.
10 | r102000040 | Pritam Nagar Tank | Ratlam | WRD | MIS | 2006-09-13 | Ratlam DDM | 35.13 | RIDF Loan upto 10 crore | Project completed. NABARD board not displayed.
10 | R102000330 | Tungi Tank | Mandsaur | WRD | MIS | 2006-08-30 | Mandsaur DDM | 138.86 | RIDF Loan upto 10 crore | NB board not displayed. WUA not formed. Progress delayed due to floating of separate tender in respect of Unit II. Dept. should complete the project within the stipulated time frame.
10 | R102000334 | Paronia Tank | Mandsaur | WRD | MIS | 2006-08-30 | Mandsaur DDM | 95.79 | RIDF Loan upto 10 crore | Progress of Unit II hampered due to floatation of separate tender. NB board not displayed. Dept. should complete the project within the stipulated period.
10 | R102000004 | Dhabla Manohar Tank | Mandsaur | WRD | MIS | 2006-08-10 | Mandsaur DDM | 91.04 | RIDF Loan upto 10 crore | Road is beneficial to the surrounding villages, useful to reach Tehsil HQ.
10 | R102000334 | Paronia Tank | Mandsaur | WRD | MIS | 2006-08-10 | OIC | 95.79 | RIDF Loan upto 10 crore | Project yet to be completed. NABARD board not displayed.
10 | R102000093 | Shivpuri (191 OG-PS) | Shivpuri | RSK | School | 2006-07-28 | Shivpuri DDM | 71.5 | RIDF Loan upto 10 crore | School room and kitchen constructed. Roof plastering and tile work expected to be completed. Toilet not sanctioned in the present scheme.
10 | R102000164 | Umaria (11 OG-MS) | Umaria | RSK | School | 2006-07-26 | Shahdol DDM | 9.12 | RIDF Loan upto 10 crore | Village Ballod. Delay in construction of school building. Uptodate records not maintained. Rural Engineering Services not providing proper guidance.
10 | r102000231 | Rajgarh (315 New-MS) | Rajgarh | RSK | School | 2006-07-21 | Shajapur DDM | 267.75 | RIDF Loan upto 10 crore | Dhanora Middle School. The school building stands completed. Construction appears to be satisfactory.
10 | R102000103 | Ujjain (350 OG-PS) | Ujjain | RSK | School | 2006-07-13 | Ujjain DDM | 148.75 | RIDF Loan upto 10 crore | Village Patpala. Jr. Engineer visited the site. School started in November 2005.
10 | R102000148 | Ujjain (267 New-PS) | Ujjain | RSK | School | 2006-07-13 | Ujjain DDM | 113.48 | RIDF Loan upto 10 crore | Village Makodia. Jr. Engineer visited the site. School started in March 2006.
10 | R102000103 | Ujjain (350 OG-PS) | Ujjain | RSK | School | 2006-07-13 | Ujjain DDM | 148.75 | RIDF Loan upto 10 crore | Village Lalpur. Jr. Engineer visited the site. School started in November 2005.
10 | R102000148 | Ujjain (267 New-PS) | Ujjain | RSK | School | 2006-07-13 | Ujjain DDM | 113.48 | RIDF Loan upto 10 crore | Village Nijatpura. Work completed in March 2006. School will start this year.
10 | r102000228 | Jabalpur (225 New-MS) | Jabalpur | RSK | School | 2006-06-30 | Jabalpur DDM | 191.25 | RIDF Loan upto 10 crore | Project has been completed.
10 | r102000228 | Jabalpur (225 New-MS) | Jabalpur | RSK | School | 2006-06-30 | Jabalpur DDM | 191.25 | RIDF Loan upto 10 crore | Project has been completed.
10 | R102000228 | Jabalpur (225 New-MS) | Jabalpur | RSK | School | 2006-06-30 | Jabalpur DDM | 191.25 | RIDF Loan upto 10 crore | Village Padaria. Building complete.
10 | R102000228 | Jabalpur (225 New-MS) | Jabalpur | RSK | School | 2006-06-30 | Jabalpur DDM | 191.25 | RIDF Loan upto 10 crore | Project has been completed.
10 | r102000332 | Ganeshpura LIS | Mandsaur | WRD | MIS | 2006-06-23 | Mandsaur DDM | 79 | RIDF Loan upto 10 crore | Project is under construction. NABARD board not displayed. WUA to be formed.
10 | R102000228 | Jabalpur (225 New-MS) | Jabalpur | RSK | School | 2006-06-22 | Jabalpur DDM | 191.25 | RIDF Loan upto 10 crore | Project has been completed.
10 | R102000228 | Jabalpur (225 New-MS) | Jabalpur | RSK | School | 2006-06-22 | Jabalpur DDM | 191.25 | RIDF Loan upto 10 crore | Project has been completed.
10 | r102000329 | Nawali Tank | Mandsaur | WRD | MIS | 2006-06-22 | Mandsaur DDM | 258.64 | RIDF Loan upto 10 crore | Project is under construction. NABARD board not displayed. WUA to be formed.
10 | R102000092 | Shajapur (174 OG-PS) | Shajapur | RSK | School | 2006-06-20 | Shajapur DDM | 70 | RIDF Loan upto 10 crore | Project has been completed and the construction appears to be satisfactory. NABARD board has not been displayed.
10 | R102000092 | Shajapur (174 OG-PS) | Shajapur | RSK | School | 2006-06-20 | Shajapur DDM | 70 | RIDF Loan upto 10 crore | Project has been completed. NABARD board not displayed.
10 | R102000092 | Shajapur (174 OG-PS) | Shajapur | RSK | School | 2006-06-14 | Shajapur DDM | 70 | RIDF Loan upto 10 crore | Project has been completed and the construction appears satisfactory. NABARD board has not been displayed.
10 | r102000181 | Shajapur (41 OG-MS) | Shajapur | RSK | School | 2006-06-14 | Shajapur DDM | 33.54 | RIDF Loan upto 10 crore | Project has been completed. NABARD board not displayed. Construction satisfactory.
10 | R102000296 | Chargaon Karbal Tank | Chhindwara | WRD | MIS | 2006-06-13 | Chindwara DDM | 87.19 | RIDF Loan upto 10 crore | NABARD board displayed. Site is regularly visited by EE.
10 | R102000181 | Shajapur (41 OG-MS) | Shajapur | RSK | School | 2006-06-08 | Shajapur DDM | 33.54 | RIDF Loan upto 10 crore | Project has been completed and the construction appears to be satisfactory. NABARD board not displayed.
10 | R102000181 | Shajapur (41 OG-MS) | Shajapur | RSK | School | 2006-06-08 | Shajapur DDM | 33.54 | RIDF Loan upto 10 crore | Project has been completed and the building construction is satisfactory. NABARD board has not been displayed.
10 | r102000181 | Shajapur (41 OG-MS) | Shajapur | RSK | School | 2006-06-08 | Shajapur DDM | 33.54 | RIDF Loan upto 10 crore | Project has been completed and construction is satisfactory.
10 | r102000092 | Shajapur (174 OG-PS) | Shajapur | RSK | School | 2006-05-23 | Shajapur DDM | 70 | RIDF Loan upto 10 crore | Project has been completed and the construction appears to be satisfactory.
10 | r102000092 | Shajapur (174 OG-PS) | Shajapur | RSK | School | 2006-05-23 | Shajapur DDM | 70 | RIDF Loan upto 10 crore | Project has been completed and the construction appears to be satisfactory. NABARD board has not been displayed.
10 | r102000092 | Shajapur (174 OG-PS) | Shajapur | RSK | School | 2006-05-23 | Shajapur DDM | 70 | RIDF Loan upto 10 crore | Project has been completed and the construction appears to be satisfactory. NABARD board has not been displayed.
10 | r102000092 | Shajapur (174 OG-PS) | Shajapur | RSK | School | 2006-05-23 | Shajapur DDM | 70 | RIDF Loan upto 10 crore | Project has been completed and the construction appears to be satisfactory. NABARD board has not been displayed.
10 | r102000096 | Gwalior (345 OG-PS) | Gwalior | RSK | School | 2006-04-21 | Gwalior DDM | 139.11 | RIDF Loan upto 10 crore | Construction completed. School being used for storing gunny bags of Coop. Society and materials of mid-day meals also occupied space in the bldg.
10 | r102000184 | Gwalior (4 OG-MS) | Gwalior | RSK | School | 2006-04-21 | Gwalior DDM | 2.04 | RIDF Loan upto 10 crore | Classrooms have been constructed. Pavilion/verandah converted into classrooms. Additional kutcha platform constructed.
10 | r102000184 | Gwalior (4 OG-MS) | Gwalior | RSK | School | 2006-04-21 | Gwalior DDM | 2.04 | RIDF Loan upto 10 crore | Construction work completed. Building occupied by agri. labourers working in the field of local leader.
10 | r102000184 | Gwalior (4 OG-MS) | Gwalior | RSK | School | 2006-04-21 | Gwalior DDM | 2.04 | RIDF Loan upto 10 crore | Construction of classroom completed with pavilion/verandah converted into a classroom.
10 | r102000096 | Gwalior (345 OG-PS) | Gwalior | RSK | School | 2006-04-21 | Gwalior DDM | 139.11 | RIDF Loan upto 10 crore | Plinth, brick work completed. Plaster other finishing painting etc to be done.
10 | r102000096 | Gwalior (345 OG-PS) | Gwalior | RSK | School | 2006-04-21 | Gwalior DDM | 139.11 | RIDF Loan upto 10 crore | Classrooms have been constructed. Verandahs converted into a classroom, closed by grills.
10 | r102000184 | Gwalior (4 OG-MS) | Gwalior | RSK | School | 2006-04-21 | Gwalior DDM | 2.04 | RIDF Loan upto 10 crore | Construction work completed with closed grills and platform
10 | r102000096 | Gwalior (345 OG-PS) | Gwalior | RSK | School | 2006-04-21 | Gwalior DDM | 139.11 | RIDF Loan upto 10 crore | Finishing to be done
10 | r102000184 | Gwalior (4 OG-MS) | Gwalior | RSK | School | 2006-04-21 | Gwalior DDM | 2.04 | RIDF Loan upto 10 crore | PCR verification. Road users are happy.
10 | R102000130 | Khargone (568 New-PS) | Khargone | RSK | School | 2006-04-20 | Khargone DDM | 241.4 | RIDF Loan upto 10 crore | Project completed. Site visited by Engineers at various stages.
10 | R102000085 | Khargone (478 OG-PS) | Khargone | RSK | School | 2006-04-20 | Khargone DDM | 182.97 | RIDF Loan upto 10 crore | Project completed. Site visited by Engineers at various stages.
10 | R102000130 | Khargone (568 New-PS) | Khargone | RSK | School | 2006-04-20 | Khargone DDM | 241.4 | RIDF Loan upto 10 crore | Project completed. Site visited by Engineers at various stages.
10 | R102000085 | Khargone (478 OG-PS) | Khargone | RSK | School | 2006-04-20 | Khargone DDM | 182.97 | RIDF Loan upto 10 crore | Project completed. Site visited by Engineers at various stages.
10 | R102000319 | LBC Dongariya 5.00-23 km | Narsinghpur | NVDA | MIP | 2006-04-20 | Narsinghpur DDM | 2811.11 | RIDF Loan 25 crore & above | Tender finalisation process not done. Work is yet to commence.
10 | R102000318 | LBC RD 130.67-136.87 km | Narsinghpur | NVDA | MIP | 2006-04-20 | Narsinghpur DDM | 3352.26 | RIDF Loan 25 crore & above | Tender finalisation process to be expedited. Work is yet to commence. NABARD board not displayed.
10 | r102000130 | Khargone (568 New-PS) | Khargone | RSK | School | 2006-04-20 | Khargone DDM | 241.4 | RIDF Loan upto 10 crore | Project completed. Site visited by Engineers at various stages.
10 | R102000321 | Sadumar Br.Canal RD.9-21 | Narsinghpur | NVDA | MIP | 2006-04-20 | Narsinghpur DDM | 3136.73 | RIDF Loan 25 crore & above | Tender finalisation process not done. Work is yet to commence.
10 | r102000130 | Khargone (568 New-PS) | Khargone | RSK | School | 2006-04-20 | Khargone DDM | 241.4 | RIDF Loan upto 10 crore | Project completed. Site visited by Engineers at various stages.
10 | R102000320 | Sadumar Br.canal RD 4.5 | Narsinghpur | NVDA | MIP | 2006-04-20 | Narsinghpur DDM | 3987.09 | RIDF Loan 25 crore & above | Work is yet to commence. NABARD board not displayed.
10 | R102000130 | Khargone (568 New-PS) | Khargone | RSK | School | 2006-04-19 | Khargone DDM | 241.4 | RIDF Loan upto 10 crore | Project completed. Site visited by Engineers at various stages.
10 | r102000130 | Khargone (568 New-PS) | Khargone | RSK | School | 2006-04-19 | Khargone DDM | 241.4 | RIDF Loan upto 10 crore | Project completed. Site visited by Engineers at various stages.
10 | R102000085 | Khargone (478 OG-PS) | Khargone | RSK | School | 2006-04-19 | Khargone DDM | 182.97 | RIDF Loan upto 10 crore | Project completed. Site visited by Engineers at various stages.
10 | R102000085 | Khargone (478 OG-PS) | Khargone | RSK | School | 2006-04-19 | Khargone DDM | 182.97 | RIDF Loan upto 10 crore | Project completed. Site visited by Engineers at various stages.
10 | r102000085 | Khargone (478 OG-PS) | Khargone | RSK | School | 2006-04-19 | Khargone DDM | 182.97 | RIDF Loan upto 10 crore | Project completed. Site visited by Engineers at various stages.
10 | R102000130 | Khargone (568 New-PS) | Khargone | RSK | School | 2006-04-19 | Khargone DDM | 241.4 | RIDF Loan upto 10 crore | Project completed. Site visited by Engineers at various stages.
10 | r102000096 | Gwalior (345 OG-PS) | Gwalior | RSK | School | 2006-04-18 | Gwalior DDM | 139.11 | RIDF Loan upto 10 crore | Construction of the school building completed.
10 | R102000085 | Khargone (478 OG-PS) | Khargone | RSK | School | 2006-04-18 | Khargone DDM | 182.97 | RIDF Loan upto 10 crore | Project completed. Site visited by Engineers at various stages.
10 | r102000184 | Gwalior (4 OG-MS) | Gwalior | RSK | School | 2006-04-18 | Gwalior DDM | 2.04 | RIDF Loan upto 10 crore | Construction of the building has been completed. Maintenance is very poor.
10 | R102000174 | Khargone (13 OG-MS) | Khargone | RSK | School | 2006-04-18 | Khargone DDM | 8.72 | RIDF Loan upto 10 crore | Project completed. Site visited by Engineers at various stages.
10 | r102000096 | Gwalior (345 OG-PS) | Gwalior | RSK | School | 2006-04-18 | Gwalior DDM | 139.11 | RIDF Loan upto 10 crore | Classrooms, pavilion/verandah closed with grills have been constructed
10 | R102000209 | Khargone (247 New-MS) | Khargone | RSK | School | 2006-04-18 | Khargone DDM | 209.95 | RIDF Loan upto 10 crore | Project completed. Site visited by Engineers at various stages.
10 | r102000096 | Gwalior (345 OG-PS) | Gwalior | RSK | School | 2006-04-18 | Gwalior DDM | 139.11 | RIDF Loan upto 10 crore | Construction of the building completed. Poor construction. Poor maintenance. Electricity provided. Tap water is also available.
10 | r102000096 | Gwalior (345 OG-PS) | Gwalior | RSK | School | 2006-04-18 | Gwalior DDM | 139.11 | RIDF Loan upto 10 crore | Construction of building completed.
10 | r102000096 | Gwalior (345 OG-PS) | Gwalior | RSK | School | 2006-04-18 | Gwalior DDM | 139.11 | RIDF Loan upto 10 crore | Construction has been completed. Maintenance is very poor.
10 | r102000184 | Gwalior (4 OG-MS) | Gwalior | RSK | School | 2006-04-18 | Gwalior DDM | 2.04 | RIDF Loan upto 10 crore | Construction work completed.
10 | r102000096 | Gwalior (345 OG-PS) | Gwalior | RSK | School | 2006-04-18 | Gwalior DDM | 139.11 | RIDF Loan upto 10 crore | Construction completed.
10 | r102000096 | Gwalior (345 OG-PS) | Gwalior | RSK | School | 2006-04-18 | Gwalior DDM | 139.11 | RIDF Loan upto 10 crore | Construction of school building has been completed.
10 | r102000096 | Gwalior (345 OG-PS) | Gwalior | RSK | School | 2006-04-18 | Gwalior DDM | 139.11 | RIDF Loan upto 10 crore | Construction has been completed. Electricity has been provided. Building made attractive.
10 | r102000096 | Gwalior (345 OG-PS) | Gwalior | RSK | School | 2006-04-18 | Gwalior DDM | 139.11 | RIDF Loan upto 10 crore | The work in kitchenshed is incomplete. Finishing and painting is yet to be done.
10 | r102000184 | Gwalior (4 OG-MS) | Gwalior | RSK | School | 2006-04-18 | Gwalior DDM | 2.04 | RIDF Loan upto 10 crore | Finishing work to be completed. Brick work, slab plaster work completed.
10 | r102000096 | Gwalior (345 OG-PS) | Gwalior | RSK | School | 2006-04-18 | Gwalior DDM | 139.11 | RIDF Loan upto 10 crore | Roof slab yet to be laid. Flooring, plastering, finishing and painting yet to be done
10 | R102000174 | Khargone (13 OG-MS) | Khargone | RSK | School | 2006-04-18 | Khargone DDM | 8.72 | RIDF Loan upto 10 crore | Project completed. Site visited by Engineers at various stages.
10 | r102000001 | Jaleshwar | Ashoknagar | WRD | MIS | 2006-04-18 | Guna DDM | 87.75 | RIDF Loan upto 10 crore | Construction of school building completed. Additional room and kitchen shed is being constructed.
10 | r102000096 | Gwalior (345 OG-PS) | Gwalior | RSK | School | 2006-04-18 | Gwalior DDM | 139.11 | RIDF Loan upto 10 crore | Construction of school building has been completed.
10 | R102000209 | Khargone (247 New-MS) | Khargone | RSK | School | 2006-04-18 | Khargone DDM | 209.95 | RIDF Loan upto 10 crore | Project completed. Site visited by Engineers at various stages.
10 | r102000096 | Gwalior (345 OG-PS) | Gwalior | RSK | School | 2006-04-18 | Gwalior DDM | 139.11 | RIDF Loan upto 10 crore | Work of kitchen shed is incomplete. Finishing and painting is yet to be done.
10 | r102000096 | Gwalior (345 OG-PS) | Gwalior | RSK | School | 2006-04-18 | Gwalior DDM | 139.11 | RIDF Loan upto 10 crore | Two classrooms have been constructed.
10 | R102000174 | Khargone (13 OG-MS) | Khargone | RSK | School | 2006-04-18 | Khargone DDM | 8.72 | RIDF Loan upto 10 crore | Project completed. Site visited by Engineers at various stages.
10 | R102000139 | Vidisha (404 New-PS) | Vidisha | RSK | School | 2006-03-31 | DDM | 171.7 | RIDF Loan upto 10 crore | School building at village Khamtala, block Vidisha visited. Project completed. Water leakage from ceiling was complained.
10 | R102000139 | Vidisha (404 New-PS) | Vidisha | RSK | School | 2006-03-31 | DDM | 171.7 | RIDF Loan upto 10 crore | School building at village Bagri, block Vidisha visited. Project was completed and functioning.
10 | R102000139 | Vidisha (404 New-PS) | Vidisha | RSK | School | 2006-03-31 | DDM | 171.7 | RIDF Loan upto 10 crore | School building at village Kotra Lashkarpur, block Vidisha visited. Construction quality was unsatisfactory on account of plastering, toilet blocks and window roofs.
10 | R102000139 | Vidisha (404 New-PS) | Vidisha | RSK | School | 2006-03-31 | DDM | 171.7 | RIDF Loan upto 10 crore | School building at village Nagpipariya, block Vidisha visited. The school was locked at the time of visit.
10 | R102000144 | Hoshangabad (41 New-PS) | Hoshangabad | RSK | School | 2006-03-30 | DDM | 17.43 | RIDF Loan upto 10 crore | School building at village Gandhishala, block Sohagpur visited. Construction is complete except handpump. Quality of construction is not satisfactory.
10 | R102000144 | Hoshangabad (41 New-PS) | Hoshangabad | RSK | School | 2006-03-30 | DDM | 17.43 | RIDF Loan upto 10 crore | School building at village Semriharchand, block Sohagpur visited. Project is complete though quality is not satisfactory.
10 | R102000144 | Hoshangabad (41 New-PS) | Hoshangabad | RSK | School | 2006-03-30 | DDM | 17.43 | RIDF Loan upto 10 crore | School building at village Marupura, block Sohagpur visited. Project under progress.
10 | R102000144 | Hoshangabad (41 New-PS) | Hoshangabad | RSK | School | 2006-03-30 | DDM | 17.43 | RIDF Loan upto 10 crore | School building at village Matapura, block Sohagpur visited. Project is complete.
10 | r102000073 | Satna (474 OG-PS) | Satna | RSK | School | 2006-03-29 | DDM | 197.62 | RIDF Loan upto 10 crore | Primary school at Chopda village in Maihar block visited. Building is completed.
10 | R102000118 | Satna (612 New-PS) | Satna | RSK | School | 2006-03-29 | DDM | 260.1 | RIDF Loan upto 10 crore | School building at village Chopra, block Maihar visited. Building constructed though incomplete in many respects.
10 | R102000118 | Satna (612 New-PS) | Satna | RSK | School | 2006-03-29 | DDM | 260.1 | RIDF Loan upto 10 crore | School building at village Piparhar, block Maihar visited. Building constructed though incomplete in many respects.
10 | R102000118 | Satna (612 New-PS) | Satna | RSK | School | 2006-03-29 | DDM | 260.1 | RIDF Loan upto 10 crore | School building at village Nadipar Sonwari, block Maihar visited. Building constructed though incomplete in many respects.
10 | R102000190 | Sidhi (74 OG-MS) | Sidhi | RSK | School | 2006-03-27 | DDM | 52.35 | RIDF Loan upto 10 crore | School building at village Sonakhad visited. Super structure work under progress. Hand pump work not started.
10 | R102000190 | Sidhi (74 OG-MS) | Sidhi | RSK | School | 2006-03-27 | DDM | 52.35 | RIDF Loan upto 10 crore | School building at village Koluha visited. Project complete though flooring work found damaged.
10 | R102000190 | Sidhi (74 OG-MS) | Sidhi | RSK | School | 2006-03-27 | DDM | 52.35 | RIDF Loan upto 10 crore | School building at village Majhreti visited. Project completed.
10 | R102000117 | Rewa (664 New-PS) | Rewa | RSK | School | 2006-03-27 | DDM | 282.2 | RIDF Loan upto 10 crore | School building at village Majhreti visited. Super structure work and handpump work were under progress.
10 | R102000117 | Rewa (664 New-PS) | Rewa | RSK | School | 2006-03-27 | DDM | 282.2 | RIDF Loan upto 10 crore | School building at village Nebuha visited. Super structure work was under progress.
10 | R102000106 | Sagar (637 OG-PS) | Sagar | RSK | School | 2006-03-24 | DDM | 269.4 | RIDF Loan upto 10 crore | Primary School building at Ganjara village, Sagar dist visited. Building is completed.
10 | R102000106 | Sagar (637 OG-PS) | Sagar | RSK | School | 2006-03-24 | DDM | 269.4 | RIDF Loan upto 10 crore | Primary school at Saboolal Ward, Garhakota village, Sagar dist visited. School building completed.
10 | R102000106 | Sagar (637 OG-PS) | Sagar | RSK | School | 2006-03-24 | DDM | 269.4 | RIDF Loan upto 10 crore | Primary school at Berkheda Tola in Sagar Dist visited. Building completed
10 | R102000151 | Sagar (183 New-PS) | Sagar | RSK | School | 2006-03-24 | DDM | 77.78 | RIDF Loan upto 10 crore | School building at Berkhera Gantam village Sagar Dist visited. School building is completed. Drinking water /hand pump is yet to be provided.
10 | R102000151 | Sagar (183 New-PS) | Sagar | RSK | School | 2006-03-24 | DDM | 77.78 | RIDF Loan upto 10 crore | Primary school at Adivasi Tola, Sagar district visited. Building is completed. Drinking water facility to be constructed.
10 | R102000223 | Hoshangabad (213 New-MS) | Hoshangabad | RSK | School | 2006-03-23 | DDM | 181.05 | RIDF Loan upto 10 crore | School building at village Baharpur, block Babai visited. Project is complete except toilet blocks.
10 | R102000144 | Hoshangabad (41 New-PS) | Hoshangabad | RSK | School | 2006-03-23 | DDM | 17.43 | RIDF Loan upto 10 crore | School building at village Meghaly visited. Project is complete and operational.
10 | R102000144 | Hoshangabad (41 New-PS) | Hoshangabad | RSK | School | 2006-03-23 | DDM | 17.43 | RIDF Loan upto 10 crore | School building at village Goal visited. Project is complete and functional.
10 | R102000144 | Hoshangabad (41 New-PS) | Hoshangabad | RSK | School | 2006-03-23 | DDM | 17.43 | RIDF Loan upto 10 crore | School building at village Gujarwada, block Babai visited. Project is under progress. School is running over part construction.
10 | R102000144 | Hoshangabad (41 New-PS) | Hoshangabad | RSK | School | 2006-03-23 | DDM | 17.43 | RIDF Loan upto 10 crore | School building at village Silarikhurd, block Babai visited. Project under progress. School is running over part construction.
10 | R102000144 | Hoshangabad (41 New-PS) | Hoshangabad | RSK | School | 2006-03-23 | DDM | 17.43 | RIDF Loan upto 10 crore | School building at village Akhman, block Babai visited. Project is under progress. School is running over part construction.
10 | R102000082 | Dewas (122 OG-PS) | Dewas | RSK | School | 2006-03-23 | DDM | 37.81 | RIDF Loan upto 10 crore | Primary school at Jirad visited. Work in progress.
10 | R102000082 | Dewas (122 OG-PS) | Dewas | RSK | School | 2006-03-23 | DDM | 37.81 | RIDF Loan upto 10 crore | Primary school at Mogra Pathar visited. Work in progress.
10 | R102000082 | Dewas (122 OG-PS) | Dewas | RSK | School | 2006-03-23 | DDM | 37.81 | RIDF Loan upto 10 crore | Primary school at Manasa visited. Work in progress.
10 | R102000082 | Dewas (122 OG-PS) | Dewas | RSK | School | 2006-03-23 | DDM | 37.81 | RIDF Loan upto 10 crore | Primary school at Hathner visited. Work in progress.
10 | R102000127 | Dewas (58 New-PS) | Dewas | RSK | School | 2006-03-23 | DDM | 24.65 | RIDF Loan upto 10 crore | Primary school at Hathnori visited. Work in progress.
10 | R102000127 | Dewas (58 New-PS) | Dewas | RSK | School | 2006-03-23 | DDM | 24.65 | RIDF Loan upto 10 crore | Primary school at Balakheda visited. Work in progress.
10 | R102000127 | Dewas (58 New-PS) | Dewas | RSK | School | 2006-03-23 | DDM | 24.65 | RIDF Loan upto 10 crore | Primary school at Jharkhedi visited. Work in progress.
10 | R102000127 | Dewas (58 New-PS) | Dewas | RSK | School | 2006-03-23 | DDM | 24.65 | RIDF Loan upto 10 crore | Primary school at Samgi visited. Work in progress.
10 | R102000188 | Guna / Ashoknagar (4 OG-MS) | Ashoknagar | RSK | School | 2006-03-22 | DDM | 3.4 | RIDF Loan upto 10 crore | Middle School building at Pilighata Village, Ashoknagar Dist visited. Foundation completed. Super structure is under construction.
10 | R102000188 | Guna / Ashoknagar (4 OG-MS) | Ashoknagar | RSK | School | 2006-03-22 | DDM | 3.4 | RIDF Loan upto 10 crore | Middle School at Seji village in Ashoknagar Dist visited. Construction of the school building is completed.
10 | R102000232 | Guna / Ashoknagar (410 New-MS) | Ashoknagar | RSK | School | 2006-03-22 | DDM | 348.5 | RIDF Loan upto 10 crore | School building at village Pilighata in Ashoknagar block visited. Building under construction. Quality control lab not available.
10 | R102000232 | Guna / Ashoknagar (410 New-MS) | Ashoknagar | RSK | School | 2006-03-22 | DDM | 348.5 | RIDF Loan upto 10 crore | School building at village Seji in block Ashoknagar visited. Construction is completed.
10 | R102000232 | Guna / Ashoknagar (410 New-MS) | Ashoknagar | RSK | School | 2006-03-22 | DDM | 348.5 | RIDF Loan upto 10 crore | School building at village Pilighata, block Ashoknagar visited. Super structure work under progress. There is quality lab for material testing.
10 | R102000232 | Guna / Ashoknagar (410 New-MS) | Ashoknagar | RSK | School | 2006-03-22 | DDM | 348.5 | RIDF Loan upto 10 crore | School building at village Seji, block Ashoknagar visited. Project is complete.
10 | R102000130 | Khargone (568 New-PS) | Khargone | RSK | School | 2006-03-12 | Khargone DDM | 241.4 | RIDF Loan upto 10 crore | Project completed. Site visited by Engineers at various stages.
10 | R102000174 | Khargone (13 OG-MS) | Khargone | RSK | School | 2006-03-12 | Khargone DDM | 8.72 | RIDF Loan upto 10 crore | Project completed. Site visited by Engineers at various stages.
10 | R102000209 | Khargone (247 New-MS) | Khargone | RSK | School | 2006-03-12 | Khargone DDM | 209.95 | RIDF Loan upto 10 crore | Project completed. Site visited by Engineers at various stages.
10 | R102000209 | Khargone (247 New-MS) | Khargone | RSK | School | 2006-03-12 | Khargone DDM | 209.95 | RIDF Loan upto 10 crore | Project completed. Site visited by Engineers at various stages.
10 | R102000085 | Khargone (478 OG-PS) | Khargone | RSK | School | 2006-03-12 | Khargone DDM | 182.97 | RIDF Loan upto 10 crore | Project completed. Site visited by Engineers at various stages.
10 | R102000046 | Devri Tank | Sidhi | WRD | MIS | 2006-03-11 | DDM | 355.09 | RIDF Loan upto 10 crore | Earthwork in Unit I is in progress. Due to delay in land acquisition work started in March 2005. Though the project is scheduled for completion in March 2006, actual completion may take place in March 2007.
10 | R102000045 | Padry Tank | Singrauli | WRD | MIS | 2006-03-10 | DDM | 481.7 | RIDF Loan upto 10 crore | Work is in progress in Unit I. NABARD board is not displayed.
10 | R102000087 | Mandla (350 OG-PS) | Mandla | RSK | School | 2006-03-10 | DDM | 139.82 | RIDF Loan upto 10 crore | School at Badangatola visited. Building is complete.
10 | R102000176 | Mandla (15 OG-MS) | Mandla | RSK | School | 2006-03-10 | DDM | 11.06 | RIDF Loan upto 10 crore | School at Danitola visited. Building is completed except drinking water and toilet blocks which are under construction.
10 | R102000233 | Dhar (180 New-MS) | Dhar | RSK | School | 2006-03-10 | Dhar DDM | 153 | RIDF Loan upto 10 crore | Water was not sufficient. Finishing of the building poor. Sub-standard material used.
10 | R102000168 | Bhind (10 OG-MS) | Bhind | RSK | School | 2006-03-09 | DDM | 7.5 | RIDF Loan upto 10 crore | Middle school at Imleda village, Bhind dist visited. Foundation work completed. Work is in progress.
10 | R102000079 | Bhind (197 OG-PS) | Bhind | RSK | School | 2006-03-09 | DDM | 83.73 | RIDF Loan upto 10 crore | Primary school at Dubekapura village, Bhind dist visited. Foundation and super structure completed. Internal and external plastering, flooring is yet to be done.
10 | R102000079 | Bhind (197 OG-PS) | Bhind | RSK | School | 2006-03-09 | DDM | 83.73 | RIDF Loan upto 10 crore | Primary School at Jaganathkapura village, Bhind dist visited. Building is completed. Kitchen and toilet block yet to be taken up.
10 | R102000079 | Bhind (197 OG-PS) | Bhind | RSK | School | 2006-03-09 | DDM | 83.73 | RIDF Loan upto 10 crore | Primary school in Subhashnagar (Bhind) visited. School building completed. Kitchen, toilet block & drinking water facility to be taken up. Quality of construction is good.
10 | R102000063 | Sone 3/2 | Satna | PWD | Bridge | 2006-03-08 | DDM | 364.17 | RIDF Loan upto 10 crore | Work is in progress in foundation, substructure and super structure. Land acquisition is yet to be completed.
10 | R102000296 | Chargaon Karbal Tank | Chhindwara | WRD | MIS | 2006-03-07 | DDM | 87.19 | RIDF Loan upto 10 crore | Unit I Headwork 50% complete. Project likely to be completed by June 2006.
10 | R102000174 | Khargone (13 OG-MS) | Khargone | RSK | School | 2006-03-07 | Khargone DDM | 8.72 | RIDF Loan upto 10 crore | Project completed. Site visited by Engineers at various stages.
10 | R102000209 | Khargone (247 New-MS) | Khargone | RSK | School | 2006-03-07 | Khargone DDM | 209.95 | RIDF Loan upto 10 crore | Project completed. Site visited by Engineers at various stages.
10 | R102000174 | Khargone (13 OG-MS) | Khargone | RSK | School | 2006-03-07 | Khargone DDM | 8.72 | RIDF Loan upto 10 crore | Project completed. Site visited by Engineers at various stages.
10 | R102000174 | Khargone (13 OG-MS) | Khargone | RSK | School | 2006-03-07 | Khargone DDM | 8.72 | RIDF Loan upto 10 crore | Project completed. Site visited by Engineers at various stages.
10 | R102000209 | Khargone (247 New-MS) | Khargone | RSK | School | 2006-03-05 | Khargone DDM | 209.95 | RIDF Loan upto 10 crore | Project completed. Site visited by Engineers at various stages.
10 | R102000209 | Khargone (247 New-MS) | Khargone | RSK | School | 2006-03-05 | Khargone DDM | 209.95 | RIDF Loan upto 10 crore | Project completed. Site visited by Engineers at various stages.
10 | R102000209 | Khargone (247 New-MS) | Khargone | RSK | School | 2006-03-05 | Khargone DDM | 209.95 | RIDF Loan upto 10 crore | Project completed. Site visited by Engineers at various stages.
10 | R102000072 | Rewa (620 OG-PS) | Rewa | RSK | School | 2006-03-04 | DDM | 263.5 | RIDF Loan upto 10 crore | Primary school at Govindgarh village, Rewa dist visited. Foundation work is completed. Super structure is under construction.
10 | R102000072 | Rewa (620 OG-PS) | Rewa | RSK | School | 2006-03-04 | DDM | 263.5 | RIDF Loan upto 10 crore | Primary school at Kolvaru village visited. Building is completed and flooring/finishing is to be completed.
10 | R102000072 | Rewa (620 OG-PS) | Rewa | RSK | School | 2006-03-04 | DDM | 263.5 | RIDF Loan upto 10 crore | Primary school at Paipakhara village visited. Building is completed and finishing is to be completed.
10 | R102000072 | Rewa (620 OG-PS) | Rewa | RSK | School | 2006-03-04 | DDM | 263.5 | RIDF Loan upto 10 crore | Primary school at Silpura village visited. Foundation completed and super structure is under construction.
10 | R102000072 | Rewa (620 OG-PS) | Rewa | RSK | School | 2006-03-04 | DDM | 263.5 | RIDF Loan upto 10 crore | Girls primary school at Rupauli village visited. Foundation and structure completed. Flooring is to be done.
10 | R102000162 | Rewa (14 OG-MS) | Rewa | RSK | School | 2006-03-04 | DDM | 7.25 | RIDF Loan upto 10 crore | Middle school at Karhiya No.2 visited. Foundation & super structure completed. Work on toilet block and drinking water yet to start.
10 | R102000072 | Rewa (620 OG-PS) | Rewa | RSK | School | 2006-03-04 | DDM | 263.5 | RIDF Loan upto 10 crore | Boys' Primary school at Rupauli visited. Foundation & super structure completed. Fixing of windows/doors, flooring to be done.
10 | R102000162 | Rewa (14 OG-MS) | Rewa | RSK | School | 2006-03-04 | DDM | 7.25 | RIDF Loan upto 10 crore | Middle School at Karhiya No.1 visited. Building is completed.
10 | R102000095 | Balaghat (371 OG-PS) | Balaghat | RSK | School | 2006-03-04 | DDM | 157.68 | RIDF Loan upto 10 crore | Primary school at Khidkitola village visited. Building construction completed.
10 | R102000095 | Balaghat (371 OG-PS) | Balaghat | RSK | School | 2006-03-04 | DDM | 157.68 | RIDF Loan upto 10 crore | Primary school at Khedseonitola village visited. Building is completed in all respects.
10 | R102000095 | Balaghat (371 OG-PS) | Balaghat | RSK | School | 2006-03-04 | DDM | 157.68 | RIDF Loan upto 10 crore | Primary school at Dubitola village visited. Building is constructed.
10 | R102000095 | Balaghat (371 OG-PS) | Balaghat | RSK | School | 2006-03-04 | DDM | 157.68 | RIDF Loan upto 10 crore | School at Khidkitola visited. Building is complete.
10 | R102000095 | Balaghat (371 OG-PS) | Balaghat | RSK | School | 2006-03-04 | DDM | 157.68 | RIDF Loan upto 10 crore | School at Khedseonitola visited. Building is completed.
10 | R102000095 | Balaghat (371 OG-PS) | Balaghat | RSK | School | 2006-03-04 | DDM | 157.68 | RIDF Loan upto 10 crore | School at Dhobitola visited. Building is complete in all respects.
10 | R102000081 | Datia (93 OG-PS) | Datia | RSK | School | 2006-03-03 | DDM | 32.46 | RIDF Loan upto 10 crore | Primary school at Vijaypur village visited. Building completed upto roof level. Plastering and flooring is yet to be done.
10 | R102000081 | Datia (93 OG-PS) | Datia | RSK | School | 2006-03-03 | DDM | 32.46 | RIDF Loan upto 10 crore | Primary school at Hada Pahad visited. Building is completed. Flooring & finishing is yet to be done.
10 | R102000081 | Datia (93 OG-PS) | Datia | RSK | School | 2006-03-03 | DDM | 32.46 | RIDF Loan upto 10 crore | Primary School at Chitua Dera village visited. The building is complete in all respect. Toilet block is yet to be constructed.
10 | R102000081 | Datia (93 OG-PS) | Datia | RSK | School | 2006-03-03 | DDM | 32.46 | RIDF Loan upto 10 crore | Primary school at Kalapuram village visited. Building is completed except for flooring and painting.
10 | R102000085 | Khargone (478 OG-PS) | Khargone | RSK | School | 2006-03-03 | DDM | 182.97 | RIDF Loan upto 10 crore | Primary school at Dhamva Village visited
10 | R102000085 | Khargone (478 OG-PS) | Khargone | RSK | School | 2006-03-03 | DDM | 182.97 | RIDF Loan upto 10 crore | Primary school at Temla village visited
10 | R102000085 | Khargone (478 OG-PS) | Khargone | RSK | School | 2006-03-03 | DDM | 182.97 | RIDF Loan upto 10 crore | Primary school at Pipal Jhopa village visited
10 | R102000085 | Khargone (478 OG-PS) | Khargone | RSK | School | 2006-03-02 | DDM | 182.97 | RIDF Loan upto 10 crore | Primary school at Gaybed village visited
10 | R102000085 | Khargone (478 OG-PS) | Khargone | RSK | School | 2006-03-02 | DDM | 182.97 | RIDF Loan upto 10 crore | Primary school at Abhapuri village visited
10 | R102000010 | Maniyapura Tank | Rajgarh | WRD | MIS | 2006-03-01 | DDM | 270.47 | RIDF Loan upto 10 crore | Work in progress. Delay in land acquisition. NB board not displayed.
10 | r102000041 | Jagthar Tank | Sagar | WRD | MIS | 2006-03-01 | DDM | 147.36 | RIDF Loan upto 10 crore | Headworks are in progress. Quality of works satisfactory.
10 | R102000291 | Bistan-Tensemali | Khargone | PWD | Road | 2006-03-01 | DDM | 684.09 | RIDF Loan upto 10 crore | RA
10 | R102000085 | Khargone (478 OG-PS) | Khargone | RSK | School | 2006-03-01 | DDM | 182.97 | RIDF Loan upto 10 crore | Primary School at Umardal village visited.
10 | R102000085 | Khargone (478 OG-PS) | Khargone | RSK | School | 2006-03-01 | DDM | 182.97 | RIDF Loan upto 10 crore | Primary School at Shivna village visited
10 | R102000085 | Khargone (478 OG-PS) | Khargone | RSK | School | 2006-03-01 | DDM | 182.97 | RIDF Loan upto 10 crore | Primary school at Mithawar village visited.
10 | R102000143 | Narsinghpur (150 New-PS) | Narsinghpur | RSK | School | 2006-03-01 | DDM | 63.75 | RIDF Loan upto 10 crore | School building at village Bahadurpur visited. Super structure work under progress. Quality of work not satisfactory.
10 | R102000143 | Narsinghpur (150 New-PS) | Narsinghpur | RSK | School | 2006-03-01 | DDM | 63.75 | RIDF Loan upto 10 crore | School building at village Pipariya Tola visited. Super structure work under progress.
10 | R102000143 | Narsinghpur (150 New-PS) | Narsinghpur | RSK | School | 2006-03-01 | DDM | 63.75 | RIDF Loan upto 10 crore | School building at village Narsinghpur visited. Construction work yet to start.
10 | R102000143 | Narsinghpur (150 New-PS) | Narsinghpur | RSK | School | 2006-03-01 | DDM | 63.75 | RIDF Loan upto 10 crore | School building at village Pachama visited. Building is complete.
10 | R102000036 | Dhabi Tank | Khandwa | WRD | MIS | 2006-02-26 | DDM | 48.72 | RIDF Loan upto 10 crore | Earthwork completed to the extent of70%. Pitching work in progress and around 40% completed. Spill work too was in progress. Excavation needs to be made still in some parts.
10 | R102000098 | Narsinghpur (285 OG-PS) | Narsinghpur | RSK | School | 2006-02-20 | DDM | 121.13 | RIDF Loan upto 10 crore | Primary school at Rathamati tola village visited. Building is completed.
10 | R102000098 | Narsinghpur (285 OG-PS) | Narsinghpur | RSK | School | 2006-02-20 | DDM | 121.13 | RIDF Loan upto 10 crore | Primary school at Gotegaon Kheda village visited. Building is constructed.
10 | R102000044 | Birgod Motakhora Tank | Shajapur | WRD | MIS | 2006-02-18 | DDM | 126 | RIDF Loan upto 10 crore | Slow work progress. Project likely to be completed by 4-10-06. Delay in land acquisition. NB board not displayed.
10 | R102000098 | Narsinghpur (285 OG-PS) | Narsinghpur | RSK | School | 2006-02-17 | DDM | 121.13 | RIDF Loan upto 10 crore | School building at Kamjhour village visited. Building is completed except for tiling and painting.
10 | R102000098 | Narsinghpur (285 OG-PS) | Narsinghpur | RSK | School | 2006-02-17 | DDM | 121.13 | RIDF Loan upto 10 crore | Primary school at Barua, Bagaaspur village visited. Building is completed.
10 | R102000098 | Narsinghpur (285 OG-PS) | Narsinghpur | RSK | School | 2006-02-17 | DDM | 121.13 | RIDF Loan upto 10 crore | Primary school at Mahuakheda village visited. School building is completed. Toilet blocks and drinking water is yet to be taken up.
10 | R102000075 | Panna (341 OG-PS) | Panna | RSK | School | 2006-02-14 | DDM | 99 | RIDF Loan upto 10 crore | School building at village Bakchur visited. Building completed.
10 | R102000075 | Panna (341 OG-PS) | Panna | RSK | School | 2006-02-14 | DDM | 99 | RIDF Loan upto 10 crore | School building at village Chaneni visited. Building completed.
10 | R102000075 | Panna (341 OG-PS) | Panna | RSK | School | 2006-02-14 | DDM | 99 | RIDF Loan upto 10 crore | School building at village Kunjhwan visited. Work is in progress.
10 | R102000199 | Panna (250 New-MS) | Panna | RSK | School | 2006-02-14 | DDM | 212.5 | RIDF Loan upto 10 crore | School building at Village Jaruapur visited. Work is in progress.
10 | r102000075 | Panna (341 OG-PS) | Panna | RSK | School | 2006-02-14 | DDM | 99 | RIDF Loan upto 10 crore | School building at village Nahri visited. Building completed except part kitchen and toilet block.
10 | R102000098 | Narsinghpur (285 OG-PS) | Narsinghpur | RSK | School | 2006-02-14 | DDM | 121.13 | RIDF Loan upto 10 crore | Primary school at Bus stand tola, Bhaisa village visited. School building is completed. Plastering and painting is to be done. Kitchen & toilets yet to be taken up.
10 | R102000098 | Narsinghpur (285 OG-PS) | Narsinghpur | RSK | School | 2006-02-14 | DDM | 121.13 | RIDF Loan upto 10 crore | Primary school at Bargitola, Bhaisa visited. Building completed.
10 | r102000098 | Narsinghpur (285 OG-PS) | Narsinghpur | RSK | School | 2006-02-14 | DDM | 121.13 | RIDF Loan upto 10 crore | Primary school at Kodsa village visited. Building work completed but internal and external plastering is to be done.
10 | R102000334 | Paronia Tank | Mandsaur | WRD | MIS | 2006-02-13 | DDM | 95.79 | RIDF Loan upto 10 crore | Work is in progress in Unit I. Project likely to be completed by June 2007. NABARD Board not displayed.
10 | R102000330 | Tungi Tank | Mandsaur | WRD | MIS | 2006-02-13 | DDM | 138.86 | RIDF Loan upto 10 crore | Work is in progress in Unit I. NABARD board is not displayed.
10 | R102000006 | Palkhanda Tank | Mandsaur | WRD | MIS | 2006-02-08 | DDM | 93.14 | RIDF Loan upto 10 crore | Project is completed. PCR yet to be submitted. NABARD board is not displayed.
10 | R102000048 | Deo 10/4-6 | Balaghat | PWD | Bridge | 2006-02-08 | DDM | 213.58 | RIDF Loan upto 10 crore | Bridge is completed and work is in progress in respect of approach road. Project likely to be completed by March 2006.
10 | R102000207 | Jhabua (145 New-MS) | Jhabua | RSK | School | 2006-02-06 | DDM | 123.25 | RIDF Loan upto 10 crore | School at village Dhebarbadi visited. Work completed upto 80%.
10 | R102000207 | Jhabua (145 New-MS) | Jhabua | RSK | School | 2006-02-06 | DDM | 123.25 | RIDF Loan upto 10 crore | School at village Navagaon visited. Works completed upto 95%.
10 | R102000172 | Jhabua (104 OG-MS) | Jhabua | RSK | School | 2006-02-06 | DDM | 79.65 | RIDF Loan upto 10 crore | School at village Udaipuriya visited. 50% works are completed.
10 | R102000098 | Narsinghpur (285 OG-PS) | Narsinghpur | RSK | School | 2006-02-06 | DDM | 121.13 | RIDF Loan upto 10 crore | Primary school at Durnajpur village visited. Foundation completed. Slab work is in progress.
10 | R102000098 | Narsinghpur (285 OG-PS) | Narsinghpur | RSK | School | 2006-02-06 | DDM | 121.13 | RIDF Loan upto 10 crore | Primary school at Katothia village visited. Building is completed. Cost increased due to increase in prices of steel & cement. Balance funds yet to be received by PTA.
10 | R102000098 | Narsinghpur (285 OG-PS) | Narsinghpur | RSK | School | 2006-02-06 | DDM | 121.13 | RIDF Loan upto 10 crore | Primary school at Adilasi tola, Pala visited. Building completed and plastering work is to be completed.
10 | R102000182 | Shivpuri (20 OG-MS) | Shivpuri | RSK | School | 2006-02-04 | DDM | 14.14 | RIDF Loan upto 10 crore | Middle school at Bhatnawar Block Pohari visited. Construction work is in progress.
10 | R102000085 | Khargone (478 OG-PS) | Khargone | RSK | School | 2006-01-31 | DDM | 182.97 | RIDF Loan upto 10 crore | School bldg at village Temla visited. Work is completed.
10 | R102000004 | Dhabla Manohar Tank | Mandsaur | WRD | MIS | 2006-01-24 | DDM | 91.04 | RIDF Loan upto 10 crore | Work in progress. Delay due to land acquisition.
10 | R102000016 | Parasthani Tank | Betul | WRD | MIS | 2006-01-17 | DDM | 150.19 | RIDF Loan upto 10 crore | Headworks under progress. To be completed by May 2006.
10 | R102000018 | Maika Sarra Tank | Betul | WRD | MIS | 2006-01-16 | DDM | 65.43 | RIDF Loan upto 10 crore | Work is in progress. Likely to be completed by 31/3/2006
10 | r102000098 | Narsinghpur (285 OG-PS) | Narsinghpur | RSK | School | 2005-12-27 | DDM | 121.13 | RIDF Loan upto 10 crore | Primary school at Chiyali village visited. Work under progress.
10 | r102000052 | Pench 9/10 | Chhindwara | PWD | Bridge | 2005-12-26 | DDM | 199 | RIDF Loan upto 10 crore | Work is in progress and likely to be completed by December 2006. NABARD Board is not displayed.
10 | r102000051 | Kulbhera 3/4 | Chhindwara | PWD | Bridge | 2005-12-26 | DDM | 54.46 | RIDF Loan upto 10 crore | Tendering process completed for the bridge and approach road. Work is likely to be completed by June 2006.
10 | r102000060 | Amak 7/2 | Khandwa | PWD | Bridge | 2005-12-17 | DDM | 59.92 | RIDF Loan upto 10 crore | Project has been completed.
10 | R102000110 | Shahdol / Anuppur (485 OG-PS) | Anuppur | RSK | School | 2005-12-14 | DDM | 177.25 | RIDF Loan upto 10 crore | 1. Primary school at Itor Pushparajgarh block, Anuppur district visited. 2. Foundation and super-structure completed. 3. Kitchenshed, toilet blocks yet to be constructed.
10 | R102000278 | Shahdol / Anuppur (450 KS) | Anuppur | RSK | School | 2005-12-14 | DDM | 23.91 | RIDF Loan upto 10 crore | 1. Kitchenshed is yet to be taken up.
10 | R102000110 | Shahdol / Anuppur (485 OG-PS) | Anuppur | RSK | School | 2005-12-14 | DDM | 177.25 | RIDF Loan upto 10 crore | 1. Primary School at Khali Tola Bhejri- Pushprajgarh Block - Annupur Dist visited. 2. Work is satisfactory.
10 | R102000278 | Shahdol / Anuppur (450 KS) | Anuppur | RSK | School | 2005-12-14 | DDM | 23.91 | RIDF Loan upto 10 crore | 1. School at Khali Tola Bhejri, Pushparajgarh block, Anuppur district. 2. Kitchenshed yet to be constructed.
10 | R102000110 | Shahdol / Anuppur (485 OG-PS) | Anuppur | RSK | School | 2005-12-14 | DDM | 177.25 | RIDF Loan upto 10 crore | 1. School at Hadariya, Pushparajgarh block, Anuppur district. 2. Foundation and superstructure completed. 3. Handpump not yet installed.
10 | R102000278 | Shahdol / Anuppur (450 KS) | Anuppur | RSK | School | 2005-12-14 | DDM | 23.91 | RIDF Loan upto 10 crore | 1. School at Padariya, Pushparajgarh block, Anuppur visited. 2. Kitchenshed yet to be constructed.
10 | R102000233 | Dhar (180 New-MS) | Dhar | RSK | School | 2005-12-14 | DDM | 153 | RIDF Loan upto 10 crore | Middle school at Awali village visited. Foundation and superstructure completed.
10 | R102000285 | Nisarpur-Padiyal-Ali | Dhar | PWD | Road | 2005-12-12 | DDM | 578.29 | RIDF Loan upto 10 crore | Work is in progress. CD works at 5/2 km, 5/6 km, 8/8 km and 10/4 km need plastering.
10 | r102000098 | Narsinghpur (285 OG-PS) | Narsinghpur | RSK | School | 2005-12-07 | DDM | 121.13 | RIDF Loan upto 10 crore | Primary school at Dahalwada visited. Work is under progress.
10 | r102000098 | Narsinghpur (285 OG-PS) | Narsinghpur | RSK | School | 2005-12-07 | DDM | 121.13 | RIDF Loan upto 10 crore | Primary school at Sudhraj village visited. Work is under progress.
10 | R102000284 | Sardarpur-Baloda | Dhar | PWD | Road | 2005-12-02 | DDM | 210.12 | RIDF Loan upto 10 crore | Earthwork and gravel base completed. WBM and BT is yet to be done. 1 out of 11 CD works completed.
10 | R102000021 | Chotiyabardi Tank | Alirajpur | WRD | MIS | 2005-12-01 | DDM | 51.02 | RIDF Loan upto 10 crore | (1) Work in respect of Unit I is under progress and the project is likely to be completed by June 2006. (2) Canals are yet to be taken up. (3) NABARD board not displayed.
10 | R102000319 | LBC Dongariya 5.00-23 km | Narsinghpur | NVDA | MIP | 2005-11-17 | DDM | 2811.11 | RIDF Loan 25 crore & above | (1) Land acquisition is under process (2) Tenders invited for works and agency is yet to be fixed
10 | R102000318 | LBC RD 130.67-136.87 km | Narsinghpur | NVDA | MIP | 2005-11-17 | DDM | 3352.26 | RIDF Loan 25 crore & above | (1) Land acquisition is in process (2) Tenders are invited for works and agency is to be fixed
10 | R102000066 | Ghikhani 15/8 | Sidhi | PWD | Bridge | 2005-11-12 | DDM | 46.69 | RIDF Loan upto 10 crore | 1. Project is completed. 2. NABARD Board is not displayed
10 | R102000320 | Sadumar Br.canal RD 4.5 | Narsinghpur | NVDA | MIP | 2005-11-11 | DDM | 3987.09 | RIDF Loan 25 crore & above | (1) Land acquisition is in process (2) Tenders are invited for works and agency is to be fixed
10 | R102000321 | Sadumar Br.Canal RD.9-21 | Narsinghpur | NVDA | MIP | 2005-11-11 | DDM | 3136.73 | RIDF Loan 25 crore & above | (1) Land acquisition is in process (2) Tenders are invited for works and agency is yet to be fixed
10 | R102000290 | Jobat-Bori-Para | Alirajpur | PWD | Road | 2005-11-10 | DDM | 616.9 | RIDF Loan upto 10 crore | 1. Tendering completed and agency fixed.
10 | R102000035 | Shergarh Tank | Dhar | WRD | MIS | 2005-09-29 | DDM | 134.39 | RIDF Loan upto 10 crore | 1. Work in progress. 25% of work in Head Works completed. 2. Canal work is completed 60%
10 | R102000031 | Moriya Tank | Ratlam | WRD | MIS | 2005-09-08 | DDM | 164.93 | RIDF Loan upto 10 crore | 1. Land acquisition not completed. 2. Only masonry structures completed. 3. NABARD board not displayed.
10 | R102000032 | Richha Tank | Ratlam | WRD | MIS | 2005-08-17 | DDM | 284.59 | RIDF Loan upto 10 crore | 1. Excavation of foundation under progress. 2. NABARD board not displayed.
10 | R102000178 | Morena (7 OG-MS) | Morena | RSK | School | 2005-08-10 | DDM | 5.95 | RIDF Loan upto 10 crore | Foundation is complete, the super structure is under construction and the floorings & window are incomplete. Construction is not upto the mark. A tractor had hit the wall and a big crack has appeared on the wall and the thickness of the slab is thin.
10 | R102000089 | Morena (266 OG-PS) | Morena | RSK | School | 2005-08-09 | DDM | 105.5 | RIDF Loan upto 10 crore | Foundation has been completed since last one year but the contractor is not completing the building and the villagers do not seem to know the reason behind it. Super structure has not yet started.
10 | R102000213 | Morena (100 New-MS) | Morena | RSK | School | 2005-08-09 | DDM | 85 | RIDF Loan upto 10 crore | Except for the kitchen and toilet rest of the building is complete. Construction is good but there is no provision for boundary wall and roof for the toilets.
10 | R102000040 | Pritam Nagar Tank | Ratlam | WRD | MIS | 2005-07-22 | DDM | 35.13 | RIDF Loan upto 10 crore | The project is almost complete. Due to scanty rainfall there is no water in the tank.
10 | R102000048 | Deo 10/4-6 | Balaghat | PWD | Bridge | 2005-06-28 | DDM | 213.58 | RIDF Loan upto 10 crore | Progress of work is satisfactory. NABARD board was not displayed. Bridge division does not have a vehicle and the same may be provided to the division for monitoring purpose.
10 | R102000293 | Godhna Tank | Betul | WRD | MIS | 2005-06-19 | DDM | 717.73 | RIDF Loan upto 10 crore | NABARD board was not displayed. the work is likely to be completed by 31 March 2007.
10 | R102000308 | Kundiya Pada Tank | Jhabua | WRD | MIS | 2005-04-26 | DDM | 74.86 | RIDF Loan upto 10 crore | The 60% of the earthwork of the project has been completed. NABARD Board was not displayed.
10 | r102000127 | Dewas (58 New-PS) | Dewas | RSK | School | 2005-03-31 | DDM | 24.65 | RIDF Loan upto 10 crore | Khonapir Pipalya & Gitti Machine Fawda - Finishing work yet to be done. Work slow on account of funds constraints. Bhalai Kala - construction completed. finishing work yet to be done. On account of increase in cement prices the estimate increased.
10 | R102000206 | Dewas (212 New-MS) | Dewas | RSK | School | 2005-03-31 | DDM | 180.2 | RIDF Loan upto 10 crore | Enabad - Construction work is completed only electric fittings & fixing of doors and windows was uet to be done. no boundary wall to the school.
10 | R102000002 | Pivray Tank | Indore | WRD | MIS | 2005-02-07 | DDM | 73.3 | RIDF Loan upto 10 crore | The progress hampered due to the problem of land acqisition. NABARD BOard not displayed.
10 | R102000034 | Ahmedabad Khilli Tank | Vidisha | WRD | MIS | 2004-12-16 | DDM | 207.98 | RIDF Loan upto 10 crore | Only 80% of the earthwork has been completed so far. WUA has not formed. NABARD Board has not displayed. Maintenance arrangement should be made.
10 | r102000290 | Jobat-Bori-Para | Alirajpur | PWD | Road |  |  | 616.9 | RIDF Loan upto 10 crore
10 | r102000025 | Khamaria Chandora Tank | Raisen | WRD | MIS |  |  | 252.99 | RIDF Loan upto 10 crore
10 | r102000285 | Nisarpur-Padiyal-Ali | Dhar | PWD | Road |  |  | 578.29 | RIDF Loan upto 10 crore
10 | R102000005 | Kotda Bujurg | Mandsaur | WRD | MIS |  |  | 124.16 | RIDF Loan upto 10 crore
10 | R102000007 | Surakhedi Tank | Mandsaur | WRD | MIS |  |  | 88.31 | RIDF Loan upto 10 crore
10 | R102000011 | Motakhoyra Tank | Rajgarh | WRD | MIS |  |  | 131.3 | RIDF Loan upto 10 crore
10 | R102000012 | Sariyakua Tank | Rajgarh | WRD | MIS |  |  | 86.48 | RIDF Loan upto 10 crore
10 | R102000017 | Tura Boargaon | Betul | WRD | MIS |  |  | 143.7 | RIDF Loan upto 10 crore
10 | R102000019 | Tumra Tank | Bhopal | WRD | MIS |  |  | 181.84 | RIDF Loan upto 10 crore
10 | R102000022 | Hinoti Tank | Katni | WRD | MIS |  |  | 143.22 | RIDF Loan upto 10 crore
10 | R102000024 | Kundiya Tank | Khargone | WRD | MIS |  |  | 57.67 | RIDF Loan upto 10 crore
10 | R102000037 | Sat Talai Tank | Khargone | WRD | MIS |  |  | 43.95 | RIDF Loan upto 10 crore
10 | R102000038 | Ramnagar LIS | Mandsaur | WRD | MIS |  |  | 65.79 | RIDF Loan upto 10 crore
10 | R102000039 | Ashapuri Tank | Raisen | WRD | MIS |  |  | 277.7 | RIDF Loan upto 10 crore
10 | R102000047 | Champakhedi LIS | Vidisha | WRD | MIS |  |  | 107.19 | RIDF Loan upto 10 crore
10 | R102000050 | Goi 23/10 | Badwani | PWD | Bridge |  |  | 90 | RIDF Loan upto 10 crore
10 | R102000053 | Bhutiya 2/6 | Dewas | PWD | Bridge |  |  | 7.17 | RIDF Loan upto 10 crore
10 | R102000054 | Kanti 9/8 | Guna | PWD | Bridge |  |  | 35.72 | RIDF Loan upto 10 crore
10 | R102000056 | Khan 31/2 | Indore | PWD | Bridge |  |  | 92 | RIDF Loan upto 10 crore
10 | R102000059 | Suhar 16/6 | Katni | PWD | Bridge |  |  | 61.15 | RIDF Loan upto 10 crore
10 | R102000061 | Halali 9/2 | Raisen | PWD | Bridge |  |  | 45.85 | RIDF Loan upto 10 crore
10 | R102000065 | Sone 8/4 | Singrauli | PWD | Bridge |  |  | 453.83 | RIDF Loan upto 10 crore
10 | R102000069 | Betul (191 OG-PS) | Betul | RSK | School |  |  | 57.17 | RIDF Loan upto 10 crore
10 | R102000070 | Raisen (221 OG-PS) | Raisen | RSK | School |  |  | 28.62 | RIDF Loan upto 10 crore
10 | R102000071 | Sehore (256 OG-PS) | Sehore | RSK | School |  |  | 89.27 | RIDF Loan upto 10 crore
10 | R102000076 | Mandsaur (102 OG-PS) | Mandsaur | RSK | School |  |  | 43.35 | RIDF Loan upto 10 crore
10 | R102000077 | Neemuch (35 OG-PS) | Neemuch | RSK | School |  |  | 14.26 | RIDF Loan upto 10 crore
10 | R102000078 | Ratlam (185 OG-PS) | Ratlam | RSK | School |  |  | 78.63 | RIDF Loan upto 10 crore
10 | R102000083 | Jhabua (167 OG-PS) | Jhabua | RSK | School |  |  | 54.17 | RIDF Loan upto 10 crore
10 | R102000084 | Khandwa/Burhanpur (253 OG-PS) | Burhanpur | RSK | School |  |  | 107.53 | RIDF Loan upto 10 crore
10 | R102000086 | Barwani (419 OG-PS) | Badwani | RSK | School |  |  | 157.12 | RIDF Loan upto 10 crore
10 | R102000088 | Dindori (138 OG-PS) | Dindori | RSK | School |  |  | 56.9 | RIDF Loan upto 10 crore
10 | R102000090 | Sheopur (115 OG-PS) | Sheopur | RSK | School |  |  | 48.88 | RIDF Loan upto 10 crore
10 | R102000091 | Seoni (229 OG-PS) | Seoni | RSK | School |  |  | 81.46 | RIDF Loan upto 10 crore
10 | R102000094 | Vidisha (294 OG-PS) | Vidisha | RSK | School |  |  | 108.58 | RIDF Loan upto 10 crore
10 | R102000097 | Bhopal (157 OG-PS) | Bhopal | RSK | School |  |  | 49.6 | RIDF Loan upto 10 crore
10 | R102000099 | Hoshangabad (270 OG-PS) | Hoshangabad | RSK | School |  |  | 84.15 | RIDF Loan upto 10 crore
10 | R102000100 | Harda (42 OG-PS) | Harda | RSK | School |  |  | 3.54 | RIDF Loan upto 10 crore
10 | R102000101 | Indore (199 OG-PS) | Indore | RSK | School |  |  | 77.34 | RIDF Loan upto 10 crore
10 | R102000102 | Chhindwara (592 OG-PS) | Chhindwara | RSK | School |  |  | 250.5 | RIDF Loan upto 10 crore
10 | R102000104 | Jabalpur (311 OG-PS) | Jabalpur | RSK | School |  |  | 102.26 | RIDF Loan upto 10 crore
10 | R102000105 | Katni (377 OG-PS) | Katni | RSK | School |  |  | 160.23 | RIDF Loan upto 10 crore
10 | R102000107 | Rajgarh (191 OG-PS) | Rajgarh | RSK | School |  |  | 31.1 | RIDF Loan upto 10 crore
10 | R102000108 | Guna / Ashoknagar (518 OG-PS) | Ashoknagar | RSK | School |  |  | 141.25 | RIDF Loan upto 10 crore
10 | R102000109 | Dhar (487 OG-PS) | Dhar | RSK | School |  |  | 206.98 | RIDF Loan upto 10 crore
10 | R102000111 | Sidhi (247 OG-PS) | Sidhi | RSK | School |  |  | 92.34 | RIDF Loan upto 10 crore
10 | R102000112 | Chhatarpur (118 OG-PS) | Chattarpur | RSK | School |  |  | 44.2 | RIDF Loan upto 10 crore
10 | R102000113 | Tikamgarh (245 OG-PS) | Tikamgarh | RSK | School |  |  | 100 | RIDF Loan upto 10 crore
10 | R102000114 | Betul (83 New-PS) | Betul | RSK | School |  |  | 35.28 | RIDF Loan upto 10 crore
10 | R102000115 | Raisen (157 New-PS) | Raisen | RSK | School |  |  | 66.73 | RIDF Loan upto 10 crore
10 | R102000116 | Sehore (128 New-PS) | Sehore | RSK | School |  |  | 54.4 | RIDF Loan upto 10 crore
10 | R102000119 | Umaria (72 New-PS) | Umaria | RSK | School |  |  | 30.6 | RIDF Loan upto 10 crore
10 | R102000121 | Mandsaur (29 New-PS) | Mandsaur | RSK | School |  |  | 12.33 | RIDF Loan upto 10 crore
10 | R102000122 | Neemuch (36 New-PS) | Neemuch | RSK | School |  |  | 15.3 | RIDF Loan upto 10 crore
10 | R102000123 | Ratlam (42 New-PS) | Ratlam | RSK | School |  |  | 17.85 | RIDF Loan upto 10 crore
10 | R102000125 | Damoh (402 New-PS) | Damoh | RSK | School |  |  | 170.85 | RIDF Loan upto 10 crore
10 | R102000126 | Datia (28 New-PS) | Datia | RSK | School |  |  | 11.9 | RIDF Loan upto 10 crore
10 | R102000129 | Khandwa/Burhanpur (32 New-PS) | Burhanpur | RSK | School |  |  | 13.6 | RIDF Loan upto 10 crore
10 | R102000131 | Barwani (513 New-PS) | Badwani | RSK | School |  |  | 218.03 | RIDF Loan upto 10 crore
10 | R102000137 | Shajapur (140 New-PS) | Shajapur | RSK | School |  |  | 59.5 | RIDF Loan upto 10 crore
10 | R102000138 | Shivpuri (228 New-PS) | Shivpuri | RSK | School |  |  | 96.9 | RIDF Loan upto 10 crore
10 | R102000140 | Balaghat (202 New-PS) | Balaghat | RSK | School |  |  | 85.85 | RIDF Loan upto 10 crore
10 | R102000141 | Gwalior (296 New-PS) | Gwalior | RSK | School |  |  | 125.8 | RIDF Loan upto 10 crore
10 | R102000142 | Bhopal (212 New-PS) | Bhopal | RSK | School |  |  | 90.1 | RIDF Loan upto 10 crore
10 | R102000145 | Harda (60 New-PS) | Harda | RSK | School |  |  | 25.5 | RIDF Loan upto 10 crore
10 | R102000146 | Indore (36 New-PS) | Indore | RSK | School |  |  | 15.3 | RIDF Loan upto 10 crore
10 | R102000147 | Chhindwara (388 New-PS) | Chhindwara | RSK | School |  |  | 164.9 | RIDF Loan upto 10 crore
10 | R102000149 | Jabalpur (161 New-PS) | Jabalpur | RSK | School |  |  | 68.43 | RIDF Loan upto 10 crore
10 | R102000150 | Katni (278 New-PS) | Katni | RSK | School |  |  | 118.15 | RIDF Loan upto 10 crore
10 | R102000152 | Rajgarh (82 New-PS) | Rajgarh | RSK | School |  |  | 34.85 | RIDF Loan upto 10 crore
10 | R102000153 | Guna / Ashoknagar (251 New-PS) | Ashoknagar | RSK | School |  |  | 106.68 | RIDF Loan upto 10 crore
10 | R102000155 | Shahdol / Anuppur (233 New-PS) | Anuppur | RSK | School |  |  | 99.03 | RIDF Loan upto 10 crore
10 | R102000156 | Sidhi (409 New-PS) | Sidhi | RSK | School |  |  | 173.83 | RIDF Loan upto 10 crore
10 | R102000157 | Chhatarpur (2 New-PS) | Chattarpur | RSK | School |  |  | 0.85 | RIDF Loan upto 10 crore
10 | R102000158 | Tikamgarh (68 New-PS) | Tikamgarh | RSK | School |  |  | 28.9 | RIDF Loan upto 10 crore
10 | R102000159 | Betul (57 OG-MS) | Betul | RSK | School |  |  | 29.44 | RIDF Loan upto 10 crore
10 | R102000160 | Raisen (2 OG-MS) | Raisen | RSK | School |  |  | 1.37 | RIDF Loan upto 10 crore
10 | R102000161 | Sehore (5 OG-MS) | Sehore | RSK | School |  |  | 3.56 | RIDF Loan upto 10 crore
10 | R102000163 | Satna (5 OG-MS) | Satna | RSK | School |  |  | 4.25 | RIDF Loan upto 10 crore
10 | R102000165 | Mandsaur (36 OG-MS) | Mandsaur | RSK | School |  |  | 30.6 | RIDF Loan upto 10 crore
10 | R102000166 | Neemuch (29 OG-MS) | Neemuch | RSK | School |  |  | 21.51 | RIDF Loan upto 10 crore
10 | R102000167 | Ratlam (26 OG-MS) | Ratlam | RSK | School |  |  | 15.89 | RIDF Loan upto 10 crore
10 | R102000170 | Datia (21 OG-MS) | Datia | RSK | School |  |  | 15.56 | RIDF Loan upto 10 crore
10 | R102000171 | Dewas (14 OG-MS) | Dewas | RSK | School |  |  | 8.6 | RIDF Loan upto 10 crore
10 | R102000173 | Khandwa/Burhanpur (8 OG-MS) | Burhanpur | RSK | School |  |  | 6.12 | RIDF Loan upto 10 crore
10 | R102000175 | Barwani (15 OG-MS) | Badwani | RSK | School |  |  | 10.65 | RIDF Loan upto 10 crore
10 | R102000179 | Sheopur (7 OG-MS) | Sheopur | RSK | School |  |  | 5.95 | RIDF Loan upto 10 crore
10 | R102000180 | Seoni (8 OG-MS) | Seoni | RSK | School |  |  | 1.13 | RIDF Loan upto 10 crore
10 | R102000183 | Vidisha (12 OG-MS) | Vidisha | RSK | School |  |  | 8.4 | RIDF Loan upto 10 crore
10 | R102000185 | Harda (5 OG-MS) | Harda | RSK | School |  |  | 2.66 | RIDF Loan upto 10 crore
10 | R102000186 | Indore (16 OG-MS) | Indore | RSK | School |  |  | 7.12 | RIDF Loan upto 10 crore
10 | R102000187 | Rajgarh (5 OG-MS) | Rajgarh | RSK | School |  |  | 3.14 | RIDF Loan upto 10 crore
10 | R102000189 | Shahdol / Anuppur (4 OG-MS) | Anuppur | RSK | School |  |  | 3.4 | RIDF Loan upto 10 crore
10 | R102000191 | Chhatarpur (93 OG-MS) | Chattarpur | RSK | School |  |  | 70.39 | RIDF Loan upto 10 crore
10 | R102000192 | Tikamgarh (34 OG-MS) | Tikamgarh | RSK | School |  |  | 27.31 | RIDF Loan upto 10 crore
10 | R102000193 | Betul (290 New-MS) | Betul | RSK | School |  |  | 246.5 | RIDF Loan upto 10 crore
10 | R102000194 | Raisen (230 New-MS) | Raisen | RSK | School |  |  | 195.5 | RIDF Loan upto 10 crore
10 | R102000195 | Sehore (215 New-MS) | Sehore | RSK | School |  |  | 182.75 | RIDF Loan upto 10 crore
10 | R102000196 | Rewa (250 New-MS) | Rewa | RSK | School |  |  | 212.5 | RIDF Loan upto 10 crore
10 | R102000197 | Satna (195 New-MS) | Satna | RSK | School |  |  | 165.75 | RIDF Loan upto 10 crore
10 | R102000198 | Umaria (58 New-MS) | Umaria | RSK | School |  |  | 49.3 | RIDF Loan upto 10 crore
10 | R102000200 | Mandsaur (115 New-MS) | Mandsaur | RSK | School |  |  | 97.75 | RIDF Loan upto 10 crore
10 | R102000201 | Neemuch (95 New-MS) | Neemuch | RSK | School |  |  | 80.75 | RIDF Loan upto 10 crore
10 | R102000202 | Ratlam (207 New-MS) | Ratlam | RSK | School |  |  | 175.95 | RIDF Loan upto 10 crore
10 | R102000203 | Bhind (325 New-MS) | Bhind | RSK | School |  |  | 276.25 | RIDF Loan upto 10 crore
10 | R102000205 | Datia (143 New-MS) | Datia | RSK | School |  |  | 121.55 | RIDF Loan upto 10 crore
10 | R102000208 | Khandwa/Burhanpur (211 New-MS) | Burhanpur | RSK | School |  |  | 179.35 | RIDF Loan upto 10 crore
10 | R102000210 | Barwani (228 New-MS) | Badwani | RSK | School |  |  | 193.8 | RIDF Loan upto 10 crore
10 | R102000214 | Sheopur (62 New-MS) | Sheopur | RSK | School |  |  | 52.7 | RIDF Loan upto 10 crore
10 | R102000215 | Seoni (202 New-MS) | Seoni | RSK | School |  |  | 171.7 | RIDF Loan upto 10 crore
10 | R102000217 | Shivpuri (328 New-MS) | Shivpuri | RSK | School |  |  | 278.8 | RIDF Loan upto 10 crore
10 | R102000218 | Vidisha (170 New-MS) | Vidisha | RSK | School |  |  | 144.5 | RIDF Loan upto 10 crore
10 | R102000220 | Gwalior (205 New-MS) | Gwalior | RSK | School |  |  | 174.25 | RIDF Loan upto 10 crore
10 | R102000221 | Bhopal (139 New-MS) | Bhopal | RSK | School |  |  | 118.15 | RIDF Loan upto 10 crore
10 | R102000222 | Narsinghpur (151 New-MS) | Narsinghpur | RSK | School |  |  | 128.35 | RIDF Loan upto 10 crore
10 | R102000225 | Indore (261 New-MS) | Indore | RSK | School |  |  | 221.85 | RIDF Loan upto 10 crore
10 | R102000226 | Chhindwara (197 New-MS) | Chhindwara | RSK | School |  |  | 167.45 | RIDF Loan upto 10 crore
10 | R102000227 | Ujjain (232 New-MS) | Ujjain | RSK | School |  |  | 197.2 | RIDF Loan upto 10 crore
10 | R102000229 | Katni (181 New-MS) | Katni | RSK | School |  |  | 153.85 | RIDF Loan upto 10 crore
10 | R102000234 | Shahdol / Anuppur (255 New-MS) | Anuppur | RSK | School |  |  | 216.75 | RIDF Loan upto 10 crore
10 | R102000235 | Sidhi (385 New-MS) | Sidhi | RSK | School |  |  | 327.25 | RIDF Loan upto 10 crore
10 | R102000236 | Chhatarpur (160 New-MS) | Chattarpur | RSK | School |  |  | 136 | RIDF Loan upto 10 crore
10 | R102000237 | Tikamgarh (219 New-MS) | Tikamgarh | RSK | School |  |  | 186.15 | RIDF Loan upto 10 crore
10 | R102000238 | Betul (248 KS) | Betul | RSK | School |  |  | 13.18 | RIDF Loan upto 10 crore
10 | R102000239 | Raisen (185 KS) | Raisen | RSK | School |  |  | 9.83 | RIDF Loan upto 10 crore
10 | R102000240 | Sehore (261 KS) | Sehore | RSK | School |  |  | 13.86 | RIDF Loan upto 10 crore
10 | R102000241 | Rewa (557 KS) | Rewa | RSK | School |  |  | 29.59 | RIDF Loan upto 10 crore
10 | R102000242 | Satna (268 KS) | Satna | RSK | School |  |  | 14.24 | RIDF Loan upto 10 crore
10 | R102000243 | Umaria (59 KS) | Umaria | RSK | School |  |  | 3.14 | RIDF Loan upto 10 crore
10 | R102000244 | Panna (356 KS) | Panna | RSK | School |  |  | 18.91 | RIDF Loan upto 10 crore
10 | R102000245 | Mandsaur (111 KS) | Mandsaur | RSK | School |  |  | 5.9 | RIDF Loan upto 10 crore
10 | R102000246 | Neemuch (69 KS) | Neemuch | RSK | School |  |  | 3.66 | RIDF Loan upto 10 crore
10 | R102000247 | Ratlam (151 KS) | Ratlam | RSK | School |  |  | 8.02 | RIDF Loan upto 10 crore
10 | R102000248 | Bhind (80 KS) | Bhind | RSK | School |  |  | 4.25 | RIDF Loan upto 10 crore
10 | R102000249 | Damoh (200 KS) | Damoh | RSK | School |  |  | 10.62 | RIDF Loan upto 10 crore
10 | R102000250 | Datia (100 KS) | Datia | RSK | School |  |  | 5.31 | RIDF Loan upto 10 crore
10 | R102000251 | Dewas (195 KS) | Dewas | RSK | School |  |  | 10.36 | RIDF Loan upto 10 crore
10 | R102000252 | Jhabua (276 KS) | Jhabua | RSK | School |  |  | 14.66 | RIDF Loan upto 10 crore
10 | R102000253 | Khandwa/Burhanpur (35 KS) | Burhanpur | RSK | School |  |  | 1.86 | RIDF Loan upto 10 crore
10 | R102000254 | Khargone (293 KS) | Khargone | RSK | School |  |  | 15.56 | RIDF Loan upto 10 crore
10 | R102000255 | Barwani (287 KS) | Badwani | RSK | School |  |  | 15.25 | RIDF Loan upto 10 crore
10 | R102000256 | Mandla (315 KS) | Mandla | RSK | School |  |  | 16.74 | RIDF Loan upto 10 crore
10 | R102000257 | Dindori (200 KS) | Dindori | RSK | School |  |  | 10.62 | RIDF Loan upto 10 crore
10 | R102000258 | Morena (130 KS) | Morena | RSK | School |  |  | 6.91 | RIDF Loan upto 10 crore
10 | R102000259 | Sheopur (40 KS) | Sheopur | RSK | School |  |  | 2.12 | RIDF Loan upto 10 crore
10 | R102000260 | Seoni (287 KS) | Seoni | RSK | School |  |  | 15.25 | RIDF Loan upto 10 crore
10 | R102000261 | Shajapur (246 KS) | Shajapur | RSK | School |  |  | 13.07 | RIDF Loan upto 10 crore
10 | R102000262 | Shivpuri (100 KS) | Shivpuri | RSK | School |  |  | 5.31 | RIDF Loan upto 10 crore
10 | R102000263 | Vidisha (155 KS) | Vidisha | RSK | School |  |  | 8.23 | RIDF Loan upto 10 crore
10 | R102000264 | Balaghat (120 KS) | Balaghat | RSK | School |  |  | 6.38 | RIDF Loan upto 10 crore
10 | R102000266 | Bhopal (126 KS) | Bhopal | RSK | School |  |  | 6.69 | RIDF Loan upto 10 crore
10 | R102000267 | Hoshangabad (250 KS) | Hoshangabad | RSK | School |  |  | 13.28 | RIDF Loan upto 10 crore
10 | R102000268 | Harda (111 KS) | Harda | RSK | School |  |  | 5.9 | RIDF Loan upto 10 crore
10 | R102000269 | Indore (112 KS) | Indore | RSK | School |  |  | 5.95 | RIDF Loan upto 10 crore
10 | R102000270 | Chhindwara (322 KS) | Chhindwara | RSK | School |  |  | 17.11 | RIDF Loan upto 10 crore
10 | R102000271 | Ujjain (20 KS) | Ujjain | RSK | School |  |  | 1.06 | RIDF Loan upto 10 crore
10 | R102000272 | Jabalpur (315 KS) | Jabalpur | RSK | School |  |  | 16.73 | RIDF Loan upto 10 crore
10 | R102000273 | Katni (180 KS) | Katni | RSK | School |  |  | 9.56 | RIDF Loan upto 10 crore
10 | R102000274 | Sagar (390 KS) | Sagar | RSK | School |  |  | 20.72 | RIDF Loan upto 10 crore
10 | R102000275 | Rajgarh (321 KS) | Rajgarh | RSK | School |  |  | 17.05 | RIDF Loan upto 10 crore
10 | R102000276 | Guna / Ashoknagar (489 KS) | Ashoknagar | RSK | School |  |  | 25.98 | RIDF Loan upto 10 crore
10 | R102000277 | Dhar (514 KS) | Dhar | RSK | School |  |  | 27.31 | RIDF Loan upto 10 crore
10 | R102000279 | Sidhi (326 KS) | Sidhi | RSK | School |  |  | 17.32 | RIDF Loan upto 10 crore
10 | R102000280 | Chhatarpur (213 KS) | Chattarpur | RSK | School |  |  | 11.32 | RIDF Loan upto 10 crore
10 | R102000281 | Tikamgarh (200 KS) | Tikamgarh | RSK | School |  |  | 10.63 | RIDF Loan upto 10 crore
10 | R102000282 | Rajpur-Pipari-Khajuri-Barsalai | Badwani | PWD | Road |  |  | 181.22 | RIDF Loan upto 10 crore
10 | R102000287 | Simrol Udainagar | Indore | PWD | Road |  |  | 155.77 | RIDF Loan upto 10 crore
10 | R102000288 | Bisenkheda Panod | Indore | PWD | Road |  |  | 128.03 | RIDF Loan upto 10 crore
10 | R102000289 | Khawasa-Bajna | Jhabua | PWD | Road |  |  | 53.12 | RIDF Loan upto 10 crore
10 | R102000302 | Palatwara Tank | Chhindwara | WRD | MIS |  |  | 102.9 | RIDF Loan upto 10 crore
10 | R102000303 | Seoni Tank | Chhindwara | WRD | MIS |  |  | 62.56 | RIDF Loan upto 10 crore
10 | R102000304 | Bhandargondi Tank | Chhindwara | WRD | MIS |  |  | 154.18 | RIDF Loan upto 10 crore
10 | R102000305 | Palamau Tank | Chhindwara | WRD | MIS |  |  | 161.07 | RIDF Loan upto 10 crore
10 | R102000310 | Himmatpura Tank | Sehore | WRD | MIS |  |  | 73.63 | RIDF Loan upto 10 crore
10 | R102000312 | Malgaon 43/10 | Badwani | PWD | Bridge |  |  | 114.15 | RIDF Loan upto 10 crore
10 | R102000313 | Ghunshi 22/2 | Bhopal | PWD | Bridge |  |  | 58.34 | RIDF Loan upto 10 crore
10 | R102000314 | Utavali 22/2 | Burhanpur | PWD | Bridge |  |  | 160.81 | RIDF Loan upto 10 crore
10 | R102000316 | Kunda 10/4 | Khargone | PWD | Bridge |  |  | 187.28 | RIDF Loan upto 10 crore
10 | R102000322 | Lud Tank | Balaghat | WRD | MIS |  |  | 159.4 | RIDF Loan upto 10 crore
10 | R102000324 | Bada Itara Tank | Alirajpur | WRD | MIS |  |  | 62.76 | RIDF Loan upto 10 crore
10 | R102000327 | Bhalot Tank | Mandsaur | WRD | MIS |  |  | 102.99 | RIDF Loan upto 10 crore
10 | R102000328 | Gajakhedi Naria Tank | Mandsaur | WRD | MIS |  |  | 96.13 | RIDF Loan upto 10 crore
10 | R102000331 | Kanwala LIS | Mandsaur | WRD | MIS |  |  | 84.6 | RIDF Loan upto 10 crore
10 | R102000333 | Ralayta Tank | Mandsaur | WRD | MIS |  |  | 120.46 | RIDF Loan upto 10 crore
10 | R102000335 | Nipaniya Garhi Tank | Rajgarh | WRD | MIS |  |  | 149.61 | RIDF Loan upto 10 crore
10 | R102000336 | Jharkheda Gua Tank | Sehore | WRD | MIS |  |  | 193.85 | RIDF Loan upto 10 crore
11 | R112000058 | Rajnagar Bachhan Chandla Road | Chattarpur | PWD | Road | 2011-11-03 | DDM | 397.12 | RIDF Loan upto 10 crore | Works like LA, EW,WBM,BT and CD are 76% completed.T+COR due to delay in culvert designing and non- availability of material.Monitoring done QC tests carried out. Records were N.A .NAb brd nt displ. Road Qlty poor, no maint. by cntrct/PWD.
11 | r112000198 | Benibari Chandanghat Road | Anuppur | PWD | Road | 2011-03-18 | RO Official | 57.14 | RIDF Loan upto 10 crore | Project is already completed.TOR due to contractors problem.Due to lack of maintenance the BT surface of the road got damaged at few places and need to be repaired.Bushes found to be grown over shoulder of the road which required to be removed.
11 | r112000060 | Indergarh Kamad Road | Datia | PWD | Road | 2011-03-10 | DDM | 318.28 | RIDF Loan upto 10 crore | CD more than 76%,EW 51%,WBM 26%,BTupto 25% complete.COR due to change n specification revised approval of add. Rs.127 lkh is required.TOR is due to failure of contractors n completing project on time leading to cancellation of contract twice.NB brd nt di
11 | r112000141 | SUB HEALTH CENTRES | Sidhi | DHFW | Health | 2011-03-03 | DDM | 57.22 | RIDF Loan upto 10 crore | LR, WH,Wards,dispensary,toilets more than 76% complete.TOR due to delay in LA.NABARD board not displayed at the site.
11 | r112000135 | SUB HEALTH CENTRES | Katni | DHFW | Health | 2011-02-25 | DDM | 257.5 | RIDF Loan upto 10 crore | WH,MMR,AMR,Boundry walls more than 76% complete.TOR & COR due to poor fund flow.Site visit book not maintained.
11 | r112000153 | Maheshpura Tank | Guna | WRD | MIS | 2011-02-22 | DDM | 165.55 | RIDF Loan upto 10 crore | HW,HR,MC,Minor-subminor,CD Works 100% complete.TOR due to delay in LA & lackadaisical approach of contractor.NB board not displayed.WUA not formed.Maintenance not done by Dept.Pitch & canal work is of poor quality.
11 | r112000202 | Naogaon Baldevgarh Road | Chattarpur | PWD | Road | 2011-02-22 | DDM | 106.88 | RIDF Loan upto 10 crore | 2 km road not cnstructed due to forest land, encroachment on road near bridges,site order book and top official visit register not available.NB board not displayed.road need immediate repairing.
11 | r112000207 | Sanjaysagar MIP Irr.Proje | Vidisha | WRD | MIP | 2011-02-07 | RO Official | 10251.56 | RIDF Loan 25 crore & above | HW,SW more than 51%,MC,CD more than 26% & HR upto 25% complete,TOR due to delay in LA.COR due to revision of project cost .No social audit connected.NB name not displayed in project board.
11 | r112000057 | Chandla Bansiya Gohani Road | Chattarpur | PWD | Road | 2011-01-13 | DDM | 302.07 | RIDF Loan upto 10 crore | LA,CD work,foundation,sub & superstructure more than 76% complete.NB board nt displayed.site order book,visit register not available.water scarcity due to drought,design of bridges nt finalised,TOR due to delay n release of fund,agency selection faulty
11 | r112000056 | Badagawn Harpalpur Road | Chattarpur | PWD | Road | 2010-11-11 | DDM | 96.8 | RIDF Loan upto 10 crore | LA EW WBM BT CD Works more than 75% complete.TOR due to delay in designing of culverts,non availability of tarcoal.NB board nt dispalyed, test record site visit book not maintained.
11 | r112000165 | Kokan Piparia Tank | Chhindwara | WRD | MIS | 2010-05-14 | DDM | 275.84 | RIDF Loan upto 10 crore | Time overrun due to implementation problems procedural delays in payment of compensation.Quality tests conducted.Records maintained.Site visit displayed.More than 76% work completed.Likely to be completed by 31Mar/11.canal & masonary work to be completed
11 | r112000166 | Murgitola Tank | Chhindwara | WRD | MIS | 2010-05-14 | DDM | 359.34 | RIDF Loan upto 10 crore | Time overrun due to delay in LA,procedural delay in payment of compensation,quality tests conducted.Rec maintained.Site visits book maintained.HW,SW,MC,BC,WC/. FC all are 26 to 50% completed. Likely DOC is 30/06/11. Appropriate monitoring mec req
11 | r112000217 | Kandiapar Tank | Seoni | WRD | MIS | 2010-05-12 | DDM | 130.41 | RIDF Loan upto 10 crore | HW, SW,MC, BC more than 76% completed .Field channels rae 51-75% completed. delay in Land acquisition led to tiome overrun. Quality control was done by dept. Test records maintained. Canal work needs to be expedited
11 | R112000074 | Bhikangaon Dhakalgaon Sanawad Road | Khargone | PWD | Road | 2010-03-23 | DDM | 399.96 | RIDF Loan upto 10 crore | The road has bdeen completed. Tests done records maintained. Board displaying NABARD assistance was dislayed.
11 | R112000163 | Sitapur Tank | Burhanpur | WRD | MIS | 2010-03-11 | DDM | 84.3 | RIDF Loan upto 10 crore | Project is completed TOR due to delay in LA and shifting of electric pole. Quality control insatlled. Records maintained.Visit registers maintained
11 | R112000162 | Kiratpur Tank | Raisen | WRD | MIS | 2010-03-10 | RO Official | 294.17 | RIDF Loan upto 10 crore | HW and sluic comppleted 90% and 80% respectively. Big trees to be removed in submergence, Watch and ward needed. LA for canal tio be done.WUA yet to be formed
11 | R112000128 | PRIMARY HEALTH CENTRES | Umaria | DHFW | Health | 2010-03-04 | DDM | 47.6 | RIDF Loan upto 10 crore | PHC were visited. Jamudi PHC was completed. Chouria PHC construction was withheld due to land dispute with a farmer. This could be attributed to only 50% availment by GoMP.supervised. compound wall ,generator and posting of doctors are required to reali
11 | R112000080 | Banda Shahpur Road | Sagar | PWD | Road | 2010-02-03 | DDM | 257.6 | RIDF Loan upto 10 crore | BT on the rioad was completed eroded and needs to be repaired . NO COR tests carried out . Records maintained. NABARD assistance not displayed
11 | R112000210 | Shankarpura Tank | Ujjain | WRD | MIS | 2010-01-14 | DDM | 314.53 | RIDF Loan upto 10 crore | Only head works is more than 75% completed. Other items of works are 25-50% completed. TOR due to delay in LA. COR due to increase in LA cost.. Tests acrried out. Records maintained. NABARD assistance is not displayed.
11 | R112000164 | Dilawar Mohgaon Tank | Chhindwara | WRD | MIS | 2009-12-23 | DDM | 250.61 | RIDF Loan upto 10 crore | HW,SW more than 76% completed. MC,BC 51-75% completed COR in LA and masonry work TOR due to LA. Delay in payment of compensation. Tests done Supervision records, test records maintained. NAB assistance dusplayed. Likely date of completion 31 Jan 2010
11 | R112000144 | TIVRA KAMATH FEEDER TANK | Chhindwara | WRD | MIS | 2009-12-11 | DDM | 273.59 | RIDF Loan upto 10 crore | HW PW >76% completed MC,BC 51-75% completed.Minors nad subminors 51-75% completed TOR due to LA comp delayed Test records, visit records maintained. NAB ass board stolen
11 | R112000171 | Kherkhedi Tank | Mandsaur | WRD | MIS | 2009-10-29 | DDM | 159.69 | RIDF Loan upto 10 crore | Head work , canal work more than 75% completed.Dept is monitoring Tests carried out. Records maintained Assistance displayed
11 | R112000170 | Sammatkhedi Tank | Mandsaur | WRD | MIS | 2009-10-29 | DDM | 219.64 | RIDF Loan upto 10 crore | Head work and canal work more than 100% completed. La is delayed and led to cost over run. Monitoring done recordss maintained Tests carried out . NABARD board displayed.
11 | R112000150 | KUDA PADON TANK | Shivpuri | WRD | MIS | 2009-10-29 | DDM | 121.49 | RIDF Loan upto 10 crore | LA is completed , Masonry 32% completed. EW for dam 86% completed Spill way 24.45%completed Masopnry of canal work 50% completed. Tests done visited by de Due to non - receipt of funds , payment to contractor is deayed. NABARD assistance not displayed
11 | R112000142 | KHEDJIYA MEGHA TANKNEW PR | Mandsaur | WRD | MIP | 2009-07-16 | DDM | 66.63 | RIDF Loan upto 10 crore | The projects is completed CoR due to high LA cost.Tests carried out. Records not shown. NAB assistance not displayed.
11 | r112000145 | CHANDWASA TANK | Mandsaur | WRD | MIS | 2009-07-16 | DDM | 102.99 | RIDF Loan upto 10 crore | Project completed. COR due to high LA. Tests caried out. Records were not shown. NAB assistance not displayed
11 | R112000168 | Jawania Tank | Alirajpur | WRD | MIS | 2009-06-17 | DDM | 46.27 | RIDF Loan upto 10 crore | HW,SW,HR >75% completed.MC 25-50% completed.TOR due to contractor's problem. COR due to LA . Monthly monitoring done Tests carried out . Records maintained NABARD assistance was not displayed.
11 | R112000153 | Maheshpura Tank | Guna | WRD | MIS | 2009-05-08 | DDM | 165.55 | RIDF Loan upto 10 crore | Hw 40% completed HR,MC 80% completed, Minors,subminors 90% completed CD 100% completed Sr engr visiterd,, tests carried out but recorsds not shown. NABARD assitance not displayed. Work to be copmpleted by June 09
11 | R112000086 | Baboopur Goraiya Road | Satna | PWD | Road | 2009-03-20 | DDM | 122.93 | RIDF Loan upto 10 crore | Recd in May 09. EW and CD more than 76% completed. Black topping and WBM .51-75% completed. tests carried out . Records maintained . Contractor's problem is leading to TOR . NABARD assistance not displayed
11 | R112000089 | Kripalpur Ramsthan Road | Satna | PWD | Road | 2009-03-20 | DDM | 175.45 | RIDF Loan upto 10 crore | Recd in May 09.LA, EW, CD more than 76% completed. BT 51-75% completed.Test records maintained. Tests carried out. Contractor's problem is leading to TOR. NABARD assistance not displayed.
11 | R112000074 | Bhikangaon Dhakalgaon Sanawad Road | Khargone | PWD | Road | 2009-03-17 | DDM | 399.96 | RIDF Loan upto 10 crore | LA,EW,WBM,BT CD >76% completed Sr engi visited qulaity tests done Records maintained.NABARD assistance displayed Project work is almost over
11 | R112000187 | Raghunathpur Murtala Road | Sidhi | PWD | Road | 2009-03-02 | DDM | 211.27 | RIDF Loan upto 10 crore | LA,EW,WBM,BT,CD more than 76% completed. TOr due to contractorSr Engineers visited the project. Tests carried out. Records maintained.NABARD assistance not displayed
11 | R112000207 | Sanjaysagar MIP Irr.Proje | Vidisha | WRD | MIP | 2009-02-26 | OIC | 10251.56 | RIDF Loan 25 crore & above | HR<25%CD <25% SW 26-50% MC 26-50%. Compaction of main dam yet to be done255500Cum HW to be done. High way over bridge is required at a road crossing. Rehab is unde way. Sr En visited records nm qtrec main LA for Mc and distributary expeditious completio
11 | R112000151 | Ragadgaon Tank | Betul | WRD | MIS | 2009-02-24 | DDM | 106.83 | RIDF Loan upto 10 crore | Work completed compensation pauid for LA. Sen Engineers visited. Quality control put inplaceTests carried test records mainatained NAB ass displayed.Lining of canal is required.
11 | R112000104 | PRIMARY HEALTH CENTRES | Dindori | DHFW | Health | 2009-02-11 | DDM | 142.8 | RIDF Loan upto 10 crore | The project has been completed. Non- availability of water and power is hampering institutional delivery for women patients. Staff constaint - nurses, phamacist and ward boy are not appted. NAB assistance not displayed
11 | R112000209 | Swami Sagar Tank | Narsinghpur | WRD | MIS | 2009-02-10 | DDM | 229.69 | RIDF Loan upto 10 crore | HW,Sw,HR and MC 26-50% completed. Thogh visited By Sr Eng, no records maintained. Tests carried out Test records not maintained.NABARD assistance not displayed. Progress is slow follow up with contrcator for time;y completion of work.
11 | R112000106 | PRIMARY HEALTH CENTRES | Gwalior | DHFW | Health | 2009-02-08 | DDM | 95.2 | RIDF Loan upto 10 crore | Wards,labour room, doctor room nurse duty room,store waiting hall quarters completed > No drinking qwater facility Compound wall not done. Poor mainatenan Sub pumpset of bore well stolen tsts carried visited by Sr eng Records maint assist displayed
11 | R112000184 | Mangawan Rampurwa Road | Rewa | PWD | Road | 2009-01-30 | DDM | 73.13 | RIDF Loan upto 10 crore | La,EW, WBM,BT and CD more than 76% completed.Visited by Sr Engineers, Tests carried out; Records maintained.; NABARD assistance displayed.
11 | R112000214 | Jharkheda Tank | Rajgarh | WRD | MIS | 2009-01-06 | DDM | 214.94 | RIDF Loan upto 10 crore | HW,spill way, head regulator and Main canal more than 76% completed.Quality control system in HW 26-50 % coQuality control system inplace; Tests carried out; Records maintained Dealy in tender La inad moni COr due to La. NABARD assistance not displayed
11 | R112000053 | Amla Amarpura Samaspura Samasgarh R | Bhopal | PWD | Road | 2008-12-24 | RO Officer | 316.13 | RIDF Loan upto 10 crore | Work is more than 76% complete. No cost and time overrun. The project is monitored by senior engineers. Quality test records maintained. NABARD assistance displayed. Bushes over shoulder of road need to be removed.
11 | R112000054 | Sukhi Sevaniya Mugaliyak to Chanche | Bhopal | PWD | Road | 2008-12-24 | RO Officer | 286.82 | RIDF Loan upto 10 crore | Work is more than 76% complete.No cost and time overrun. Monitored by sen engineers, tests recorded .NAB ass displayed. A 500m bridge across patra nalla is tobe completed. Bushy overgrowth on shoulders neeeds to be rem Tele dep dug up filled and compact
11 | R112000199 | Rajendragram Dharmdas Road | Anuppur | PWD | Road | 2008-12-17 | RO Officer | 137.06 | RIDF Loan upto 10 crore | Works like lA,EW,Waterbound Macadam,black topping, CD works have been completed . Project completed on 16 Sep 07, No cost overrun,Visit records and test records not shown, NABARD board not displayed
11 | R112000217 | Kandiapar Tank | Seoni | WRD | MIS | 2008-10-03 | DDM | 130.41 | RIDF Loan upto 10 crore | Land acquisition for canal delayed.hawed work completed. slab on head regulator patch work of spill way pending. Executive engineers visit regularly.Quality test lab was set up records maintained. NAB assitance not displayed
11 | r112000165 | Kokan Piparia Tank | Chhindwara | WRD | MIS | 2008-09-30 | DDM | 275.84 | RIDF Loan upto 10 crore | Time overrun due to elay in LA.WRS engineers visit the project.quality tests conducted.records maintained NABARD assistance not displayed.About 70% work completed likely to be completed by Feb 09.
11 | R112000207 | Sanjaysagar MIP Irr.Proje | Vidisha | WRD | MIP | 2008-07-21 | DDM | 10251.56 | RIDF Loan 25 crore & above | Time over run-delay in land acquisition;quality control testing lab to test material; tests caried out; NABARD assistance was not displayed. Visited by geologist to test the quality of rock before commencing CC work
11 | R112000158 | Hirapur Tank | Khargone | WRD | MIS | 2008-06-16 | DDM | 228.92 | RIDF Loan upto 10 crore | There is cost escalation - it is bound to increase by Rs.20 Lakh. Non clearance of of warads by Revenue authority on time.Quality tests carried out and records maintained.NABARD assistance is dsiplayed, but needs replacement due to damages.
11 | R112000157 | Mejampura Tank | Khargone | WRD | MIS | 2008-06-05 | DDM | 54.9 | RIDF Loan upto 10 crore | Good progress. Tests are conducted from Engineering college, Borawa and records of the same are maintained. NABARD assistance is displayed
11 | R112000171 | Kherkhedi Tank | Mandsaur | WRD | MIS | 2008-05-28 | DDM | 159.69 | RIDF Loan upto 10 crore | Payment of Rs.40 lakh for land acquisition is yet to be made. Irrigation started from the tank year 2007.WUA is yet to be formed. NABARD assistance is yet to be displayed.
11 | R112000069 | Ambari Sorwa Road | Alirajpur | PWD | Road | 2008-05-27 | DDM | 102.02 | RIDF Loan upto 10 crore | Due to contractor's delay, the progress is slow.Qulaity control tests have been carried out. NABARD board is not displayed
11 | R112000149 | IMJHERA M I TANK | Guna | WRD | MIS | 2008-05-27 | DDM | 132.58 | RIDF Loan upto 10 crore | Slow progess in haed works and spill works due to land disputre with farmers and labour problem.75% canal work completed.Quality tests were conducted but records are not amde available. NABARD assistance is displayed
11 | R112000146 | SILAOTI TANK | Guna | WRD | MIS | 2008-05-27 | DDM | 140.09 | RIDF Loan upto 10 crore | Slow due to labour problem. quality tests conducted records not available NABARD assistance displayed
11 | R112000172 | Gariyakhedi Tank | Mandsaur | WRD | MIS | 2008-05-21 | DDM | 113.22 | RIDF Loan upto 10 crore | Emnabkment and waste weir were constructed. Farmers protested to part with land for main canal excavation and demanded stop dam from which they can lify water. The matter is under consideration.WUA is yet to be formed. NABARD assistance was not displ
11 | R112000070 | Malpur Barzar Mandore Road | Alirajpur | PWD | Road | 2008-05-13 | DDM | 117.94 | RIDF Loan upto 10 crore | There was dealy in completion due to delay in receipt of allotment. Requisite tests were carried out. Test records were maintained.NABARD assistance was displayed
11 | R112000053 | Amla Amarpura Samaspura Samasgarh R | Bhopal | PWD | Road | 2008-03-18 | RO Officer | 316.13 | RIDF Loan upto 10 crore | NABARD board has been displayed. Delay in utilisation of money for land acquisition.
11 | R112000054 | Sukhi Sevaniya Mugaliyak to Chanche | Bhopal | PWD | Road | 2008-03-18 | RO Officer | 286.82 | RIDF Loan upto 10 crore | NABARD board has been displayed. More than 75% of work completed.
11 | r112000217 | Kandiapar Tank | Seoni | WRD | MIS | 2008-03-11 | Chindwara DDM | 130.41 | RIDF Loan upto 10 crore | NABARD board displayed. Project is likely to be completed before June 2008
11 | r112000200 | Ahamadpur Malgaon Bhojakhedi Road | Khandwa | PWD | Road | 2008-03-10 | Khandwa DDM | 148.34 | RIDF Loan upto 10 crore | NABARD board not displayed. The road is almost complete. The work of the drainage channel are incomplete at some places. There was damage to the road at some places due to some potholes on the road.
11 | r112000170 | Sammatkhedi Tank | Mandsaur | WRD | MIS | 2008-03-07 | Mandsaur DDM | 219.64 | RIDF Loan upto 10 crore | NABARD board not displayed. WUA should beformed after the project is completed
11 | r112000161 | Sanjalpur Tank | Mandsaur | WRD | MIS | 2008-03-07 | Mandsaur DDM | 159.05 | RIDF Loan upto 10 crore | NABARD board not displayed. Construction of bund and waste weir was over more than a year back. However, the work of excavation of main canal is pending. WUA to be formed.
11 | r112000199 | Rajendragram Dharmdas Road | Anuppur | PWD | Road | 2008-03-04 | RO Officer | 137.06 | RIDF Loan upto 10 crore | NABARD board displayed. More than 70% of the projects has been completed.
11 | r112000198 | Benibari Chandanghat Road | Anuppur | PWD | Road | 2008-03-04 | RO Officer | 57.14 | RIDF Loan upto 10 crore | More than 76% of work has been completed. NABARD board has been displayed. PCR to be submitted if the project is completed in all respects.
11 | r112000207 | Sanjaysagar MIP Irr.Proje | Vidisha | WRD | MIP | 2008-03-04 | Vidisha DDM | 10251.56 | RIDF Loan 25 crore & above | NABARD board not displayed. Maintenance of records was satisfactory. The work was running at least 60% behind schedule.
11 | r112000175 | Darariya Tank | Sagar | WRD | MIS | 2008-02-26 | Sagar DDM | 104.07 | RIDF Loan upto 10 crore | There is timeoverrun due to delay in payment of land compensation.NABARD board has not been displayed. There is contractors problem because of poor fund flow.
11 | r112000061 | Jujharpur Pachokhara Goraghat Road | Datia | PWD | Road | 2008-02-19 | Gwalior DDM | 64.94 | RIDF Loan upto 10 crore | NABARD board not displayed. Many places road has been damaged. Visits by officials is regular. Records not available readily.
11 | r112000102 | PRIMARY HEALTH CENTRES | Datia | DHFW | Health | 2008-02-19 | Gwalior DDM | 285.6 | RIDF Loan upto 10 crore | No water supply in the health centre. Borewell to be provided. Post of Doctor is vacant and as there is no Doctor the PHC is not functioning for the past 5 months. PHC is beneficial to 32 villages in the vicinity.
11 | r112000153 | Maheshpura Tank | Guna | WRD | MIS | 2007-10-30 | Guna DDM | 165.55 | RIDF Loan upto 10 crore | Land acquisition, inter-departmental tussle, contractors problem, poor fund flow are the problems. NABARD board not displayed. The physical progress is negligible
11 | R112000207 | Sanjaysagar MIP Irr.Proje | Vidisha | WRD | MIP | 2007-10-04 | Vidisha DDM | 10251.56 | RIDF Loan 25 crore & above | NABARD board has not been displayed. The construction drawing to the contractor was handed over to him on the day of monitoring visit.
11 | r112000064 | Itarsi Dolariya Tigariya Road | Hoshangabad | PWD | Road | 2007-06-26 | Hoshangabad DDM | 130.71 | RIDF Loan upto 10 crore | NABARD board has been displayed. The road is incomplete and is likely to be completed by December 2007. There was inordinate delay from the contractors side.
11 | r112000074 | Bhikangaon Dhakalgaon Sanawad Road | Khargone | PWD | Road | 2007-06-13 | Khargone DDM | 399.96 | RIDF Loan upto 10 crore | There is time overrun because of labour shortage and cost overrun because of material shortage and increase in cost of bitumen.NABARD board has been displayed. The project may require another 6 months to complete.
11 | r112000156 | Minors of Ambaknall Tank | Khargone | WRD | MIP | 2007-06-12 | Khargone DDM | 107.28 | RIDF Loan upto 10 crore | NABARD board has been displayed. As the land acquisition was delayed, the time required for completion of the project will be another six months.
11 | r112000072 | Andad Bhikangaon Road | Khargone | PWD | Road | 2007-06-08 | Khargone DDM | 244.51 | RIDF Loan upto 10 crore | Time overrun because of labour shortage. Cost overrun because of material shortage.The construction of road is over. However, the shoulder work has been completed upto 90%.
11 | r112000135 | SUB HEALTH CENTRES | Katni | DHFW | Health | 2007-06-05 | Jabalpur DDM | 257.5 | RIDF Loan upto 10 crore | Kudan project. NABARD board not displayed. Flooring not done properly. Doors and windows not fixed. Progress in kitchen very slow. Electric supply line not available from MPEB. Poor fund flow. Contractor not attending to the work.
11 | r112000135 | SUB HEALTH CENTRES | Katni | DHFW | Health | 2007-06-05 | Jabalpur DDM | 257.5 | RIDF Loan upto 10 crore | Amgawa Project. Electric supply line not available from MPEB. NABARD board has not been displayed. Flooring of the room, courtyard and front side was not done properly. No arrangement has been made to supply water to SHC.
11 | r112000135 | SUB HEALTH CENTRES | Katni | DHFW | Health | 2007-06-05 | Jabalpur DDM | 257.5 | RIDF Loan upto 10 crore | Deogaon Project. Electricity supply line not available. Poor fundflow. No monitoring visits. NABARD board not displayed. Doors and windows not fixed. no electrical fittings. Flooring of court yard not done properly. No water supply arrangement.
11 | r112000147 | SADARBAN TANK | Khargone | WRD | MIS | 2007-06-04 | Khargone DDM | 74.15 | RIDF Loan upto 10 crore | The work is in progress. NABARD board has been displayed.
11 | r112000006 | Agar Sarangpur to Deharipal -Gondal | Shajapur | PWD | Road | 2007-05-18 | Shajapur DDM | 156.56 | RIDF Loan upto 10 crore | Project has been completed in time. NABARD board to be displayed at both ends of the road. The Department to complete Project Completion Report.
11 | r112000215 | Dalchi Tank | Khargone | WRD | MIS | 2007-05-17 | Khargone DDM | 35.56 | RIDF Loan upto 10 crore | NABARD board has not been displayed.
11 | r112000193 | Deonagar Sihoda Abhana Road | Jabalpur | PWD | Road | 2007-04-17 | Jabalpur DDM | 56.2 | RIDF Loan upto 10 crore | The work has been completed within the time schedule. NABARD board has not been displayed. PCR has not been received.
11 | r112000103 | PRIMARY HEALTH CENTRES | Dhar | DHFW | Health | 2007-04-14 | Dhar DDM | 190.4 | RIDF Loan upto 10 crore | There is no compound wall to protect the property from animals. 70-75% work is completed. Plastering work was in progress. Electricity fitting and plumbing work to be done. NABARD board was not displayed.
11 | r112000012 | Karariya Shamshabad (16/2) to Nater | Vidisha | PWD | Road | 2007-04-13 | Vidisha DDM | 399.24 | RIDF Loan upto 10 crore | Contractors problem exist. Nabard board has been displayed. Work is expected to be completed within 3 months.
11 | r112000001 | Paraswada Naxi Mundesara Timkitola | Balaghat | PWD | Road | 2007-04-13 | Balaghat DDM | 255.42 | RIDF Loan upto 10 crore | NABARD board has been displayed. The progress is upto 75%.
11 | r112000158 | Hirapur Tank | Khargone | WRD | MIS | 2007-04-09 | Khargone DDM | 228.92 | RIDF Loan upto 10 crore | NABARD board has been displayed. All records are maintained.
11 | r112000143 | SILOTA TANK | Chhindwara | WRD | MIS | 2007-03-24 | Chindwara DDM | 182.32 | RIDF Loan upto 10 crore | NABARD board has not been displayed. Physical progress is upto 25% in regard to headworks, spillways and head regulator.
11 | r112000017 | Lashkarpur Jamaldi Kheruahat Road | Vidisha | PWD | Road | 2007-03-23 | Vidisha DDM | 110.78 | RIDF Loan upto 10 crore | NABARD board has been displayed. Complaints and suggestion book has been maintained. There is contractor's problem.
11 | r112000011 | Baisenagar-Tila-Nimkhiriya Cheerkhe | Vidisha | PWD | Road | 2007-03-23 | Vidisha DDM | 215.67 | RIDF Loan upto 10 crore | NABARD board has been displayed. Work has been completed in all respects.
11 | r112000013 | Khamkheda Lodakheri Gangarwara to P | Vidisha | PWD | Road | 2007-03-15 | Vidisha DDM | 241.63 | RIDF Loan upto 10 crore | More than 75% of the work has been completed. A good quality NABARD board has been displayed. The work is in progress.
11 | r112000201 | Masangaon Kamtada Road | Harda | PWD | Road | 2007-03-07 | Hoshangabad DDM | 67.29 | RIDF Loan upto 10 crore | The work is incomplete as on date. The CC work at both ends need maintenance at this stage. Presently the work is halted.
11 | r112000207 | Sanjaysagar MIP Irr.Proje | Vidisha | WRD | MIP | 2007-02-20 | Vidisha DDM | 10251.56 | RIDF Loan 25 crore & above | 8% of excavation work has been done. There is no progress in head work and canals.
11 | r112000153 | Maheshpura Tank | Guna | WRD | MIS | 2007-02-20 | Guna DDM | 165.55 | RIDF Loan upto 10 crore | Work only upto 15% is completed. NABARD board has not been displayed. No site visit or order book was available at the site.
11 | r112000003 | Udainagar Kanad Road | Dewas | PWD | Road | 2007-02-07 | Mandsaur DDM | 248.17 | RIDF Loan upto 10 crore | 9.25/12 Kms comes under RIDF and rest under PMGSY. NABARD board not displayed. The project has not been completed fully. The work of the shoulders (both sides) are at incomplete stage.
11 | r112000195 | Pawai-Prathvipura Road | Bhind | PWD | Road | 2007-01-31 | Morena DDM | 104.87 | RIDF Loan upto 10 crore | The physical progress ranges between 25% and 50%. No other officer excepting the EE has visited the project site. NABARD board has not been displayed.
11 | r112000196 | Meghpura Asokhar Saheed Road | Bhind | PWD | Road | 2007-01-31 | Morena DDM | 151.82 | RIDF Loan upto 10 crore | The progress of work is between 25% - 50%. NABARD board has not been displayed. No other officer above the ranks of EE has visited the project site.
11 | r112000115 | PRIMARY HEALTH CENTRES | Narsinghpur | DHFW | Health | 2007-01-17 | Narsinghpur DDM | 47.6 | RIDF Loan upto 10 crore | Bhama PHC. PHC foundation and superstructure is complete and finishing work is in progress. The project is likely to be completed by March 2007
11 | r112000115 | PRIMARY HEALTH CENTRES | Narsinghpur | DHFW | Health | 2007-01-16 | Narsinghpur DDM | 47.6 | RIDF Loan upto 10 crore | Barman PHC. PHC foundation work is complete and slab of superstructure is in progress. The schedule date of completion is 31 January 2007 but it is likely to be completed in March 2007.
11 | r112000154 | Rangawasa Tank | Indore | WRD | MIS | 2007-01-16 | Indore DDM | 45.37 | RIDF Loan upto 10 crore | NABARD board has been displayed. More than 75% of the project has been completed.
11 | r112000155 | Sejwani Tank | Indore | WRD | MIS | 2007-01-16 | Indore DDM | 89.58 | RIDF Loan upto 10 crore | More than 75% of headwork has been completed. Due to land acquisition time overrun is possible. NABARD board has been displayed.
11 | r112000167 | Amlipada Tank | Dhar | WRD | MIS | 2007-01-15 | Dhar DDM | 87.93 | RIDF Loan upto 10 crore | Quality of work is good. NABARD board has not been displayed. WUA has not been formed. The project is very useful to the villagers and it will provide irrigation facility to 2 villages.
11 | r112000067 | Seoni Malwa Babri Ghat Road | Hoshangabad | PWD | Road | 2007-01-11 | Hoshangabad DDM | 372.93 | RIDF Loan upto 10 crore | Due to non construction of culvert, bridges and cross drainage the work is not satisfactory and at 15 places there are gaps on the road where black topping has not been done and culvert with hume pipes, slab bridges and cross drainages are to be made.
11 | r112000214 | Jharkheda Tank | Rajgarh | WRD | MIS | 2007-01-09 | Shajapur DDM | 214.94 | RIDF Loan upto 10 crore | The progress of work is slow, there is delay in acquisition of land, delay in tendering and fixing agency, likely hood of time overrun and cost overrun. NABARD board has not been displayed.
11 | R112000021 | Anandpur Unarsikalan Road | Vidisha | PWD | Road | 2006-12-14 | Vidisha DDM | 170.17 | RIDF Loan upto 10 crore | The construction work of the road was in progress but at a very low pace. The Department has already warned the contractor concerned to expedite work and complete the project by March 2007.
11 | R112000020 | Semalkhedi Barenda Road | Vidisha | PWD | Road | 2006-12-14 | Vidisha DDM | 109.86 | RIDF Loan upto 10 crore | The construction work of the road was in progress but at a very low pace. The Department has already warned the contractor concerned to expedite the work and complete the project by March 2007.
11 | r112000144 | TIVRA KAMATH FEEDER TANK | Chhindwara | WRD | MIS | 2006-12-07 | RO Officer | 273.59 | RIDF Loan upto 10 crore | The project is expected to be completed by December 2007. Land acquisition is complete but the formal sanction/awards are yet to be granted.
11 | R112000015 | Nateran-Kharai-Mundra pitamber-Nipa | Vidisha | PWD | Road | 2006-12-01 | Vidisha DDM | 242.66 | RIDF Loan upto 10 crore | As per the agreement work was to be completed by March 2006. The progress of work is very slow. During the visit no work was being done excepting for collection of some material. The Dept. should expedite the work.
11 | R112000016 | Seu-Nateran to Vidisha-Ashoknagar R | Vidisha | PWD | Road | 2006-12-01 | Vidisha DDM | 133.64 | RIDF Loan upto 10 crore | As per the agreement, the work was to be completed by January 2006. The progress of work is very slow. No work was being done during the visit. The Dept. should expedite the work.
11 | R112000018 | Chhapkheda Kolinja Andiya Road | Vidisha | PWD | Road | 2006-12-01 | Vidisha DDM | 156.42 | RIDF Loan upto 10 crore | As per the agreement the work was to be completed by 18 July 2006. The progress of work is very slow. No work was being done during the visit. The Dept. should expedite the work.
11 | r112000152 | Bhajipani Khurd Tank | Chhindwara | WRD | MIS | 2006-11-28 | Chindwara DDM | 258.93 | RIDF Loan upto 10 crore | NABARD board has been displayed at site. SE has visited the project. EE visits the project regularly. Work is in progress.
11 | r112000144 | TIVRA KAMATH FEEDER TANK | Chhindwara | WRD | MIS | 2006-11-28 | Chindwara DDM | 273.59 | RIDF Loan upto 10 crore | NABARD board has been displayed at site. Work in progress. It is likely to be completed in June 2008.
11 | r112000076 | Ajaygarh Toriya Baryarpur Road | Panna | PWD | Road | 2006-11-18 | Satna DDM | 267.31 | RIDF Loan upto 10 crore | NABARD board has not been displayed. Service ducts to be provided every 200 meters not done. Shoulder work is not satisfactory.
11 | r112000190 | Beohari Bansukali Sidhi Road | Shahdol | PWD | Road | 2006-11-18 | Shahdol DDM | 398.92 | RIDF Loan upto 10 crore | NABARD board has not been displayed. The progress of work is slow. Out of 56 KM, 9.7 KM road has been taken up under Prime Minister Gramin Sasak Yojna. No permission was taken from NABARD to make changes in the project.
11 | r112000076 | Ajaygarh Toriya Baryarpur Road | Panna | PWD | Road | 2006-11-18 | Satna DDM | 267.31 | RIDF Loan upto 10 crore | NABARD board has not been displayed. Shoulder work is not satisfactory and 86 service ducts to be provided every 200 meters not done.
11 | r112000019 | Basoda Bareth Udaypur Road | Vidisha | PWD | Road | 2006-11-10 | Vidisha DDM | 217.16 | RIDF Loan upto 10 crore | Work has been delayed. Reasons attributed was heavy rains. Due to heavy rains the black top was damaged and was repaired by the contractor after the monsoon. In general the quality of work was found satisfactory.
11 | r112000007 | Ranayal Approach Road | Shajapur | PWD | Road | 2006-11-10 | Shajapur DDM | 213.02 | RIDF Loan upto 10 crore | Progress of the work appears to be satisfactory. The project is likely to be completed by 31.3.2007. Quality of work is satisfactory.
11 | r112000008 | Devlabihar Kaithai Akodiya Road | Shajapur | PWD | Road | 2006-11-10 | Shajapur DDM | 272.06 | RIDF Loan upto 10 crore | The road completed. Shoulders/berms of the Kaithlai offshoot require compaction. No milestone and caution boards erected. NABARD board not displayed. About 1 kms in bad shape affecting traffic and requires black topping.
11 | R112000002 | Jhallar Amla Barhapur Road | Betul | PWD | Road | 2006-11-02 | Betul DDM | 200 | RIDF Loan upto 10 crore | Around 75% of the construction work has been completed.
11 | R112000130 | SUB HEALTH CENTRES | Betul | DHFW | Health | 2006-11-02 | Betul DDM | 381.48 | RIDF Loan upto 10 crore | SHC in village Akalwadi visited. Work in progress.
11 | R112000130 | SUB HEALTH CENTRES | Betul | DHFW | Health | 2006-11-02 | Betul DDM | 381.48 | RIDF Loan upto 10 crore | SHC at village Pandurna visited. Work in progress.
11 | R112000130 | SUB HEALTH CENTRES | Betul | DHFW | Health | 2006-11-02 | Betul DDM | 381.48 | RIDF Loan upto 10 crore | SHC at village Umari visited. Work in progress.
11 | r112000103 | PRIMARY HEALTH CENTRES | Dhar | DHFW | Health | 2006-10-14 | Dhar DDM | 190.4 | RIDF Loan upto 10 crore | Bharudpura village. It is running in old building. The H type quarters work not started. 65-70% work completed. Renovation work of old building in progress as well as Doctors quarters.
11 | R112000103 | PRIMARY HEALTH CENTRES | Dhar | DHFW | Health | 2006-10-14 | Dhar DDM | 190.4 | RIDF Loan upto 10 crore | Gujari village. Running in old building. Approach road to be laid, existing road is very narrow - Ambulance cannot reach the centre. 70-75% of work completed. Plastering work is in progress. Electricity fitting done. Plumbing work completed.
11 | R112000063 | Bankhedi Umardha Road | Hoshangabad | PWD | Road | 2006-09-26 | Hoshangabad DDM | 105.14 | RIDF Loan upto 10 crore | The road will benefit 4 villages. The dept. should supervise the completion of the road as per specification and need to keep close watch on maintenance of road in future.
11 | R112000001 | Paraswada Naxi Mundesara Timkitola | Balaghat | PWD | Road | 2006-09-15 | Balaghat DDM | 255.42 | RIDF Loan upto 10 crore | Project yet to be completed and behind schedule. The delay was on account of heavy rains, non-availability of raw material, labour, etc. The project is likely to be completed by March 07.
11 | R112000001 | Paraswada Naxi Mundesara Timkitola | Balaghat | PWD | Road | 2006-09-15 | RO Officer | 255.42 | RIDF Loan upto 10 crore | Excavation of soil on the carriage way done. Sub grading of the excavated portion was underway. Overall the construction appeared to be satisfactory.
11 | R112000171 | Kherkhedi Tank | Mandsaur | WRD | MIS | 2006-08-31 | Mandsaur DDM | 159.69 | RIDF Loan upto 10 crore | Land acquisition problem. NB board not displayed. Department to follow up for early disposal of land acquisition problem. Project is yet to be completed.
11 | r112000169 | Lasuria Tank | Mandsaur | WRD | MIS | 2006-08-31 | OIC | 221.23 | RIDF Loan upto 10 crore | Delay in land acquisition hindered the progress. Project is yet to be completed. NABARD board not displayed.
11 | R112000177 | Chhoti Rangir | Sagar | WRD | MIS | 2006-07-28 | Sagar DDM | 150.6 | RIDF Loan upto 10 crore | The digging work of the tank was taken up. However, due to rains the work was stopped. NABARD board not displayed.
11 | r112000170 | Sammatkhedi Tank | Mandsaur | WRD | MIS | 2006-06-23 | Mandsaur DDM | 219.64 | RIDF Loan upto 10 crore | Project is under construction. NABARD board not displayed. WUA to be formed.
11 | r112000161 | Sanjalpur Tank | Mandsaur | WRD | MIS | 2006-06-22 | Mandsaur DDM | 159.05 | RIDF Loan upto 10 crore | Project is under construction. WUA to be formed. NABARD board not displayed.
11 | R112000090 | Kotar Birsinghpur road | Satna | PWD | Road | 2006-05-24 | Satna DDM | 166.58 | RIDF Loan upto 10 crore | Non-availability of NP-4 Hume Pipes. Contractors problem - shortage of material and labour problem.
11 | R112000065 | Itarsi Dum Dum Rampur Maroda Road | Hoshangabad | PWD | Road | 2005-11-09 | OIC+RO Officials | 105.24 | RIDF Loan upto 10 crore | 1. Earthwork of sub-grade completed and sub-base was completed in 4 km 2. Works have started in 11 out of 19 CD works sanctioned.
11 | r112000002 | Jhallar Amla Barhapur Road | Betul | PWD | Road | 2005-10-08 | DDM | 200 | RIDF Loan upto 10 crore | Tendering process has been completed for road as well as CD works. Overall progress is 10%.
11 | R112000175 | Darariya Tank | Sagar | WRD | MIS | 2012-01-11 | DDM | 104.07 | RIDF Loan upto 10 crore | Hd wrks>76%. ToR due to rain, water in river, contractor complacence.CoR-delay due to LA, local issues with villagers. Balance wrk strtd.
11 | R112000214 | Jharkheda Tank | Rajgarh | WRD | MIS | 2011-11-15 | DDM | 214.94 | RIDF Loan upto 10 crore | Hd wrks complete, Land acquisition-40%, prblms-LA, ToR-LA, CoR-LA & Cost escalation.NB Brd- not displayed
11 | R112000212 | Narainpura Tank | Rajgarh | WRD | MIS | 2011-11-15 | DDM | 197.71 | RIDF Loan upto 10 crore | Hd wrks complete, Canal Wrks-40%, Prblms-LA, ToR-LA, CoR-cost escalation. NB brd not displayed.
11 | R112000210 | Shankarpura Tank | Ujjain | WRD | MIS | 2011-08-16 | DDM | 314.53 | RIDF Loan upto 10 crore | Hd wrks, Hd Rgltr>76%, Splways upto 25%, ttl physical prgrs:45%. Delay due to slw prgrs of contrctr, fresh cntrct awarded. Slow prgrs in LA. ToR&CoR-yes. NB brd nt displayed. tender awarded ignores aspects like experience, infra etc.
11 | R112000058 | Rajnagar Bachhan Chandla Road | Chattarpur | PWD | Road | 2011-11-03 | DDM | 397.12 | RIDF Loan upto 10 crore | All heads achieved more than 76%. prblms-labour, water, delay in payment to contractor, poor fund flow.NB brd not displayed, maintenance/test register not available.
11 | R112000209 | Swami Sagar Tank | Narsinghpur | WRD | MIS | 2011-12-16 | DDM | 229.69 | RIDF Loan upto 10 crore | Hd wrks, constrn of bund each:51-75%, spillways, Mn cnl each>76%. Slw prgrs by contrctr, Re tenderin of balnce wrk. Blasting of hard rock hindered by farmers. NB brd nt displayed.
11 | R112000005 | Itarsi Chhipaner Road | Sehore | PWD | Road |  |  | 158.82 | RIDF Loan upto 10 crore
11 | R112000009 | Sultaniya Pipalkheda Saliya Road | Vidisha | PWD | Road |  |  | 178.87 | RIDF Loan upto 10 crore
11 | R112000010 | Constraction of 28 Nos CDs on Gurod | Vidisha | PWD | Road |  |  | 41.16 | RIDF Loan upto 10 crore
11 | R112000014 | Lateri Shamshabad to Berkheda Jagi | Vidisha | PWD | Road |  |  | 193.08 | RIDF Loan upto 10 crore
11 | R112000050 | Barkheda Pathani to Bagroda Road | Bhopal | PWD | Road |  |  | 195.37 | RIDF Loan upto 10 crore
11 | R112000051 | Bagli Katara Barrai Jhagariya Road | Bhopal | PWD | Road |  |  | 231.29 | RIDF Loan upto 10 crore
11 | R112000052 | Gunga Manikhedi Dillod Road | Bhopal | PWD | Road |  |  | 138.05 | RIDF Loan upto 10 crore
11 | R112000055 | Bhatkheda Satpayri Palasur Saikheda | Burhanpur | PWD | Road |  |  | 189.62 | RIDF Loan upto 10 crore
11 | R112000059 | Ghutariya Raneh Road | Damoh | PWD | Road |  |  | 123.96 | RIDF Loan upto 10 crore
11 | R112000062 | Unao Baswaha Road | Datia | PWD | Road |  |  | 229.66 | RIDF Loan upto 10 crore
11 | R112000066 | Semari Sangakheda Road | Hoshangabad | PWD | Road |  |  | 54.5 | RIDF Loan upto 10 crore
11 | R112000068 | Depalpur Kaisur Road | Indore | PWD | Road |  |  | 293.45 | RIDF Loan upto 10 crore
11 | R112000071 | Umarkote Tarkhedi Raipria Road | Jhabua | PWD | Road |  |  | 141.9 | RIDF Loan upto 10 crore
11 | R112000073 | Besarkhund Maltar Road | Khargone | PWD | Road |  |  | 219.89 | RIDF Loan upto 10 crore
11 | R112000075 | Maheshwar Mehatwada Bablai Somalkhe | Khargone | PWD | Road |  |  | 390.7 | RIDF Loan upto 10 crore
11 | R112000077 | Dehgaon Bamhori Road(From 1 to 4 Km | Raisen | PWD | Road |  |  | 62.07 | RIDF Loan upto 10 crore
11 | R112000078 | Maheshwar Magardha Road | Raisen | PWD | Road |  |  | 103.03 | RIDF Loan upto 10 crore
11 | R112000079 | Misrod Chiklod Goharganj Road | Raisen | PWD | Road |  |  | 51.26 | RIDF Loan upto 10 crore
11 | R112000081 | Bilehra Panari Chandoni Road | Sagar | PWD | Road |  |  | 138.36 | RIDF Loan upto 10 crore
11 | R112000082 | Chourai Madiya Agresen Harra Sahuwa | Sagar | PWD | Road |  |  | 147.89 | RIDF Loan upto 10 crore
11 | R112000083 | Dhanora Balai Bhangarh Road | Sagar | PWD | Road |  |  | 251.62 | RIDF Loan upto 10 crore
11 | R112000084 | Kisanpura Mugryaow Road | Sagar | PWD | Road |  |  | 167.2 | RIDF Loan upto 10 crore
11 | R112000085 | Masurhai Toda Road | Sagar | PWD | Road |  |  | 206.73 | RIDF Loan upto 10 crore
11 | R112000087 | Bathiya Charahta Road | Satna | PWD | Road |  |  | 258.2 | RIDF Loan upto 10 crore
11 | R112000088 | Jharkua Raigaon Karsara Road | Satna | PWD | Road |  |  | 338.55 | RIDF Loan upto 10 crore
11 | R112000091 | Girwani Gajigarh Road | Shivpuri | PWD | Road |  |  | 110.46 | RIDF Loan upto 10 crore
11 | R112000092 | Padora to Gora Road | Shivpuri | PWD | Road |  |  | 119.34 | RIDF Loan upto 10 crore
11 | R112000094 | PRIMARY HEALTH CENTRES | Badwani | DHFW | Health |  |  | 23.8 | RIDF Loan upto 10 crore
11 | R112000095 | PRIMARY HEALTH CENTRES | Betul | DHFW | Health |  |  | 23.8 | RIDF Loan upto 10 crore
11 | R112000096 | PRIMARY HEALTH CENTRES | Bhind | DHFW | Health |  |  | 119 | RIDF Loan upto 10 crore
11 | R112000097 | PRIMARY HEALTH CENTRES | Bhopal | DHFW | Health |  |  | 23.8 | RIDF Loan upto 10 crore
11 | R112000098 | PRIMARY HEALTH CENTRES | Burhanpur | DHFW | Health |  |  | 95.2 | RIDF Loan upto 10 crore
11 | R112000099 | PRIMARY HEALTH CENTRES | Chattarpur | DHFW | Health |  |  | 71.4 | RIDF Loan upto 10 crore
11 | R112000100 | PRIMARY HEALTH CENTRES | Chhindwara | DHFW | Health |  |  | 71.4 | RIDF Loan upto 10 crore
11 | R112000101 | PRIMARY HEALTH CENTRES | Damoh | DHFW | Health |  |  | 23.8 | RIDF Loan upto 10 crore
11 | R112000105 | PRIMARY HEALTH CENTRES | Guna | DHFW | Health |  |  | 23.8 | RIDF Loan upto 10 crore
11 | R112000107 | PRIMARY HEALTH CENTRES | Harda | DHFW | Health |  |  | 23.8 | RIDF Loan upto 10 crore
11 | R112000108 | PRIMARY HEALTH CENTRES | Indore | DHFW | Health |  |  | 142.8 | RIDF Loan upto 10 crore
11 | R112000109 | PRIMARY HEALTH CENTRES | Jabalpur | DHFW | Health |  |  | 23.8 | RIDF Loan upto 10 crore
11 | R112000110 | PRIMARY HEALTH CENTRES | Khandwa | DHFW | Health |  |  | 285.6 | RIDF Loan upto 10 crore
11 | R112000111 | PRIMARY HEALTH CENTRES | Khargone | DHFW | Health |  |  | 142.8 | RIDF Loan upto 10 crore
11 | R112000112 | PRIMARY HEALTH CENTRES | Mandla | DHFW | Health |  |  | 47.6 | RIDF Loan upto 10 crore
11 | R112000113 | PRIMARY HEALTH CENTRES | Mandsaur | DHFW | Health |  |  | 166.6 | RIDF Loan upto 10 crore
11 | R112000114 | PRIMARY HEALTH CENTRES | Morena | DHFW | Health |  |  | 95.2 | RIDF Loan upto 10 crore
11 | R112000116 | PRIMARY HEALTH CENTRES | Panna | DHFW | Health |  |  | 47.6 | RIDF Loan upto 10 crore
11 | R112000118 | PRIMARY HEALTH CENTRES | Ratlam | DHFW | Health |  |  | 309.4 | RIDF Loan upto 10 crore
11 | R112000119 | PRIMARY HEALTH CENTRES | Rewa | DHFW | Health |  |  | 166.6 | RIDF Loan upto 10 crore
11 | R112000120 | PRIMARY HEALTH CENTRES | Sagar | DHFW | Health |  |  | 47.6 | RIDF Loan upto 10 crore
11 | R112000121 | PRIMARY HEALTH CENTRES | Satna | DHFW | Health |  |  | 333.2 | RIDF Loan upto 10 crore
11 | R112000122 | PRIMARY HEALTH CENTRES | Sehore | DHFW | Health |  |  | 47.6 | RIDF Loan upto 10 crore
11 | R112000123 | PRIMARY HEALTH CENTRES | Seoni | DHFW | Health |  |  | 23.8 | RIDF Loan upto 10 crore
11 | R112000124 | PRIMARY HEALTH CENTRES | Shahdol | DHFW | Health |  |  | 47.6 | RIDF Loan upto 10 crore
11 | R112000125 | PRIMARY HEALTH CENTRES | Sidhi | DHFW | Health |  |  | 238 | RIDF Loan upto 10 crore
11 | R112000126 | PRIMARY HEALTH CENTRES | Tikamgarh | DHFW | Health |  |  | 23.8 | RIDF Loan upto 10 crore
11 | R112000127 | PRIMARY HEALTH CENTRES | Ujjain | DHFW | Health |  |  | 166.6 | RIDF Loan upto 10 crore
11 | R112000129 | PRIMARY HEALTH CENTRES | Vidisha | DHFW | Health |  |  | 23.8 | RIDF Loan upto 10 crore
11 | R112000132 | SUB HEALTH CENTRES | Dindori | DHFW | Health |  |  | 71.53 | RIDF Loan upto 10 crore
11 | R112000133 | SUB HEALTH CENTRES | Hoshangabad | DHFW | Health |  |  | 81.05 | RIDF Loan upto 10 crore
11 | R112000134 | SUB HEALTH CENTRES | Jabalpur | DHFW | Health |  |  | 224.12 | RIDF Loan upto 10 crore
11 | R112000136 | SUB HEALTH CENTRES | Narsinghpur | DHFW | Health |  |  | 9.53 | RIDF Loan upto 10 crore
11 | R112000137 | SUB HEALTH CENTRES | Ratlam | DHFW | Health |  |  | 57.22 | RIDF Loan upto 10 crore
11 | R112000138 | SUB HEALTH CENTRES | Rewa | DHFW | Health |  |  | 395.79 | RIDF Loan upto 10 crore
11 | R112000139 | SUB HEALTH CENTRES | Satna | DHFW | Health |  |  | 176.43 | RIDF Loan upto 10 crore
11 | R112000140 | SUB HEALTH CENTRES | Sehore | DHFW | Health |  |  | 4.77 | RIDF Loan upto 10 crore
11 | R112000159 | Goverdhanpura Tank | Mandsaur | WRD | MIS |  |  | 120.56 | RIDF Loan upto 10 crore
11 | R112000160 | Badodia Tank | Mandsaur | WRD | MIS |  |  | 106.01 | RIDF Loan upto 10 crore
11 | R112000172 | Gariyakhedi Tank | Mandsaur | WRD | MIS |  |  | 113.22 | RIDF Loan upto 10 crore
11 | R112000173 | BahikhedaTank | Mandsaur | WRD | MIS |  |  | 56.13 | RIDF Loan upto 10 crore
11 | R112000174 | Junia Tank | Sagar | WRD | MIS |  |  | 320.62 | RIDF Loan upto 10 crore
11 | R112000176 | Kevlari Tank | Sagar | WRD | MIS |  |  | 141.14 | RIDF Loan upto 10 crore
11 | R112000178 | Pisanhari ki Toriya | Shivpuri | WRD | MIS |  |  | 117.66 | RIDF Loan upto 10 crore
11 | R112000179 | Godahar Chhijwar Road | Rewa | PWD | Road |  |  | 139.84 | RIDF Loan upto 10 crore
11 | R112000182 | Rewa Semariya via Bankuiya Road | Rewa | PWD | Road |  |  | 329.82 | RIDF Loan upto 10 crore
11 | R112000183 | Ambi Tiwani Road | Rewa | PWD | Road |  |  | 40.27 | RIDF Loan upto 10 crore
11 | R112000185 | Jhurai Sarai Road | Singrauli | PWD | Road |  |  | 288 | RIDF Loan upto 10 crore
11 | R112000186 | Barka Purail Road | Singrauli | PWD | Road |  |  | 176.56 | RIDF Loan upto 10 crore
11 | R112000188 | Barkheda Shahgunj Road | Raisen | PWD | Road |  |  | 36.8 | RIDF Loan upto 10 crore
11 | R112000189 | Chourahat Furtala Road | Hoshangabad | PWD | Road |  |  | 13.1 | RIDF Loan upto 10 crore
11 | R112000191 | Chuhari Lafda Maika Road | Shahdol | PWD | Road |  |  | 362.03 | RIDF Loan upto 10 crore
11 | R112000192 | Chatbai-Patasi Road | Shahdol | PWD | Road |  |  | 162.96 | RIDF Loan upto 10 crore
11 | R112000194 | Padana Talen Road | Rajgarh | PWD | Road |  |  | 107.05 | RIDF Loan upto 10 crore
11 | R112000203 | Chauka Ishannagar Road | Chattarpur | PWD | Road |  |  | 175.39 | RIDF Loan upto 10 crore
11 | R112000205 | Umar 3/2 | Narsinghpur | PWD | Bridge |  |  | 62.6 | RIDF Loan upto 10 crore
11 | R112000206 | Parvati 1/2 | Sheopur | PWD | Bridge |  |  | 223.77 | RIDF Loan upto 10 crore
11 | R112000208 | Banderchuha Tank | Katni | WRD | MIS |  |  | 127.57 | RIDF Loan upto 10 crore
11 | R112000213 | Jorkiya Tank | Rajgarh | WRD | MIS |  |  | 168.67 | RIDF Loan upto 10 crore
11 | R112000216 | Kurlasi Tank | Mandsaur | WRD | MIS |  |  | 104.59 | RIDF Loan upto 10 crore
12 | R122000042 | Kudila Pacher Road | Tikamgarh | PWD | Road | 2011-10-13 | DDM | 214.4 | RIDF Loan upto 10 crore | Work completed in July 2007. There was no T & C overrun. Project visited by senior engineers. Various tests carried out and were recorded. NAB brd not displayed. Road Qlty poor, guarantee period should be increased to 5 yrs. Qlty of PMGSY > NAB Road.
12 | r122000072 | IMLIDHANA TANK | Harda | WRD | MIS | 2011-03-20 | DDM | 1717.88 | RIDF Loan 10.01-24.99 crore | Head work is more than 75% completed.Minors upto 25% complete.Delay was due to delay in LA.COR due to increase in LA cost, Seepage and lack of lining of canal is hampering the efficency of tnk.enhancement in quantities of work as per site conditions.
12 | r122000021 | Deri Triveni Tank | Ratlam | WRD | MIS | 2011-03-20 | DDM | 1625.92 | RIDF Loan 10.01-24.99 crore | HW,SW work more than 26% complete.HR upto 25% complete.MC,minors & CD work more than 51% complete.TOR due to cancellation of tender to earlier contractor agency. Now contract given to new agency.Time given for completion is 23/2/2012.
12 | r122000076 | PARASALI TANK | Mandsaur | WRD | MIS | 2011-03-18 | DDM | 588.88 | RIDF Loan upto 10 crore | HW,SW,HR,MC,CD works more than 76% complete.TOR due to slow pace in LA.COR due to increasing cost of land.Due to scanty rainfall in catchment area water level is only 30%.
12 | r122000036 | Mahendra Banoli Kota Road | Panna | PWD | Road | 2011-03-15 | DDM | 742.23 | RIDF Loan upto 10 crore | EW more than 76%,CD,WBM more than 26% complete.TOR due to shortage of water & contractors problem.NB board not displayed.Road has been handed over to PMGSY now
12 | r122000026 | Retam Barrage | Mandsaur | WRD | MIP | 2011-03-08 | DDM | 3064.5 | RIDF Loan 25 crore & above | HW,SW,HR,MC,BC more than 76% complete.TOR due to slow progress in rehabilitation of displaced villagers.COR due to high cost of civil work.NB board nt yet displayed.
12 | r122000028 | Banda - Gadar - Chhapri Road | Sagar | PWD | Road | 2011-03-07 | DDM | 268.8 | RIDF Loan upto 10 crore | LA,EW,WBM,BT,CD works more than 76% complete.TOR due to non availability of funds.test record,site visit book not available,3 small patches incomplete due to nalas crossing road.road has scraped off due to use & weather
12 | r122000060 | Surdaha Parasmaniya Rampur Maihar Road | Satna | PWD | Road | 2011-03-04 | RO Official | 657.6 | RIDF Loan upto 10 crore | LA,EW,WBM,BT,CD works more than 76% complete.TOR due to delay in clearence from forest department & delay on part of contractr due to scarcity of water & labour problem.NB name not displayed on board.
12 | r122000001 | Machhi Tank | Betul | WRD | MIS | 2011-02-24 | DDM | 86.03 | RIDF Loan upto 10 crore | HW,CW,LA,EW more than 76% complete.Tor due to second survey undertaken by dept.COR due to more EW required for dam.WRd has released water for crops.
12 | r122000083 | Bargi Diversion Phase-Ii | Jabalpur | NVDA | MJP | 2011-02-04 | RO Official | 17632.28 | RIDF Loan 25 crore & above | HW,SW,HR,MC,BC,LC,CD works more than 76% complete.TOR due to delay in LA from farmers,court cases,incomplete work by contractors,due to delay in revised approvals from various authorities.COR due to work left incomplete at 83.5 km HR.NB board not displa
12 | r122000082 | BARGI DIVERSION PHASE-I | Jabalpur | NVDA | MJP | 2011-02-04 | RO Official | 6285.68 | RIDF Loan 25 crore & above | MC,LC,distributories,CD works,tunnel more than 76% complete.Tor due to retendering of work between 33-35 km as earlier contractr left work.COR due to new contractors engagement in in cut & cover structure.NB board not displayed.
12 | r122000066 | Ashir Dhulkot Road | Burhanpur | PWD | Road | 2011-02-03 | DDM | 110.16 | RIDF Loan upto 10 crore | EW 85% complete,WBM,BT 35% complete,CD works 100% complete.TOR due to quoting of new tender,contractor problem.slow progress of project
12 | r122000067 | OMKARESWAR CANAL PHASE I | Khandwa | NVDA | MJP | 2011-01-25 | RO Official | 22945.38 | RIDF Loan 25 crore & above | hw,PH 100% complete,cwc,rbc,lbc more than 75% complete.problems due to delay in permission for railway crossing of RBC,stay on LA by HC,delay in clearence from forest department.lining of lbc needs to be expedieted,formation of WUAs need to be taken up
12 | r122000038 | Digora Bairwar Jatara Road | Tikamgarh | PWD | Road | 2011-01-25 | DDM | 224.08 | RIDF Loan upto 10 crore | TOR due to extension of work granted.Road needs immediate repairing.NABARd board not displayed.Delay in allotment of funds,migration of labour,bridges were not finalised on time,delay in release of funds to agency.site visit book not available
12 | r122000056 | Barud Sonkhedi Roshni Road | Khandwa | PWD | Road | 2011-01-19 | DDM | 382.36 | RIDF Loan upto 10 crore | EW,CD works more than 76% complete. WBM,BT more than 51% complete.TOR & cost overrun due to contractors problem.NB board not displayed.Inordinate delay in completion of road. overall quality of road not upto mark.
12 | r122000005 | Dokdoh Tank | Chhindwara | WRD | MIS | 2011-01-11 | RO Official | 795.56 | RIDF Loan upto 10 crore | HW more than 76% complete,SW,HR,MC,BC, distributaries,minors,subminors 51 to 75% complete,CD works & field channels upto 25% complete.TOR due to delay in LA & on account of presence of hard rock near spillway,NB board displayed.
12 | R122000037 | Phoolpur Magrai Pali Chari Pacherghat Road | Tikamgarh | PWD | Road | 2011-01-04 | DDM | 382.03 | RIDF Loan upto 10 crore | LA,EW,WBM,BT,CD works more than 76% complete.Files not maintained properly.Design of bridges not finalised on time.TOR and cost overrun due to delay in designing of culverts.NABARD board not displayed.
12 | r122000063 | Gol - Amaravatkala Road | Bhopal | PWD | Road | 2010-12-10 | RO Official | 301 | RIDF Loan upto 10 crore | Road work complete in most respects only Appr.Rd. for Two bridges yet to be completed.NB Assistance board not displayed.TOR due to change in design of bridges. Visit record of visiting officers not available.
12 | R122000080 | PILIYAKHAL DAM | Shajapur | WRD | MIS | 2010-12-07 | RO Official | 1118.24 | RIDF Loan 10.01-24.99 crore | Only 45% work is completed.Structu like dam, canal, minor , spill way are yet to be completed. Relocation of Ruparail village is yet to be done. LA for minors yet to be done. Rec main NAB assistance displayed.
12 | R122000076 | PARASALI TANK | Mandsaur | WRD | MIS | 2010-03-29 | DDM | 588.88 | RIDF Loan upto 10 crore | HW, HW regulator and cross drainage >76% completed.SW 51-75%..COR due to LA. TOR due to LA. Records maintained.Senior Engineers viisted. Assistance was not dispalyed.
12 | R122000026 | Retam Barrage | Mandsaur | WRD | MIP | 2010-03-29 | DDM | 3064.5 | RIDF Loan 25 crore & above | HW, HWR >76% completed.SW 51-75% completed. MC and BC 26-50% completed TOR sdue to LA, Four villagfes were affected and not rehabilitated.Tests carried out, supervised NABARd assistance not displaced
12 | R122000083 | Bargi Diversion Phase-Ii | Jabalpur | NVDA | MJP | 2010-03-29 | DDM | 17632.28 | RIDF Loan 25 crore & above | HR,MC,ling of canal &CD are >76% completed.Distri, minors, FC 51-75% completed.Work done up to 102 KM and contrs left new trendering started.TOR due to LA COR due to hifher SOR. Service roads are needed.supervised, records maint assist not displayed
12 | R122000005 | Dokdoh Tank | Chhindwara | WRD | MIS | 2010-03-28 | DDM | 795.56 | RIDF Loan upto 10 crore | SW, MC, BC minors and sub minors 51-75% completed.TOR due tio delay in LA from Forest Dep and Hard rock in forest land where waste weir is located.Likely to be completed by Mar 11. Rec maintained . Tests carried out. Implementation needs to be expedite
12 | R122000072 | IMLIDHANA TANK | Harda | WRD | MIS | 2010-03-25 | DDM | 1717.88 | RIDF Loan 10.01-24.99 crore | HW,HR,SW and MC >76% completed..Revised pro has lining, CD is 51-75% completed.TOR due to LA COR - increase in EW and inclusion of lining' LA prob in minors and sub minors still persists.For dam safety during monsoon, lightg is neded Ass not displayed
12 | R122000082 | BARGI DIVERSION PHASE-I | Jabalpur | NVDA | MJP | 2010-03-24 | DDM | 6285.68 | RIDF Loan 25 crore & above | MC,BC, minors sub minors & CD >76% completed.Lining of canal and minors and sub minors 51-75% completed.TOR replacement of contrctr and LA. COR due to SOR.Shrubs need to removed, lining scoured by rains farmers drw excess water ass not displayed.
12 | R122000025 | Khamkhareli Tank | Seoni | WRD | MIS | 2010-03-20 | DDM | 217.74 | RIDF Loan upto 10 crore | HW SW more than 76% completed. Main canal nad branch canal 51-75% completed. Canals 51-75% completed TOR due to delayed LAS.Tests done Records mainatined. Visit records maintained.The project is likely to be completed by 31 March2010
12 | R122000068 | SUKALIA TANK | Bhopal | WRD | MIS | 2010-03-08 | RO Official | 334.76 | RIDF Loan upto 10 crore | Main dam, sluice and spill way were completed. Tenders have been called for canal work. WUA is not formed. Assistance to be displayed on concrete board as metal board was eported to be stolen.
12 | r122000069 | JUNAPANI TANK | Bhopal | WRD | MIS | 2010-03-08 | RO Official | 135.56 | RIDF Loan upto 10 crore | Main dam, sluice and spill way were completed. The project was completed. Tests done Records maintained.Metal board was reported to be stolen. concrete board is to be installed. WUAs are to be formed for maintenance of the project.
12 | r122000070 | BAGSI TANK | Bhopal | WRD | MIS | 2010-03-08 | RO Official | 138.34 | RIDF Loan upto 10 crore | Main dam, sluice and spill way were completed. The project was completed. Tests done Records maintained.Metal board was reported to be stolen. concrete board is to be installed. WUAs are to be formed for maintenance of the project.
12 | R122000067 | OMKARESWAR CANAL PHASE I | Khandwa | NVDA | MJP | 2010-02-22 | OIC+RO Officials | 22945.38 | RIDF Loan 25 crore & above | Only 25 % work was completed in distributaries , minors and sub minorThe project is getting del;ayed due to deferred cleaarnace from forest department , railways and a court case. It requires 6 months to complete the project Cor due to LA cost
12 | R122000040 | Prithvipur Teharka Ghooghsi Road | Tikamgarh | PWD | Road | 2010-02-04 | DDM | 204.59 | RIDF Loan upto 10 crore | The project has been completed.Tests carriedout Visit records not shown Mainatained by Ctr fr 3 yrs. Records amintained. assiustance displayed
12 | R122000031 | Sironja - Pamakhedi - Teelakhedi Road | Sagar | PWD | Road | 2010-02-03 | DDM | 119.72 | RIDF Loan upto 10 crore | bl;lack topping on a small portion of road was satled by LA disputte with farmer. NO COR. Records maintained. Tests carried out.NABARD assistance was not displayed.
12 | R122000059 | Bankhedi Poniya Kakarhata Road | Jabalpur | PWD | Road | 2009-12-22 | DDM | 286.57 | RIDF Loan upto 10 crore | Tor due to lA for cc road in Pnadariya Village.supervised by Deptr,Revords maintained .assistance displayed. Shoulderuing required near Ponadarira vilage. At some places edging is to be done.
12 | R122000057 | Khedi Khar Road | Khandwa | PWD | Road | 2009-12-19 | DDM | 208.57 | RIDF Loan upto 10 crore | The PWD completed execution of 13.4 Km Road in Kalwa block . There was time overrun and no cost overrun.Supervised byPWD. Records maintained.Tests conducted.Mile stones are to be fixed. Damaged patches are to be reapaired.
12 | R122000067 | OMKARESWAR CANAL PHASE I | Khandwa | NVDA | MJP | 2009-09-16 | DDM | 22945.38 | RIDF Loan 25 crore & above | MC > 75% completed. Lining of canal 51-75% CD 51-75% Distri , Minors and sub minors upto 25% completed. TOR due to LA litigations, Forest cleaarnace and RL permission . Likely DOc Dec09. Tests carried out.Monitored by NVDA, Rec mtnd ASSt displa
12 | R122000021 | Deri Triveni Tank | Ratlam | WRD | MIS | 2009-07-03 | OIC | 1625.92 | RIDF Loan 10.01-24.99 crore | Work on l HW,MC and SW is less than 25% completed. Spill way is 25-50% completed. Contacts problem : not implement as per schedule; was terminated; new tendering process was initiated.Tests were carriexd out; Rec main TOR NAB ass displ
12 | R122000080 | PILIYAKHAL DAM | Shajapur | WRD | MIS | 2009-06-02 | DDM | 1118.24 | RIDF Loan 10.01-24.99 crore | SW,HR less than 25% completed. TOR is likely. COR is likely.Monitoring done but inadequate. Tests carried out . Records maintained. TOR due to dely in lA, tendering process. Rehabilitation of habitat in suber area not done .NB ass dis COR RR,LA Hi tendr.
12 | R122000062 | Rampayali- Garra- Chowki- Road | Balaghat | PWD | Road | 2009-05-26 | DDM | 352.8 | RIDF Loan upto 10 crore | EW,WBM,BT,CD more than 70% completed TOR due to rainy season and poor fund flow. Senior engineers visited . Tests done Records werer not shown. Pot holes need to be repaired.
12 | R122000066 | Ashir Dhulkot Road | Burhanpur | PWD | Road | 2009-03-30 | DDM | 110.16 | RIDF Loan upto 10 crore | Recd in Apr 09 EW is only 15% completed. WBM is 10% completed. Contractor;s problem is leading to time overrun
12 | R122000083 | Bargi Diversion Phase-Ii | Jabalpur | NVDA | MJP | 2009-03-17 | RO Officer | 17632.28 | RIDF Loan 25 crore & above | HR,MC,BC,distributories, minors , sub minors more than 76% completed. Lining of canal 51-75% completed. Though tech con was,t involved, qulaitywork satisfactory.Orig DOC Mar 08 to be comple by Dec 09. quality cotl in pll Records main Brg not disp WUA
12 | R122000051 | Jhijhari- Bilahari - Deogaon Road | Katni | PWD | Road | 2009-02-27 | DDM | 360.26 | RIDF Loan upto 10 crore | Road completed. CD not provided At 4Km ,50m patch of 50m damaged. Road connected 18 villages.Cement road in villages is not up to the mark. NAB assistance displayed.
12 | R122000078 | BADWAI TANK | Raisen | WRD | MIS | 2009-02-18 | RO Officer | 279.28 | RIDF Loan upto 10 crore | HW,SW,HR >76%MC 51-75% Sluice gate WW >76%. Reported to be monitored by Sr eng records notshown,Test done records not shown. Ass board dioes not have NABARd address. WUA is yet to be formed.
12 | R122000053 | Lehachua Shikarganj Bharatpur Road | Sidhi | PWD | Road | 2009-01-16 | DDM | 188.88 | RIDF Loan upto 10 crore | LA, EW,WBM,BT and CD more than 76% completed; Visited by senior engineers; Tests carried out; Records maintained; NABARD assistance displayed
12 | R122000081 | RULKI TANK | Shajapur | WRD | MIS | 2009-01-09 | DDM | 151.4 | RIDF Loan upto 10 crore | HW,spill way, head regulator and Main canal more than 76% completed.Quality control system in place; Tssts carried out; Records maintained Dealy in tender La inad moni COr due to La material cost. NABARD assistance not displayed
12 | R122000021 | Deri Triveni Tank | Ratlam | WRD | MIS | 2008-12-30 | DDM | 1625.92 | RIDF Loan 10.01-24.99 crore | Slow progress due to delay on part of contractor and LA on consequent time overrun. New contrcator has been hired. Senior engineers visited Records maintained.Board displayed, not in prescribed format.
12 | R122000038 | Digora Bairwar Jatara Road | Tikamgarh | PWD | Road | 2008-12-19 | RO Officer | 224.08 | RIDF Loan upto 10 crore | Work is 40% complete. Cost overrun is unlikely. No time overrun due to extension of phasing upto 31 March 2009.The project was inspected by senior engineers.Quality control tests carried out. NABARd assistance was displayed.Tests records maintained
12 | R122000026 | Retam Barrage | Mandsaur | WRD | MIP | 2008-12-18 | DDM | 3064.5 | RIDF Loan 25 crore & above | Head works,spill ways, head regu,main canal,branch canal25-50% completed.Spillway 51-75% completed. Time overrun due to delay in LA.Senior engineers visited. Records maintained. NABARD board not displatyed
12 | R122000007 | Khedi Tank | Khandwa | WRD | MIS | 2008-12-12 | DDM | 306.45 | RIDF Loan upto 10 crore | Uoto 25% of spill way work and main canal is completed.Head work is 25-50% completed.Time overrun due to delay in land acquisition.Senior engineeers visited the project. Records maintained.Board not displayed.To be completed by March 2009.
12 | R122000022 | Haliyakhedi Tank | Sehore | WRD | MIS | 2008-12-11 | RO Officer | 103.02 | RIDF Loan upto 10 crore | Dam work is 60% complete. Time over run due to delay in LA for 2.06 Km canal. Senior Engineers visit records not shown. Cost overrun due to LA and higher tender. WUA to be formed after completion
12 | R122000023 | Kalapipal Tank | Sehore | WRD | MIS | 2008-12-11 | RO Officer | 180.25 | RIDF Loan upto 10 crore | EW for dam and spill way completed is 60% and more than 76% respectively. Time over run due to delay in LA for 2.5 Km canal. Senior Engineers visit records not shown. Cost overrun due to LA and higher tender. WUA to be formed after completion
12 | R122000024 | Jharkheda Tank | Sehore | WRD | MIS | 2008-12-11 | RO Officer | 113.02 | RIDF Loan upto 10 crore | EW for dam and spill way completed is 60% and more than 76% respectively. Time over run due to delay in LA for 2.5 Km canal. Senior Engineers visit records not shown. Cost overrun due to LA and higher tender. WUA to be formed after completion
12 | R122000076 | PARASALI TANK | Mandsaur | WRD | MIS | 2008-12-04 | DDM | 588.88 | RIDF Loan upto 10 crore | Spill way, Mian canal, CD are 51-75% completed. Head works and head regulators are more than 76% completed.LA is hampering progress of the project. Senior engineers visit the project.Records maintained .Board displayeed Will benefit 850Ha
12 | R122000044 | Damoh Jamuniya Balakot Road | Damoh | PWD | Road | 2008-11-18 | DDM | 394.14 | RIDF Loan upto 10 crore | Works like LA, EW, Macadam including gravel soiling, black topping and CD are more than 76% completed.Completed on 13 Jan 07. Senior officers visited project. Tests conducted. Test records maintained NAB brd not displ connected 20 vill incr eco activity.
12 | R122000060 | Surdaha Parasmaniya Rampur Maihar Road | Satna | PWD | Road | 2008-11-06 | DDM | 657.6 | RIDF Loan upto 10 crore | EW 51-75% completed WBM >76% BT >76% CD 51-75% TOR due to scarcity of water and contrcator's problem. Sr engineers visited.Quality control system put in place. Test records maintained. NABARD assistance not displayed
12 | R122000072 | IMLIDHANA TANK | Harda | WRD | MIS | 2008-10-24 | DDM | 1717.88 | RIDF Loan 10.01-24.99 crore | No time overrrun .Likely to be completed by Mar 09.Cost escalation due to land cost and material. WRD executives vist regularly.Necessary lan facilities for soil testing. Test records maintained.NAB assis displ Main canal minor and CD in progress
12 | R122000036 | Mahendra Banoli Kota Road | Panna | PWD | Road | 2008-10-23 | DDM | 742.23 | RIDF Loan upto 10 crore | Slow progress. Visited by EE tests done test records maintained Transferred to PMGSY
12 | R122000082 | BARGI DIVERSION PHASE-I | Jabalpur | NVDA | MJP | 2008-10-08 | DDM | 6285.68 | RIDF Loan 25 crore & above | More than 70% work main canal,lining of canal,tunnel and cross drainage.Problems delay in land acquisition,contractor, rains in June 08,shifting of poles. Random tests not doner by NVDA collapse of lining,silting andshrub growth in canal, board not disp
12 | R122000079 | PATHARIYA TANK | Seoni | WRD | MIS | 2008-10-03 | DDM | 149.19 | RIDF Loan upto 10 crore | Delay in compensation for land acquisition,Monitored by executive engineers of WRD. Quality control systems are in place. Records maintained NAB assist not displ. Head work is in progresds . Quality of soil is poor compaction work needs to be improv
12 | R122000083 | Bargi Diversion Phase-Ii | Jabalpur | NVDA | MJP | 2008-09-25 | OIC | 17632.28 | RIDF Loan 25 crore & above | Works on canal prelim,LA,Lining and masonry work is >76% completed.Likely date Dec09.Scope for improving quality of work. reported maintenance of Test and visit records but not shown. Board not disp,enroach of canal,cracks in lining du to pilfering
12 | R122000067 | OMKARESWAR CANAL PHASE I | Khandwa | NVDA | MJP | 2008-09-19 | DDM | 22945.38 | RIDF Loan 25 crore & above | Slow progress Main canal 51-70%,lining 25-50%;distributaries ,amians sub mains<25% Delay due to Litigation, railway approval forest land acquisition, Monitoing and quality test by dept,records maintained few cracks in lining to be rectified,board displa
12 | R122000073 | GANGANALA TANK | Indore | WRD | MIS | 2008-09-12 | DDM | 180.16 | RIDF Loan upto 10 crore | About 50% of haed works and spill ways completed;Time over run due to delay in land acquisition;supervised by the WRD; Quality tests carried out; Project to realise the envisaged benefits;NABARD assistance displyed.
12 | R122000008 | Temla No.1 Tank | Khargone | WRD | MIS | 2008-09-09 | DDM | 147.11 | RIDF Loan upto 10 crore | Head works, canal works 100% completed; Project engineers are monitoring the project;quality tests carried out; test records maintained; cost over ru due to high cost of land acquisition; NABARD assistance displayed.
12 | R122000010 | Bandia Nala Irrigation Tank-Phase-II | Guna | WRD | MIP | 2008-05-26 | DDM | 216.68 | RIDF Loan upto 10 crore | Slow progres. Contractor cited labour problem. Records of quality test are available for perusal . NABARD assistance not displayed
12 | R122000067 | OMKARESWAR CANAL PHASE I | Khandwa | NVDA | MJP | 2008-03-15 | RO Officer | 22945.38 | RIDF Loan 25 crore & above | Acquisition of balance land for the canal to be expedited. Forest land to be cleared by the Ministry of Environment and Forest. Court cases to be followed up. Cracks at few places in the main canal/LBC/RBC to be attended immediately.
12 | r122000025 | Khamkhareli Tank | Seoni | WRD | MIS | 2008-03-11 | Chindwara DDM | 217.74 | RIDF Loan upto 10 crore | NABARD board not displayed. Project implementation is slow.
12 | r122000054 | Sulgaon Nimarkhedi Bangarda Dhangaon Road | Khandwa | PWD | Road | 2008-03-10 | Khandwa DDM | 185.78 | RIDF Loan upto 10 crore | NABARD board not displayed. The road is under construction. The work of the shoulders and the drainage channel are incomplete at some places. The work of CC road is yet to be taken up near railway gate.
12 | r122000074 | GADI TANK | Indore | WRD | MIS | 2008-01-08 | Indore DDM | 90.71 | RIDF Loan upto 10 crore | NABARD board not displayed. Work in regard to Headworks and spillways only 25% progress.
12 | r122000073 | GANGANALA TANK | Indore | WRD | MIS | 2008-01-04 | Indore DDM | 180.16 | RIDF Loan upto 10 crore | NABARD board not displayed. Work is complete upto 25% only.
12 | r122000076 | PARASALI TANK | Mandsaur | WRD | MIS | 2007-12-20 | Mandsaur DDM | 588.88 | RIDF Loan upto 10 crore | NABARD board to be displayed. Surface of the bund needs dressing.
12 | r122000026 | Retam Barrage | Mandsaur | WRD | MIP | 2007-12-11 | Mandsaur DDM | 3064.5 | RIDF Loan 25 crore & above | NABARD board not displayed. Project cost likely to increase. Monitoring by CE, SE AND EE to be done at regular intervals.
12 | r122000021 | Deri Triveni Tank | Ratlam | WRD | MIS | 2007-10-06 | Ratlam DDM | 1625.92 | RIDF Loan 10.01-24.99 crore | Delay in land acquisition. Work by contractor is slow. NABARD board has been displayed.
12 | r122000046 | Kodiya Bandhi Dhuri Pipariya Road | Katni | PWD | Road | 2007-07-05 | Jabalpur DDM | 213.65 | RIDF Loan upto 10 crore | Filling and rolling of the shoulder road work was incomplete. No provision to provide drainage at the village portion of cement road to avoid water logging due to excess water and drainage water from the village houses.
12 | r122000001 | Machhi Tank | Betul | WRD | MIS | 2007-05-31 | Betul DDM | 86.03 | RIDF Loan upto 10 crore | NABARD board has been displayed. Monitoring is being done frequently.
12 | r122000050 | Imaliya - Khamariya - Kunda - Bakal Road | Katni | PWD | Road | 2007-05-29 | Jabalpur DDM | 259.16 | RIDF Loan upto 10 crore | Time overrun due non allotment of requisite funds. NABARD board has been displayed. Regular visit has been taken by the E.Engineer. Construction of road with 3.75 m width has been completed upto 7.2 km.
12 | r122000052 | Bartara Sihundi Salaiya Road | Katni | PWD | Road | 2007-05-29 | Jabalpur DDM | 225.22 | RIDF Loan upto 10 crore | Fillding and rolling of the shoulder work was incomplete. No provision to provide drainage at the village portion of the cement road to avoid water logging due to excess water and drainage water from the village houses.
12 | r122000064 | Ranital Roopnath Bahoribandh Road | Jabalpur | PWD | Road | 2007-05-26 | Jabalpur DDM | 491.9 | RIDF Loan upto 10 crore | Work is in progress. NABARD board has not been displayed. Height of the cement structure constructed at the villages was found not as per specification.
12 | r122000058 | Indrana Ganiyari Murrai Road | Jabalpur | PWD | Road | 2007-05-26 | Jabalpur DDM | 284.62 | RIDF Loan upto 10 crore | Land acquisition was a problem. Fillding of shoulder road has not been done properly. NABARD board has not been displayed. Extension of 3 months has been sought for complete comenting work.
12 | r122000059 | Bankhedi Poniya Kakarhata Road | Jabalpur | PWD | Road | 2007-05-25 | Jabalpur DDM | 286.57 | RIDF Loan upto 10 crore | Delay in acquisition of land. NABARD board has not been displayed.
12 | r122000062 | Rampayali- Garra- Chowki- Road | Balaghat | PWD | Road | 2007-05-17 | Balaghat DDM | 352.8 | RIDF Loan upto 10 crore | NABARD board has been displayed. Monitoring is regular. Records are maintained.
12 | r122000009 | Lakhunder Medium Project: Phase -II-CC Lining of Canal | Shajapur | WRD | MIP | 2007-05-11 | Shajapur DDM | 439.53 | RIDF Loan upto 10 crore | project likely to be completed by March 2008. There has been cost escalation. NABARD board not displayed. Senior officials also to visit the site and closely monitor the work to arrest further cost escalation.
12 | r122000081 | RULKI TANK | Shajapur | WRD | MIS | 2007-05-11 | Shajapur DDM | 151.4 | RIDF Loan upto 10 crore | Department to erect prominent NABARD board at the highway point of deviation leading to the dam site and also at the dam site. Senior officials other than EE may also visit and closely monitor the work to arrest further cost escalation.
12 | r122000072 | IMLIDHANA TANK | Harda | WRD | MIS | 2007-05-09 | Hoshangabad DDM | 1717.88 | RIDF Loan 10.01-24.99 crore | One slice gate is completed upto 80% another slice gate is under progress. Waste weirs and 3 numbers of falls are under progress. Left flank earthwork is 70% complete. Right flank earthwork is under progress. NABARD board has not been displayed.
12 | r122000008 | Temla No.1 Tank | Khargone | WRD | MIS | 2007-04-17 | Khargone DDM | 147.11 | RIDF Loan upto 10 crore | High land cost awarded and hence cost overrun. NABARD board has been displayed.
12 | r122000011 | Charmoli Tank | Khargone | WRD | MIS | 2007-04-16 | Khargone DDM | 81.76 | RIDF Loan upto 10 crore | 50% of headway and spillways work has been completed. NABARD board has been displayed.
12 | r122000030 | Rangir Approach Road | Sagar | PWD | Road | 2007-03-22 | Sagar DDM | 235.02 | RIDF Loan upto 10 crore | Tendering work has been completed. Progress is satisfactory. Likely date of completion is 31 May 2007. Quality is satisfactory. NABARD board has been displayed.
12 | r122000032 | Sagar Bye Pass Road | Sagar | PWD | Road | 2007-03-22 | Sagar DDM | 264.8 | RIDF Loan upto 10 crore | Tendering work has been completed. Progress of work is satsifactory. NABARD board has been displayed. Quality of work is satisfactory.
12 | r122000033 | Bilehra- Nanhi Deori Road | Sagar | PWD | Road | 2007-03-22 | Sagar DDM | 288.94 | RIDF Loan upto 10 crore | Progress of implementation is satisfactory. NABARD board has been displayed. Quality of work is satisfactory.
12 | r122000025 | Khamkhareli Tank | Seoni | WRD | MIS | 2007-03-09 | Chindwara DDM | 217.74 | RIDF Loan upto 10 crore | NABARD board has been displayed. The physical progress is upto 25% only.
12 | R122000082 | BARGI DIVERSION PHASE-I | Jabalpur | NVDA | MJP | 2011-09-19 | RO Official | 6285.68 | RIDF Loan 25 crore & above | Head wrks>76%, (Head Regulator, Main canal, Branch Canal, Canal Lining, Minors and Subminors)each>76%, Distributories:51-75%, Water courses/Field Channels upto 25%. Total progress:95%, Prblms-LA, Fund availability, slow progress by contractors.
12 | R122000083 | Bargi Diversion Phase-Ii | Jabalpur | NVDA | MJP | 2011-09-02 | RO Official | 17632.28 | RIDF Loan 25 crore & above | (Main Canal, Branch Canal, Distributories, Minors & Subminors)each>76%, Canal Lining:51-75%, Total progress 85%, ToR:2 Yrs, CoR:10% NB Brd nt displayed prominently.
12 | R122000082 | BARGI DIVERSION PHASE-I | Jabalpur | NVDA | MJP | 2012-03-15 | HO Official | 6285.68 | RIDF Loan 25 crore & above | (Main Cnl,Cnl Lining,Distrbtries,Minrs&Sb minrs, Cd wrks) each >76%, Field channels:upto76%. Ttl prgrs:95%, Delay-LA, ToR&CoR-contrctr prblm, NB brd nt displayed
12 | R122000083 | Bargi Diversion Phase-Ii | Jabalpur | NVDA | MJP | 2012-03-16 | HO Official | 17632.28 | RIDF Loan 25 crore & above | (Head Rgltr, Main Cnl, Brnch Cnl, Cnl Lining,Distrbtrs, CD wrks each>76%), Minrs&Sb minrs51-75%,Filed Channels:upto25%. Delay-LA, no PERT/CPM Chart,ToR&CoR-contrctrs prblm, NB brd-nil
12 | R122000014 | Tendua Nalla Tank | Chattarpur | WRD | MIS | 2011-10-12 | DDM | 257.93 | RIDF Loan upto 10 crore | Prblms-labr,water,non coprtn frm villagrs,delay in pymnt to cntrctr. Nor maintnce registers, NB brd-nil, filed lvl rvw:(Hdwrks,Splwys,Mn cnl:each26-50%),Mnr&Sbmnrs,Field Channls,Cd wrks-upto25%
12 | R122000019 | Motipura Tank | Rajgarh | WRD | MIS | 2011-11-15 | DDM | 332.19 | RIDF Loan upto 10 crore | ttl physcal prgrs-70%, prblms-LA, CoR-cost escalation.
12 | R122000075 | DEORI HATAI TANK | Katni | WRD | MIS | 2011-07-08 | DDM | 198.7 | RIDF Loan upto 10 crore | (EW,Main cnl,cnl lining,CD wrks)each upto 25%, Hd rgltr>76%.ToR-Contrct sub let wrk: 6 extensions. Poor fund flow, lack of execution skills etc. no record of tests shown. no proper mntrng by dept. no wrk dne durng last yr.
12 | R122000079 | PATHARIYA TANK | Seoni | WRD | MIS | 2011-11-16 | DDM | 149.19 | RIDF Loan upto 10 crore | (Hd wrks,splwys,Mn cnl,brnch cnl,Field chnnl,CD wrks: each>76%) Delayed LA, prjct cmpltd in time. delay in paymnt of cmpnstn.
12 | R122000042 | Kudila Pacher Road | Tikamgarh | PWD | Road | 2011-10-13 | DDM | 214.4 | RIDF Loan upto 10 crore | work completed. prblms-labour,water,delay in payment to contrctr, poor fund flow.maintenance of test record/site visit -nt available. Qlty of road very poor, no maintenance.
12 | R122000002 | Kapasiya Tank | Betul | WRD | MIS |  |  | 70.36 | RIDF Loan upto 10 crore
12 | R122000003 | Pisata Tank | Betul | WRD | MIS |  |  | 37.56 | RIDF Loan upto 10 crore
12 | R122000004 | Sukhakheri Tank | Betul | WRD | MIS |  |  | 71.01 | RIDF Loan upto 10 crore
12 | R122000006 | Lalpani Tank | Damoh | WRD | MIS |  |  | 199.43 | RIDF Loan upto 10 crore
12 | R122000012 | Dahua Tank | Betul | WRD | MIS |  |  | 154.86 | RIDF Loan upto 10 crore
12 | R122000013 | Kheron Tank | Chattarpur | WRD | MIS |  |  | 201.83 | RIDF Loan upto 10 crore
12 | R122000015 | Pandrikhapa Tank | Chhindwara | WRD | MIS |  |  | 249.66 | RIDF Loan upto 10 crore
12 | R122000016 | Khaniamba Tank | Dhar | WRD | MIS |  |  | 376.64 | RIDF Loan upto 10 crore
12 | R122000017 | Neemkhera Barrage | Raisen | WRD | MIS |  |  | 291.19 | RIDF Loan upto 10 crore
12 | R122000018 | Khairasi Tank | Rajgarh | WRD | MIS |  |  | 157.05 | RIDF Loan upto 10 crore
12 | R122000020 | Rampuriya Tank | Ratlam | WRD | MIS |  |  | 23.09 | RIDF Loan upto 10 crore
12 | R122000027 | Khurai- Pathari Road | Sagar | PWD | Road |  |  | 127.82 | RIDF Loan upto 10 crore
12 | R122000029 | Awarmata - Adavan Road | Sagar | PWD | Road |  |  | 57.52 | RIDF Loan upto 10 crore
12 | R122000034 | Udaypura-Babupura-Padariya-Barkheda-Sinkadar Road | Sagar | PWD | Road |  |  | 323.49 | RIDF Loan upto 10 crore
12 | R122000035 | Saptaiya Jharkua Bamhori Pagara Road | Panna | PWD | Road |  |  | 147.51 | RIDF Loan upto 10 crore
12 | R122000039 | Bamhori Mohangarh Road | Tikamgarh | PWD | Road |  |  | 173.32 | RIDF Loan upto 10 crore
12 | R122000041 | Goa Khajuri Road | Tikamgarh | PWD | Road |  |  | 153.7 | RIDF Loan upto 10 crore
12 | R122000043 | Bari Sadpur Road | Damoh | PWD | Road |  |  | 175.45 | RIDF Loan upto 10 crore
12 | R122000045 | Gokulpur Gunawad Road | Indore | PWD | Road |  |  | 229.5 | RIDF Loan upto 10 crore
12 | R122000047 | Kusmi Singpur Bhajiya Pondi Singrampur Road | Damoh | PWD | Road |  |  | 406.9 | RIDF Loan upto 10 crore
12 | R122000048 | Narsinghpur Dhamna Sankal Road | Narsinghpur | PWD | Road |  |  | 123.2 | RIDF Loan upto 10 crore
12 | R122000049 | Bodaman Kahri Road | Rewa | PWD | Road |  |  | 164.94 | RIDF Loan upto 10 crore
12 | R122000055 | Jalkua Bhagiyapur Semliyagudi Road | Khandwa | PWD | Road |  |  | 342.44 | RIDF Loan upto 10 crore
12 | R122000061 | Medki- Lingmara- Dini Road | Balaghat | PWD | Road |  |  | 99.9 | RIDF Loan upto 10 crore
12 | R122000065 | Multai Pisata Virul Bazar Road | Betul | PWD | Road |  |  | 326.58 | RIDF Loan upto 10 crore
12 | R122000071 | GHUDAN KHAPA TANK | Chhindwara | WRD | MIS |  |  | 168.42 | RIDF Loan upto 10 crore
12 | R122000077 | LEDI TANK | Mandsaur | WRD | MIS |  |  | 257.36 | RIDF Loan upto 10 crore
12 | R122000082 | BARGI DIVERSION PHASE-I | Jabalpur | NVDA | MJP | 2013-02-16 | OIC+C | 6285.68 | RIDF Loan 25 crore & above | phy progress-70%, LA- Farmers are not ready to give land easily,delay occur due to court cases & stay is made on the running works, contractors left midway without completing the project, Procedural delays in calling for retenders,ToR-& CoR-Yes,NB Brd-No
12 | R122000067 | OMKARESWAR CANAL PHASE I | Khandwa | NVDA | MJP | 2013-03-16 | OIC+C | 22945.38 | RIDF Loan 25 crore & above | Overall phy progs-44%. Agitation by villagers, slow speed of working agencies. Contractor not handed over completed reaches. Work remains (completed) unattended & in shabby condition. NB Brd-No
12 | R122000082 | BARGI DIVERSION PHASE-I | Jabalpur | NVDA | MJP |  |  | 6285.68 | RIDF Loan 25 crore & above
12 | R122000083 | Bargi Diversion Phase-Ii | Jabalpur | NVDA | MJP | 2014-10-30 | HO Official | 17632.28 | RIDF Loan 25 crore & above | Phy prgs-95%.ToR-LA,CoR-due to price escalation & cost of tendering & LA, NB Brd not displayed, Failure of contractors to complete the work as per schedule time, contractor problem.
13 | r132000002 | Bohna Nalla Tank Project | Chhindwara | WRD | MIS | 2011-01-12 | RO Official | 1347.35 | RIDF Loan 10.01-24.99 crore | No Physical progress as land is yet to be acquired by WRD.Department has received payment for land acquisition only on 26/12/2009.TOR due to delay in LA.Cost overrun due revision in schedule of rates.NABARD board not displayed.
13 | R132000002 | Bohna Nalla Tank Project | Chhindwara | WRD | MIS | 2010-03-27 | DDM | 1347.35 | RIDF Loan 10.01-24.99 crore | No physical progres as LA is yet to be coompleted. Due to and delay in receipt of funds and elections alsdo LA is delayed..Likely to be completed by Mar 12.Tests done. Records amintained.
13 | R132000003 | Likhari Tank Project | Chhindwara | WRD | MIS |  |  | 155.3 | RIDF Loan upto 10 crore
13 | R132000004 | Asrakund Tank Project | Dhar | WRD | MIS |  |  | 318.79 | RIDF Loan upto 10 crore
13 | R132000006 | Dongargaon Tank Project | Indore | WRD | MIS | 2008-09-02 | DDM | 171.29 | RIDF Loan upto 10 crore | About 75 % of spill way work is completed; more than 75% of Haed works is completed;quality trsts carried out; Records maintained Supervised by WRD; Beneficail to the area; NABARD board displayed
13 | R132000007 | Khadi Tank Project | Indore | WRD | MIS | 2009-12-15 | DDM | 283.3 | RIDF Loan upto 10 crore | Land acquisition and head works were more than 76% completed. Spill way, earth work for dam and spill are less than 25% completed. Due to LA problem there is cost and time over run. Since land is yet to be acq for canal Rec mamin Ass dipsla
13 | R132000008 | Bhokriya Tank Project | Khandwa | WRD | MIS | 2008-12-12 | DDM | 144.86 | RIDF Loan upto 10 crore | Head works, spill ways and head regulator is more than 76% completed. Main canal 51-75% completed.Minors and sub minors upto 25% completed.Sr engineers visited. Records maintained. Board not displayed.
13 | R132000009 | Shrinagar Tank Project | Mandsaur | WRD | MIS |  |  | 158.93 | RIDF Loan upto 10 crore
13 | R132000010 | Hadkho Tank Project | Mandsaur | WRD | MIS |  |  | 201.03 | RIDF Loan upto 10 crore
13 | R132000012 | Shahbad Tilendi Tank | Raisen | WRD | MIS |  |  | 432.54 | RIDF Loan upto 10 crore
13 | r132000013 | Kalajhora Tank Project | Raisen | WRD | MIS | 2010-11-24 | RO Official | 270.57 | RIDF Loan upto 10 crore | Main canal > 75% spill ways >75%;sluice gate>75% Tor due to delay in La.reprted to be monitored by senior engineers.records were not shown tests dn recrds maintained NB board not displayed, project almost complete,expenditure undertaken by State Govt
13 | R132000013 | Kalajhora Tank Project | Raisen | WRD | MIS | 2009-02-18 | RO Officer | 270.57 | RIDF Loan upto 10 crore | Main canal upto 25% ;spill ways 51-75%;waste weir >76% Tor due to delay in La.reprted to be monitored by senior engineers records were not shown La for canal yet to be completed;structures fo canals yet to be done. tests dn recrds main ass not displayed
13 | R132000014 | Hanoti Tank | Shajapur | WRD | MIS |  |  | 234.41 | RIDF Loan upto 10 crore
13 | R132000015 | Jamuniya Tank | Chhindwara | WRD | MIS | 2011-05-01 | DDM | 152.86 | RIDF Loan upto 10 crore | Fincial achvmt:91% Project compltd almost in time. LA delayed,delay in payment of cmpnsation.
13 | R132000016 | Panwadi Tank Project | Mandsaur | WRD | MIS | 2012-03-20 | DDM | 155.34 | RIDF Loan upto 10 crore | Work Completed. The project was delayed by 16 months due to delay in Land Acquisition.Main canal retained but Branch canal was deleted from the project as per the requirements of local conditions.
13 | R132000017 | Kharela Tank | Ujjain | WRD | MIS |  |  | 154.38 | RIDF Loan upto 10 crore
13 | R132000018 | Gureha Pipra Tank | Katni | WRD | MIS |  |  | 135.57 | RIDF Loan upto 10 crore
13 | R132000019 | Beejanagaree | Shajapur | WRD | MIS |  |  | 133.15 | RIDF Loan upto 10 crore
13 | R132000020 | Kunwarpura Tank | Mandsaur | WRD | MIS |  |  | 120.09 | RIDF Loan upto 10 crore
13 | R132000021 | Imlia Nala Closure Scheme | Sagar | WRD | MIS | 2012-01-11 | DDM | 116.93 | RIDF Loan upto 10 crore | Hd wrks>76%. ToR due to rain, water in river, contractor complacence.
13 | R132000022 | Jaalkhedi Tank | Mandsaur | WRD | MIS |  |  | 122.3 | RIDF Loan upto 10 crore
13 | R132000023 | Nayapura Tank | Raisen | WRD | MIS |  |  | 103.05 | RIDF Loan upto 10 crore
13 | R132000024 | Bichhiya Weir | Sagar | WRD | MIS | 2009-02-20 | DDM | 85.71 | RIDF Loan upto 10 crore | only head worksd is more than 76% completed. Slow progress by the contractors. Visited by Sr engineers Tests carried out. Records were not shown. NABARd assistance not displayed.
13 | R132000024 | Bichhiya Weir | Sagar | WRD | MIS | 2012-01-11 | DDM | 85.71 | RIDF Loan upto 10 crore | Hd wrks>76%. ToR due to rain, water in river, cntrctr complacence.
13 | R132000025 | Vijaypur Weir | Sagar | WRD | MIS | 2012-01-12 | DDM | 83.24 | RIDF Loan upto 10 crore | Hd wrks>76%. ToR due to rain, water in river, contractor complacence.
13 | R132000026 | Duttapura Nalla Closure Scheme | Sagar | WRD | MIS | 2009-02-20 | DDM | 78.76 | RIDF Loan upto 10 crore | Only Head works is more than 76% completed. TOr due to contractor's problem. COR due to higher % of tender and change in the desig of weir. Tests carried out Sr engineers vsited . NABARD assistance not displayed. Due to closure of nala, water recharg
13 | R132000026 | Duttapura Nalla Closure Scheme | Sagar | WRD | MIS | 2012-01-12 | DDM | 78.76 | RIDF Loan upto 10 crore | Hd wrks>76%. ToR due to rain, water in river, contractor complacence.
13 | R132000027 | Karonda Tank | Katni | WRD | MIS |  |  | 92.4 | RIDF Loan upto 10 crore
13 | R132000028 | Simraha Tank | Katni | WRD | MIS |  |  | 88.09 | RIDF Loan upto 10 crore
13 | R132000029 | Lahori Tank | Shajapur | WRD | MIS |  |  | 86.93 | RIDF Loan upto 10 crore
13 | R132000030 | Palsoda Solid Weir | Neemuch | WRD | MIS | 2009-03-27 | DDM | 45.12 | RIDF Loan upto 10 crore | BC,lining of canaldistributaries and field channel are more than 76% completed No TOr COR due to higher % of tender Tests carried out NABARd assistance not displayed benefited 61 Ha
13 | R132000031 | Tulsapura Tank | Ujjain | WRD | MIS | 2009-11-17 | DDM | 65.85 | RIDF Loan upto 10 crore | Head works, Main canal and Cross drainage works is more than 75% completed. TOR due to delay in LA. COR due to LA. Tests done Records maintained and NABARd assistance was not displayed.
13 | R132000032 | Salakhedi Barrage | Ujjain | WRD | MIS |  |  | 54.73 | RIDF Loan upto 10 crore
13 | R132000033 | Dongargaon Pickup Weir | Shajapur | WRD | MIS | 2011-11-02 | DDM | 67.15 | RIDF Loan upto 10 crore | Work complete, however delayed by 6 months. ToR & CoR due to election.
13 | R132000034 | Bijaura Tank | Katni | WRD | MIS |  |  | 61.91 | RIDF Loan upto 10 crore
13 | R132000035 | Kalukheda Koyalaghat Barragecumcaus | Ujjain | WRD | MIS |  |  | 47.77 | RIDF Loan upto 10 crore
13 | R132000036 | Manasa Pickup Weir | Shajapur | WRD | MIS |  |  | 55.86 | RIDF Loan upto 10 crore
13 | R132000037 | Bagula Mukhi Pickup Weir | Shajapur | WRD | MIS | 2009-06-02 | DDM | 55.53 | RIDF Loan upto 10 crore | Project comprises Head work only and is 95% completed.Monitoring done by senior engineers. Quality control; tests done. Records maintainedSlow fund flow had resulted in time over run COr is due to higher tender result in CE. NABARD assis not displayed.
13 | R132000038 | Arjun Baroda Tank | Indore | WRD | MIS |  |  | 41.69 | RIDF Loan upto 10 crore
13 | R132000039 | Dehri Gurjar Pickup Weir | Shajapur | WRD | MIS |  |  | 51.12 | RIDF Loan upto 10 crore
13 | R132000041 | Shivghat Barrage | Ujjain | WRD | MIS |  |  | 41.97 | RIDF Loan upto 10 crore
13 | R132000042 | Mahurikhema Barrage | Ujjain | WRD | MIS | 2012-03-26 | DDM | 17.29 | RIDF Loan upto 10 crore | Work Completed with 3 months delay. NB Brd-Not displayed
13 | r132000043 | Dharola Pick-up Weir | Shajapur | WRD | MIS | 2011-02-09 | DDM | 46.67 | RIDF Loan upto 10 crore | Work is complete in all the aspects.NB board displayed.Records ,aintained.Time over run and Cost over run
13 | R132000043 | Dharola Pick-up Weir | Shajapur | WRD | MIS | 2008-05-13 | DDM | 46.67 | RIDF Loan upto 10 crore | Project to be completed by 31-12-08; satisfactory progressCost over run by Rs.15.70 Lakh due to higher percentage of tender;quality tests carried out; Supervision by the WRD; NABARD assistance displayed
13 | R132000044 | Arrolia Dewra Barrage | Ujjain | WRD | MIS |  |  | 26.85 | RIDF Loan upto 10 crore
13 | R132000045 | Malhargarh Barrage | Ujjain | WRD | MIS | 2010-12-06 | DDM | 25.54 | RIDF Loan upto 10 crore | EW, gate fixing and cement concrete are more than 76% completed. Delay due to contrcator's problem and poor follow up by the WRD. Tests conducted. Records maintained. NAB asistance not displayed. Tendr process has selec contr with nil exp, resulted TOR
13 | R132000045 | Malhargarh Barrage | Ujjain | WRD | MIS | 2009-02-27 | DDM | 25.54 | RIDF Loan upto 10 crore | The progress is only 51-75% .To be completed by Mar 09.Sub eng visit regularly. Senr engineers visit during the progress of work. Contractor does't possess experience Order book maintained Ass not displayed.
13 | R132000046 | Bhilkhedi Weir | Shajapur | WRD | MIS | 2008-05-13 | DDM | 44.59 | RIDF Loan upto 10 crore | Project to be completed by 31-12-08; Satisfactory Progress; Cost over run by Rs.19.72 Lakh due to higher percentage of tender;quality tests carried out;records maniatrained ; supervision by the WRD;NABARD assistance displyed.
13 | R132000047 | Gundarlia Barrage | Ujjain | WRD | MIS | 2009-02-27 | DDM | 38.31 | RIDF Loan upto 10 crore | Work is 51-75% completed. Contractor does't have expertise. Manually gates have been stolen or opened by viallgers leading to defeated purpose. Instaed capstan/radial gates can be installed. Ass not displayed
13 | R132000048 | Bilkeshwar (Dhaturia) Barrage | Ujjain | WRD | MIS |  |  | 32.99 | RIDF Loan upto 10 crore
13 | R132000049 | Saloda Solid Weir | Neemuch | WRD | MIS |  |  | 18.08 | RIDF Loan upto 10 crore
13 | R132000050 | Burhi Barlai Tank | Indore | WRD | MIS |  |  | 25.51 | RIDF Loan upto 10 crore
13 | R132000051 | Shekhpur Barrage | Ujjain | WRD | MIS | 2009-02-27 | DDM | 32.01 | RIDF Loan upto 10 crore | Work is more than 76 % completed. To be completed by March 09. Contractor does' t have experience. Manually operated gates rae stolen or removed by DS villagers leading to defeated purpose. Instead capstan/radial gates can be installed. Asss not diplaye
13 | R132000052 | Kachhala Solid Weir | Neemuch | WRD | MIS |  |  | 1.86 | RIDF Loan upto 10 crore
13 | r132000053 | Indira Sagar Proj PhI &II | Khandwa | NVDA | MJP | 2011-01-24 | RO Official | 4480.48 | RIDF Loan 25 crore & above | HW,HR,SW 100% complete,LBC ph. I 80% & II 70% complete.TOR due to Forest clearenceproblem, labour shortage,contractor problem.NB board displayed.monitoring visits & QC tests undertaken.
13 | R132000053 | Indira Sagar Proj PhI &II | Khandwa | NVDA | MJP | 2010-03-25 | DDM | 4480.48 | RIDF Loan 25 crore & above | MC and LOC are 85% and 80% completed respectivdely. BC distributaries, minors and subminors are 60% completed. TOR due legal problems in LA . Likely to be completed in 2012..NVDA is mintoring, Records mainatained. Quality control tests done.
13 | R132000053 | Indira Sagar Proj PhI &II | Khandwa | NVDA | MJP | 2009-02-11 | DDM | 4480.48 | RIDF Loan 25 crore & above | Main canal & lining >76% completed; Distributaries and sub minors upto 25% completed.quality control tests carried out. Records maintained. Sen engineers visited. NABARD assistance not displayed.
13 | R132000053 | Indira Sagar Proj PhI &II | Khandwa | NVDA | MJP | 2013-03-15 | OIC+C | 4480.48 | RIDF Loan 25 crore & above | LA & Fund flow problem.Slow progs of construction agencies. ToR-Yes(17% is yet to be completed). Phy progs-64%. NB Brd-No
13 | R132000054 | Luharra-Kandipur-Chainpura-Hindoriy | Damoh | PWD | Road |  |  | 83.47 | RIDF Loan upto 10 crore
13 | R132000055 | Hindoriya- Pipariya-Ronda Road | Damoh | PWD | Road |  |  | 67.39 | RIDF Loan upto 10 crore
13 | R132000056 | Anoo- Bandakpur road | Damoh | PWD | Road | 2009-03-06 | DDM | 91.83 | RIDF Loan upto 10 crore | LA,EW >76% completed WBM CD 26-50% Bt upto 25% Poor fund flow is leading to TOR. NABARD assistance not disdplayed tests carried out , Records maintained. Sr Engineers visited
13 | R132000057 | Sanai Talwada Siganpur Road | Guna | PWD | Road |  |  | 122.4 | RIDF Loan upto 10 crore
13 | R132000058 | Ratatalai - Mangrul road | Harda | PWD | Road | 2008-05-13 | DDM | 101.18 | RIDF Loan upto 10 crore | NABARD assistance is not displayed. There has been time over run.
13 | R132000059 | Kamadpur- Chainpura- Khedi- Sihod r | Indore | PWD | Road |  |  | 63.94 | RIDF Loan upto 10 crore
13 | R132000060 | Kanjarda - Diken road | Neemuch | PWD | Road | 2012-03-21 | DDM | 291.98 | RIDF Loan upto 10 crore | Work cmpltd with 29 months delay. Delay due to contractors inability to complete the work in prescribed time limit.
13 | R132000061 | Seamou-Pipaliya-Tada Road | Raisen | PWD | Road |  |  | 151.68 | RIDF Loan upto 10 crore
13 | R132000062 | Chandan Pipaliya Pratapgarh Road | Raisen | PWD | Road |  |  | 260.32 | RIDF Loan upto 10 crore
13 | r132000063 | Bhyana Karlawad Road | Rajgarh | PWD | Road | 2011-02-24 | DDM | 342.08 | RIDF Loan upto 10 crore | LA,EW,WBM,BT,CD works 100% complete.
13 | R132000064 | Semali Ramgarh Road | Rajgarh | PWD | Road |  |  | 254.43 | RIDF Loan upto 10 crore
13 | R132000065 | Bonda Sendri Umari Kandara Kotari R | Rajgarh | PWD | Road |  |  | 312.69 | RIDF Loan upto 10 crore
13 | R132000066 | Pidarua to Sagar Malthone Approach | Sagar | PWD | Road |  |  | 123.1 | RIDF Loan upto 10 crore
13 | R132000067 | Longar-Semra-Lodhi-Parson-Madiya-Ro | Sagar | PWD | Road |  |  | 198.75 | RIDF Loan upto 10 crore
13 | r132000068 | Bilkishganj to Neebukheda Road | Sehore | PWD | Road | 2010-11-25 | RO Official | 184.06 | RIDF Loan upto 10 crore | Work almost complete. work delayed due to delay in clearence from forest department & poor fund flow, patch of road damaged due to change in level Nabard board displayed
13 | R132000068 | Bilkishganj to Neebukheda Road | Sehore | PWD | Road | 2010-02-15 | RO Official | 184.06 | RIDF Loan upto 10 crore | LA,EW,WBM, BT and CD are more than 76% completed. Monitrg done by the dept. Tests done. Rec maintain .TOR due clearance from MP forest dep for constructiion of Km road in forest area. completed . Ew on shoul willbe complete in Feb 10 Asst not display
13 | r132000069 | Charnal-Chadwad- Gawa-Parasone road | Sehore | PWD | Road | 2010-11-25 | RO Official | 398.69 | RIDF Loan upto 10 crore | G-III Work complete.BT work done in 2 Km but being relaid.BT les than 25% complete. Work delayed due to change of allignment. Nabard Board not displayed.
13 | R132000070 | Nandi - Shaila - Umarwada road | Seoni | PWD | Road |  |  | 185.33 | RIDF Loan upto 10 crore
13 | R132000071 | Maili - Tikari - Partapur road | Seoni | PWD | Road |  |  | 121.59 | RIDF Loan upto 10 crore
13 | R132000072 | Gulana -Sakatkhedi-Nichma-Bumtalai | Shajapur | PWD | Road |  |  | 116.28 | RIDF Loan upto 10 crore
13 | R132000073 | Bachchukheda Runaheda Road | Ujjain | PWD | Road |  |  | 231.92 | RIDF Loan upto 10 crore
13 | R132000074 | Chheerkheda to Nimkheda Road | Vidisha | PWD | Road | 2008-11-19 | DDM | 39.74 | RIDF Loan upto 10 crore | Good progress No time overrrun project was completed on 29 Dec07. Senior engineers' visit records were not shownQuality tests carried out. Test records were maintained.As against 4kM 3.56 Km was constructed due to interception of rivulet.Bri un Construc
13 | R132000075 | Kodi Mehgaon Sothiya Vidisha Road | Vidisha | PWD | Road |  |  | 90.36 | RIDF Loan upto 10 crore
13 | R132000076 | Mudra-Murraiya to Barkheda Jagir ro | Vidisha | PWD | Road | 2008-12-04 | DDM | 365.49 | RIDF Loan upto 10 crore | LA,EW,WBM, black topping and CD work is more than 75% complete.NO cost and time over run. Visited by senior engineers.Quality tests conducted. NABARD assistance is displayed. Construction of road is expected to be over in a month
13 | R132000077 | Madhura Bagal Harukhedi to Basoda S | Vidisha | PWD | Road | 2008-12-04 | DDM | 91.19 | RIDF Loan upto 10 crore | Works like LA, EW,WBM, black topping and CD are more than 75% completed.Visited by senior engineers; quality tests carried ou; Time over run due to contractor's delay. TL 33Km 8Km un PMGSY.Assist displayed. likelly DOC DEC 08
13 | R132000078 | Ashoknagar Thubon Piplod Road | Ashoknagar | PWD | Road | 2012-01-04 | DDM | 246.35 | RIDF Loan upto 10 crore | Project completed with 6 months delay.monitoring system by PWD nt adhered. No test report shown. No register of order book/site visit. NB brd displayed bt nt as per specification. Poor qlty materials used. Road requires repair.
13 | R132000079 | Sehrai Achalgarh Piprai Road | Ashoknagar | PWD | Road |  |  | 180.26 | RIDF Loan upto 10 crore
13 | R132000080 | Balai Karaila Mata Mandir Road | Ashoknagar | PWD | Road |  |  | 172.39 | RIDF Loan upto 10 crore
13 | R132000081 | Katedara - Tirodi -Khawasa Road | Balaghat | PWD | Road |  |  | 197.19 | RIDF Loan upto 10 crore
13 | R132000082 | Halditola -Badgaon -Dahedi- Mate - | Balaghat | PWD | Road |  |  | 218.85 | RIDF Loan upto 10 crore
13 | R132000083 | Gohad- Dhamasha-Dhanulli road | Bhind | PWD | Road | 2009-12-24 | DDM | 267.22 | RIDF Loan upto 10 crore | EW and WBM more than 76% completed. Black topping 51-75% completed. Records maintained. Tests carried out. COR due to higher tender percentage. Tor due to poor fund flow. NABARD assistance not displayed
13 | R132000084 | Newton Mayavadi Road | Chhindwara | PWD | Road |  |  | 26.26 | RIDF Loan upto 10 crore
13 | R132000085 | Bansa - Deoran- Bhouransa Road | Damoh | PWD | Road |  |  | 85.97 | RIDF Loan upto 10 crore
13 | R132000086 | Bandakpur Hindoriya Road | Damoh | PWD | Road |  |  | 80.15 | RIDF Loan upto 10 crore
13 | r132000087 | Bhander - Sarsai - Dhamna Road | Datia | PWD | Road | 2011-03-10 | DDM | 337.74 | RIDF Loan upto 10 crore | CD wrk more than 76%,WBM upto 25%,EW more than 51% complete.TOR due to cntrctrs problm and floating of fresh tenders.NB board was not on the project site
13 | r132000088 | Kuda-Chandrani road | Dindori | PWD | Road | 2011-02-25 | DDM | 201.07 | RIDF Loan upto 10 crore | Damages were observed in CC portion of the road and needs urgent repair before onset of monsoon. NABARD board not displayed at the site.
13 | R132000089 | Ralamandal Tillorekhurd Tillorebuzu | Indore | PWD | Road |  |  | 176.21 | RIDF Loan upto 10 crore
13 | R132000090 | Pondi - Bhita - Kainthra - Khatolid | Jabalpur | PWD | Road |  |  | 100.8 | RIDF Loan upto 10 crore
13 | R132000091 | Tilsani- Baghraji Road | Jabalpur | PWD | Road | 2009-11-07 | DDM | 340 | RIDF Loan upto 10 crore | Work is under progres. Permission from Forest Depat awaited Supervised by the de[partment. Tests conducted. Records maintained. NABARD assistance is displayed.
13 | R132000091 | Tilsani- Baghraji Road | Jabalpur | PWD | Road | 2009-02-04 | DDM | 340 | RIDF Loan upto 10 crore | EW 51-75% BT <25% WBM and CD >75% Visited by engineers, Tests carried out records maintained. Slow progress due to delay in fund flow .NAB assistance not displayed
13 | r132000092 | Sihora - Gourkha - Nandghat Road | Jabalpur | PWD | Road | 2011-03-29 | DDM | 329.31 | RIDF Loan upto 10 crore | LA,EW,WBM,BT,CD more than 76% complete.TOR due to delay in land acquisition due to ressistance from villagers,slow work by contractor & poor fund flow.Shouldering of road left incomplete.Some 100m of road had bad patches near ganjtal village.
13 | R132000093 | Kudam - Chiraipani road | Jabalpur | PWD | Road | 2009-11-07 | DDM | 220 | RIDF Loan upto 10 crore | Road is completed. COR due to higher tender %. Project inspected by PWD. Records maintained. Tests carried.NABARD assistance displayed
13 | R132000094 | Kanjai - Sakri - Andua - Singaldip | Jabalpur | PWD | Road |  |  | 86.96 | RIDF Loan upto 10 crore
13 | R132000095 | Ponda - Bachaiya Road | Katni | PWD | Road |  |  | 255 | RIDF Loan upto 10 crore
13 | R132000096 | Vijayraghavgarh- Kharkhri-Padkhuri | Katni | PWD | Road | 2009-02-20 | DDM | 314.7 | RIDF Loan upto 10 crore | TOR due to slow flow of funds. Sr engineers visited, Quality tests carried Test reccord not shown. NAB ass displayed. BT is pending due to paucity of funds; Damaged by heavy rains. Shouldering to be done immediately
13 | R132000097 | Sleemnabad Bahoriband Road | Katni | PWD | Road |  |  | 182.2 | RIDF Loan upto 10 crore
13 | R132000098 | Katni-Kailwara- Kharkhari -Hathkuri | Katni | PWD | Road | 2009-02-27 | DDM | 249.08 | RIDF Loan upto 10 crore | Engineers regularly viisted th eproject; Quality control insatlledts.Test record not shown . assistance displayed.Road is completeFilling &rolling of shoulder At 14 Km One Km Seal coat is to be done.At12/2Km, Phase volve to be provided to construct sho
13 | r132000099 | Vilayatkalan Ganeshpur Salhna Road | Katni | PWD | Road | 2011-01-27 | DDM | 421.54 | RIDF Loan upto 10 crore | EW,WBM,CD,BT more than 76% complete.shouldering of work yet to be done.poor fund flow due to non-availabiliy of funds.Road damaged due to putting up of irrigation pipes on road.TOR due to poor fund flow.10m cc work yet to be done by contractor.
13 | R132000100 | Bartari- Pakar - Masandha -Bakal ro | Katni | PWD | Road |  |  | 211.11 | RIDF Loan upto 10 crore
13 | R132000101 | Dharampuri-Garangaon-Bhagwanpur roa | Khandwa | PWD | Road | 2009-12-19 | DDM | 208.27 | RIDF Loan upto 10 crore | The PWD completed execution of 14.50 Km Road in Pandhana block . There was time overrun and no cost overrun.Supervised by PWD. Records maintained.Tests conducted.Damaged patches are to be reapaired.
13 | R132000102 | Mandla Pindrai Nainpur Road | Mandla | PWD | Road |  |  | 213.63 | RIDF Loan upto 10 crore
13 | R132000103 | Bichhiya Danitola Ghughri Road | Mandla | PWD | Road |  |  | 156.36 | RIDF Loan upto 10 crore
13 | R132000104 | Suwasra Guradiya Kalan Road | Mandsaur | PWD | Road |  |  | 236.53 | RIDF Loan upto 10 crore
13 | r132000105 | Malhargarh Narayangarh Road | Mandsaur | PWD | Road | 2011-03-11 | DDM | 66.55 | RIDF Loan upto 10 crore | EW,WBM,BT more than 76% complete.TOR due to slow progress,delay in calling tender,non availability of resources,COR due to high cost tender.
13 | R132000106 | Runija Angari Road | Mandsaur | PWD | Road |  |  | 138.32 | RIDF Loan upto 10 crore
13 | R132000107 | Chichli Link road | Narsinghpur | PWD | Road | 2010-03-12 | DDM | 88.73 | RIDF Loan upto 10 crore | Project is completed TOR and COR COR due higher tende percentage.Testsdone Records maintained NAB assist displayed.Shoulders neeed partial repaier.Revised estimates to be submitted by the PWD to GoMP
13 | r132000108 | Narsinghpur Devkachachar Road | Narsinghpur | PWD | Road | 2011-02-24 | DDM | 232.78 | RIDF Loan upto 10 crore | EW,WBM,BT,CD works more than 76% complete.many pot holes & bad patches on road.caution boards yet to be provided.contractor is not taking interest in repair so new tenders are invited by report.
13 | R132000108 | Narsinghpur Devkachachar Road | Narsinghpur | PWD | Road | 2010-03-12 | DDM | 232.78 | RIDF Loan upto 10 crore | The project is completed. TOR due to slow pace of contractor. COR due to higher tender percentage..Partly dmagaed shoulders need repair.Potholes in chainage 2-8 to 2-6 need to be repaired. NAB asistance borad to installed. Testsd done records maintai
13 | R132000109 | Podar - Salichouka- Barha Road | Narsinghpur | PWD | Road |  |  | 291.2 | RIDF Loan upto 10 crore
13 | R132000110 | Manasa - Arniamali - Bordiakala roa | Neemuch | PWD | Road |  |  | 196.6 | RIDF Loan upto 10 crore
13 | R132000111 | Bhatkhedi - Jamunia Rao Ji - Lasoor | Neemuch | PWD | Road |  |  | 162.65 | RIDF Loan upto 10 crore
13 | r132000112 | Talen - Kudlasa Road | Rajgarh | PWD | Road | 2011-02-24 | DDM | 84.02 | RIDF Loan upto 10 crore | LA,EW,WBM,BT,CD works 100% complete.No COR or TOR observed.lab establihed at site.
13 | R132000113 | Chhapikheda- Nalkheda Road | Rajgarh | PWD | Road |  |  | 98.86 | RIDF Loan upto 10 crore
13 | R132000114 | Alot-Talode road | Ratlam | PWD | Road | 2010-03-27 | DDM | 214.7 | RIDF Loan upto 10 crore | LA,EW,WBM,BT and Cd are >76% completed. COR due to higher tender% quoted by CTCR.quality conttorl tests done. Supervuised by PWD. Km stone not install, 30m length road needs recast. CD to be done at 7/9 KM NAB assistance not displayed
13 | R132000115 | Dhodhar - Rola road | Ratlam | PWD | Road | 2008-12-26 | DDM | 37.33 | RIDF Loan upto 10 crore | Work is more than 76% completed.Time overrun due to LA, inter departmental tussle and contractor's delay. A portion cut by ID needs repairs. Shoulder dressing and milestone fixation are yet to be done. Board not installed due to threat of theft.
13 | R132000116 | Bahera Dabar Piparahi Road | Rewa | PWD | Road |  |  | 352 | RIDF Loan upto 10 crore
13 | R132000117 | Pratapganj Hata Road | Rewa | PWD | Road |  |  | 284.98 | RIDF Loan upto 10 crore
13 | r132000118 | Deo Talab Naigarhi Road | Rewa | PWD | Road | 2011-01-28 | DDM | 244.27 | RIDF Loan upto 10 crore | LA,EW,WBM,BT,CD Works more than 76% complete.TOR due to extra work which was sanctioned by competent authority(escalation).
13 | R132000118 | Deo Talab Naigarhi Road | Rewa | PWD | Road | 2009-01-29 | DDM | 244.27 | RIDF Loan upto 10 crore | lA,EW,WBM and CD more than 76% completed. BT less than 25% Sr engineeers visited, Records maintained Tests carried out . NABARD assistance displayed.
13 | R132000119 | Naigarhi Garh road | Rewa | PWD | Road |  |  | 227.12 | RIDF Loan upto 10 crore
13 | R132000120 | Deotalab- Garh Road | Rewa | PWD | Road |  |  | 218.02 | RIDF Loan upto 10 crore
13 | R132000121 | Kuthuliya Hardi Road | Rewa | PWD | Road |  |  | 181.33 | RIDF Loan upto 10 crore
13 | R132000122 | Ichhawar- Ramnagar Road | Sehore | PWD | Road |  |  | 180.4 | RIDF Loan upto 10 crore
13 | R132000123 | Jamoniya- Semradangi Road | Sehore | PWD | Road |  |  | 124.16 | RIDF Loan upto 10 crore
13 | R132000124 | Sunwara - Pindrai - Keolari Road | Seoni | PWD | Road |  |  | 32.18 | RIDF Loan upto 10 crore
13 | R132000125 | Gohparu - Rasmohni- Burhar road | Shahdol | PWD | Road | 2010-03-29 | DDM | 696.92 | RIDF Loan upto 10 crore | Physical progrees statistics show that project is completed in all respects except black topping. But field visit revealed that contractor has abdoned the pro and even BT patch cracks and worn out . QC . Reor & Sup slack. tender proc frr new contrc
13 | R132000126 | Kanad-Pachlana Road | Shajapur | PWD | Road | 2009-06-02 | DDM | 68.36 | RIDF Loan upto 10 crore | The project was completed on time No TOR. No CORTsts done Reciords maintained. NABARD board not displayed.Pot holes need to be repaired. Shoulders required to be provided.Approaches were to be levelled upto the level of CD
13 | R132000127 | Sundarsi-Khadi- Polay -Piparanva Ro | Shajapur | PWD | Road |  |  | 255.58 | RIDF Loan upto 10 crore
13 | R132000128 | Digora Mohangarh Road | Tikamgarh | PWD | Road |  |  | 109.66 | RIDF Loan upto 10 crore
13 | R132000129 | Dablafanth - Sipawara Road | Ujjain | PWD | Road |  |  | 178.04 | RIDF Loan upto 10 crore
13 | R132000130 | Gogapur-Bappiya-Zutawad-Ranayarapee | Ujjain | PWD | Road |  |  | 198.37 | RIDF Loan upto 10 crore
13 | R132000131 | Zarda- Gelakhedi Nagpura road | Ujjain | PWD | Road |  |  | 89.22 | RIDF Loan upto 10 crore
13 | R132000132 | Sasstra Kathotiya Road | Umaria | PWD | Road |  |  | 73.73 | RIDF Loan upto 10 crore
13 | R132000133 | Barhi Singroli Manpur Road | Umaria | PWD | Road |  |  | 178.78 | RIDF Loan upto 10 crore
13 | R132000134 | HLB a/c Goi river in KM 1/6 | Badwani | PWD | Bridge |  |  | 233.16 | RIDF Loan upto 10 crore
13 | R132000135 | HLB a/c Khar Nala in KM 2/2 | Bhind | PWD | Bridge |  |  | 49.07 | RIDF Loan upto 10 crore
13 | r132000136 | SB a/c Morar river in KM 2/2 | Bhind | PWD | Bridge | 2011-02-22 | DDM | 51.82 | RIDF Loan upto 10 crore | Foun. more than 51% complete,Abutment more than 76% complete,App. road upto 25% complete.TOR due to delay in LA.COR due to delay in completion of project.NB board not displayed.
13 | r132000137 | SB a/c Vasily river in KM 1/2 | Bhind | PWD | Bridge | 2011-02-22 | DDM | 40 | RIDF Loan upto 10 crore | Foun.,pier,abutment,sup.str. more than 76% complete.App. road upto 25% complete.TOR due to delay in LA.COR due to delay in completion.NB board not displayed.
13 | R132000138 | HLB a/c Vasily river in KM 1/2 | Bhind | PWD | Bridge |  |  | 91.7 | RIDF Loan upto 10 crore
13 | R132000139 | HLB a/c Kunwari river in KM 2/2 | Bhind | PWD | Bridge | 2010-03-28 | DDM | 823.68 | RIDF Loan upto 10 crore | Foundation and piers <25% completed COR - high tender %. Poor fund flowe, delay in approval of design. LA amount yet to be relesedby Revenue dept. Department supervised Tests carried out . Records maintained.
13 | R132000140 | HLB a/c Vasily river in KM 1/4-6 | Bhind | PWD | Bridge |  |  | 90.76 | RIDF Loan upto 10 crore
13 | R132000141 | HLB a/c Gouraiya river in KM 79/10 | Damoh | PWD | Bridge |  |  | 124.72 | RIDF Loan upto 10 crore
13 | R132000142 | HLB a/c Gouraiya river in KM 71/10 | Damoh | PWD | Bridge |  |  | 106.03 | RIDF Loan upto 10 crore
13 | R132000143 | SB a/c Bairma river | Damoh | PWD | Bridge | 2009-12-17 | DDM | 268.2 | RIDF Loan upto 10 crore | Foundation, pier,abutment and superstructure were more than 76% completed.Approach road 51-75% completed. Tssts carried out. Records maintained. The bridge will reduce travelling distance and connects to markets in Damoh. NAB ass not displayed.
13 | R132000144 | HLB a/c Sindh river in KM 2/2 | Datia | PWD | Bridge | 2010-03-18 | OIC | 486.75 | RIDF Loan upto 10 crore | Works like superstructure and others are to be done. TOR poor planning, delay in payment to contractor.Mon to be intensely. REcords maintained Tests done.
13 | R132000145 | HLB a/c Sukni river in KM 6/6 | Harda | PWD | Bridge |  |  | 77.23 | RIDF Loan upto 10 crore
13 | R132000146 | HLB a/c Abna river in KM 3/8 | Khandwa | PWD | Bridge |  |  | 51.06 | RIDF Loan upto 10 crore
13 | R132000147 | HLB a/c Karanj Nalla in KM 6/4 | Khandwa | PWD | Bridge |  |  | 66.65 | RIDF Loan upto 10 crore
13 | R132000148 | HLB a/c Siltiya Nalla in KM 3/2 | Khandwa | PWD | Bridge |  |  | 38.84 | RIDF Loan upto 10 crore
13 | R132000149 | HLB a/c Ghorwa river in KM 2/6 | Khandwa | PWD | Bridge |  |  | 56.02 | RIDF Loan upto 10 crore
13 | R132000150 | HLB a/c Sukta river in KM 13/6 | Harda | PWD | Bridge |  |  | 145.47 | RIDF Loan upto 10 crore
13 | R132000151 | HLB a/c Lasudia Nallah in KM 18/10 | Mandsaur | PWD | Bridge |  |  | 67.12 | RIDF Loan upto 10 crore
13 | r132000152 | SB a/c Ken river in KM 15/2 | Panna | PWD | Bridge | 2011-03-12 | DDM | 936.11 | RIDF Loan upto 10 crore | LA,Foun.,pier,abutment,S.S. more than 76% App. Road more than 51% complete.TOr due to change in design.LA for app. road is pending due to opposition by farmers.
13 | R132000152 | SB a/c Ken river in KM 15/2 | Panna | PWD | Bridge | 2009-11-10 | DDM | 936.11 | RIDF Loan upto 10 crore | LA 51-75% completed. Foundation and abutment 25-50% completed Super structure and approach Road upto 25% hange in design lading to COR. LA for approach road to be completed. Dept is monitoring. Tests are also done.NABA as displayed
13 | R132000153 | HLB a/c Khand river in KM4 | Raisen | PWD | Bridge |  |  | 87.06 | RIDF Loan upto 10 crore
13 | R132000154 | HLB a/c Ugal river in KM 22/10 | Rajgarh | PWD | Bridge | 2009-05-27 | DDM | 128.61 | RIDF Loan upto 10 crore | Work not commenced yet.Inadequate moni. Delay in tender leading to TOR COR due to adoption of the latraest SOR. NAB assitance not displayed
13 | R132000155 | SB a/c Parvati river | Rajgarh | PWD | Bridge | 2009-05-27 | DDM | 341.34 | RIDF Loan upto 10 crore | Slow progress due to revision in the length of bridge whichi is yet to get AA.Delay in tenxdering.LA for appr Road not done. Only boring for 6 piers has been complerted.COR likely.Inadequate monitoring by the dept.
13 | r132000156 | HLB a/c Rojar river in KM 18/10 | Ratlam | PWD | Bridge | 2011-02-17 | DDM | 97.5 | RIDF Loan upto 10 crore | Found.,pier,abutment,super stru.,Apr. Road upto 25% complete.TOR due to change of location.COR due to change in SOR.lack of staff was noticed.
13 | R132000157 | SB a/c Mandha River bridge in KM 19 | Rewa | PWD | Bridge |  |  | 75.46 | RIDF Loan upto 10 crore
13 | R132000158 | HLB a/c river Bihar in KM 2/10 | Rewa | PWD | Bridge |  |  | 96.27 | RIDF Loan upto 10 crore
13 | r132000159 | SB a/c Narain river in KM 6/2 | Sagar | PWD | Bridge | 2011-03-03 | DDM | 54.78 | RIDF Loan upto 10 crore | Foun.,pier,abutment,Sup. str.,App. road more than 76% complete.TOR due to delay in land acquisition,non availability of fund,sttopage of work in rains.NB board not displayed. Site visit book was not available.
13 | R132000160 | HLB a/c Dhasan river in KM 25/8 | Sagar | PWD | Bridge | 2010-02-09 | DDM | 136.22 | RIDF Loan upto 10 crore | Only foundation and pier have been completed Autment is 125-50% completed. Super stru appr road yet to start. LA and poor fundflowc hamoered project .Based on onserv during monsoon, PWD wants to either increase height of brid or make it SB. Ass nt displ
13 | R132000161 | HLB a/c Kaith river in KM 8/4 | Sagar | PWD | Bridge | 2009-02-05 | DDM | 135.28 | RIDF Loan upto 10 crore | Found Pier >76% completed, Abut Super srtruc Apr rd upto 25% completed. LA oor fund flow are leading to time over run. Viist Recordds not shown Tests records mintained. Assistance not displayed
13 | r132000162 | SB a/c Sukha Nalla in KM 15/6 | Sagar | PWD | Bridge | 2011-03-03 | DDM | 117.23 | RIDF Loan upto 10 crore | Found.,Pier,Abutment,sup.str.,App. road more than 76% complete.TOR due to delay in acquisition of land,non avaolability of fund & stoppage of work due to rains.NB Board not displayed.Site visit book was not available.
13 | R132000163 | HLB a/c Jamni river in KM 6/4 | Tikamgarh | PWD | Bridge |  |  | 136.36 | RIDF Loan upto 10 crore
13 | R132000164 | SB a/c Piliya Khal Nalla in KM 3/4 | Ujjain | PWD | Bridge |  |  | 96.58 | RIDF Loan upto 10 crore
13 | R132000165 | HLB a/c Sagad river in KM 2/6 | Vidisha | PWD | Bridge |  |  | 126.03 | RIDF Loan upto 10 crore
13 | R132000166 | HLB a/c Sapan river in KM 38/10 | Vidisha | PWD | Bridge |  |  | 213.8 | RIDF Loan upto 10 crore
13 | r132000167 | Bansagar MJP UnitIICanals | Rewa | WRD | MJP | 2011-01-20 | OIC | 94358.75 | RIDF Loan 25 crore & above | MC more than 51% complete,BC more tha 25% complete,Distributories & MC upto 25% complete.TOr due to delay in execution by contractors,COR due to retendering of balance work left incomplete by contractors.lining of canal to be taken up.
13 | R132000167 | Bansagar MJP UnitIICanals | Rewa | WRD | MJP | 2009-03-07 | OIC | 94358.75 | RIDF Loan 25 crore & above | MC more than 76% completed, Distributaries 26-50% minors and sub minors upto 25% completed. Incomplete works Minr to be compl poor maintenance TOr due to LA COR due to rev S.R.pilfering water by farmers.delayed fund flow Frequent transfer to be avoided
13 | R132000167 | Bansagar MJP UnitIICanals | Rewa | WRD | MJP | 2008-09-30 | DDM | 94358.75 | RIDF Loan 25 crore & above | Upper Purwa canal was visited Time overrun Delay in compensation for LA; Cost overrun due to revision in rates. Monitoring by department engineer; Tests carried out records maintained. NABARD board not displayed
13 | R132000167 | Bansagar MJP UnitIICanals | Rewa | WRD | MJP | 2008-09-25 | DDM | 94358.75 | RIDF Loan 25 crore & above | Sihawal Canal system was visited. Time overrun delay in compensation for LA Cost overrun due to revision in rates. Visited by project engineersTests carried out.records maontained NABARD assistance not displayed
13 | R132000167 | Bansagar MJP UnitIICanals | Rewa | WRD | MJP | 2011-10-01 | RO Official | 94358.75 | RIDF Loan 25 crore & above | Main Cnl>76%,(brnch cnl,CD wrks):26-50%,(Cnl lng,Dstrbtries,Mnrs&Sb mnrs,Wtr courses:each upto 25%) Ttl prgrs:40%, Prblms-LA,slw prgs by cntrctrs. ToR&CoR-yes.NB brd-nil, no tests carried out
13 | R132000167 | Bansagar MJP UnitIICanals | Rewa | WRD | MJP | 2013-03-19 | RO Official | 94358.75 | RIDF Loan 25 crore & above | (HW,Spiw,HR Main Cnl,Dstrbtries,CD)>76%,(brnch cnl,mNRS&Sbmnrs):51-75%, (Cnl lng,Wtr courses:each upto 25%) Ttl prgrs:85%, Prblms-LA,slw prgs by cntrctrs. ToR&CoR-yes.NB brd-nil
13 | R132000167 | Bansagar MJP UnitIICanals | Rewa | WRD | MJP | 2014-11-21 | RO Official | 94358.75 | RIDF Loan 25 crore & above | Phys prgs-96%,Wrok under RIDF are almost complete, It appears that Dept also took up works on new canals,Majhgawan,Gurh Mauganj,Teothar LIS etc&exp incurred unde RIDF,may be clarified fm them,cracks observed in lining of Sirmaur Dist,NB Brd not displayed
14 | r142000002 | Bariyarpur LBC Canals Pro | Chattarpur | WRD | MJP | 2011-03-16 | DDM | 11424.23 | RIDF Loan 25 crore & above | HW,SW,HR,MC,BC,CD more than 76% complete.Lining upto 26% complete.Dist.,minors,FC upto 25% complete.TOR due to unavailability of funds & COR due to non completion of work in time.NB board not displayed at site.
14 | r142000001 | Sindh Phase II | Shivpuri | WRD | MJP | 2011-03-10 | DDM | 86067.86 | RIDF Loan 25 crore & above | LA,EW,Masonry more than 75% complete.Revised admin approval yet to be received.TOR due to delay in forest clearence,area of dam is dacoit infected,NB board nt displayed.
14 | r142000001 | Sindh Phase II | Shivpuri | WRD | MJP | 2010-12-27 | RO Official | 86067.86 | RIDF Loan 25 crore & above | Revised admin. approval yet to be given by state govt,appropriate funding not made available by state govt.TOR due to slow flow of funds.NB board not displayed.No social audit conducted so far.Monitoring being done by officials through monitoring visits
14 | R142000001 | Sindh Phase II | Shivpuri | WRD | MJP | 2010-03-30 | DDM | 86067.86 | RIDF Loan 25 crore & above | Around 90% opf EW for dam is completed.Poor fundflow delayed payment to contractoer. NABARD asski not displayedlabour force busy with arg work. Work ion feeder canal yet to be completed.
14 | R142000002 | Bariyarpur LBC Canals Pro | Chattarpur | WRD | MJP | 2010-03-27 | DDM | 11424.23 | RIDF Loan 25 crore & above | Works like HW,SW,HR,MC,BC and CD are >76% completed.. lining of canal, distributaruies, minors and field channels are <25% completed. LA, contrctor's irregularities, non availability of budget affected Mon by WRD,tests done Rec main NAB asst display
14 | R142000001 | Sindh Phase II | Shivpuri | WRD | MJP | 2011-09-21 | RO Official | 86067.86 | RIDF Loan 25 crore & above | (Head Works,Spillways,Head Rglatr) each>76%, Main Cnl(26-50%),(Brnch Cnl, Cnl lng, Distbtries, Cd wrks each upto 25%) Total progrs;40%,QA/QC cntrl good
14 | R142000001 | Sindh Phase II | Shivpuri | WRD | MJP | 2011-11-30 | RO Official | 86067.86 | RIDF Loan 25 crore & above | Total Physical progress :99%, Lack of proper funding from State Govt- bottleneck, RAA of project yet to be done. Likely date of completion June 2013.
14 | R142000002 | Bariyarpur LBC Canals Pro | Chattarpur | WRD | MJP | 2013-02-16 | RO Official | 11424.23 | RIDF Loan 25 crore & above | Works like HW,SW,HR,MC,BC, lining of canal, distributaruies, minors and CD are >76% completed.. and field channels are <25% completed. Delay in completion of project due to inclusion of linining. Mon by WRD,tests done Rec main NAB asst not display
15 | r152000001 | Bargi Di-III (RBC104-154KM) | Katni | NVDA | MJP | 2011-01-21 | OIC | 79859.22 | RIDF Loan 25 crore & above | MC,LC works 51 to 75% complete,cd works more than 26% complete.TOR due to delay in LA,clearence from forest department,slow fund flow.work at 148 km pilongy dist. to be completed at earliest.tedering work at 129-154 km to be completed at earliest.
15 | r152000001 | Bargi Di-III (RBC104-154KM) | Katni | NVDA | MJP | 2010-11-02 | DDM | 79859.22 | RIDF Loan 25 crore & above | MC,LC & CD work more than 50% complete, at 121.125 SL absent(in 104 to 129Kms),LC,CD work less than 50% complete,MC more than 50%.At Vijayraghavgarh br.canal dispute between ACC & dept tendering yet to be done(129-154 kms Region VI)
15 | r152000001 | Bargi Di-III (RBC104-154KM) | Katni | NVDA | MJP | 2010-10-08 | DDM | 79859.22 | RIDF Loan 25 crore & above | Work at MC,lining & CD works is more than 50% complete.cost overrun caused due to tunnel design,80% parts of tunnel boring machine yet to be received.LA in khirhani village delayed.NABARD board not displayed.Absence & fall of lining at some places
15 | R152000001 | Bargi Di-III (RBC104-154KM) | Katni | NVDA | MJP | 2011-09-26 | RO Official | 79859.22 | RIDF Loan 25 crore & above | For 104-129 km(Main Canal, Canal Lining, CD Works) each>76%, (Cut&Cover, Tunnel) each upto 25% tot prgrs14.26%; 129-154km (Main Canal, CD wrk each 51-75%)Canal Lining 26-50%.Ttl prgrs 65%.Delay in LA, TBM
15 | R152000001 | Bargi Di-III (RBC104-154KM) | Katni | NVDA | MJP | 2012-03-17 | HO Official | 79859.22 | RIDF Loan 25 crore & above | EW.93%, Main cnl(tunnel)4.45%, main cnl;51-75%, brnch cnl-upto25%,(cnl lng,cd wrks)each51-75%.Ttl prgrs-35%, Prblm-TBM cmsng, tendrng.ToR-cntrct delay, TBM.0% irrgn potential reached.NB brd-nil
15 | R152000001 | Bargi Di-III (RBC104-154KM) | Katni | NVDA | MJP | 2013-02-16 | OIC+C | 79859.22 | RIDF Loan 25 crore & above | phy progress-70%, LA- Farmers are not ready to give land easily,delay occur due to court cases & stay is made on the running works, contractors left midway without completing the project, Procedural delays in calling for retenders,ToR-& CoR-Yes,NB Brd-No
15 | R152000001 | Bargi Di-III (RBC104-154KM) | Katni | NVDA | MJP | 2014-10-30 | HO Official | 79859.22 | RIDF Loan 25 crore & above | Phy prgs-22.85%,ToR-mixed geology causing damage to cutters of TBM,LA,Formation of sink holes,high water table,management problem, NB Brd not displayed. If the tunnel is complete the project is complete otherwise there will be no water beyond RD 116km
15 | R152000002 | Sarai- Ahirganwa road | Anuppur | PWD | Road |  |  | 23.22 | RIDF Loan upto 10 crore
15 | R152000003 | Gram Parmandal-Sarra hety Khedly ba | Betul | PWD | Road |  |  | 253.45 | RIDF Loan upto 10 crore
15 | R152000004 | Nasirabad via Ratanpur-Alampur road | Betul | PWD | Road |  |  | 367.22 | RIDF Loan upto 10 crore
15 | R152000005 | Bhoura- Sataldehi -chopna road | Betul | PWD | Road |  |  | 39.48 | RIDF Loan upto 10 crore
15 | R152000006 | Masod-Wandly-Tiwarkhed road | Betul | PWD | Road |  |  | 24.24 | RIDF Loan upto 10 crore
15 | R152000007 | Mau-Chhekuri-Karoli-Kanathar road | Bhind | PWD | Road | 2011-11-19 | DDM | 192.04 | RIDF Loan upto 10 crore | LA>76%, EW:51-75%, CD works:upto 25%, ToR-work nt done by contractor.NB brd nt displayed.
15 | R152000008 | Bijawar-Mankari-Badamalehra road | Chattarpur | PWD | Road |  |  | 108.09 | RIDF Loan upto 10 crore
15 | R152000009 | Sahu Junction- Itava-Hirdepur road | Damoh | PWD | Road |  |  | 122.14 | RIDF Loan upto 10 crore
15 | R152000010 | Hatta-Subjail-Khari-Jamunia-Ronda-B | Damoh | PWD | Road |  |  | 324 | RIDF Loan upto 10 crore
15 | R152000011 | Gunji-Nonpani-Biltara road | Damoh | PWD | Road |  |  | 123.47 | RIDF Loan upto 10 crore
15 | R152000012 | Bangaun-Rewjha Kala- Bamhori- Mango | Damoh | PWD | Road |  |  | 442.02 | RIDF Loan upto 10 crore
15 | R152000013 | Rond-Salaiya-Bagalwara road | Damoh | PWD | Road |  |  | 43.04 | RIDF Loan upto 10 crore
15 | R152000014 | Sakore-Puraina road | Damoh | PWD | Road |  |  | 150.74 | RIDF Loan upto 10 crore
15 | R152000015 | Manpura-Lidhora-Karaiya-Badoli Sam | Damoh | PWD | Road |  |  | 250.3 | RIDF Loan upto 10 crore
15 | R152000016 | Hinota- Murachh-Muhrai road | Damoh | PWD | Road |  |  | 196.51 | RIDF Loan upto 10 crore
15 | R152000017 | Harrai- Ramadehi--Amwahi-Badipura- | Damoh | PWD | Road |  |  | 133.97 | RIDF Loan upto 10 crore
15 | R152000018 | Vijayganjmandi-Jawasiya road | Dewas | PWD | Road |  |  | 60.85 | RIDF Loan upto 10 crore
15 | r152000019 | Nagda-Kadod-Chirakhan road | Dhar | PWD | Road | 2011-03-18 | DDM | 527.79 | RIDF Loan upto 10 crore | Damage to CC road near Karod for 1km,certain potholes on road which are being repaired.NABARD board not displayed at the site.
15 | r152000019 | Nagda-Kadod-Chirakhan road | Dhar | PWD | Road | 2012-03-14 | RO Official | 527.79 | RIDF Loan upto 10 crore | (EW, WBM, BT, CD Works) each stands>76%, Total physical progress 100%, Delay attributed to contractors fault, shifting of poles by MPSEB. ToR-Yes. NB brd nt displayed.
15 | R152000020 | Sakka-Amarpur road | Dindori | PWD | Road |  |  | 137.84 | RIDF Loan upto 10 crore
15 | R152000021 | Sabramodi-Khiyawada road | Guna | PWD | Road |  |  | 170.76 | RIDF Loan upto 10 crore
15 | R152000022 | Rangawa - Deagarh - Jigania road | Gwalior | PWD | Road | 2015-03-20 | DDM | 255.31 | RIDF Loan upto 10 crore | Phy prgs-more than 76%. ToR-due to Forest clearance. Visit book not available at site, NB Brd not displayed,
15 | R152000023 | Danda Khirak-Tighra road | Gwalior | PWD | Road | 2015-03-18 | DDM | 330.33 | RIDF Loan upto 10 crore | Phy prgs-upto 25%, ToR-Road lies in Sona Chiriya Abhyaranya Forest Dept clearance is still awaited,CoR-due to FC, project cost likely to be enhanced due to ToR. Visit book not available.NB Brd not displayed
15 | R152000024 | Sawal Kheda- Palanpur - Talnagri Ro | Hoshangabad | PWD | Road |  |  | 82.18 | RIDF Loan upto 10 crore
15 | R152000025 | Yashwant Sagar-Mirjapur-Arniya-Baro | Indore | PWD | Road | 2010-10-15 | DDM | 147.83 | RIDF Loan upto 10 crore | LA,EW,Water Bound macadam,BT,CD Works more than 75% complete.Project Board Not displayed.Cost overrun.poor convergence with other departments,poor connectivity at begining, encroachments on both side of road
15 | R152000026 | Dhanpuri-Padwar-Imlai- Khandiya roa | Jabalpur | PWD | Road |  |  | 241.23 | RIDF Loan upto 10 crore
15 | R152000027 | Tilwara-Chargawan-Gotegaon road | Jabalpur | PWD | Road |  |  | 81.18 | RIDF Loan upto 10 crore
15 | R152000028 | Barwaha-Katkut-Udaya Nagar road | Khargone | PWD | Road |  |  | 75.12 | RIDF Loan upto 10 crore
15 | r152000029 | Surva-Sagur-Rahgaon road | Khargone | PWD | Road | 2011-02-23 | DDM | 85.15 | RIDF Loan upto 10 crore | Work is complete in all the aspects.COR due to price variation of material like cement,fuel etc.TOR due to code of conduct of LS elections,delay in receiving of funds,non availability of bitumen.NB board not established.About 200m rd nr Surva vill not do
15 | R152000030 | Dethali-Bujurg-Panwadi road | Mandsaur | PWD | Road |  |  | 54.55 | RIDF Loan upto 10 crore
15 | r152000031 | Noorabad Padawali -Sanichara road | Morena | PWD | Road | 2011-02-25 | DDM | 206.07 | RIDF Loan upto 10 crore | EW more than 76% complete,WBM 26% complete,CD works upto 25% complete.TOR due to poor ffund flow
15 | R152000031 | Noorabad Padawali -Sanichara road | Morena | PWD | Road | 2011-08-23 | DDM | 206.07 | RIDF Loan upto 10 crore | (EW,WBM, CD works>76%), ToR-poor fund flow frm Govt. NB brd nt displayed.
15 | r152000032 | Bichola Rithora to Bhensora app. ro | Morena | PWD | Road | 2011-02-25 | DDM | 93.24 | RIDF Loan upto 10 crore | LA,EW,WBM,BT,CD works more than 76% complete.TOR due to poor fund flow,Water logging in project area. NB Brd-No
15 | R152000032 | Bichola Rithora to Bhensora app. ro | Morena | PWD | Road | 2011-08-18 | DDM | 93.24 | RIDF Loan upto 10 crore | All heads>76%, ToR- poor fund flow from Govt. Water logging in the project area. NB brd nt displayed.
15 | r152000032 | Bichola Rithora to Bhensora app. ro | Morena | PWD | Road | 2012-12-31 | DDM | 93.24 | RIDF Loan upto 10 crore | All heads>76%, ToR-Poor fund flow from Govt. Water logging in the project area. NB brd nt displayed
15 | R152000033 | Maheba-Kot road | Panna | PWD | Road |  |  | 86.57 | RIDF Loan upto 10 crore
15 | R152000034 | Umraoganj-Rojorachak road | Raisen | PWD | Road |  |  | 108.16 | RIDF Loan upto 10 crore
15 | R152000035 | Sanchi-Gulgaon-Chiroli-Banskheda Ro | Raisen | PWD | Road |  |  | 101.9 | RIDF Loan upto 10 crore
15 | R152000036 | NH12-Kingi-Baniyakhedi-Khairwada-Ma | Raisen | PWD | Road |  |  | 161.35 | RIDF Loan upto 10 crore
15 | R152000037 | Simrai Berasia- Hazli Khasrod road | Raisen | PWD | Road |  |  | 125.87 | RIDF Loan upto 10 crore
15 | R152000038 | Datagram-Patrikala-Kila Amergarh ra | Rajgarh | PWD | Road | 2012-01-05 | DDM | 374.09 | RIDF Loan upto 10 crore | Work Cmpltd. ToR-LA.
15 | R152000039 | Ghindhorhaat- Bhagora Bilas road | Rajgarh | PWD | Road | 2013-02-05 | DDM | 122.65 | RIDF Loan upto 10 crore | Phy progress-100%, CoR- LA, NB Brd-Not displayed. Record maintained
15 | R152000040 | Lhodipura- Padli Maharaj road | Rajgarh | PWD | Road | 2013-07-08 | DDM | 105.7 | RIDF Loan upto 10 crore | Phy prgs-100%, act.exps till dt 95.04 lakh, ToR-LA, NB BRD-No
15 | R152000041 | Jhadla-Dhabla road via Hikmi | Rajgarh | PWD | Road | 2011-09-13 | DDM | 80.9 | RIDF Loan upto 10 crore | Work completed. ToR:LA.
15 | R152000042 | Biaora Sujhaliya road -Nariyabay Ka | Rajgarh | PWD | Road | 2012-01-05 | DDM | 98.4 | RIDF Loan upto 10 crore | Work cimpltd. ToR-LA.
15 | R152000043 | Gangeo-Tikuri road | Rewa | PWD | Road | 2014-11-20 | DDM | 109.48 | RIDF Loan upto 10 crore | Phy prgs-only 35% (WBM/BT/CD work not done), work is presently stopped. Land dispute & hence work would not be start till vacation of stay by the Jabalpur HC. NB Board not displayed
15 | R152000044 | Saw-Hardi-Rahat-Dadar road | Rewa | PWD | Road | 2014-02-13 | DDM | 220.22 | RIDF Loan upto 10 crore | Phy prgs(whole)-35%, BT & CD yet to be done, Earthwork has been done utp WBM level, No records could be seen, NB Brd not displayed, Road furniture not fixed, Action against first contractor was initiated for his failure in completing the work
15 | r152000045 | Piparahi-Jadkund road | Rewa | PWD | Road | 2011-03-21 | DDM | 509.54 | RIDF Loan upto 10 crore | EW,WBM,BT more than 26% complete,CD works more than 51% complete.TOR due to lack of timely execution of work.NABARD assistance board not displayed.
15 | R152000046 | Lalgaon-Mangawan road | Rewa | PWD | Road |  |  | 237.63 | RIDF Loan upto 10 crore
15 | R152000047 | Karrapur-Tinsua- Padwar - Nimon- Ma | Sagar | PWD | Road |  |  | 390.27 | RIDF Loan upto 10 crore
15 | R152000048 | Ujnethi-Patan road | Sagar | PWD | Road |  |  | 163.82 | RIDF Loan upto 10 crore
15 | r152000049 | Mothi-Gadoli-Baheriya Sahani- Barch | Sagar | PWD | Road | 2011-03-07 | DDM | 122.01 | RIDF Loan upto 10 crore | LA,EW,WBM,BT,CD works more than 76% completeTOr due to non availability of funds.COR due to site requirement as drainage was made in 9 places.BT nt done at one place due to opposition of farmers.NB board nt displayed.Test recrd site visit book nt availab
15 | R152000050 | Pajnari-Kandari Tigadda road | Sagar | PWD | Road |  |  | 153.65 | RIDF Loan upto 10 crore
15 | R152000051 | Satna-Bardadih Siding-Dagdiha Road | Satna | PWD | Road |  |  | 132.93 | RIDF Loan upto 10 crore
15 | R152000052 | Shyamnagar Jarkhi Lalpur Road, Nagaud | Satna | PWD | Road | 2011-10-05 | DDM | 202.27 | RIDF Loan upto 10 crore | Work compltd by 2 yrs delay. Actual expenditure nt furnished by dept. Villagers complain contractor has recieved payment from PMGSY as wel as NB loan for same project.
15 | R152000053 | Bhaukhedi-Dhamanda-Amalaha road | Sehore | PWD | Road |  |  | 186.06 | RIDF Loan upto 10 crore
15 | R152000054 | Neelbad Approach road | Sehore | PWD | Road |  |  | 93.83 | RIDF Loan upto 10 crore
15 | R152000055 | Salkanpur-Mardanpur road | Sehore | PWD | Road |  |  | 237.31 | RIDF Loan upto 10 crore
15 | r152000056 | Gopalpur-Seegaon-Narayanpura road | Sehore | PWD | Road | 2011-02-17 | RO Official | 444.35 | RIDF Loan upto 10 crore | LA,EW,WBM,BT,CD works more than 76% complete.Road is complete in most aspects only certain patches are incomplete. NB board not displayed.Road will be complete in lesser amount than estimated approval
15 | R152000057 | Rala-Tiladiya road | Sehore | PWD | Road |  |  | 197.66 | RIDF Loan upto 10 crore
15 | R152000058 | O'ganj to Shahganj road | Sehore | PWD | Road | 2014-08-22 | DDM | 439.16 | RIDF Loan upto 10 crore | Project has been transferred from PWD to MPRDC vide E-in-C Order dtd 27/02/2014, Project is completed,
15 | R152000059 | Burhar-Hardi road | Shahdol | PWD | Road |  |  | 221.41 | RIDF Loan upto 10 crore
15 | R152000060 | Kanchanpur-Udhiya-Singhpur road | Shahdol | PWD | Road | 2011-10-20 | DDM | 112.2 | RIDF Loan upto 10 crore | Work completed. Road surface uneven, Surface coat shoddy quality.
15 | R152000061 | Tanodiya-Madkota road | Shajapur | PWD | Road | 2012-07-19 | DDM | 139.54 | RIDF Loan upto 10 crore | Work 100% Completed
15 | R152000062 | Bhasoda-Badagaon road | Shajapur | PWD | Road | 2012-07-10 | DDM | 86.08 | RIDF Loan upto 10 crore | work 100% completed.
15 | r152000063 | Bjarlle-Makra wala road | Sheopur | PWD | Road | 2010-11-30 | DDM | 228.8 | RIDF Loan upto 10 crore | WBM work 10% complete.scraping of existing bitumen surface layer of 10.7 km road to be done.GSB work in progress.Delay in commencement of project due to non availability of job card hoder NREGA labourers.NB board displayed.
15 | r152000064 | Badagong-Baldeogarh | Tikamgarh | PWD | Road | 2011-03-04 | DDM | 167.86 | RIDF Loan upto 10 crore | LA more than 76%,EW,WBM,CD work upto 25% complete.TOR & COR due to change in selection criteria for cntrctr,awarding of fresh cntrct.NB board not displayed.
15 | R152000065 | Baldeogarh-Nowgong road | Tikamgarh | PWD | Road |  |  | 186.66 | RIDF Loan upto 10 crore
15 | r152000066 | Lidhora-Gotet-Chanderaroad | Tikamgarh | PWD | Road | 2011-11-14 | DDM | 96.64 | RIDF Loan upto 10 crore | >76% Work completed. T&C overrun due to labour, wate prblms etc. Visits undertaken by top officials, site order book N.A on dt if inspection. NAB brd shd b repainted. Road Qlty poor, guarantee period should be increased to 5 yrs. Qlty of PMGSY> NAB Road.
15 | R152000066 | Lidhora-Gotet-Chanderaroad | Tikamgarh | PWD | Road | 2011-11-14 | DDM | 96.64 | RIDF Loan upto 10 crore | All heads of work achieved more than 76%, Prblms-labour,water,delay in paymnt to cntrctr, poor fund flow. CoR&ToR-yes. Test record-nt available. Qlty of road very poor. requires maintenance.
15 | r152000067 | Alampura-Banne Buzurg road | Tikamgarh | PWD | Road | 2011-12-27 | DDM | 110.54 | RIDF Loan upto 10 crore | Time and cost overrun due to labour, water, delay in payment etc. tests carried out, Road quality good, but pending works. Nabard Board displayed requires repainting. Guarantee period should be increased from 3 to 5 years.
15 | R152000067 | Alampura-Banne Buzurg road | Tikamgarh | PWD | Road | 2011-12-27 | DDM | 110.54 | RIDF Loan upto 10 crore | Project complete. Prblms : Labour, water, delay in payment to contractor. maintenance of test record: nt available.NB nt very prominent.
15 | R152000068 | Chandra-Mendwara-Jewar road | Tikamgarh | PWD | Road |  |  | 197.57 | RIDF Loan upto 10 crore
15 | R152000069 | Jawasiyapanth - Narayana road | Ujjain | PWD | Road |  |  | 298.71 | RIDF Loan upto 10 crore
15 | R152000070 | Lalpur- Biyvara Road | Ujjain | PWD | Road |  |  | 366.34 | RIDF Loan upto 10 crore
15 | R152000071 | Zarda-Tarot-Dhablasiya- Gogakheda r | Ujjain | PWD | Road |  |  | 261.06 | RIDF Loan upto 10 crore
15 | R152000072 | Mahidpur-Dhablasiya-Ranayrapeer roa | Ujjain | PWD | Road | 2013-08-08 | DDM | 342.5 | RIDF Loan upto 10 crore | Phy prgs-100%, Completion dt 30/11/2010,Total Road length-15.70km, completed-12kms, 0to0.7km taken over by PMSY and same is not moterable kaccha road, End portion completed under PMSY. ToR-18 mths, Road from 0 to 0.78km which is still kaccha, No NB Brd .
15 | R152000073 | Narsingha - Pirzhalar road | Ujjain | PWD | Road | 2011-10-21 | DDM | 150.59 | RIDF Loan upto 10 crore | EW>76%, ttl physical prgrs:50%, Prblms-slow prgrs of cntrctr, termination of cntrct. ToR-&CoR(cost escalation)-yes. NB brd nt displayed. PWD while quoting tender-ignores experience and logistics availability
15 | r152000074 | Sagwali-Zutawad Road | Ujjain | PWD | Road | 2010-12-07 | DDM | 101.34 | RIDF Loan upto 10 crore | EW,WBM,CD works more than 75% complete,BT work completed between 26 & 50%.TOR due to improper follow up & lack of coordination,slow progress of the work by contractor.NB board not displayed.Road is in bad shape.
15 | R152000075 | Kurwai-Barual via Kethora Nahi road | Vidisha | PWD | Road |  |  | 131.35 | RIDF Loan upto 10 crore
15 | R152000076 | Daynandpur-Badanpur-Bhiyakhedi-Gang | Vidisha | PWD | Road |  |  | 95.31 | RIDF Loan upto 10 crore
15 | r152000077 | Sanchi-Udaygiri-Vidisha-Gulabganj B | Vidisha | PWD | Road | 2011-01-28 | RO Official | 1045.69 | RIDF Loan 10.01-24.99 crore | LA,EW,WBM,BT,CD works more than 76% complete.TOR due to revised technical sanction,delay in getting raw material,delay in payment to contractors.NABARD board not displayed,gap in road project was observed.
15 | R152000078 | Hausua - Katsara road | Vidisha | PWD | Road | 2011-11-19 | DDM | 40.01 | RIDF Loan upto 10 crore | Work completed except road signs. NO records of senior PWD officials visiting the site. No records of maintenance. NB Brd nt displayed.
15 | R152000079 | Santoshpur-Bhouriya road | Vidisha | PWD | Road |  |  | 41.52 | RIDF Loan upto 10 crore
15 | R152000080 | Gyaraspur-Inderwas road | Vidisha | PWD | Road | 2011-11-21 | DDM | 185.12 | RIDF Loan upto 10 crore | Road project cmpltd except road signs. Clearance from forest dept delayed. ToR-labour shortage, late permsn from state govt.test record/site visit register nt available. NB brd nt as per specifications.
15 | R152000081 | Hatkheda - Tarawali approach road | Vidisha | PWD | Road | 2011-11-20 | DDM | 45.19 | RIDF Loan upto 10 crore | Road project cmpltd except road signs.ToR-labour shortage, late permsn from state govt.test record/site visit register nt available. NB brd nt displayed.
15 | R152000082 | Laharpur-Pepaldhar road | Vidisha | PWD | Road |  |  | 115.68 | RIDF Loan upto 10 crore
15 | R152000083 | Pry Health Centre Sakra | Annupur | DHFW | Health | 2013-02-26 | DDM | 55.25 | RIDF Loan upto 10 crore | Phy progress- 100%, NB Brd-No, Qual.Control System, Books maintained, qualt of const-Very Good. There is a saving of an amt of Rs.4.42 lakh by PWD
15 | R152000084 | Pry Health Centre Cholna | Annupur | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000085 | Pry Health Centre Raipur | Ashoknagar | DHFW | Health | 2013-03-08 | DDM | 55.25 | RIDF Loan upto 10 crore | Phy prgs >76%, ToR-Delay in receiving the mone by PWD Ashoknagar Div., Excpt boundary wall & finishing work the work has been completed. NB Brd- yet to be displayed. No register of test record/site visit/order book was available
15 | R152000086 | Pry Health Centre Babdad | Badwani | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000087 | Pry Health Centre RajeGaon | Balaghat | DHFW | Health | 2010-09-10 | DDM | 55.25 | RIDF Loan upto 10 crore | The work is yetv to be started by contractor though work order was given by the PWD. Supervision register not maintained . No boundary stone was fixed to show acquisition of land by DHFW
15 | R152000088 | Pry Health Centre Jaam | Balaghat | DHFW | Health | 2012-12-26 | DDM | 55.25 | RIDF Loan upto 10 crore | HC Bl-upto 25%, No sign brd, No boundry stone were fixed.DHFW advised vide let dtd 15.06.2009 dept to stop the work due to paucity of fund
15 | R152000089 | Pry Health Centre Mohgaon | Balahgat | DHFW | Health | 2012-11-09 | DDM | 55.25 | RIDF Loan upto 10 crore | Project yet to commenced. , No sign brd, No boundry stones were fixed, No recrd of vist of SE/EE or off of HD
15 | R152000090 | Pry Health Centre Borgaon | Betul | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000091 | Pry Health Centre Bamnora | Chattarpur | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000092 | Pry Health Centre Bajna | Chattarpur | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000093 | Pry Health Centre Geldubba | Chhindwara | DHFW | Health | 2013-03-20 | DDM | 55.25 | RIDF Loan upto 10 crore | phy pgrs-95%. ToR-delays due to hard rock strata & poor coordination. No sign board, No record of visit by other official from Health dept. The work was severely hampered on a/c of difficult terrain, steep slopes and lack of proper approach road.
15 | R152000094 | Pry Health Centre Nohta | Damoh | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000095 | Pry Health Centre Sadguva | Damoh | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000096 | Pry Health Centre Jerath | Damoh | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000097 | Pry Health Centre Imaliyaghat | Damoh | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000098 | Pry Health Centre Gondal | Datia | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000099 | Pry Health Centre Satipura | Dhar | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000100 | Pry Health Centre Rusha | Dindori | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000101 | Pry Health Centre Bamhani | Dindori | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000102 | Pry Health Centre Sontalai | Harda | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000103 | Pry Health Centre Singod | Jabalpur | DHFW | Health | 2013-07-13 | DDM | 55.25 | RIDF Loan upto 10 crore | Act expt 58.8% of TS o/w disbt NB 15.13L (20%).Phy Prog proj 70%.Likely compl 31.12.2013. Delay lack interdept coordn,cntract cancld n reissued,wrk May 2013,contr probs, no NB board,shamshan struct shove be remvd, land levlng, no recrd ofcls vist
15 | R152000104 | Pry Health Centre Boriya | Jabalpur | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000105 | Pry Health Centre Padwar | Jabalpur | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000106 | Pry Health Centre Belkhadu | Jabalpur | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000107 | Pry Health Centre Indana | Jabalpur | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000108 | Pry Health Centre Bhidki | Jabalpur | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000109 | Pry Health Centre Ublad | Jhabua | DHFW | Health | 2015-02-18 | DDM | 55.25 | RIDF Loan upto 10 crore | Phy prgs-100%, ToR-LA, NB Brd not displayed , Visit records were not readily available
15 | R152000110 | Pry Health Centre Sobhavade | Jhabua | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | r152000111 | Pry Health Centre Umrath | Jhabua | DHFW | Health | 2011-03-01 | DDM | 55.25 | RIDF Loan upto 10 crore | Only plinth work complete in health centre building.No other work has started Due to Not receiveng of funds from FD project was not started in time and work stopped after two months.COR due to revised estimate is yet to be finalizedNB board not displayed
15 | R152000112 | Pry Health Centre Phulmal | Jhabua | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000113 | Pry Health Centre Katkut | Khargone | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000114 | Pry Health Centre Guradiya | Khargone | DHFW | Health | 2013-12-27 | DDM | 55.25 | RIDF Loan upto 10 crore | Phy prgs=90%, ToR-due to non availability of fund, NB Brd not displayed, No separate record of the visit to the project maintained
15 | R152000115 | Pry Health Centre Kabadiya | Khargone | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000116 | Pry Health Centre Helabdava | Khargone | DHFW | Health | 2013-12-27 | DDM | 55.25 | RIDF Loan upto 10 crore | Phy prgs=100%, completion date 04/07/2013, ToR due to fund & labour problem, Dept Officials visit record not maintained, NB Brd not displayed
15 | r152000117 | Pry Health Centre Pipariya | Mandla | DHFW | Health | 2012-02-24 | DDM | 55.25 | RIDF Loan upto 10 crore | Financial achvmt:52.6%, Constrn of PHC block, quarter for doc, nurses>76%, (Doors, windows etc:51-75%).Prblms-Painting, granite platforms, doors not yet done.Non receipt of funds at regular intervals-reasn for delay
15 | R152000118 | Pry Health Centre Davla Mahesh | Mandsour | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000119 | Pry Health Centre Ridhora | Morena | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000120 | Pry Health Centre Bhangroll | Morena | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000121 | Pry Health Centre Jodori | Rewa | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000122 | Pry Health Centre Khannodi | Shahdol | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000123 | Pry Health Centre Avanitpur Badotiy | Shajapur | DHFW | Health | 2013-01-04 | DDM | 55.25 | RIDF Loan upto 10 crore | Phy progress- >80%, TOR-LA, Land is not available for staff qtrs (PHC), NB Brd-No
15 | R152000124 | Pry Health Centre Premsar | Sheopur | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000125 | Pry Health Centre Dantardakla | Sheopur | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000126 | Pry Health Centre Sirsod | Shivpuri | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000127 | Pry Health Centre Chhapara | Seoni | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000128 | Pry Health Centre Chandera | Tikamgarh | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000129 | Pry Health Centre Kachhora | Tikamgarh | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000130 | Pry Health Centre Jaruaa | Tikamgarh | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000131 | Pry Health Centre Luharguvan | Tikamgarh | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000132 | Pry Health Centre Rupakhedi | Ujjain | DHFW | Health | 2013-02-22 | DDM | 55.25 | RIDF Loan upto 10 crore | Phy Prgs-95%. Main PHC bldg & qtrs completed Elec &dev of area pending. ToR-Yes(Delayed completion). mntnce of rcrd-No. NB Brd-No. Delay in execution of work due to land encroached & Contractor was very slow.
15 | R152000133 | Pry Health Centre Panth Pipalai | Ujjain | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000134 | Pry Health Centre Chintaman Javasiy | Ujjain | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000135 | Pry Health Centre Kaytha | Ujjain | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | r152000136 | Pry Health Centre Bizori | Umaria | DHFW | Health | 2010-11-09 | DDM | 55.25 | RIDF Loan upto 10 crore | Work not yet commenced, delay on the part of department to invite tenders. tenders has been floated only recently(27 October,2010)
15 | r152000137 | Pry Health Centre Dhamokhar | Umaria | DHFW | Health | 2010-11-09 | DDM | 55.25 | RIDF Loan upto 10 crore | Work not yet commenced, delay on the part of department to invite tenders. tenders has been floated only recently(27 October,2010)
15 | r152000138 | Pry Health Centre Nourozabad | Umaria | DHFW | Health | 2010-11-09 | DDM | 55.25 | RIDF Loan upto 10 crore | Work not yet commenced, delay on the part of department to invite tenders. tenders has been floated only recently(27 October,2010)
15 | R152000139 | Pry Health Centre Bardha | Vidisha | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | R152000140 | Pry Health Centre Sayar | Vidisha | DHFW | Health | 2013-03-25 | DDM | 55.25 | RIDF Loan upto 10 crore | Phy progress-98% except that Tube well for water supply has not been installed & no internal roads as envisaged in the project, ToR-2 yrs, Dept officials visit details- not made available by deptt, NB Brd-No
15 | R152000141 | Pry Health Centre Ahmadpur | Vidisha | DHFW | Health | 2013-03-25 | DDM | 55.25 | RIDF Loan upto 10 crore | Phy progress-98% except that Tube well for water supply has not been installed & no internal roads as envisaged in the project, ToR-2 yrs, Dept officials visit details- not made available by deptt, NB Brd-No
15 | R152000142 | Pry Health Centre Udaipur | Vidisha | DHFW | Health |  |  | 55.25 | RIDF Loan upto 10 crore
15 | r152000143 | C/o H.L. Br Wainganga Ri in KM 7/ | Balaghat | PWD | Bridge | 2011-03-09 | DDM | 1127.34 | RIDF Loan 10.01-24.99 crore | foun.,pier,abutment,sub str.more than 51% complete.super st app. road upto 25% complete.Delay due to occurence of hard rock,work not possible fr 6 mnths due to rapid flow of wainganga river.NB board not displayed.const. of app. road nd 1 pier incomplete.
15 | R152000144 | C/o H.L. Br Chandan Ri in KM 1/8 | Balaghat | PWD | Bridge |  |  | 330.51 | RIDF Loan upto 10 crore
15 | R152000145 | C/o H.L.Br Son Ri in KM 7/4 on Bh | Balaghat | PWD | Bridge |  |  | 334.76 | RIDF Loan upto 10 crore
15 | r152000146 | C/o Sub Br Machana Ri in KM 2/8 o | Betul | PWD | Bridge | 2011-10-13 | DDM | 151.46 | RIDF Loan upto 10 crore | Project cmpltd with 5 mnths delay. SE & EE made frequent visits. Bottleneck:LA, Cost overrun, revised estimate. Test+maint. of record/site visit are proper. NB brd displayed.
15 | R152000146 | C/o Sub Br Machana Ri in KM 2/8 o | Betul | PWD | Bridge | 2011-10-13 | DDM | 151.46 | RIDF Loan upto 10 crore | Work cmpltd by 5 months delay. Delay due to land acquisition, Project cost overrun and revised estimate submitted.
15 | R152000147 | C/o Sub Br Tawa Ri in KM 1/6 on B | Betul | PWD | Bridge |  |  | 433.7 | RIDF Loan upto 10 crore
15 | R152000148 | C/o H.L. Br Tapti Ri in KM 16/4 | Betul | PWD | Bridge | 2011-10-19 | DDM | 297.46 | RIDF Loan upto 10 crore | Work compltd by 4 months delay.NB Board nt displayed.
15 | R152000149 | C/o H.L. Br Tapti Ri in KM 31/10 | Betul | PWD | Bridge | 2015-01-15 | DDM | 391.37 | RIDF Loan upto 10 crore | Phy prgs-Foundation& pillar-25%, Abutment-80%,Super structure-35%) ToR-due to increase of High Flood Level in 2013,design of bridge has been changed for strengthening & therefore change in SOR,NABARD Brd not displayed
15 | R152000150 | C/o Sub Br Pench Ri on Top - Bans | Chhindwara | PWD | Bridge | 2013-09-18 | DDM | 239.87 | RIDF Loan upto 10 crore | Delay due to lack of accessibility, Land aq. Problems. Board not displayed
15 | r152000151 | C/o H.L.Br Kanhan Ri in Km 12/4 | Chhindwara | PWD | Bridge | 2011-01-11 | RO Official | 602.9 | RIDF Loan upto 10 crore | Foundation,pier,abutment upto 51 to 75% complete,superstructure & approach road upto 25% complete,NB Board not displayed.Delay due to deposition of slit,occurance of hard rock.Monitoring done by senior officers of pwd.
15 | R152000152 | C/o Sub Br Bairma Ri in KM 9/2 on | Damoh | PWD | Bridge |  |  | 475.05 | RIDF Loan upto 10 crore
15 | R152000153 | C/o Sub Br Kunda Ri in Khargone c | Khargone | PWD | Bridge |  |  | 318.46 | RIDF Loan upto 10 crore
15 | R152000154 | C/o Sub Br Burarewa Ri in KM 119/ | Narsinghpur | PWD | Bridge |  |  | 141.97 | RIDF Loan upto 10 crore
15 | R152000155 | C/o Sub Br Maleni Ri in KM 9/2 o | Ratlam | PWD | Bridge |  |  | 290.42 | RIDF Loan upto 10 crore
15 | r152000156 | C/o H.L.Br Tons Ri in KM 1/2 on | Rewa | PWD | Bridge | 2011-03-17 | DDM | 1253.14 | RIDF Loan 10.01-24.99 crore | Foun.,abut. more than 76% complete.pier,SS more than 51% complete.TOR due to delay in approval of design, uncertainity of rains.NABARD board not displayed at the site
15 | R152000156 | C/o H.L.Br Tons Ri in KM 1/2 on | Rewa | PWD | Bridge | 2011-10-01 | RO Official | 1253.14 | RIDF Loan 10.01-24.99 crore | Foundn, Pier each >76%, Abtmnt, Super strctr, Apprch Rd each 51-75%; Ttl physcl prgrs:75.8%. ToR due to delay in design sbmssn. mvmnt of constrn matrls difficult. NB brd nt displayed.
15 | R152000157 | C/o H.L.Br Naren Ri in KM 5/4 on | Sagar | PWD | Bridge | 2013-01-24 | DDM | 112.79 | RIDF Loan upto 10 crore | Phy progress >76%, LA-Farmers not allowing const.of abutment, NB Brd-No, Site visit book-not avlble
15 | R152000158 | C/o H.L.Br Tons Ri in Km 22/2-4 o | Satna | PWD | Bridge |  |  | 358.1 | RIDF Loan upto 10 crore
15 | r152000159 | C/o Sub Br Pahari Khera Nalla in | Satna | PWD | Bridge | 2011-02-19 | DDM | 25.52 | RIDF Loan upto 10 crore | Foundation,pier,abutment,super structure,approach road more than 76% complete.TOR due to area being dacoit affected.NB board not displayed.white washing & painting of curve & wheel guard of bridge is incomplete.
15 | R152000160 | C/o Sub Br Kolar Ri in KM 11/2 on | Sehore | PWD | Bridge |  |  | 199.58 | RIDF Loan upto 10 crore
15 | R152000161 | C/o H.L. Br Jamni Ri in KM 74/6 o | Tikamgarh | PWD | Bridge |  |  | 1287.15 | RIDF Loan 10.01-24.99 crore
15 | R152000162 | C/o Sub Br Betwa Ri in KM 81/2 on | Tikamgarh | PWD | Bridge |  |  | 464.1 | RIDF Loan upto 10 crore
15 | R152000163 | C/o H.L.Br Johilla Ri in KM 12/1 | Umaria | PWD | Bridge |  |  | 469.3 | RIDF Loan upto 10 crore
15 | R152000164 | C/o Sub Br Bais Ri in KM 3/2 on C | Vidisha | PWD | Bridge |  |  | 196.97 | RIDF Loan upto 10 crore
15 | r152000165 | Hamlapur- Malkapur to Barsali Rd | Betul | PWD | Road | 2011-02-25 | DDM | 183.01 | RIDF Loan upto 10 crore | EW more thab 76%,WBM more than 51%,BT & CD works more than 26% complete.TOR due to delay in land demarcation,COR due to price adjustment,bottlenecks in work due to contractors issues.
15 | R152000166 | Patpada-Moredongari Rd | Chhindwara | PWD | Road |  |  | 161.52 | RIDF Loan upto 10 crore
15 | R152000167 | BamanPura-Nadia-Kudai Rd | Damoh | PWD | Road |  |  | 76.99 | RIDF Loan upto 10 crore
15 | r152000168 | Amjhar-Padwar Rd | Jabalpur | PWD | Road | 2011-04-20 | DDM | 175.52 | RIDF Loan upto 10 crore | EW,BT works more than 51% complete.WBM,CD works more than 76% complete.TOR due to cntractrs problem.Delay in clearence from Forest Department,poor fund flow.NB board not displayed at project site.Shouldering work is yet to be completed.
15 | R152000168 | Amjhar-Padwar Rd | Jabalpur | PWD | Road | 2011-12-09 | DDM | 175.52 | RIDF Loan upto 10 crore | EW, sb Base, WBM, BT, CD wrks each 51-75%, prblms-cntrctr delay, cntrctr busy in cmpltng other prjcts hence payment sufferd.
15 | R152000168 | Amjhar-Padwar Rd | Jabalpur | PWD | Road | 2011-04-20 | DDM | 175.52 | RIDF Loan upto 10 crore | EW, BT eac:51-75%, WBM, CD wrks:>76%, prblms-contrct being outsider nt able to manage efficiently. poor fund flow, land clearance from forest dept took 1 year.
15 | R152000168 | Amjhar-Padwar Rd | Jabalpur | PWD | Road | 2012-06-18 | DDM | 175.52 | RIDF Loan upto 10 crore | Work Progress > 76%; Delay in project implementation & Fund flow affected; Land clearance from Forest department. No M book availble, No NB brd; contractr prblm & depts apathy to project
15 | R152000169 | Baghraji-Badua-Patnakala Rd | Jabalpur | PWD | Road | 2011-11-21 | DDM | 271.98 | RIDF Loan upto 10 crore | All heads achieved>76%, prblms- contractr delay, poor fund flow from dept. project implementation delayed. repairing yet to be done.
15 | R152000169 | Baghraji-Badua-Patnakala Rd | Jabalpur | PWD | Road | 2011-05-06 | DDM | 271.98 | RIDF Loan upto 10 crore | ALL heads achieved?76%, prblms-cntrctr being outsider nt able to manage project efficiently.
15 | r152000170 | Bhagour- Hatyadeli -Petlawad Rd | Jhabua | PWD | Road | 2011-02-02 | RO Official | 515.53 | RIDF Loan upto 10 crore | Project Completed.TOR due to transfer of 15 kms road to PMGSY & delay from contractors side.Department is advised to submit PCR at earliest.In pmgsy roads are not connecting main road.A pot. of 140 km road in jhabua with 70 cr budget requirement.
15 | r152000171 | Suddi-Rajarwara - Barhata Rd | Katni | PWD | Road | 2011-02-23 | DDM | 115.84 | RIDF Loan upto 10 crore | EW,WBM,BT,CD works more than 76% complete.TOR due to poor fund flow.Site visit order book not available.Records not maintained properly.
15 | r152000172 | Upgradation of Kasrawad-Pipalgone-L | Khargone | PWD | Road | 2011-01-17 | RO Official | 727.75 | RIDF Loan upto 10 crore | WBM,BT work more than 51% complete,CC work more than 76% complete.COR due to revision in SOR & 16.66% increase in tender amount.Some delay in execution was observed due to delay in availability of funds.NB board not accord to specific.Bil Rs.1.49cr pend
15 | R152000173 | Bajitpura- Umariya Rd | Khargone | PWD | Road |  |  | 345.32 | RIDF Loan upto 10 crore
15 | r152000174 | Ghata- Chapartala- Bhadagi - Gaitra | Mandla | PWD | Road | 2011-02-25 | DDM | 153.43 | RIDF Loan upto 10 crore | EW,WBM more than 76% complete.NB board nt displayed.
15 | R152000175 | Jawad-Modi-Semli-Chandrawat Rd | Neemuch | PWD | Road |  |  | 131.32 | RIDF Loan upto 10 crore
15 | R152000176 | Parwariya-Sonthiya Rd | Raisen | PWD | Road |  |  | 131.58 | RIDF Loan upto 10 crore
15 | R152000177 | Napanera-Newali Rd | Rajgarh | PWD | Road | 2012-01-24 | DDM | 64.82 | RIDF Loan upto 10 crore | Work cmpltd. ToR-LA.
15 | R152000178 | Bhatkhedi to Shilwadiya Rd | Rajgarh | PWD | Road | 2011-09-14 | DDM | 50.62 | RIDF Loan upto 10 crore | Work completed. ToR:LA, Financial prob
15 | R152000179 | Goverdhanpura- Nari to Suthaliya- M | Rajgarh | PWD | Road | 2011-09-14 | DDM | 45.67 | RIDF Loan upto 10 crore | Work completed. ToR:LA, Financial prob
15 | R152000180 | Shutaliya to Ghograghat Rd | Rajgarh | PWD | Road | 2011-09-14 | DDM | 44.05 | RIDF Loan upto 10 crore | Work completed. ToR:LA.
15 | R152000181 | Lakhanwas to Tumdia Khedi Rd | Rajgarh | PWD | Road | 2012-01-24 | DDM | 58.57 | RIDF Loan upto 10 crore | Work cmpltd. ToR:LA, CoR-yes
15 | R152000182 | Dabdiya-Talod Rd | Ratlam | PWD | Road |  |  | 79.83 | RIDF Loan upto 10 crore
15 | R152000183 | Alot- Sherpurkhurd Via Malya Rd | Ratlam | PWD | Road |  |  | 175.64 | RIDF Loan upto 10 crore
15 | r152000184 | Sihora-Lotna-Lotni-Ramchhayari-Heer | Sagar | PWD | Road | 2011-03-22 | DDM | 539.71 | RIDF Loan upto 10 crore | WBM,BT upto 25% complete.TOR due to non availability of fund,delay in LA & Complacence of cntractr.LA done fr 14km nly out of 17.NB board nt displayed at site.G1 was done in shoddy way by cntrctr.9 cd wrks are done only out of proposed 18.
15 | r152000185 | Khurai-Nagna-Dhonga-Kanera-Barodiya | Sagar | PWD | Road | 2011-03-22 | DDM | 511.5 | RIDF Loan upto 10 crore | BT work upto 25% complete.TOR due to non availability of funds.Site visit book not available.NB board not displayed at site.Against sanction of CC work of 1km only 700 m was made.17 cd works done against sanctioned 31.
15 | R152000186 | Upgradation of Satna Dharkundi Rd | Satna | PWD | Road |  |  | 212.11 | RIDF Loan upto 10 crore
15 | R152000187 | Raheti to Dhamanda- Chichlaha Appro | Sehore | PWD | Road |  |  | 48.21 | RIDF Loan upto 10 crore
15 | R152000188 | Gondi-Guradiya- Chakaldi Rd | Sehore | PWD | Road |  |  | 50.17 | RIDF Loan upto 10 crore
15 | R152000189 | Banya - Jhajpura Rd | Sehore | PWD | Road |  |  | 70.64 | RIDF Loan upto 10 crore
15 | R152000190 | Maksi-Jhonkar Rd | Shajapur | PWD | Road | 2011-12-23 | DDM | 55.51 | RIDF Loan upto 10 crore | Work completed. ToR- slow progress of contractor. NB Brd nt displayed.
15 | R152000191 | Nanawad to Gurdha via Amalda Rd | Sheopur | PWD | Road | 2011-08-29 | DDM | 78.85 | RIDF Loan upto 10 crore | Work nt yet started. Labours didnt possess job card as per NREGA scheme. Dist collector has advised to start work with other labourers. ToR&CoR:yes. NB brd nt displayed. No test record.
15 | R152000192 | Upgradation of Goverdhan Umari Rd | Shivpuri | PWD | Road |  |  | 160.08 | RIDF Loan upto 10 crore
15 | R152000193 | Kundhikheda to Khedakhajuriya Rd | Ujjain | PWD | Road |  |  | 327.79 | RIDF Loan upto 10 crore
15 | R152000194 | Nagda Gogapur Rd | Ujjain | PWD | Road |  |  | 224.33 | RIDF Loan upto 10 crore
15 | R152000195 | Eklod-Sironj to Vidisha-AshokNagar | Vidisha | PWD | Road |  |  | 484.2 | RIDF Loan upto 10 crore
15 | R152000196 | Dhudhawari to Chapara Rd | Vidisha | PWD | Road |  |  | 94.4 | RIDF Loan upto 10 crore
15 | R152000197 | Berasiya Rd to Bagri Jamber Chhirkh | Vidisha | PWD | Road |  |  | 38.89 | RIDF Loan upto 10 crore
15 | r152000198 | Lower Goi Irrigation Proj | Barwani | NVDA | MJP | 2011-01-31 | RO Official | 3180.6 | RIDF Loan 25 crore & above | HW,SW upto 25% complete,TOR due to delay in LA.
15 | R152000198 | Lower Goi Irrigation Proj | Barwani | NVDA | MJP | 2011-09-29 | RO Official | 3180.6 | RIDF Loan 25 crore & above | (Hd wrks,Splways,Mn Cnl):each 26-50%, CD wrks-upto 25%. Physical prgrs-26%. Delay in LA, NB brd nt as per specification.
16 | R162000001 | brg Kewai River at Gulidand - Pac | Anuppur | PWD | Bridge |  |  | 313.35 | RIDF Loan upto 10 crore
16 | R162000002 | brg Choti Bagh River on Ghansa Na | Balaghat | PWD | Bridge |  |  | 247.6 | RIDF Loan upto 10 crore
16 | R162000003 | High Level brg Bagh River in Km. 2 | Balaghat | PWD | Bridge | 2014-08-25 | DDM | 762 | RIDF Loan upto 10 crore | Phy prgs-75%, site/visit book not available, NB Brd not fixed, ToR-due to rapid flow of bagh river for about 5-6 mths in a year & delay on account of Land Acquisition.
16 | R162000004 | High level brg Maru River on Gond | Betul | PWD | Bridge |  |  | 94.14 | RIDF Loan upto 10 crore
16 | R162000005 | brg UD-Nalla on Sonora Sopai Ro | Betul | PWD | Bridge |  |  | 75.96 | RIDF Loan upto 10 crore
16 | R162000006 | High Level brg Semri Nalla on Bhop | Bhopal | PWD | Bridge |  |  | 45.58 | RIDF Loan upto 10 crore
16 | R162000007 | High Level brg Shyamri River in Km | Chhatarpur | PWD | Bridge |  |  | 276.21 | RIDF Loan upto 10 crore
16 | R162000008 | brg Narmada River on Shahpur - Ba | Dindori | PWD | Bridge |  |  | 385.36 | RIDF Loan upto 10 crore
16 | R162000009 | Construction of High level brg Nal | Harda | PWD | Bridge |  |  | 114.14 | RIDF Loan upto 10 crore
16 | R162000010 | brg Machak River on Sirali- Daga | Harda | PWD | Bridge |  |  | 174.62 | RIDF Loan upto 10 crore
16 | R162000011 | brg Machak River on Mahendragaon | Harda | PWD | Bridge |  |  | 161.91 | RIDF Loan upto 10 crore
16 | R162000012 | brg Ashamati River in Km 15/2 of | Indore | PWD | Bridge |  |  | 131.71 | RIDF Loan upto 10 crore
16 | R162000013 | brg Gambhir River on Ajnod - Bana | Indore | PWD | Bridge |  |  | 57.98 | RIDF Loan upto 10 crore
16 | R162000014 | High Level brg Katkala Nallah at B | Indore | PWD | Bridge |  |  | 70.94 | RIDF Loan upto 10 crore
16 | R162000015 | brg Abna River in Km 6/6 of Khand | Khandwa | PWD | Bridge | 2011-10-12 | DDM | 196.97 | RIDF Loan upto 10 crore | Foundn, pier, abutment, supr strctr:each>76%, Apprch Rd:26-50%.ToR-poor fund flow, heavy rains, standing water. NB Brd not displayed.
16 | r162000016 | brg Veda River in Km 7/10 of Sail | Khargone | PWD | Bridge | 2012-03-14 | DDM | 459.44 | RIDF Loan upto 10 crore | Work Completed. ToR due to overstretching of monsoon period, labour crisis, delay in release of fund.NB brd displayed nt as per specification
16 | R162000017 | brg Budner River on Alahi - Mehli | Mandla | PWD | Bridge |  |  | 253.01 | RIDF Loan upto 10 crore
16 | R162000018 | brg Shivna River on Mandsaur - Pr | Mandsaur | PWD | Bridge |  |  | 451.31 | RIDF Loan upto 10 crore
16 | R162000019 | brg Shakkar River on Kalyanpur - | Narsinghpur | PWD | Bridge |  |  | 491.84 | RIDF Loan upto 10 crore
16 | R162000020 | High level brg Tenduni River on G | Raisen | PWD | Bridge |  |  | 133.33 | RIDF Loan upto 10 crore
16 | R162000021 | High Level brg Gahara Nalla on Sul | Raisen | PWD | Bridge |  |  | 83.18 | RIDF Loan upto 10 crore
16 | R162000022 | brg Sindoorkiya Nallah on Jaora - | Ratlam | PWD | Bridge |  |  | 106.5 | RIDF Loan upto 10 crore
16 | R162000023 | High Level brg at Paisuni River on | Satna | PWD | Bridge | 2014-12-20 | DDM | 413.46 | RIDF Loan upto 10 crore | Phy prgs-LA>76% & Foundation=51to75% (other works 0%), ToR-cost of foundation increased, CoR-Peculiar stony structure below land, NB Board not displayed
16 | R162000024 | brg Satna River on Satna - Jiganh | Satna | PWD | Bridge |  |  | 306.29 | RIDF Loan upto 10 crore
16 | r162000025 | brg Kunuk River at Jaitpur - Jhee | Shahdol | PWD | Bridge | 2012-01-19 | DDM | 136 | RIDF Loan upto 10 crore | LA>76%, Appr. Road:51-75%,reimbrsmnt-27.2;Delay in obtaining Forest clearance. Flash Floods resulted in loss of machinery. Regular visits by AE, NB bd nt displyed,QC-wrk yet to commence
16 | R162000025 | brg Kunuk River at Jaitpur - Jhee | Shahdol | PWD | Bridge | 2012-01-19 | DDM | 136 | RIDF Loan upto 10 crore | LA>76%, Approach Road:51-75%. Delay in obtaining clearances from Forest Dept. Flash Floods resulting in loss of machinery. NB nrd not displayed.
16 | R162000026 | brg Kunuk River at Jaitpur - Jhee | Shahdol | PWD | Bridge | 2012-01-19 | DDM | 111.31 | RIDF Loan upto 10 crore | Foundn, Substrctr both<25%, LA>76%, Approach Rd:51-75%. Delay in forest dept clearance. Flash floods resulting in loss of machinery.NB brd nt displayed.
16 | r162000027 | brg Kunuk River at Jaitpur - Jhee | Shahdol | PWD | Bridge | 2012-01-19 | DDM | 111.96 | RIDF Loan upto 10 crore | LA>76%, Apprch Rd:51-75%, Foundn<25%, Sub Structre<25%; disb-22.26;TOR=delayed Forest clearance, Flash floods-loss of machinery, Regular visits of AE are being taken, NB brd nt displayed, QC/QA-wrk just commencd.
16 | r162000027 | brg Kunuk River at Jaitpur - Jhee | Shahdol | PWD | Bridge | 2012-01-19 | DDM | 111.96 | RIDF Loan upto 10 crore | Actual Exp.<10%, Foundn<25%, SubStrctr<25%, LA>76%, Apprch Rd:51-75%.TOR-flash floods-loss of machinery, QC/QA-wrk just cmmncd. NB brd nt displayed. AE -takes Regular visits
16 | R162000027 | brg Kunuk River at Jaitpur - Jhee | Shahdol | PWD | Bridge | 2012-01-19 | DDM | 111.96 | RIDF Loan upto 10 crore | Foundn, Substrctr both<25%, LA>76%, Approach Rd:51-75%. Delay in forest dept clearance. Flash floods resulting in loss of machinery. NB Brd nt displayed.
16 | r162000028 | brg Kunuk River at Bhatia Bhagora | Shahdol | PWD | Bridge | 2012-01-19 | DDM | 139.33 | RIDF Loan upto 10 crore | Foundn<25%, SubStructre<25%, LA>76%, Apprch Rd:51-75%,TOR due to Flash Floods=loss of machinery. Regular visit by AE. QA/QC-wrk jus commencd. NB board not displayed
16 | R162000028 | brg Kunuk River at Bhatia Bhagora | Shahdol | PWD | Bridge | 2012-01-19 | DDM | 139.33 | RIDF Loan upto 10 crore | (Foundn, Substrctr both < 25%, LA>76%, Approach Rd:51-75%. Flash Floods duriing dec2011 and jan 12 resultd in loss of contractors machinery. NB brd nt displayed.
16 | R162000029 | brg Newaj River on Devli - Saliya | Shajapur | PWD | Bridge |  |  | 241.56 | RIDF Loan upto 10 crore
16 | R162000030 | brg Jamdhad River on Jamner Khed | Shajapur | PWD | Bridge |  |  | 51.85 | RIDF Loan upto 10 crore
16 | R162000031 | High Level brg Newaj River on Pola | Shajapur | PWD | Bridge | 2014-09-05 | DDM | 203.11 | RIDF Loan upto 10 crore | Phy prgs-100%, ToR-due to LA, NABARD Board not displayed
16 | R162000032 | brg Mahan River at Deosar - Puran | Singrauli | PWD | Bridge |  |  | 257.82 | RIDF Loan upto 10 crore
16 | R162000033 | Deharda Rajgha to Budhi Chanderi Rd | Ashoknagar | PWD | Road |  |  | 335.58 | RIDF Loan upto 10 crore
16 | R162000034 | Chanderi to Budhi Chanderi Road | Ashoknagar | PWD | Road |  |  | 113.6 | RIDF Loan upto 10 crore
16 | R162000035 | Bamuriya Chhevlai Tamasha Piprai Ro | Ashoknagar | PWD | Road |  |  | 231.12 | RIDF Loan upto 10 crore
16 | R162000036 | Ashoknagar Piprai Road to Kukaoli J | Ashoknagar | PWD | Road |  |  | 350.37 | RIDF Loan upto 10 crore
16 | R162000037 | Bharroli to Ajileshwar Via Bhagwanp | Ashoknagar | PWD | Road |  |  | 351.06 | RIDF Loan upto 10 crore
16 | R162000038 | Khajuriyakala to Mahualampur Road | Ashoknagar | PWD | Road | 2013-03-08 | DDM | 276.5 | RIDF Loan upto 10 crore | Phy prgs >76%, projct grnted extension upto 15.02.2012. NB Brd-no. No register of test record/site visit/order book was available. 9.12 km road is damaged in various places which may be due to use of poor quality of material & lack of supervision
16 | R162000039 | Mathner to Semrahat road | Ashoknagar | PWD | Road |  |  | 252.26 | RIDF Loan upto 10 crore
16 | R162000040 | Mata Mandir(Ashoknagar) Sirsi pipra | Ashoknagar | PWD | Road | 2013-03-08 | DDM | 315.24 | RIDF Loan upto 10 crore | Phy prgs->76%, One small bridge in vil-Sirsi is yet to be built by PWD. LA work of bridge is yet to be undertaken. NB Brd-No. No register of test record/site visit/order book was available. road damaged at various places due to poor quality of material
16 | R162000041 | Rijoda to Kukreta Road | Ashoknagar | PWD | Road |  |  | 75.02 | RIDF Loan upto 10 crore
16 | R162000042 | Shadora to Kundora Road | Ashoknagar | PWD | Road |  |  | 286.46 | RIDF Loan upto 10 crore
16 | R162000043 | Tirodi Chakaheti Bamhni road | Balaghat | PWD | Road | 2011-04-28 | DDM | 173.1 | RIDF Loan upto 10 crore | LA, EW, WBM each>76%, BT-51-75%, ttl physical prgrs:77%, ToR-revised sanction from Govt. nt received by dept in time. CoR-due to lumpsum tndr offer and high tender rate.NB brd nt displayed.
16 | R162000044 | Badpani Bhondki Goreghat | Balaghat | PWD | Road |  |  | 133.53 | RIDF Loan upto 10 crore
16 | R162000045 | Sadara Bhanegaon Road | Balaghat | PWD | Road |  |  | 60.9 | RIDF Loan upto 10 crore
16 | R162000046 | Upgradation of Sadra Maneri road | Balaghat | PWD | Road |  |  | 161.24 | RIDF Loan upto 10 crore
16 | R162000047 | Morkha To Nagdeo Road | Betul | PWD | Road |  |  | 56.38 | RIDF Loan upto 10 crore
16 | R162000048 | Construction of Kalagaon selgaon Ba | Betul | PWD | Road |  |  | 248.59 | RIDF Loan upto 10 crore
16 | R162000049 | Bhimpur to Khamapur Gurna | Betul | PWD | Road | 2013-12-16 | DDM | 277.86 | RIDF Loan upto 10 crore | Phy prgs=70%, LA/Earthwork/CD>70%, WBM51-75%, Black topping 26-50%Delays due to LA & permission from Forest Dept, NB Brd not displayed,
16 | R162000050 | Berasia Sironj Road to Megra Kalan | Bhopal | PWD | Road |  |  | 672.92 | RIDF Loan upto 10 crore
16 | R162000051 | Berasia To Garah Kalan | Bhopal | PWD | Road |  |  | 488.65 | RIDF Loan upto 10 crore
16 | R162000052 | Construction of Chichkheda Nandanwa | Chhindwara | PWD | Road |  |  | 276.23 | RIDF Loan upto 10 crore
16 | R162000053 | Construction of Badchicholidhana Sa | Chhindwara | PWD | Road |  |  | 139.47 | RIDF Loan upto 10 crore
16 | R162000054 | Construction of Sawajpani Pandhari | Chhindwara | PWD | Road |  |  | 156.45 | RIDF Loan upto 10 crore
16 | R162000055 | Waghoda LodhiKheda Road | Chhindwara | PWD | Road |  |  | 160.88 | RIDF Loan upto 10 crore
16 | R162000056 | Construction of Wadegaon Kalamgaon | Chhindwara | PWD | Road |  |  | 88.85 | RIDF Loan upto 10 crore
16 | R162000057 | Karanpipariya to Guddam road | Chhindwara | PWD | Road |  |  | 152.38 | RIDF Loan upto 10 crore
16 | R162000058 | Sonakhar Khutiya Road | Chhindwara | PWD | Road | 2015-01-31 | DDM | 237.21 | RIDF Loan upto 10 crore | Phy prgs-(LA->76%,E/W-51-75%,WBM-26-50%,CD->76%), ToR-LA & due to rainy season & poor fund flow, NB Brd not displayed, Side berms not fixed (lot of bushes/grass noticed on side berms)and hence virtually reduces the road width, No boundy stone fixed
16 | R162000059 | Construction of Chhinda(Chhindwara | Chhindwara | PWD | Road |  |  | 108.96 | RIDF Loan upto 10 crore
16 | R162000060 | Garreh Basan Harduwa Road | Damoh | PWD | Road |  |  | 184.16 | RIDF Loan upto 10 crore
16 | R162000061 | Construction of Ajitpur Khamaria Ro | Damoh | PWD | Road |  |  | 97.78 | RIDF Loan upto 10 crore
16 | R162000062 | Construction of Rusalli Sojna Shika | Damoh | PWD | Road | 2013-01-15 | DDM | 233.08 | RIDF Loan upto 10 crore | Phy progress>76%, TOR-non avilbility of fund in 09-10, NB Brd-Yes, 9 km road was sanctioned on the basis of initial estimate based on Toposheet survey. However, actual length was only 8.4 km finally
16 | R162000063 | Rajpura Chouraiya Shahgarh Road | Damoh | PWD | Road | 2014-07-02 | DDM | 535.26 | RIDF Loan upto 10 crore | Phy prgs>76%, oad 22km sanctind hwever later 7.8km road transferred to PMGSY. PWD gave the contract 14.2kms to the contractor, he refused to start work. Used sand,murram material from forest & thus For dpt confiscated. Site book not easily avaiable
16 | R162000064 | Construction of Talgaon Hardwani Ma | Damoh | PWD | Road | 2013-01-15 | DDM | 171.39 | RIDF Loan upto 10 crore | Phy progress->76%, TOR-non avlibty of fund in 09-10, NB Brd-Yes, 6km road was sanctioned on the basis of initial estimate based on Toposheet survey. However, actual length was only 5.4 km finally
16 | R162000065 | Construction of Shajapur Imlidol Ro | Damoh | PWD | Road |  |  | 167.12 | RIDF Loan upto 10 crore
16 | R162000066 | Balakot Chairai manka Road | Damoh | PWD | Road |  |  | 341.07 | RIDF Loan upto 10 crore
16 | R162000067 | Hatta Ghuraghat Pandajhir Road | Damoh | PWD | Road |  |  | 109.51 | RIDF Loan upto 10 crore
16 | R162000068 | Halgaj Hinota Barkhera Ballarpur Ro | Damoh | PWD | Road |  |  | 346.09 | RIDF Loan upto 10 crore
16 | R162000069 | Bakayan Piprodha Sakatpur Riyana Sa | Damoh | PWD | Road |  |  | 390.37 | RIDF Loan upto 10 crore
16 | R162000070 | Bansa Tarkheda Basni Road | Damoh | PWD | Road |  |  | 128.66 | RIDF Loan upto 10 crore
16 | R162000071 | Hathna Sihora Padaria Road | Damoh | PWD | Road |  |  | 33.77 | RIDF Loan upto 10 crore
16 | r162000072 | Tanda Bori Road | Dhar | PWD | Road | 2012-03-15 | RO Official | 767.45 | RIDF Loan upto 10 crore | (EW, WBM, BT, CD works)each stands>76%, Total physical progress 80%. Delay was due to slow progress of work on part of contractor. ToR-yes. NB brd nt displayed.
16 | r162000073 | Tanda Bakner Ajanda Jotpur Karoli Ganpur Road | Dhar | PWD | Road | 2012-03-16 | RO Official | 680.14 | RIDF Loan upto 10 crore | EW:26-50%, WBM and BT both 51-75%, CD works: upto 25%. Total physical progress 37%, Prblms-slow progress due to heavy traffic, ToR and CoR- Yes, NB brd nt displayed.
16 | R162000073 | Tanda Bakner Ajanda Jotpur Karoli Ganpur Road | Dhar | PWD | Road | 2013-03-26 | DDM | 680.14 | RIDF Loan upto 10 crore | EW-> 76%, Water bound mac & Black Topping-51 to 75%, CD-upto 25%, ToR -Due to change in SOR and design, CoR- Delay in completion of the work, NB Brd -No, Due to contractor's problem work could not be completed in scheduled time
16 | R162000074 | Manawar mandi Wayal Jotpur Road | Dhar | PWD | Road |  |  | 215.95 | RIDF Loan upto 10 crore
16 | R162000075 | Karhiya to Aron via Gilarghati Road | Gwalior | PWD | Road | 2015-03-21 | DDM | 469.21 | RIDF Loan upto 10 crore | Phy prgs-upto 25%. Work hampered as a part of road is in Son Chiraiya Abhyaranaya ( Gilarighati) & Forest clearance received now. CoR-revised cost is going to increase as due to time lag of 07 years.Visit book is not readily available,NBbrd not displayed
16 | R162000076 | Construction of Deogarh To Ratangar | Gwalior | PWD | Road |  |  | 303.6 | RIDF Loan upto 10 crore
16 | R162000077 | Construction of Khamgaon Balagaon r | Harda | PWD | Road |  |  | 227.83 | RIDF Loan upto 10 crore
16 | R162000078 | Construction of Lokhartalai Dhekna | Hoshangabad | PWD | Road | 2015-01-21 | DDM | 479.18 | RIDF Loan upto 10 crore | Phy prgs-LA-100%,E/W-75%,WBM-60%,BT-0%,CD-80%), ToR-Forest clerance/First Contractor failed to complete the work, so appointed another contractor on Risk & Cost basis, some portion(150 mtr) of earth work has not yet been completed ,NB Brd not displayed
16 | R162000079 | Construction Of Sonkhedi Misrod Roa | Hoshangabad | PWD | Road |  |  | 335.74 | RIDF Loan upto 10 crore
16 | R162000080 | Construction of Hoshangabad Link Ro | Hoshangabad | PWD | Road |  |  | 237.58 | RIDF Loan upto 10 crore
16 | R162000081 | Construction of Biora(NH 69) to Roh | Hoshangabad | PWD | Road |  |  | 239.94 | RIDF Loan upto 10 crore
16 | R162000082 | Construction of Shivpur Talkeshari | Hoshangabad | PWD | Road |  |  | 142.98 | RIDF Loan upto 10 crore
16 | R162000083 | Constructtion of Semari Dobh Road | Hoshangabad | PWD | Road |  |  | 156.74 | RIDF Loan upto 10 crore
16 | R162000084 | Semiiya Chau Power Grid to Jalode R | Indore | PWD | Road |  |  | 47.41 | RIDF Loan upto 10 crore
16 | R162000085 | Malipura to hasalpur Road | Indore | PWD | Road |  |  | 135.69 | RIDF Loan upto 10 crore
16 | R162000086 | Laxmi Bai Nagar Chota Bangarda Bada | Indore | PWD | Road | 2013-02-19 | DDM | 621.14 | RIDF Loan upto 10 crore | Phy progress-all 26to50%,Contract has been terminated& retendering process has to begun, Contractor was very slow, delay in LA, COR-to be assessed after retendering, NB Brd-Asst.from NB not displayed, Tech spec.by NB needs to be revisited
16 | R162000087 | Chouhan Khedi Khemna Road | Indore | PWD | Road | 2011-04-30 | DDM | 93.83 | RIDF Loan upto 10 crore | EW, CD works>76%, WBM 51-75%. Total physical progress:75%, Delay in Fund flow, ToR-shrtge of material on site, non availability of water&electricity, labour shortage, late payment to cntrctr.NB brd stolen.No site lab, maint .register
16 | R162000088 | Attayana Kungara Jalodiya Par Limbo | Indore | PWD | Road |  |  | 209.75 | RIDF Loan upto 10 crore
16 | R162000089 | Agra Nevri Junction to Piploda Jalo | Indore | PWD | Road | 2013-02-19 | DDM | 290.08 | RIDF Loan upto 10 crore | Phy progress-51to75%, TOR-LA, Contrctor was very slow, NB Brd-displayed but NB name not affixed, Road width may be increased from 3.75 m to 5.5 m for better utility, as both side of the road is being encroached by villagers for various uses
16 | R162000090 | Gangajakhedi Chimankhedi Banediya R | Indore | PWD | Road | 2013-08-26 | DDM | 225.85 | RIDF Loan upto 10 crore | Phy prgs-45%, ToR-30mths due to to retendering process,CoR-due to new contract has been awarded at 23% above SoR and effectively the CoR is 33.61 above SoR,NB Brd-No, Road furniture not fixed,
16 | R162000091 | Semda Renganwas Arodakot Pemalpur t | Indore | PWD | Road | 2015-01-16 | DDM | 338.08 | RIDF Loan upto 10 crore | Project completed.Earthwork-51-75%,WBM-26-50%,BT-upto 25%,CD->76%, No records could be seen,NBARD Brd not displayed
16 | R162000092 | Karapgaon Khamariya Amgaon Road | Narsinghpur | PWD | Road |  |  | 286.11 | RIDF Loan upto 10 crore
16 | r162000093 | Neemuch Singouli Road(Pipalikheda) | Neemuch | PWD | Road | 2012-03-21 | DDM | 413.19 | RIDF Loan upto 10 crore | Work Completed. the project was delayed by 33 months due to contractors inability to carry out work in prescribed time limit. hence the Cost Overrun.
16 | R162000094 | Bankpura to Jhadikya Via Lashkarpur | Rajgarh | PWD | Road |  |  | 340.94 | RIDF Loan upto 10 crore
16 | R162000095 | Mawasa to Jhalda Road | Rajgarh | PWD | Road | 2011-09-13 | DDM | 163.43 | RIDF Loan upto 10 crore | All heads achieved till 75%. ToR-LA .
16 | R162000096 | PachoreMachalpur Road to Raipuriya | Rajgarh | PWD | Road |  |  | 209.18 | RIDF Loan upto 10 crore
16 | r162000097 | Chikli Sakad Road | Ratlam | PWD | Road | 2012-03-01 | DDM | 137.3 | RIDF Loan upto 10 crore | LA>76%, EW:51-75%, WBM, BT, CD works -nil. Time overrun due to late clearance from Forest Dept and revision in work plan. Inter dept tussle. Monitrng tkn by SDO, EE, CE. tests carried out frequently. EW cutting n filling in progress.
16 | r162000097 | Chikli Sakad Road | Ratlam | PWD | Road | 2012-03-07 | DDM | 137.3 | RIDF Loan upto 10 crore | LA>76%, EW:51-75%. ToR due to late clearance from Forest Dept and revision in Work plan. Prblms- inter dept tussle, Contractor litigation.
16 | R162000098 | Deori - Raisen Road | Sagar | PWD | Road |  |  | 359.86 | RIDF Loan upto 10 crore
16 | R162000099 | Sanjay drive Kanera Dev Road | Sagar | PWD | Road |  |  | 103.99 | RIDF Loan upto 10 crore
16 | R162000100 | NH 26 to Devri Road | Sagar | PWD | Road |  |  | 314.53 | RIDF Loan upto 10 crore
16 | R162000101 | Sagar Bye Pass Road Gadoli Bangwan | Sagar | PWD | Road |  |  | 173.34 | RIDF Loan upto 10 crore
16 | R162000102 | Bamnora Tigadda Ramchhayari Person | Sagar | PWD | Road |  |  | 139.31 | RIDF Loan upto 10 crore
16 | R162000103 | Missing Link Shahpur to Pathariya R | Sagar | PWD | Road |  |  | 76.25 | RIDF Loan upto 10 crore
16 | R162000104 | Sadar Gayaganj Shyampura Garpehara | Sagar | PWD | Road |  |  | 274.73 | RIDF Loan upto 10 crore
16 | R162000105 | Aamet Rajuya Badona Road | Sagar | PWD | Road | 2013-09-21 | DDM | 243.16 | RIDF Loan upto 10 crore | Phy prgs->76%, ToR-LA & encroachment by villagers, NB Brd-not displayed
16 | R162000106 | Berkheri Mohali Tinsua Road | Sagar | PWD | Road |  |  | 241.29 | RIDF Loan upto 10 crore
16 | R162000107 | Makronia 10th Batalian Narwani Bamh | Sagar | PWD | Road |  |  | 212.97 | RIDF Loan upto 10 crore
16 | R162000108 | Padrai Bansa mahukheda Karhad Road | Sagar | PWD | Road | 2014-11-14 | DDM | 393.79 | RIDF Loan upto 10 crore | Phy prgs>76%(10.40km) ToR-due to LA&encroachment by villagers. NB brd not displayed. Asperorigl plan PWD was to prepare a flushcauseway on river Dhasan. Hwver,due to demand of MLA HL Bridge Rs.438 lakh was prepared.Hence 700mtr of approach road not made.
16 | R162000109 | Khurai Thwari App. Road | Sagar | PWD | Road |  |  | 238.7 | RIDF Loan upto 10 crore
16 | R162000110 | Bansa Singarchori Dhakari Road | Sagar | PWD | Road |  |  | 240.44 | RIDF Loan upto 10 crore
16 | R162000111 | Semradangi to atraliya Jetli Baradi | Sehore | PWD | Road | 2013-11-29 | DDM | 309.27 | RIDF Loan upto 10 crore | Phy prgs-LA/Erthwork>76%,WBM/CD-51TO75%,Black topping-upto 25%, ToR-main problem for slow prgs is that the initial plan didn't incorporate construction of the 3 bridges dut to peculiar geographical terrain.NB Brd not displayed.Width is leser at few place
16 | R162000112 | Thikari to Kusumkheda Road | Sehore | PWD | Road |  |  | 91.11 | RIDF Loan upto 10 crore
16 | R162000113 | Mandi Neelkanth Road | Sehore | PWD | Road |  |  | 122 | RIDF Loan upto 10 crore
16 | R162000114 | Dova to Vashudev Road | Sehore | PWD | Road |  |  | 105.88 | RIDF Loan upto 10 crore
16 | R162000115 | Kalwana Canal to Jholiyapur Via nar | Sehore | PWD | Road |  |  | 295.52 | RIDF Loan upto 10 crore
16 | R162000116 | Amon To Silgena Road | Sehore | PWD | Road |  |  | 44.16 | RIDF Loan upto 10 crore
16 | R162000117 | Amon To Sagpur Road | Sehore | PWD | Road |  |  | 93.08 | RIDF Loan upto 10 crore
16 | R162000118 | Aroliya to Kurawar road | Sehore | PWD | Road |  |  | 180.07 | RIDF Loan upto 10 crore
16 | R162000119 | Construction of Saliya Devli road i | Shajapur | PWD | Road | 2011-09-16 | DDM | 80.44 | RIDF Loan upto 10 crore | All heads achieved upto 65%, ToR- lack of funds, LA.
16 | R162000120 | Construction of Mansaya Semliya Bad | Shajapur | PWD | Road | 2013-02-19 | DDM | 151.75 | RIDF Loan upto 10 crore | Work Progress >100%; Delay in Site Selection; Problems/Bottlenecks - Land Acquisition, Site selection, NB Brd-No
16 | R162000121 | Construction of Barod Susner Road | Shajapur | PWD | Road | 2012-05-25 | DDM | 357.62 | RIDF Loan upto 10 crore | Work progress upto 97%; Transportation of material is difficult due to river at both sides of the road.
16 | R162000122 | Construction of Takhla Payali Mana | Shajapur | PWD | Road | 2012-05-18 | DDM | 154.52 | RIDF Loan upto 10 crore | Work 100% completed with considerable time overrun. reason being delay in land acquisition and poor fund flow
16 | R162000123 | Construction of Kalisindh Kulmankhe | Shajapur | PWD | Road | 2011-09-16 | DDM | 225.82 | RIDF Loan upto 10 crore | All heads completed uptil 60%, ToR- lack of Fund
16 | R162000124 | Construction of Poaykala to Khatsoo | Shajapur | PWD | Road | 2011-09-16 | DDM | 94.83 | RIDF Loan upto 10 crore | All heads achieved >76%, ToR-lack of funds, LA.
16 | R162000125 | Construction of Kalapipal Kurawar R | Shajapur | PWD | Road | 2012-06-19 | DDM | 160.23 | RIDF Loan upto 10 crore | More than 80% completed. ToR due to shortage of funds, CoR & Bottleneck - poor funds flow
16 | R162000126 | Saint pal Convent School Kanipura t | Ujjain | PWD | Road |  |  | 583.3 | RIDF Loan upto 10 crore
16 | R162000127 | Bisalkhedi App. Road | Ujjain | PWD | Road |  |  | 166.3 | RIDF Loan upto 10 crore
16 | R162000128 | Kiloli to Lakhesara Road | Ujjain | PWD | Road |  |  | 254.69 | RIDF Loan upto 10 crore
16 | R162000129 | B.T.B. ( Basoda-Tyoda-Bagroda) to G | Vidisha | PWD | Road |  |  | 318.91 | RIDF Loan upto 10 crore
16 | R162000130 | Sothiya Ahmadpur road Via Pasora Ro | Vidisha | PWD | Road | 2014-11-21 | RO Official | 241.9 | RIDF Loan upto 10 crore | Phy prgs-75%, ToR-due to incomplete work by Contractor, CoR-work could not completed & contract terminated & awarded at R&C to 2nd contractor.NB board not displayed, Risk & Cost issue needs to be reviewed
16 | R162000131 | Construction Of Durang Dhamaukhedi | Vidisha | PWD | Road | 2014-09-18 | DDM | 461.13 | RIDF Loan upto 10 crore | Phy prgs 100%, CoR-due to delay in obtaining the permission from Forest Dept, Visit Book/Site book was not made available, Project board was not installed.
16 | R162000132 | Pathari Kirarkhedi Batyabda Road | Vidisha | PWD | Road | 2014-11-21 | RO Official | 421.72 | RIDF Loan upto 10 crore | Phy prgs-BT 30%, ToR-due to contractor problem, CoR-due to retendering process, NABARD Board not displayed, Risk & Cost issue needs to be reviewed.
16 | R162000133 | Badi Ukawat To Mundela Road | Vidisha | PWD | Road |  |  | 214.22 | RIDF Loan upto 10 crore
16 | R162000134 | Mahoti Jhukerumaria Jarsena Dugraua | Vidisha | PWD | Road | 2014-09-18 | DDM | 517.14 | RIDF Loan upto 10 crore | Phy prgs 100%, Visit book was not made available,NABARD Board was not installed, PWD officials was advised to submit PCR to NABARD
16 | R162000135 | Construction of Puragusai Ghatera P | Vidisha | PWD | Road | 2014-11-24 | RO Official | 262.42 | RIDF Loan upto 10 crore | Phy prgsLA-51-75%,Earthwok-26-50%,WBM & CD upto 25%,),Forest clearance to be obtained, ToR-due to Contractor's problem&hard rock cutting work is difficult&hence work hampered .NB Brd not fixed.Out of 39 CDs sanctioned, only 4 CDs completed, Visit book NA
16 | R162000136 | Berkhedi Approach Road | Vidisha | PWD | Road |  |  | 125.08 | RIDF Loan upto 10 crore
16 | R162000137 | Kethora To barodiya | Vidisha | PWD | Road |  |  | 186.11 | RIDF Loan upto 10 crore
16 | R162000138 | Pench Diiversion Project (Unit-I-H/W) | Chhindwara | WRD | MJP | 2011-09-28 | RO Official | 42261.12 | RIDF Loan 25 crore & above | Dam sheet works:30%,RBC sluice:80%,(LBC,Spillway,Brnch Cnl,Cnl Lining,Distribtries,Minors & Sbminors,Watercourses/FC,CD works)each 0%, Head wrks-20%, Head regltr-RBC45%, HRLBC-20%, Main Canal RBC-45%, MCLBC-22%.NB brd nil. Delay in LA,ToR, CoR Yes
16 | R162000138 | Pench Diiversion Project (Unit-I-H/W) | Chhindwara | WRD | MJP | 2013-01-10 | OIC+C | 42261.12 | RIDF Loan 25 crore & above | phy progress-24%, CoR-Rerevised AA may be obtained by the office once approved by the Govt, progress & speed of works was found quite satisfactory. Difference of approx Rs12 cr between actual expenditure and amt drawn from NABARD
16 | R162000139 | Primary Health Centre | Badwani | DHFW | Health |  |  | 59.5 | RIDF Loan upto 10 crore
16 | R162000140 | Primary Health Centre | Betul | DHFW | Health |  |  | 59.5 | RIDF Loan upto 10 crore
16 | R162000141 | Primary Health Centre | Betul | DHFW | Health |  |  | 59.5 | RIDF Loan upto 10 crore
16 | R162000142 | Primary Health Centre | Betul | DHFW | Health |  |  | 59.5 | RIDF Loan upto 10 crore
16 | R162000143 | Primary Health Centre | Betul | DHFW | Health |  |  | 59.5 | RIDF Loan upto 10 crore
16 | R162000144 | Primary Health Centre | Dhar | DHFW | Health |  |  | 59.5 | RIDF Loan upto 10 crore
16 | R162000145 | Primary Health Centre | Dhar | DHFW | Health |  |  | 59.5 | RIDF Loan upto 10 crore
16 | R162000146 | Primary Health Centre | Dindori | DHFW | Health |  |  | 59.5 | RIDF Loan upto 10 crore
16 | R162000147 | Primary Health Centre | Katni | DHFW | Health | 2014-03-25 | DDM | 59.5 | RIDF Loan upto 10 crore | No physical progress,
16 | R162000148 | Primary Health Centre | Katni | DHFW | Health |  |  | 59.5 | RIDF Loan upto 10 crore
16 | R162000149 | Primary Health Centre | Katni | DHFW | Health |  |  | 59.5 | RIDF Loan upto 10 crore
16 | R162000150 | Primary Health Centre | Khandwa | DHFW | Health |  |  | 59.5 | RIDF Loan upto 10 crore
16 | R162000151 | Primary Health Centre | Khandwa | DHFW | Health |  |  | 59.5 | RIDF Loan upto 10 crore
16 | R162000152 | Primary Health Centre | Khandwa | DHFW | Health |  |  | 59.5 | RIDF Loan upto 10 crore
16 | R162000153 | Primary Health Centre | Khargone | DHFW | Health |  |  | 59.5 | RIDF Loan upto 10 crore
16 | R162000154 | Primary Health Centre | Khargone | DHFW | Health |  |  | 59.5 | RIDF Loan upto 10 crore
16 | R162000155 | Primary Health Centre | Khargone | DHFW | Health |  |  | 59.5 | RIDF Loan upto 10 crore
16 | R162000156 | Primary Health Centre | Khargone | DHFW | Health |  |  | 59.5 | RIDF Loan upto 10 crore
16 | R162000157 | Primary Health Centre | Khargone | DHFW | Health |  |  | 59.5 | RIDF Loan upto 10 crore
16 | R162000158 | Primary Health Centre | Mandsaur | DHFW | Health |  |  | 59.5 | RIDF Loan upto 10 crore
16 | R162000159 | Primary Health Centre | Mandsaur | DHFW | Health | 2014-11-15 | DDM | 59.5 | RIDF Loan upto 10 crore | Phy prgs-100%.Visit book was not found. NABARD name was not mentioned on project board. G type quarter of Doctor is to be completed.
16 | R162000160 | Primary Health Centre | Mandsaur | DHFW | Health |  |  | 59.5 | RIDF Loan upto 10 crore
16 | R162000161 | Primary Health Centre | Mandsaur | DHFW | Health |  |  | 59.5 | RIDF Loan upto 10 crore
16 | R162000162 | Primary Health Centre | Panna | DHFW | Health |  |  | 59.5 | RIDF Loan upto 10 crore
16 | R162000163 | Primary Health Centre | Panna | DHFW | Health |  |  | 59.5 | RIDF Loan upto 10 crore
16 | R162000164 | Primary Health Centre | Satna | DHFW | Health |  |  | 59.5 | RIDF Loan upto 10 crore
16 | R162000165 | Primary Health Centre | Satna | DHFW | Health |  |  | 59.5 | RIDF Loan upto 10 crore
16 | R162000166 | Primary Health Centre | Sehore | DHFW | Health |  |  | 59.5 | RIDF Loan upto 10 crore
16 | R162000167 | Primary Health Centre | Shahdol | DHFW | Health |  |  | 59.5 | RIDF Loan upto 10 crore
16 | R162000168 | Primary Health Centre | Shajapur | DHFW | Health |  |  | 59.5 | RIDF Loan upto 10 crore
16 | R162000169 | Primary Health Centre | Shajapur | DHFW | Health |  |  | 59.5 | RIDF Loan upto 10 crore
16 | R162000170 | Sub Health Centre | Badwani | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000171 | Sub Health Centre | Badwani | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000172 | Sub Health Centre | Badwani | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000173 | Sub Health Centre | Badwani | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000174 | Sub Health Centre | Badwani | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000175 | Sub Health Centre | Badwani | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000176 | Sub Health Centre | Badwani | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000177 | Sub Health Centre | Badwani | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000178 | Sub Health Centre | Badwani | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000179 | Sub Health Centre | Badwani | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000180 | Sub Health Centre | Balaghat | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000181 | Sub Health Centre | Balaghat | DHFW | Health | 2013-06-13 | DDM | 10.2 | RIDF Loan upto 10 crore | Phy prgs-Health centre blg->75%, 85 to 90% completion, ToR/CoR-No, Delay in getting work order from dept hence commencement of project got delays. Project Board-not displayed, no record found
16 | R162000182 | Sub Health Centre | Balaghat | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000183 | Sub Health Centre | Balaghat | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000184 | Sub Health Centre | Balaghat | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000185 | Sub Health Centre | Balaghat | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000186 | Sub Health Centre | Balaghat | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000187 | Sub Health Centre | Balaghat | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000188 | Sub Health Centre | Balaghat | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000189 | Sub Health Centre | Balaghat | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000190 | Sub Health Centre | Tikamgarh | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000191 | Sub Health Centre | Tikamgarh | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000192 | Sub Health Centre | Tikamgarh | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000193 | Sub Health Centre | Tikamgarh | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000194 | Sub Health Centre | Tikamgarh | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000195 | Sub Health Centre | Tikamgarh | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000196 | Sub Health Centre | Burhanpur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000197 | Sub Health Centre | Burhanpur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000198 | Sub Health Centre | Burhanpur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000199 | Sub Health Centre | Burhanpur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000200 | Sub Health Centre | Burhanpur | DHFW | Health | 2013-03-30 | DDM | 10.2 | RIDF Loan upto 10 crore | Phy progs-50%, NB Brd-No. Mtnance of rcord-Yes. GoMP officials Visit details available
16 | R162000201 | Sub Health Centre | Burhanpur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000202 | Sub Health Centre | Burhanpur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000203 | Sub Health Centre | Burhanpur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000204 | Sub Health Centre | Burhanpur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000205 | Sub Health Centre | Burhanpur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000206 | Sub Health Centre | Chhindwara | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000207 | Sub Health Centre | Chhindwara | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000208 | Sub Health Centre | Chhindwara | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000209 | Sub Health Centre | Chhindwara | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000210 | Sub Health Centre | Chhindwara | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000211 | Sub Health Centre | Chhindwara | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000212 | Sub Health Centre | Chhindwara | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000213 | Sub Health Centre | Chhindwara | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000214 | Sub Health Centre | Chhindwara | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000215 | Sub Health Centre | Chhindwara | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000216 | Sub Health Centre | Dewas | DHFW | Health | 2013-02-28 | DDM | 10.2 | RIDF Loan upto 10 crore | Phy progress-95%, maintained books, NB Brd-No, Quality Control System introduced,
16 | R162000217 | Sub Health Centre | Dewas | DHFW | Health | 2013-02-28 | DDM | 10.2 | RIDF Loan upto 10 crore | Phy progress-60%, Fund flow problem-delay in payment from the SG resulting in delayed payment to contractor. Slow progress, Maintained Books, NB Brd-No
16 | R162000218 | Sub Health Centre | Dewas | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000219 | Sub Health Centre | Dewas | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000220 | Sub Health Centre | Dewas | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000221 | Sub Health Centre | Dewas | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000222 | Sub Health Centre | Dewas | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000223 | Sub Health Centre | Dewas | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000224 | Sub Health Centre | Dewas | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000225 | Sub Health Centre | Dewas | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000226 | Sub Health Centre | Dewas | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000227 | Sub Health Centre | Dewas | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000228 | Sub Health Centre | Dewas | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000229 | Sub Health Centre | Dewas | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000230 | Sub Health Centre | Dindori | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000231 | Sub Health Centre | Dindori | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000232 | Sub Health Centre | Dindori | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000233 | Sub Health Centre | Dindori | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000234 | Sub Health Centre | Dindori | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000235 | Sub Health Centre | Dindori | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000236 | Sub Health Centre | Dindori | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000237 | Sub Health Centre | Dindori | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000238 | Sub Health Centre | Dindori | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000239 | Sub Health Centre | Dindori | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000240 | Sub Health Centre | Jhabua | DHFW | Health | 2013-03-07 | DDM | 10.2 | RIDF Loan upto 10 crore | Phy progress-100%, Dt of phy completion -05.10.2012, Books-after completion of the project the records have been passed on to Div Office, Bhopal. NB Brd-not displayed
16 | R162000241 | Sub Health Centre | Jhabua | DHFW | Health | 2013-03-07 | DDM | 10.2 | RIDF Loan upto 10 crore | Phy progress--90%, QC Test carried in Govt.lab, NB Brd-No. Visit records to be maintained properly
16 | R162000242 | Sub Health Centre | Jhabua | DHFW | Health | 2013-03-07 | DDM | 10.2 | RIDF Loan upto 10 crore | phy progress-100%, after completion of the project record have been transferred to Div Office, Bhopal, NB Brd-No. Visit records to be maintained
16 | R162000243 | Sub Health Centre | Jhabua | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000244 | Sub Health Centre | Jhabua | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000245 | Sub Health Centre | Jhabua | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000246 | Sub Health Centre | Jhabua | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000247 | Sub Health Centre | Jhabua | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000248 | Sub Health Centre | Jhabua | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000249 | Sub Health Centre | Jhabua | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000250 | Sub Health Centre | Katni | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000251 | Sub Health Centre | Katni | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000252 | Sub Health Centre | Katni | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000253 | Sub Health Centre | Katni | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000254 | Sub Health Centre | Katni | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000255 | Sub Health Centre | Katni | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000256 | Sub Health Centre | Katni | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000257 | Sub Health Centre | Katni | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000258 | Sub Health Centre | Katni | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000259 | Sub Health Centre | Katni | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000260 | Sub Health Centre | Khargone | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000261 | Sub Health Centre | Khargone | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000262 | Sub Health Centre | Khargone | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000263 | Sub Health Centre | Khargone | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000264 | Sub Health Centre | Khargone | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000265 | Sub Health Centre | Khargone | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000266 | Sub Health Centre | Khargone | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000267 | Sub Health Centre | Khargone | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000268 | Sub Health Centre | Khargone | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000269 | Sub Health Centre | Khargone | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000270 | Sub Health Centre | Mandsaur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000271 | Sub Health Centre | Mandsaur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000272 | Sub Health Centre | Mandsaur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000273 | Sub Health Centre | Mandsaur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000274 | Sub Health Centre | Mandsaur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000275 | Sub Health Centre | Mandsaur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000276 | Sub Health Centre | Mandsaur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000277 | Sub Health Centre | Mandsaur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000278 | Sub Health Centre | Mandsaur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000279 | Sub Health Centre | Mandsaur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000280 | Sub Health Centre | Mandla | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000281 | Sub Health Centre | Mandla | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000282 | Sub Health Centre | Mandla | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000283 | Sub Health Centre | Mandla | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000284 | Sub Health Centre | Mandla | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000285 | Sub Health Centre | Mandla | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000286 | Sub Health Centre | Mandla | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000287 | Sub Health Centre | Mandla | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000288 | Sub Health Centre | Mandla | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000289 | Sub Health Centre | Mandla | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000290 | Sub Health Centre | Ashoknagar | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000291 | Sub Health Centre | Ashoknagar | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000292 | Sub Health Centre | Ashoknagar | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000293 | Sub Health Centre | Ashoknagar | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000294 | Sub Health Centre | Ashoknagar | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000295 | Sub Health Centre | Ashoknagar | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000296 | Sub Health Centre | Ashoknagar | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000297 | Sub Health Centre | Ashoknagar | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000298 | Sub Health Centre | Ashoknagar | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000299 | Sub Health Centre | Ashoknagar | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000300 | Sub Health Centre | Ashoknagar | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000301 | Sub Health Centre | Ashoknagar | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000302 | Sub Health Centre | Ashoknagar | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000303 | Sub Health Centre | Bhind | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000304 | Sub Health Centre | Bhind | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000305 | Sub Health Centre | Bhind | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000306 | Sub Health Centre | Bhind | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000307 | Sub Health Centre | Bhind | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000308 | Sub Health Centre | Bhind | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000309 | Sub Health Centre | Bhind | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000310 | Sub Health Centre | Bhind | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000311 | Sub Health Centre | Bhind | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000312 | Sub Health Centre | Bhind | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000313 | Sub Health Centre | Bhind | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000314 | Sub Health Centre | Bhind | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000315 | Sub Health Centre | Bhind | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000316 | Sub Health Centre | Bhind | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000317 | Sub Health Centre | Bhind | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000318 | Sub Health Centre | Panna | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000319 | Sub Health Centre | Panna | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000320 | Sub Health Centre | Panna | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000321 | Sub Health Centre | Panna | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000322 | Sub Health Centre | Panna | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000323 | Sub Health Centre | Datia | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000324 | Sub Health Centre | Datia | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000325 | Sub Health Centre | Datia | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000326 | Sub Health Centre | Datia | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000327 | Sub Health Centre | Datia | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000328 | Sub Health Centre | Datia | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000329 | Sub Health Centre | Datia | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000330 | Sub Health Centre | Datia | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000331 | Sub Health Centre | Datia | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000332 | Sub Health Centre | Datia | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000333 | Sub Health Centre | Dhar | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000334 | Sub Health Centre | Dhar | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000335 | Sub Health Centre | Dhar | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000336 | Sub Health Centre | Dhar | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000337 | Sub Health Centre | Dhar | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000338 | Sub Health Centre | Dhar | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000339 | Sub Health Centre | Dhar | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000340 | Sub Health Centre | Dhar | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000341 | Sub Health Centre | Dhar | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000342 | Sub Health Centre | Dhar | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000343 | Sub Health Centre | Morena | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000344 | Sub Health Centre | Morena | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000345 | Sub Health Centre | Morena | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000346 | Sub Health Centre | Morena | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000347 | Sub Health Centre | Morena | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000348 | Sub Health Centre | Narsinghpur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000349 | Sub Health Centre | Narsinghpur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000350 | Sub Health Centre | Narsinghpur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000351 | Sub Health Centre | Narsinghpur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000352 | Sub Health Centre | Narsinghpur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000353 | Sub Health Centre | Narsinghpur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000354 | Sub Health Centre | Narsinghpur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000355 | Sub Health Centre | Narsinghpur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000356 | Sub Health Centre | Ratlam | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000357 | Sub Health Centre | Ratlam | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000358 | Sub Health Centre | Ratlam | DHFW | Health | 2013-09-13 | DDM | 10.2 | RIDF Loan upto 10 crore | Phy prgs=100%, NB Brd not displayed
16 | r162000358 | Sub Health Centre | Ratlam | DHFW | Health | 2013-09-13 | DDM | 10.2 | RIDF Loan upto 10 crore | Work completed as per plan and schedule
16 | R162000359 | Sub Health Centre | Ratlam | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000360 | Sub Health Centre | Ratlam | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000361 | Sub Health Centre | Ratlam | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000362 | Sub Health Centre | Ratlam | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000363 | Sub Health Centre | Ratlam | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000364 | Sub Health Centre | Ratlam | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000365 | Sub Health Centre | Ratlam | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000366 | Sub Health Centre | Shajapur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000367 | Sub Health Centre | Shajapur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000368 | Sub Health Centre | Shajapur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000369 | Sub Health Centre | Shajapur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000370 | Sub Health Centre | Shajapur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000371 | Sub Health Centre | Shajapur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000372 | Sub Health Centre | Shajapur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000373 | Sub Health Centre | Shajapur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000374 | Sub Health Centre | Shajapur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000375 | Sub Health Centre | Shajapur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000376 | Sub Health Centre | Shajapur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000377 | Sub Health Centre | Shajapur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000378 | Sub Health Centre | Shajapur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000379 | Sub Health Centre | Shajapur | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000380 | Sub Health Centre | Ujjain | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000381 | Sub Health Centre | Ujjain | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000382 | Sub Health Centre | Ujjain | DHFW | Health | 2013-02-22 | DDM | 10.2 | RIDF Loan upto 10 crore | Phy progress--51to75%, TOR-LA, COR-No, Visit register-no recrd, NB Brd- detial of work displayed but asst fm NB not affixed, Drainag plan shd be incld with te drawings, boundry wall shld be included as part of the project
16 | R162000383 | Sub Health Centre | Ujjain | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000384 | Sub Health Centre | Ujjain | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000385 | Sub Health Centre | Ujjain | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000386 | Sub Health Centre | Ujjain | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000387 | Sub Health Centre | Ujjain | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000388 | Sub Health Centre | Ujjain | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000389 | Sub Health Centre | Ujjain | DHFW | Health | 2013-02-22 | DDM | 10.2 | RIDF Loan upto 10 crore
16 | R162000390 | Sub Health Centre | Ujjain | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000391 | Sub Health Centre | Ujjain | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000392 | Sub Health Centre | Ujjain | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000393 | Sub Health Centre | Ujjain | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000394 | Sub Health Centre | Ujjain | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000395 | Sub Health Centre | Ujjain | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000396 | Sub Health Centre | Ujjain | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000397 | Sub Health Centre | Seoni | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000398 | Sub Health Centre | Seoni | DHFW | Health | 2013-03-26 | DDM | 10.2 | RIDF Loan upto 10 crore | phy pgrs-83%. ToR-delays due to LA,Lack of adequate &professionally qualified staff, statutory clearance . No sign board, No record of visit by other official from Health dept
16 | R162000399 | Sub Health Centre | Seoni | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000400 | Sub Health Centre | Seoni | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000401 | Sub Health Centre | Seoni | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000402 | Sub Health Centre | Seoni | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000403 | Sub Health Centre | Seoni | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000404 | Sub Health Centre | Seoni | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000405 | Sub Health Centre | Seoni | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000406 | Sub Health Centre | Seoni | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000407 | Sub Health Centre | Seoni | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000408 | Sub Health Centre | Seoni | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000409 | Sub Health Centre | Seoni | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000410 | Sub Health Centre | Seoni | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000411 | Sub Health Centre | Seoni | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000412 | Sub Health Centre | Seoni | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000413 | Sub Health Centre | Seoni | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000414 | Sub Health Centre | Rajgarh | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000415 | Sub Health Centre | Rajgarh | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000416 | Sub Health Centre | Rajgarh | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000417 | Sub Health Centre | Rajgarh | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000418 | Sub Health Centre | Rajgarh | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000419 | Sub Health Centre | Rajgarh | DHFW | Health |  |  | 10.2 | RIDF Loan upto 10 crore
16 | R162000420 | Community Health Center | Anuppur | DHFW | Health |  |  | 158.97 | RIDF Loan upto 10 crore
16 | R162000421 | Community Health Center | Ashoknagar | DHFW | Health |  |  | 169.65 | RIDF Loan upto 10 crore
16 | R162000422 | Community Health Center | Badwani | DHFW | Health |  |  | 142.75 | RIDF Loan upto 10 crore
16 | R162000423 | Community Health Center | Badwani | DHFW | Health |  |  | 166.96 | RIDF Loan upto 10 crore
16 | R162000424 | Community Health Center | Badwani | DHFW | Health |  |  | 146.46 | RIDF Loan upto 10 crore
16 | R162000425 | Community Health Center | Balaghat | DHFW | Health |  |  | 127.16 | RIDF Loan upto 10 crore
16 | R162000426 | Community Health Center | Betul | DHFW | Health | 2013-03-11 | DDM | 156.71 | RIDF Loan upto 10 crore | HC blg, Boundry wall - >76%, G & H type quarter-upto 25%, total phy proress-80%, 03mths delay due to encroachement of land handed over to for constru purpose, work may completed by 30.06.2013
16 | R162000427 | Community Health Center | Chhatarpur | DHFW | Health |  |  | 149.86 | RIDF Loan upto 10 crore
16 | R162000428 | Community Health Center | Chhatarpur | DHFW | Health |  |  | 153.11 | RIDF Loan upto 10 crore
16 | R162000429 | Community Health Center | Datia | DHFW | Health |  |  | 154.06 | RIDF Loan upto 10 crore
16 | R162000430 | Community Health Center | Datia | DHFW | Health |  |  | 130.01 | RIDF Loan upto 10 crore
16 | R162000431 | Community Health Center | Damoh | DHFW | Health | 2013-09-21 | DDM | 143.74 | RIDF Loan upto 10 crore | Phy prgs-100%, ToR-Electrical lines of MPEB passing overhead had to be shifted, NB Brd-not displayed
16 | R162000432 | Community Health Center | Dewas | DHFW | Health |  |  | 183.74 | RIDF Loan upto 10 crore
16 | R162000433 | Community Health Center | Dhar | DHFW | Health |  |  | 124.75 | RIDF Loan upto 10 crore
16 | R162000434 | Community Health Center | Dhar | DHFW | Health |  |  | 123.01 | RIDF Loan upto 10 crore
16 | R162000435 | Community Health Center | Dindori | DHFW | Health |  |  | 149.63 | RIDF Loan upto 10 crore
16 | R162000436 | Community Health Center | Guna | DHFW | Health |  |  | 61.06 | RIDF Loan upto 10 crore
16 | R162000437 | Community Health Center | Harda | DHFW | Health | 2013-10-23 | DDM | 160.85 | RIDF Loan upto 10 crore | Phy prgs=50%, ToR-LA, NB Brd not displayed
16 | R162000438 | Community Health Center | Harda | DHFW | Health |  |  | 154.96 | RIDF Loan upto 10 crore
16 | R162000439 | Community Health Center | Hoshangabad | DHFW | Health |  |  | 100.82 | RIDF Loan upto 10 crore
16 | R162000440 | Community Health Center | Indore | DHFW | Health |  |  | 129.94 | RIDF Loan upto 10 crore
16 | R162000441 | Community Health Center | Jhabua | DHFW | Health | 2014-02-05 | DDM | 152.07 | RIDF Loan upto 10 crore | Phy Prgs-100%/ No separate record of the visit to the project place is maintained/ NB Brd not displayed
16 | R162000442 | Community Health Center | Katni | DHFW | Health |  |  | 158.81 | RIDF Loan upto 10 crore
16 | R162000443 | Community Health Center | Mandla | DHFW | Health |  |  | 144.54 | RIDF Loan upto 10 crore
16 | R162000444 | Community Health Center | Morena | DHFW | Health |  |  | 140.13 | RIDF Loan upto 10 crore
16 | R162000445 | Community Health Center | Morena | DHFW | Health |  |  | 47.18 | RIDF Loan upto 10 crore
16 | R162000446 | Community Health Center | Neemuch | DHFW | Health |  |  | 82.08 | RIDF Loan upto 10 crore
16 | R162000447 | Community Health Center | Panna | DHFW | Health |  |  | 146.78 | RIDF Loan upto 10 crore
16 | R162000448 | Community Health Center | Raisen | DHFW | Health |  |  | 153.11 | RIDF Loan upto 10 crore
16 | R162000449 | Community Health Center | Rajgarh | DHFW | Health | 2013-01-02 | DDM | 149.13 | RIDF Loan upto 10 crore | Phy progress- 40to50%, TOR-LA, NB Brd-No
16 | R162000450 | Community Health Center | Rajgarh | DHFW | Health | 2013-01-02 | DDM | 102.88 | RIDF Loan upto 10 crore | Phy progress- 50to60%, TOR-LA, NB Brd-No
16 | R162000451 | Community Health Center | Ratlam | DHFW | Health |  |  | 87.49 | RIDF Loan upto 10 crore
16 | R162000452 | Community Health Center | Rewa | DHFW | Health |  |  | 121.65 | RIDF Loan upto 10 crore
16 | R162000453 | Community Health Center | Rewa | DHFW | Health |  |  | 137.73 | RIDF Loan upto 10 crore
16 | R162000454 | Community Health Center | Sagar | DHFW | Health |  |  | 148.69 | RIDF Loan upto 10 crore
16 | R162000455 | Community Health Center | Satna | DHFW | Health |  |  | 25.33 | RIDF Loan upto 10 crore
16 | R162000456 | Community Health Center | Satna | DHFW | Health |  |  | 135.34 | RIDF Loan upto 10 crore
16 | R162000457 | Community Health Center | Satna | DHFW | Health |  |  | 182.08 | RIDF Loan upto 10 crore
16 | R162000458 | Community Health Center | Sehore | DHFW | Health |  |  | 146.33 | RIDF Loan upto 10 crore
16 | R162000459 | Community Health Center | Sehore | DHFW | Health |  |  | 154.96 | RIDF Loan upto 10 crore
16 | R162000460 | Community Health Center | Shajapur | DHFW | Health | 2013-01-04 | DDM | 152.05 | RIDF Loan upto 10 crore | Phy progress-upto 90%,TOR-due to LA & shifting of High tension electricity wire, NB Brd-No
16 | R162000461 | Community Health Center | Shivpuri | DHFW | Health | 2014-08-22 | DDM | 153.16 | RIDF Loan upto 10 crore | Phy prgs-59%,(Problems-LA,Fund flow, Stautory clearance), Encroached by private party/ies, Site book not available, NB brd not fixed, Boundry wall construction work not yet commeced
16 | R162000462 | Community Health Center | Singhroli | DHFW | Health |  |  | 156.09 | RIDF Loan upto 10 crore
16 | R162000463 | Community Health Center | Tikamgarh | DHFW | Health |  |  | 149.18 | RIDF Loan upto 10 crore
16 | R162000464 | Community Health Center | Tikamgarh | DHFW | Health |  |  | 214.63 | RIDF Loan upto 10 crore
16 | R162000465 | Community Health Center | Ujjain | DHFW | Health |  |  | 147.76 | RIDF Loan upto 10 crore
16 | R162000466 | Community Health Center | Ujjain | DHFW | Health |  |  | 180.17 | RIDF Loan upto 10 crore
16 | R162000467 | Community Health Center | Umaria | DHFW | Health |  |  | 144.61 | RIDF Loan upto 10 crore
16 | R162000468 | Community Health Center | Vidisha | DHFW | Health |  |  | 167.86 | RIDF Loan upto 10 crore
16 | R162000469 | Community Health Center | Shahdol | DHFW | Health |  |  | 152.07 | RIDF Loan upto 10 crore
16 | R162000470 | Community Health Center | Anuppur | DHFW | Health |  |  | 170.09 | RIDF Loan upto 10 crore
16 | R162000471 | Community Health Center | Anuppur | DHFW | Health |  |  | 156.04 | RIDF Loan upto 10 crore
16 | R162000472 | Community Health Center | Bhopal | DHFW | Health |  |  | 170.09 | RIDF Loan upto 10 crore
16 | R162000473 | Community Health Center | Chhatarpur | DHFW | Health |  |  | 156.04 | RIDF Loan upto 10 crore
16 | R162000474 | Community Health Center | Dewas | DHFW | Health | 2013-02-28 | DDM | 156.04 | RIDF Loan upto 10 crore | Phy progress-45%, Fund flow problem, late submission of Architect's drawing, delay in payment to contractor, Books maintained, NB Brd-No
16 | R162000475 | Community Health Center | Katani | DHFW | Health |  |  | 170.09 | RIDF Loan upto 10 crore
16 | R162000476 | Community Health Center | Khargone | DHFW | Health |  |  | 170.09 | RIDF Loan upto 10 crore
16 | R162000477 | Community Health Center | Khargone | DHFW | Health |  |  | 170.09 | RIDF Loan upto 10 crore
16 | R162000478 | Community Health Center | Mandsaur | DHFW | Health |  |  | 170.09 | RIDF Loan upto 10 crore
16 | R162000479 | Community Health Center | Narsinghpur | DHFW | Health |  |  | 156.04 | RIDF Loan upto 10 crore
16 | R162000480 | Community Health Center | Neemuch | DHFW | Health |  |  | 170.09 | RIDF Loan upto 10 crore
16 | R162000481 | Community Health Center | Raisen | DHFW | Health |  |  | 170.09 | RIDF Loan upto 10 crore
16 | R162000482 | Community Health Center | Rewa | DHFW | Health |  |  | 170.09 | RIDF Loan upto 10 crore
16 | R162000483 | Community Health Center | Sehore | DHFW | Health |  |  | 156.04 | RIDF Loan upto 10 crore
16 | R162000484 | Community Health Center | Shajapur | DHFW | Health |  |  | 170.09 | RIDF Loan upto 10 crore
16 | R162000485 | Community Health Center | Shahdol | DHFW | Health |  |  | 170.09 | RIDF Loan upto 10 crore
16 | R162000486 | Community Health Center | Singhroli | DHFW | Health |  |  | 170.09 | RIDF Loan upto 10 crore
16 | R162000487 | Community Health Center | Singhroli | DHFW | Health |  |  | 170.09 | RIDF Loan upto 10 crore
16 | R162000488 | Community Health Center | Ujjain | DHFW | Health | 2013-02-23 | DDM | 170.09 | RIDF Loan upto 10 crore | phy progress-60%, ToR-Delayed due to slow work by contractor, CoR-No, Contractor was very slow, NB Brd-No, No site Lab, Meeting Hall may be included in CHC, Water Harvesting system may be included
16 | R162000489 | Amgawa to Podi Road | Anuppur | PWD | Road | 2014-12-26 | DDM | 307.46 | RIDF Loan upto 10 crore | Phy prgs-40-50%, out of 17 CD, only 6 CD completed, 6.60km is under forest land (forest permission is yet to be obtained).As on date work is on halt, Dept has given permission for 5.5m widtdh but CD work requires 7.5 m width. NB brd not displayed.
16 | R162000490 | Nigwani Kothi Road | Anuppur | PWD | Road |  |  | 151.58 | RIDF Loan upto 10 crore
16 | R162000491 | Jaithari to Jhaital Road | Anuppur | PWD | Road | 2014-03-26 | DDM | 123.21 | RIDF Loan upto 10 crore | Phy prgs -20%, Implementation delay due to contractor problem,Electricity Dept permission yet to be received, NB Brd not displayed.As regards with CC work embankment is just 4 mtr & no space is available for shoulders & allowing traffic in the road.
16 | R162000492 | Jaithari Kotma Road to Village Pondi Chondi | Anuppur | PWD | Road |  |  | 99.7 | RIDF Loan upto 10 crore
16 | R162000493 | Kotma Nigwani Road to Village Pathroud | Anuppur | PWD | Road |  |  | 82.39 | RIDF Loan upto 10 crore
16 | R162000494 | Godaru river to Dhumma Deogawan Jogi Tola road | Anuppur | PWD | Road |  |  | 105.08 | RIDF Loan upto 10 crore
16 | R162000495 | Katha,Hirapura Sikri To Lahar Road | Bhind | PWD | Road |  |  | 148.62 | RIDF Loan upto 10 crore
16 | R162000496 | Narol to Mihoni Mata Road | Bhind | PWD | Road |  |  | 123.02 | RIDF Loan upto 10 crore
16 | R162000497 | Shayampura to Rahawali Uwari Road | Bhind | PWD | Road |  |  | 147.23 | RIDF Loan upto 10 crore
16 | R162000498 | Alipura Churwani Road | Chhatarpur | PWD | Road |  |  | 146.42 | RIDF Loan upto 10 crore
16 | R162000499 | Upgrading of Girdhouri Aktoha Road | Chhatrapur | PWD | Road |  |  | 47.27 | RIDF Loan upto 10 crore
16 | R162000500 | Syami nalla Lahar Main Road to Balaji Mandir App. Road | Chhatrapur | PWD | Road |  |  | 59.82 | RIDF Loan upto 10 crore
16 | R162000501 | CC Road of Prakrima Road at Chhatrapur | Chhatrapur | PWD | Road |  |  | 170.35 | RIDF Loan upto 10 crore
16 | R162000502 | Karaboh to Khajri Road | Chhindwara | PWD | Road |  |  | 50.3 | RIDF Loan upto 10 crore
16 | R162000503 | Morli Junction to Jhanda Kudwari Rohna khurd Roa | Chhindwara | PWD | Road | 2013-03-05 | DDM | 175.69 | RIDF Loan upto 10 crore | phy pgrs>76%. ToR-LA,due to rainy season & poor fund flow. Dtls of vist not available. NB Brd-displayed. Reduction in length on a/c of the fact that the balance length/onward continuation of the road had been earmarked and completed under PMGSY
16 | R162000504 | Bomaliya Hirawadi Road | Chhindwara | PWD | Road |  |  | 169.56 | RIDF Loan upto 10 crore
16 | R162000505 | Narsala Dighori Road | Chhindwara | PWD | Road |  |  | 27.3 | RIDF Loan upto 10 crore
16 | R162000506 | Guddam Mankadehi Road | Chhindwara | PWD | Road |  |  | 82.25 | RIDF Loan upto 10 crore
16 | R162000507 | Bijagora Bhavari Road | Chhindwara | PWD | Road |  |  | 138.55 | RIDF Loan upto 10 crore
16 | R162000508 | Ponia Penchpul to Top pipria Khati | Chhindwara | PWD | Road |  |  | 115.26 | RIDF Loan upto 10 crore
16 | R162000509 | Tighara Pounhara Road | Chhindwara | PWD | Road |  |  | 84.15 | RIDF Loan upto 10 crore
16 | R162000510 | Babai Palatwada Road | Chhindwara | PWD | Road |  |  | 62.89 | RIDF Loan upto 10 crore
16 | R162000511 | Kothar Machighat Road | Chhindwara | PWD | Road |  |  | 45.69 | RIDF Loan upto 10 crore
16 | R162000512 | Lingapani Umariya Road | Chhindwara | PWD | Road |  |  | 68.7 | RIDF Loan upto 10 crore
16 | R162000513 | Kuajhiri to Girjamai Swam Road | Chhindwara | PWD | Road |  |  | 80.54 | RIDF Loan upto 10 crore
16 | R162000514 | Pindraikala Kotalbarri Bijapani Road | Chhindwara | PWD | Road |  |  | 143.86 | RIDF Loan upto 10 crore
16 | R162000515 | Bareghat Devgarh Road | Chhindwara | PWD | Road |  |  | 130.18 | RIDF Loan upto 10 crore
16 | R162000516 | Bhaisadand Payali Road | Chhindwara | PWD | Road |  |  | 45.99 | RIDF Loan upto 10 crore
16 | R162000517 | Loniyamaru Bilwa Road | Chhindwara | PWD | Road |  |  | 72.47 | RIDF Loan upto 10 crore
16 | R162000518 | Gumtara-Jamtara Road | Chhindwara | PWD | Road |  |  | 159.01 | RIDF Loan upto 10 crore
16 | R162000519 | Chhabra to Gorakhghat Road | Chhindwara | PWD | Road |  |  | 135.27 | RIDF Loan upto 10 crore
16 | R162000520 | Sheeladehi-Moary-Ghoghry-Ambada Road | Chhindwara | PWD | Road |  |  | 183.72 | RIDF Loan upto 10 crore
16 | R162000521 | Bhandai Ghogra Road | Chhindwara | PWD | Road |  |  | 115.58 | RIDF Loan upto 10 crore
16 | R162000522 | Kedarpur Jamuniya Road | Chhindwara | PWD | Road |  |  | 88.9 | RIDF Loan upto 10 crore
16 | R162000523 | Chargaon Bhajipani Road | Chhindwara | PWD | Road |  |  | 108.62 | RIDF Loan upto 10 crore
16 | R162000524 | Chargaon Bandra Road | Chhindwara | PWD | Road |  |  | 103.2 | RIDF Loan upto 10 crore
16 | R162000525 | KuabadlaNandiya to Khutty Road | Chhindwara | PWD | Road |  |  | 116.06 | RIDF Loan upto 10 crore
16 | R162000526 | Siras Dhamnia Road | Chhindwara | PWD | Road |  |  | 106.66 | RIDF Loan upto 10 crore
16 | R162000527 | Jhouth Kalan to Ghatiya Road | Chhindwara | PWD | Road |  |  | 80.54 | RIDF Loan upto 10 crore
16 | R162000528 | Chhindi Jogimouar Road | Chhindwara | PWD | Road |  |  | 162.84 | RIDF Loan upto 10 crore
16 | R162000529 | Jamuniya Hirripathar Bijoripathar Road | Chhindwara | PWD | Road |  |  | 322.26 | RIDF Loan upto 10 crore
16 | R162000530 | Damkhoh Jhirapani Road | Chhindwara | PWD | Road |  |  | 84.66 | RIDF Loan upto 10 crore
16 | R162000531 | Ekelkhera Richheda Dhanshiya Hevrad Maduua Road | Chhindwara | PWD | Road | 2013-03-05 | DDM | 303.36 | RIDF Loan upto 10 crore | phy pgrs>76%.ToR-Hard rock,LA,due to rainy season & poor fund flow.Dtls of vist not available. NB Brd-displayed at one end. As no space is avlble, the road is being diverted to rail line. side berms rquired strengthening. Surface of road rough & nt propr
16 | R162000532 | Koudiya Ghoghara Road | Chhindwara | PWD | Road |  |  | 112.11 | RIDF Loan upto 10 crore
16 | R162000533 | Goraghat Indargarh Road to Bhadol via senpura rooran village | Datia | PWD | Road |  |  | 148 | RIDF Loan upto 10 crore
16 | R162000534 | Seondha Chungi to Gwalior Jhansi Bye Pass Road | Datia | PWD | Road | 2013-02-19 | DDM | 94.5 | RIDF Loan upto 10 crore | All works excpt BT(95% progress achvd) 100% complete. TOR-Hilly & rocky terrain & low quoted rates on Contractor side, Site visit recrds-maintained at PWD office but no office has been set up at site, NB Brd-not displayed. Poor coordination
16 | R162000535 | Hinotiya to Chirol Village | Datia | PWD | Road | 2013-11-29 | DDM | 127.14 | RIDF Loan upto 10 crore | Phy prgs=100% except Black topping, ToR -unstable cut slopes due to sandy loam soil, Forest dept clearance took 2 mths, Supply of bitumen was choked for 2 mths due to maintenance shut down of Agra Refinery,NB Brd not displayed
16 | R162000536 | Baroni Sonagir Approach Road | Datia | PWD | Road |  |  | 100.77 | RIDF Loan upto 10 crore
16 | R162000537 | Goraghat to Indargarh via Khajoori village | Datia | PWD | Road |  |  | 173.73 | RIDF Loan upto 10 crore
16 | R162000538 | Construction of Ramgarh Approach Road | Datia | PWD | Road |  |  | 53.95 | RIDF Loan upto 10 crore
16 | R162000539 | Kitiya to Siraliya road | Dewas | PWD | Road |  |  | 163.86 | RIDF Loan upto 10 crore
16 | R162000540 | Kitiya to Siya Road | Dewas | PWD | Road |  |  | 92.83 | RIDF Loan upto 10 crore
16 | R162000541 | Kantaphod to Singladesh (Bairagarah to Singladeh road) | Dewas | PWD | Road | 2014-06-25 | DDM | 488.74 | RIDF Loan upto 10 crore | Project completed, ToR due delayed approval of revised drawings/designs of culverts and causeways at various levels, hindrance in access due to heavy rains . No CoR, NB Board not displayed
16 | R162000542 | Umeda To Harangaon road | Dewas | PWD | Road | 2013-07-31 | DDM | 155.14 | RIDF Loan upto 10 crore | Phy prgs-completed, ToR-LA,delayed approval of drawing/design, Hindrance in access due to heavy rains in the rainy season, No CoR, NB board not displayed
16 | R162000543 | Sundrel To Hirapur | Dewas | PWD | Road |  |  | 54.18 | RIDF Loan upto 10 crore
16 | R162000544 | Samgi Kamalpur via Kailod Road | Dewas | PWD | Road |  |  | 102.93 | RIDF Loan upto 10 crore
16 | R162000545 | Bangar Beragarh Hirli Road | Dewas | PWD | Road |  |  | 244.9 | RIDF Loan upto 10 crore
16 | R162000546 | Rabdiya Sidni Fatehpur Phata Road | Dewas | PWD | Road |  |  | 194.6 | RIDF Loan upto 10 crore
16 | R162000547 | Sohagpur Kamtee Madhai Road | Hoshangabad | PWD | Road |  |  | 147.95 | RIDF Loan upto 10 crore
16 | R162000548 | Samadhi Bamhnoda Road | Jabalpur | PWD | Road |  |  | 121.86 | RIDF Loan upto 10 crore
16 | R162000549 | Mohas Kathotia Godana Road | Katni | PWD | Road |  |  | 302.42 | RIDF Loan upto 10 crore
16 | R162000550 | Bhudsa Bhajiya Road | Katni | PWD | Road |  |  | 118.82 | RIDF Loan upto 10 crore
16 | R162000551 | Mohas Lalpur Pali Road | Katni | PWD | Road | 2015-01-17 | DDM | 324.54 | RIDF Loan upto 10 crore | Phy prgs-100%. Positive features-6 villages directly benefitted. Shortest route created for the benefits of school children, market accessibility for agri crops
16 | R162000552 | Deorkala Mehgaon Road | Katni | PWD | Road |  |  | 75.22 | RIDF Loan upto 10 crore
16 | R162000553 | Deora Mohas Road | Katni | PWD | Road |  |  | 89.02 | RIDF Loan upto 10 crore
16 | R162000554 | Sarswahi Surkhi Road | Katni | PWD | Road |  |  | 66.96 | RIDF Loan upto 10 crore
16 | R162000555 | Upgradation Of Tilgawan Bandha Magardha Road | Katni | PWD | Road |  |  | 189.52 | RIDF Loan upto 10 crore
16 | R162000556 | Kanhwara Patwara Kailwara Road | Katni | PWD | Road |  |  | 80.68 | RIDF Loan upto 10 crore
16 | R162000557 | Dhanwahi neemkheda Badkheda Kirhai Pipariy Road | Katni | PWD | Road | 2015-01-20 | DDM | 339.51 | RIDF Loan upto 10 crore | Phy prgs-100% except CD works (66.91%), Positive features-4 villages benefitted, road linked State Highway, road directly connected to school
16 | R162000558 | Tikuri Barkheda Pahari Road | Katni | PWD | Road | 2014-01-01 | DDM | 339.08 | RIDF Loan upto 10 crore | Phy prgs-(LA-N/A, Earthwork-90%, WBM-55%,BT-35%,CD-80%),
16 | R162000559 | Amadi to Gulzera Road | Khargone | PWD | Road |  |  | 235.08 | RIDF Loan upto 10 crore
16 | R162000560 | Nimrani to Satkut Road | Khargone | PWD | Road |  |  | 327.16 | RIDF Loan upto 10 crore
16 | R162000561 | Khargone Mangrool Road | Khargone | PWD | Road |  |  | 83.42 | RIDF Loan upto 10 crore
16 | R162000562 | Mohgaon Basgadhi Road | Mandla | PWD | Road |  |  | 150.43 | RIDF Loan upto 10 crore
16 | R162000563 | Surajpura Kanhargaon Dobhi Daitpura Tumergaon Khirkhiny Chhatrwada Road | Mandla | PWD | Road |  |  | 226.68 | RIDF Loan upto 10 crore
16 | R162000564 | Niwari Mohgaon Gaurachhaper Saguriya Bandha Road | Mandla | PWD | Road |  |  | 277.08 | RIDF Loan upto 10 crore
16 | R162000565 | Gonjhi Keregaon Chichgaon duddum Chiraldongwi Road | Mandla | PWD | Road | 2014-03-27 | DDM | 325.81 | RIDF Loan upto 10 crore | Phy prgs-100%,ToR-4 mth due to LA, Road damaged in some places requiring immediate repairs/patch work. As performance guarantee of the project is due to expire by 2nd week June 2015, patches filling & BT works needs to be get done,NB Brd not displayed
16 | R162000566 | Beejegaon Bharveli Putaarra Lutmara Khursipar Road | Mandla | PWD | Road |  |  | 352.66 | RIDF Loan upto 10 crore
16 | R162000567 | Manipura Road To Ishwara Mahadev Mandir Road | Morena | PWD | Road |  |  | 51.99 | RIDF Loan upto 10 crore
16 | R162000568 | Rai ka Pura To Bahadurpur Road | Morena | PWD | Road |  |  | 77.1 | RIDF Loan upto 10 crore
16 | R162000569 | Palpura To Pachoripura road (via Dugsingh ka pura phatak ka pura ) | Morena | PWD | Road | 2013-10-21 | DDM | 350.28 | RIDF Loan upto 10 crore | Phy prgs>76%, ToR-Land Acquisition problem, NB Brd-not displayed
16 | R162000569 | Palpura To Pachoripura road (via Dugsingh ka pura phatak ka pura ) | Morena | PWD | Road | 2013-10-21 | DDM | 350.28 | RIDF Loan upto 10 crore | Work more than 75% completed
16 | R162000569 | Palpura To Pachoripura road (via Dugsingh ka pura phatak ka pura ) | Morena | PWD | Road |  |  | 350.28 | RIDF Loan upto 10 crore
16 | R162000570 | Barroli To Ummedgarh Bansi Road | Morena | PWD | Road |  |  | 90.4 | RIDF Loan upto 10 crore
16 | R162000571 | Bhadbhadiya jawad Athana Sukhanand Road | Neemuch | PWD | Road | 2014-11-15 | DDM | 578.06 | RIDF Loan upto 10 crore | Phy prgs-100%. ToR due to land acquisition. NABARD Board not displayed, 060 km road was not constructed due to some dispute with the farmers. Some portion road not constructed appropriately.
16 | R162000572 | Char Gaon To Salaiya Kanwar Samnapur Kachhi Road | Raisen | PWD | Road |  |  | 175.8 | RIDF Loan upto 10 crore
16 | R162000573 | Khandawar Sultannagar jontala Nan Bhet road | Raisen | PWD | Road |  |  | 102.25 | RIDF Loan upto 10 crore
16 | R162000574 | Nayapura to Gokula Kundi road | Raisen | PWD | Road |  |  | 122.1 | RIDF Loan upto 10 crore
16 | R162000575 | N-12 to Barodiya Khurd Gehalpur Chooupan Marhaiya Kanwar Road | Raisen | PWD | Road | 2013-10-08 | DDM | 204.68 | RIDF Loan upto 10 crore | Phy prgs=70%(LA/Earthwork/WBM/CD/CC>76% & Black topping51-75%)No CoR, Fresh contract awarded after extension . However, the 2nd contractor also did not start the work,NB Brd not displayed
16 | R162000576 | Chandrapur Turnig To Baraun Market | Rewa | PWD | Road |  |  | 103.9 | RIDF Loan upto 10 crore
16 | R162000577 | Luhagar-Nabalpur-Sahua-Hardi Road | Sagar | PWD | Road |  |  | 127.41 | RIDF Loan upto 10 crore
16 | R162000578 | Rajkhedi Sagar Bye Pass Road | Sagar | PWD | Road |  |  | 109.9 | RIDF Loan upto 10 crore
16 | R162000579 | Hilgan-Bhainswahi Road | Sagar | PWD | Road |  |  | 54.37 | RIDF Loan upto 10 crore
16 | R162000580 | Bhapson to Satoriya Road | Sagar | PWD | Road |  |  | 69.1 | RIDF Loan upto 10 crore
16 | R162000581 | Hiroundi Koldari Road | Satna | PWD | Road |  |  | 103.81 | RIDF Loan upto 10 crore
16 | R162000582 | Kordarnath Kulhariya Bhakul Baba Road | Satna | PWD | Road |  |  | 95.7 | RIDF Loan upto 10 crore
16 | R162000583 | Jamuniya Kalan To Bagwada Road | Sehore | PWD | Road |  |  | 96.95 | RIDF Loan upto 10 crore
16 | R162000584 | Dholpura to Bolagaon Road | Sehore | PWD | Road |  |  | 112.2 | RIDF Loan upto 10 crore
16 | R162000585 | Jamuniya Kalan To Ranipura Road | Sehore | PWD | Road |  |  | 110.92 | RIDF Loan upto 10 crore
16 | R162000586 | Basaniya Khurd to Dhankot Road | Sehore | PWD | Road |  |  | 83.95 | RIDF Loan upto 10 crore
16 | R162000587 | Basaniya Khurd To Basaniya Kalan Road | Sehore | PWD | Road |  |  | 57.16 | RIDF Loan upto 10 crore
16 | R162000588 | Dholpur to Bagwada Road | Sehore | PWD | Road |  |  | 134.08 | RIDF Loan upto 10 crore
16 | R162000589 | Pipariya Dhapara Road | Seoni | PWD | Road | 2014-08-12 | DDM | 150.58 | RIDF Loan upto 10 crore | (Phy prgs-LA,Earthwork,WBM,CD>76% & BT=26-50%), ToR-LA,due to rainy season & poor fund flow.Proper drainage outlets have to be provided in the CC portions of the road, Road furniture not fixed, side berms required strengthening
16 | R162000590 | Gokalpur Shukla ozhatola Road | Seoni | PWD | Road |  |  | 255.36 | RIDF Loan upto 10 crore
16 | R162000591 | Lohara Bamni Road | Seoni | PWD | Road |  |  | 62.18 | RIDF Loan upto 10 crore
16 | R162000592 | Sarra Hirri To sagar Road | Seoni | PWD | Road |  |  | 156.12 | RIDF Loan upto 10 crore
16 | R162000593 | Ishwarpur Pachpedi gungli Road | Seoni | PWD | Road |  |  | 221.99 | RIDF Loan upto 10 crore
16 | R162000594 | Khoot Poniya Road | Seoni | PWD | Road |  |  | 149.06 | RIDF Loan upto 10 crore
16 | R162000595 | Beelwara(Mata) to Berja Road | Shivpuri | PWD | Road |  |  | 148.74 | RIDF Loan upto 10 crore
16 | R162000596 | Bharota to Deharda (Ganesh) Road | Shivpuri | PWD | Road |  |  | 117.18 | RIDF Loan upto 10 crore
16 | R162000597 | Saparwada to Dulhara | Shivpuri | PWD | Road |  |  | 139.4 | RIDF Loan upto 10 crore
16 | R162000598 | Purail Chhanda To Deora Railway Station Road | Singrauli | PWD | Road |  |  | 366.72 | RIDF Loan upto 10 crore
16 | R162000599 | Gadhor Pondi Road | Singrauli | PWD | Road | 2013-10-10 | DDM | 458.08 | RIDF Loan upto 10 crore | Phy prgs-35%,WBM/Black topping/CD-Not done, Work stopped, NB Brd not displayed, Re-tendering process may be initiated, Original Contractor has stopped the work at GSB stage, Contractor had quoted at 37% below SoR & requested to termination of the project
16 | R162000600 | Bairdah Sakariya Road | Singrauli | PWD | Road |  |  | 168.24 | RIDF Loan upto 10 crore
16 | R162000601 | Jatara Chandera Road | Tikamgarh | PWD | Road |  |  | 98.56 | RIDF Loan upto 10 crore
16 | R162000602 | Tikamgarh Sudha sagar Ahar Road | Tikamgarh | PWD | Road |  |  | 159.58 | RIDF Loan upto 10 crore
16 | R162000603 | Construction of Approach road for village Panjh | Vidisha | PWD | Road | 2013-03-25 | DDM | 114.4 | RIDF Loan upto 10 crore | Phy progress-98% except water bound macadam, road signs, km signs & approach connection with NH86 Highway, Dept officials visit details- not made available by deptt, NB Brd-No
16 | R162000604 | Sumer Hathiyakhedi Khiriya Suakhedi Atarikhejra Road | Vidisha | PWD | Road |  |  | 328.27 | RIDF Loan upto 10 crore
16 | R162000604 | Sumer Hathiyakhedi Khiriya Suakhedi Atarikhejra Road | Vidisha | PWD | Road |  |  | 328.27 | RIDF Loan upto 10 crore
16 | R162000605 | Durga Nagar Saraswati School To Guraiya Chidoriya Bhoriya Road | Vidisha | PWD | Road | 2014-11-24 | RO Official | 235.99 | RIDF Loan upto 10 crore | Phy prgs-E/W >76%,WBM-26-50%,BT-NIL,CD-44, work stopped,,ToR-Yes-Contractor's negligence in adhering to schedule timeline for completino of work, Visit book-CE/SE/EE visit book not available only SDO/Sub Engr visit book available, NB Board not displayed,
16 | R162000606 | Jhirniya-Karhiya-Saunthor-Andiya-Suraud-Khejra-Adampur-Goberhela-Devrajpur | Vidisha | PWD | Road | 2013-10-24 | DDM | 758.82 | RIDF Loan upto 10 crore | Phy prgs 70% (LA/Earthwork/,CD & CC>76%/WBM,Black topping51-75%/, Excess/continuous rains for consecutive two years disrupted the work for more than 2 mths, Contract has been awarded at 25.05% below SOR. NB Brd not displayed
16 | R162000607 | Berkheda Sagoda Ghatkhedi Satdhara Bhopal Road | Vidisha | PWD | Road |  |  | 772.48 | RIDF Loan upto 10 crore
16 | R162000608 | Khiriya to Layra Bothe Jarha Sargoli Akhai Road | Vidisha | PWD | Road |  |  | 646.72 | RIDF Loan upto 10 crore
16 | R162000609 | Submersible Bridge across Kanhan River on Berdi- Sayra-Partapur Road | Chhindwara | PWD | Bridge |  |  | 609.24 | RIDF Loan upto 10 crore
16 | R162000610 | H L Bridge Across Ghissari rive in Km 21/2 | Balaghat | PWD | Bridge |  |  | 420.56 | RIDF Loan upto 10 crore
16 | R162000611 | Bridge across Pandajhir Nalla | Narsinghpur | PWD | Bridge |  |  | 127.3 | RIDF Loan upto 10 crore
16 | R162000612 | Submer bridge across Wainganag river in Km 3/10 | Seoni | PWD | Bridge | 2014-02-26 | DDM | 212.51 | RIDF Loan upto 10 crore | Phy prgs-LA<25%,Foundation>76%,Sub structure-51-75%/ ToR-LA & lack of proper accessibility due to rainy season & poor fund flow,Contractor problem and rapid flow of Wainganga river & resultant deposition of silt near ongoing works/ NB Brd not displayed
16 | R162000613 | INDIRA SAGAR PROJ CAN PII | Barwani | NVDA | MJP | 2013-03-15 | OIC+C | 5135.24 | RIDF Loan 25 crore & above | Phy progress-64%, LA & Fund flow problem,slow progs, NB Brd-No
16 | R162000613 | INDIRA SAGAR PROJ CAN PII | Barwani | NVDA | MJP | 2014-03-10 | RO Official | 5135.24 | RIDF Loan 25 crore & above | Phy prgs=85%(Head Regulator-95%/Main canal-90%/Lining of canal-55%/Distributories-40%/Minors-35%/CD-100%), ToR-due to land acquisition problem
16 | R162000614 | OMKARESWAR PRO CANAL | Dhar | NVDA | MJP | 2015-03-23 | RO Official | 3364.43 | RIDF Loan 25 crore & above | Phy prgs-85% (H/R100/ M canal-94.15//Br cabak-67/ Lining-94/ Distributories 67/ Minor/subminors-66 & CD-100%), ToR-in some pockets resistence/organised agitation against LA.Water is not available due to phase II is not complete,NB Brd not displayed
17 | R172000001 | Sagad MIP | Vidisha | WRD | MIP |  |  | 9864.89 | RIDF Loan 25 crore & above
17 | R172000002 | PENCH DIVERSION PROJECT UNIT II CANAL | Chhindwara | WRD | MJP | 2013-01-10 | OIC+C | 35858.2 | RIDF Loan 25 crore & above | phy prog-2%,LA-344 /1030 ha acquired, CoR-Yes previously but satisfactorily progressing, LA Payment for field channels and water courses is not being paid - complained by cultivators.
17 | R172000003 | Mahuar MIP | Shivpuri | WRD | MIP |  |  | 12853.99 | RIDF Loan 25 crore & above
17 | R172000004 | Sip-Kolar Link MIP | Sehore | WRD | MIP | 2015-02-26 | OIC+RO Officials | 7659.87 | RIDF Loan 25 crore & above | Phy prgs(-40%H/w-25%,Maincanal-60%,Br canal-25%), ToR-delay in Forest clearance,loose strata issues(at shaft no.2) of tunnel,this delay resulted in abt one year overrun
17 | R172000005 | BALWADI - DEOLI - DHAWALI ROAD | Barwani | PWD | Road |  |  | 586.91 | RIDF Loan upto 10 crore
17 | R172000006 | BARWANI BHAGWATI MORKATTA BORKHEDI | Balaghat | PWD | Road |  |  | 892.82 | RIDF Loan upto 10 crore
17 | R172000007 | BAWADIYAPHATA TO LOHARA ROAD | Barwani | PWD | Road |  |  | 144.86 | RIDF Loan upto 10 crore
17 | R172000008 | BIRULBAZAR TO SAWALMENDA GHANA ROAD | BETUL | PWD | Road |  |  | 173.55 | RIDF Loan upto 10 crore
17 | R172000009 | BISALKHEDI TO BEELKHEDA ROAD | BHOPAL | PWD | Road |  |  | 157.82 | RIDF Loan upto 10 crore
17 | R172000010 | BISALKHEDI TO MILLENIUM COLLEGE VIA SHUTING RENGE | BHOPAL | PWD | Road |  |  | 267.96 | RIDF Loan upto 10 crore
17 | R172000011 | HATHNOOR TO BADKHEDI ROAD | BURHANPUR | PWD | Road |  |  | 114.17 | RIDF Loan upto 10 crore
17 | R172000012 | NAWLA GHAGHARLA ROAD | BURHANPUR | PWD | Road |  |  | 143.9 | RIDF Loan upto 10 crore
17 | R172000013 | SHAHPUR DHAMANGAON ROAD | BURHANPUR | PWD | Road | 2014-03-14 | DDM | 319.02 | RIDF Loan upto 10 crore | Phy prgs-completed, NB Brd not displayed
17 | R172000014 | JAITPUR TO VARDHA ROAD | CHHATARPUR | PWD | Road |  |  | 61.21 | RIDF Loan upto 10 crore
17 | R172000015 | PATHAPUR TO HATHNA ROAD | CHHATARPUR | PWD | Road |  |  | 100.24 | RIDF Loan upto 10 crore
17 | R172000016 | RAJNAGAR ROAD TO SARANI VIA RADHEPUR | CHHATARPUR | PWD | Road | 2014-09-23 | DDM | 103.55 | RIDF Loan upto 10 crore | Phy prgs-LA & earthwork>75%, WBM & CD-51 to 75%,BT-upto 25%, ( ToR due to encroachement by villagers, heavy rainfall last year, shortage of labour), NABARD board not displayed
17 | R172000017 | MALAPODI TO BHANGARH ROAD | DAMOH | PWD | Road | 2013-09-06 | DDM | 780.1 | RIDF Loan upto 10 crore | Phy prgs->76%, CoR-due to higher tender premium, cost escalation due to pavment of escalation of price, variation in POL, cenment, HYSD steel & Bitumen
17 | R172000018 | BATIAGARH TO KERWANA ROAD | DAMOH | PWD | Road |  |  | 1013.78 | RIDF Loan 10.01-24.99 crore
17 | R172000019 | MEHGUON TO KAUWAKHOH ROAD | DAMOH | PWD | Road |  |  | 361.92 | RIDF Loan upto 10 crore
17 | R172000020 | BALWARI GANDHWANI ROAD | DHAR | PWD | Road | 2013-03-19 | DDM | 208.23 | RIDF Loan upto 10 crore | LA & EW>76%, Water bound macadam,Black topping & CD- 51 to 75%, ToR-Contractor problem, NB Brd-No, Contractor accepted tender at low cost & hence couldn't complete the work
17 | R172000021 | KHADAKIPHATA TO CHIRWALI ROAD | DHAR | PWD | Road | 2013-03-26 | DDM | 131.33 | RIDF Loan upto 10 crore | LA & EW->76%, Water bound macadam,Black topping & CD- 51 to 75%,ToR-Contractor problem, NB Brd-No, Due to contractor's problem, the work could not be completed in scheduled time, contractor accepted the tender at low cost & hence couldn't completed
17 | R172000022 | KOD TO BHANSOLA CHAUPATI ROAD | DHAR | PWD | Road | 2014-09-03 | DDM | 761.55 | RIDF Loan upto 10 crore | Project completed, CoR-Due to revised SoR, NABARD Board not displayed
17 | R172000023 | NISARPUR TO KOTESHWAR ROAD | DHAR | PWD | Road |  |  | 190.72 | RIDF Loan upto 10 crore
17 | R172000024 | KUMTHI TO KAMADPURA ROAD | INDORE | PWD | Road |  |  | 220.14 | RIDF Loan upto 10 crore
17 | R172000025 | BHARDA (SHARDA) NIPANIYA MADHAI ROAD | JABALPUR | PWD | Road |  |  | 235.38 | RIDF Loan upto 10 crore
17 | R172000026 | GORAIYAGHAT TO JAMTARA NARBADAGHAT ROAD | JABALPUR | PWD | Road |  |  | 116.1 | RIDF Loan upto 10 crore
17 | R172000027 | KUNDAM BILTIKURI ROAD | JABALPUR | PWD | Road | 2013-03-14 | DDM | 500.62 | RIDF Loan upto 10 crore | phy progress- 51 to 75%, pipe culverts work to be done, originally proposal was for 22 km road of this 9 km was to be taken up under PMGSY which is not considered now
17 | R172000027 | KUNDAM BILTIKURI ROAD | JABALPUR | PWD | Road | 2013-10-18 | DDM | 500.62 | RIDF Loan upto 10 crore | Work more than 75% completed. About 3.5 Kms tarring yet to be done. DDM has included the project under Critical infrA PROJECTS
17 | R172000028 | NARLAI IMLAI NARGAWAN ROAD | JABALPUR | PWD | Road |  |  | 201.16 | RIDF Loan upto 10 crore
17 | R172000029 | SIHORA SARDA MADAI ROAD | JABALPUR | PWD | Road | 2013-08-02 | DDM | 422.47 | RIDF Loan upto 10 crore | Phys prgs-100%, Problems- faced problems like Pole shifting by MPEB/removal of trees by Forest staff, Monitoring system not in place. 1km black topping near Sarda village,800 m CC road, 30m widening work & some portion of drain yet to be coompletd
17 | R172000030 | TALAD TO PADWAR ROAD | JABALPUR | PWD | Road | 2014-06-26 | DDM | 276.82 | RIDF Loan upto 10 crore | Phy prgs-EW=51-75%, WBM & BT=26-50%, CD=>76%, ToR-Delay due to change of agency,poor fund flow , CC work suffered due to Assmbly/Lok Sabha election work, shoulder work to be in most of the places
17 | R172000031 | SAILWARA BHANDRA KACHHARGAON ROAD | KATNI | PWD | Road |  |  | 283.26 | RIDF Loan upto 10 crore
17 | R172000032 | KEHLARI TO PHATEHPUR ROAD | Katani | PWD | Road |  |  | 72.88 | RIDF Loan upto 10 crore
17 | R172000033 | SURGAON TO NIPANI BIJORI ROAD | KHNADWA | PWD | Road |  |  | 98.63 | RIDF Loan upto 10 crore
17 | R172000034 | BABLAI TO SOMEKHEDI KARAI KODIAKHEDI TO PIPALIAPH | KHARGONE | PWD | Road | 2014-12-10 | DDM | 226.82 | RIDF Loan upto 10 crore | Phy prgs-95% (7 out of 11 CD work done), Due to CC road could not be done .opposition by farmers for construction of CD wrok, NB Brd not displayed
17 | R172000035 | CHOLI TO BABLAI ROAD | KHARGONE | PWD | Road |  |  | 157.57 | RIDF Loan upto 10 crore
17 | R172000036 | MAHESHWAR TO MARMUR ROAD | KHARGONE | PWD | Road |  |  | 207.68 | RIDF Loan upto 10 crore
17 | R172000037 | MAHESHWAR TO MEHATWARA ROAD | KHARGONE | PWD | Road |  |  | 256.59 | RIDF Loan upto 10 crore
17 | R172000038 | MUDIA TO DHASALGON ROAD | KHARGONE | PWD | Road |  |  | 261.02 | RIDF Loan upto 10 crore
17 | R172000039 | SADARKHEDA MANOLA VIA DASOLIBER ROAD | GUNA | PWD | Road |  |  | 228.09 | RIDF Loan upto 10 crore
17 | R172000040 | SIRSI TO MUSAREDI UPTO RAJASTHAN BORDAR ROAD | GUNA | PWD | Road | 2014-10-31 | DDM | 373.98 | RIDF Loan upto 10 crore | Out of 13.5km,only 11.38km road constructed, culvert constructed near spilway of irrigation dam was at the level of spillway (as Irri.Dept had not given permission)thus resulting in water logging over the culvert, No NB Brd displayed, ToR-LA
17 | R172000041 | SIRSI TO SADARKHEDA ROAD | GUNA | PWD | Road |  |  | 209.39 | RIDF Loan upto 10 crore
17 | R172000042 | BHAGORE TO BARKHEDAKALAN ROAD | MANDSAUR | PWD | Road |  |  | 124.46 | RIDF Loan upto 10 crore
17 | R172000043 | JHARDA TO IRLI ROAD | MANDSAUR | PWD | Road | 2014-11-20 | DDM | 265.75 | RIDF Loan upto 10 crore | Phy prgs-35%.(only LA & EW-51%to75%). Visit book not available.NB Brd not affixed. Land dispute-Land owner has obtained stay from Jabalpur HC. Work is presently stopped. Road furniture not fixed appropriately.
17 | R172000044 | KATIA RAGHUNATHPURA ROAD | MANDSAUR | PWD | Road |  |  | 189.73 | RIDF Loan upto 10 crore
17 | R172000045 | MUNDADI TO NARAYANGARH ROAD | MANDSAUR | PWD | Road |  |  | 155.56 | RIDF Loan upto 10 crore
17 | R172000046 | NARAYANGARH BAJRUA RAOD | MANDSAUR | PWD | Road |  |  | 170.3 | RIDF Loan upto 10 crore
17 | R172000047 | KHERA TO DATERA ROAD | MORENA | PWD | Road | 2012-12-31 | DDM | 282.7 | RIDF Loan upto 10 crore | LA & EW>76%, WBM-26-50%, CD>76%. No Test carried out as per IRC specification
17 | R172000048 | UPGRADATION AMGAON BAGHAWAR ROAD | Annupur | PWD | Road |  |  | 128.66 | RIDF Loan upto 10 crore
17 | R172000049 | UPGRADATIN OF CHARGAWAN GUNDARAI ROAD | NARSINGHPUR | PWD | Road |  |  | 102.57 | RIDF Loan upto 10 crore
17 | R172000050 | UPGRADATION OF GARHA TO AJANSARA MARKA BOHANI ROAD | NARSINGHPUR | PWD | Road | 2014-03-13 | DDM | 460.34 | RIDF Loan upto 10 crore | Phy prgs-(LA>76%/Earthwork-51-75%/WBM & BT-0%/CD-26-50%), ToR due to retendering the project, No records maintained in r/o visit by top officials and test record.. NB Brd not displayed
17 | R172000051 | UPGRADATION OF KHADCHARI MEHGUAN SUJWARA BOHANI ME | NARSINGHPUR | PWD | Road | 2014-11-13 | DDM | 366.22 | RIDF Loan upto 10 crore | Road completed. ToR-due to contractor's problem. NABARD board not displayed.
17 | R172000052 | HINOTIYA MAHALPUR GHATKHEDI ROAD | RAISEN | PWD | Road | 2014-11-11 | DDM | 275.7 | RIDF Loan upto 10 crore | Phy prgs=90%.ToR-due to LA. Visit book not available, NB Brd not displayed. At one place the road has caved in due to underneath loose sand. Due to this the movement of vehicles has been greately hampered and dangerous which can result into accidents
17 | R172000053 | AMAJHIR TO LASUDIYA RAM ROAD | SEHORE | PWD | Road |  |  | 196.94 | RIDF Loan upto 10 crore
17 | R172000054 | BAI TO BORI TO BERKHEDI ROAD | SEHORE | PWD | Road |  |  | 132.17 | RIDF Loan upto 10 crore
17 | R172000055 | BARKHEDA HASAN TO DEHRI ROAD | SEHORE | PWD | Road |  |  | 131.28 | RIDF Loan upto 10 crore
17 | R172000056 | BARKHEDAHASAN TO NAIKHEDI ROAD | SEHORE | PWD | Road |  |  | 127.3 | RIDF Loan upto 10 crore
17 | R172000057 | BARKHEDA HASAN TO SUAKHEDI ROAD | SEHORE | PWD | Road |  |  | 95.14 | RIDF Loan upto 10 crore
17 | R172000058 | BEEBDA SATMUNDI JAHAJPURA ROAD | SEHORE | PWD | Road |  |  | 173.22 | RIDF Loan upto 10 crore
17 | R172000059 | BODRA BABDI TO SAMNAPUR ROAD | SEHORE | PWD | Road |  |  | 229.04 | RIDF Loan upto 10 crore
17 | R172000060 | CHHAPARIKHURD VIA CHHAPARIKALAN ROAD | SEHORE | PWD | Road |  |  | 90.3 | RIDF Loan upto 10 crore
17 | R172000061 | DUDLAI TO RUPADEH TO RUPADI ROAD | SEHORE | PWD | Road |  |  | 92.7 | RIDF Loan upto 10 crore
17 | R172000062 | DUPADIYA CHACHAKHEDI ROAD | SEHORE | PWD | Road |  |  | 200.24 | RIDF Loan upto 10 crore
17 | R172000063 | GILEHARI TO VASUDEV ROAD | SEHORE | PWD | Road |  |  | 142.09 | RIDF Loan upto 10 crore
17 | R172000064 | HATHLEWA, CHACHMAU, NAYAPURA TO SHAHGANJ ROAD | SEHORE | PWD | Road |  |  | 187.41 | RIDF Loan upto 10 crore
17 | R172000065 | JAHANGIRPURA TO DEVSTHAN DARGAH ROAD | SEHORE | PWD | Road |  |  | 144.6 | RIDF Loan upto 10 crore
17 | R172000066 | JONTALA TO BAKTARA ROAD | SEHORE | PWD | Road |  |  | 182.39 | RIDF Loan upto 10 crore
17 | R172000067 | JONTALA TO SILGENA ROAD | SEHORE | PWD | Road |  |  | 189.82 | RIDF Loan upto 10 crore
17 | R172000068 | KHARPA TO HEDARGANJ ROAD | SEHORE | PWD | Road |  |  | 80.1 | RIDF Loan upto 10 crore
17 | R172000069 | KULASHKALA TO BARVAKHEDI ROAD | SEHORE | PWD | Road |  |  | 193.26 | RIDF Loan upto 10 crore
17 | R172000070 | KURI TO NAYAPURA ROAD | SEHORE | PWD | Road |  |  | 233.66 | RIDF Loan upto 10 crore
17 | R172000071 | MOGRARAM TO GUDVELA ROAD | SEHORE | PWD | Road |  |  | 146.23 | RIDF Loan upto 10 crore
17 | R172000072 | RUPADEH TO GADIYA ROAD | SEHORE | PWD | Road |  |  | 228.62 | RIDF Loan upto 10 crore
17 | R172000073 | SILGENA TO NANDNER ROAD | SEHORE | PWD | Road |  |  | 223.45 | RIDF Loan upto 10 crore
17 | R172000074 | SEMRI - KHANPURA TO RATANPUR ROAD | SEHORE | PWD | Road | 2014-08-22 | DDM | 266.02 | RIDF Loan upto 10 crore | Project completed, ToR due to LA, NABARD board not displayed
17 | R172000075 | SH - 18 TO ATARALIYA TO KHEJDAKHEDA ROAD | SEHORE | PWD | Road |  |  | 179.44 | RIDF Loan upto 10 crore
17 | R172000076 | SONKHEDI TO SEELKANTH ROAD | SEHORE | PWD | Road |  |  | 151.8 | RIDF Loan upto 10 crore
17 | R172000077 | TEEKMOD TO MANGROL ROAD | SEHORE | PWD | Road |  |  | 114.92 | RIDF Loan upto 10 crore
17 | R172000078 | TUMDA MARG TO TAJ VIA AMROD ROAD | SEHORE | PWD | Road |  |  | 116.69 | RIDF Loan upto 10 crore
17 | R172000079 | UDAYPURA PATARIYA VIA PATARIYA SINGHA ROAD | SEHORE | PWD | Road |  |  | 200.04 | RIDF Loan upto 10 crore
17 | R172000080 | BHURSI TO MAHROI BELA ROAD | SHAHDOL | PWD | Road |  |  | 175.86 | RIDF Loan upto 10 crore
17 | R172000081 | GOPALPUR TO CHANDELA ROAD | SHAHDOL | PWD | Road |  |  | 128.61 | RIDF Loan upto 10 crore
17 | R172000082 | BARKHEDA BHAURASA MALHARGARH ROAD | VIDISHA | PWD | Road |  |  | 65.01 | RIDF Loan upto 10 crore
17 | R172000083 | BAREJ TO AKABARPUR BAMURIYATAL ROAD | VIDISHA | PWD | Road |  |  | 72.87 | RIDF Loan upto 10 crore
17 | R172000084 | BARWAI TO KASWATAL ROAD | VIDISHA | PWD | Road | 2014-11-11 | DDM | 301.69 | RIDF Loan upto 10 crore | Phy prgs=55%.ToR-due to contractor problem, LA & forest clearance .CoR-25% likely increase. Visit book not available, NB Brd not displayed.
17 | R172000085 | DEVLI TO BARETH ROAD VIA THARKA TIKOD ROAD | VIDISHA | PWD | Road |  |  | 219.94 | RIDF Loan upto 10 crore
17 | R172000086 | DHAMNOD TO DASIPUR ROAD | VIDISHA | PWD | Road |  |  | 114.22 | RIDF Loan upto 10 crore
17 | R172000087 | GRAM IMLAWADA TO CHIRWATA, SIRAWALI ROAD | VIDISHA | PWD | Road |  |  | 391.67 | RIDF Loan upto 10 crore
17 | R172000088 | IMLANI KHAMKHERA TO SIRONJ BERASIA ROAD VIA TILIYA | VIDISHA | PWD | Road |  |  | 247.7 | RIDF Loan upto 10 crore
17 | R172000089 | MUNDRA GANESHPUR TO NIPANIYA BHADAR ROAD | VIDISHA | PWD | Road |  |  | 148.58 | RIDF Loan upto 10 crore
17 | R172000090 | N. H. 86 TO SUWAKHEDI SONTHIYA ROAD | VIDISHA | PWD | Road |  |  | 105.42 | RIDF Loan upto 10 crore
17 | R172000091 | NOLASA LAKHOLI DARGAWAN TILAK ROAD | VIDISHA | PWD | Road |  |  | 335.16 | RIDF Loan upto 10 crore
17 | R172000092 | PIPALIYAHAT - BAMANKHEDI TO KHIRIYADANGI ROAD | VIDISHA | PWD | Road |  |  | 230.22 | RIDF Loan upto 10 crore
17 | R172000093 | SANAI TO DANKHEDI ROAD | VIDISHA | PWD | Road |  |  | 163.9 | RIDF Loan upto 10 crore
17 | R172000094 | SHAMSHABAD ROAD TO KATARA NAMAKHEDI KOTHICHARKALAN | VIDISHA | PWD | Road |  |  | 451.82 | RIDF Loan upto 10 crore
17 | R172000095 | VIDISHA LASHKARPUR TO KOTHICHAR GULABGANJ ROAD TO | VIDISHA | PWD | Road |  |  | 114.21 | RIDF Loan upto 10 crore
17 | R172000096 | Highlevel Bridge across SON RIVER in K.M. 3/2 of Kadta Sarra | Balaghat | PWD | Bridge |  |  | 670.33 | RIDF Loan upto 10 crore
17 | R172000097 | H.L. Bridge across Urmil River on Rajnagar-Bachhon Road | Chhatarpur | PWD | Bridge |  |  | 305.92 | RIDF Loan upto 10 crore
17 | R172000098 | Highlevel Bridge across SINDH RIVER in K.M. 10/4-6 | Datia | PWD | Bridge |  |  | 838.02 | RIDF Loan upto 10 crore
17 | R172000099 | Construction of Submersible Bridge on Hanumantia nallah | Neemuch | PWD | Bridge |  |  | 116.36 | RIDF Loan upto 10 crore
17 | R172000100 | Construction of Submersible Bridge across Gambhiri river | Neemuch | PWD | Bridge |  |  | 110.13 | RIDF Loan upto 10 crore
17 | R172000101 | Construction of Submersible Bridge ON HARKIYAKHAL River | Neemuch | PWD | Bridge |  |  | 98.02 | RIDF Loan upto 10 crore
17 | R172000102 | Construction of High level across Bhadaksanawad nallah | Neemuch | PWD | Bridge |  |  | 97.08 | RIDF Loan upto 10 crore
17 | R172000103 | Construction of H.L. Bridge across Ken River on Bishani | Panna | PWD | Bridge |  |  | 272.77 | RIDF Loan upto 10 crore
17 | R172000104 | Construction of Submersible Bridge on Tikod-Ninor- | Rajgarh | PWD | Bridge |  |  | 303.06 | RIDF Loan upto 10 crore
17 | R172000105 | Construction of Submersible Bridge across Narmada | Raisen | PWD | Bridge | 2015-03-27 | RO Official | 1635.39 | RIDF Loan 10.01-24.99 crore | Phy prgs-(LA/Foundation/Sub-structure/Super-structure/CD Works->75%)(App road-upto 25%),(Protection-51-75%),Other(pitching)-26-50%, ToR-due to LA, Bridge work completed except pitching work at both ends, NB brd not displayed.
17 | R172000106 | Construction of H.L. Bridge across Sonar River on | Sagar | PWD | Bridge | 2014-07-08 | DDM | 157.3 | RIDF Loan upto 10 crore | Phy Prgs-(Foundatin-upto 25%), Site Book was not easily available, NABARD Board not fixed
17 | R172000107 | Construction of Submersible Bridge Across Waingang | Seoni | PWD | Bridge |  |  | 337.72 | RIDF Loan upto 10 crore
17 | R172000108 | Construction of High level Bridge on Chillar River | Shajapur | PWD | Bridge | 2013-07-08 | DDM | 330.1 | RIDF Loan upto 10 crore | Phy pgrs-65to70%, ToR-due to rain, LA, Court case lodged by the villagers for connectivity road & approaches to the bridge, NB Brd-Not displayed
17 | R172000109 | Construction of High level Bridge across Sheep River-Sheopur | Sheopur | PWD | Bridge |  |  | 277.42 | RIDF Loan upto 10 crore
17 | R172000110 | Submersible Bridge across Ur River on Khera-Vijaypur Road | Tikamgarh | PWD | Bridge |  |  | 283.07 | RIDF Loan upto 10 crore
17 | R172000111 | H.L. Bridge across Ur River on Larkhurd-Jarua Road | Tikamgarh | PWD | Bridge |  |  | 130.7 | RIDF Loan upto 10 crore
17 | R172000112 | Construction of Submersible Bridge on Kshipra River Alot-Jharda | Ujjain | PWD | Bridge |  |  | 329.94 | RIDF Loan upto 10 crore
17 | R172000113 | Construction of Submersible Bridge on Bagedi River | Ujjain | PWD | Bridge |  |  | 108.02 | RIDF Loan upto 10 crore
17 | R172000114 | Construction of Submersible Bridge across Chhoti Kalisindh | Ujjain | PWD | Bridge |  |  | 207.23 | RIDF Loan upto 10 crore
17 | R172000115 | Construction of Submersible Bridge across Kshipra-Panbihar Road | Ujjain | PWD | Bridge |  |  | 233.86 | RIDF Loan upto 10 crore
17 | R172000116 | Construction of H. L. Bridge across Kethan River on Pamakhedi | Vidisha | PWD | Bridge |  |  | 123.18 | RIDF Loan upto 10 crore
17 | R172000117 | Bargi Diversion Project Phase IV Right Bank Canal | Katni | NVDA | MJP | 2014-10-29 | HO Official | 43124 | RIDF Loan 25 crore & above | Phy prgs-87%ToR-d/t LA, NHAI permission for NH crossing, 03 major structures are to be done, Finalising of earthwork profile be completed as per design, Lining damaged in some portion, Pitching to be done properly, NB Brd not displayed
17 | R172000118 | Kushalpura MIP | Rajgarh | WRD | MIP | 2014-10-31 | HO Official | 2878.86 | RIDF Loan 25 crore & above | Phy prgs-85%.ToR-LA,inter departmental coordination, fund flow,clearances. Water distribution system is not operationalised fully, NB Brd not displayed, CC lining to be completed, Excessive seepage in block no.4,8,9,10.
17 | R172000119 | Rehti MIP | Vidisha | WRD | MIP | 2014-10-13 | RO Official | 1914.28 | RIDF Loan 10.01-24.99 crore | Phy prgs-90%, Test records/site visit records/order book not available, WUA to be formed, Water courses & field channel works to be completed, NB Board not displayed
17 | R172000120 | Godown | Hoshangabad | MPWLC | Godown | 2013-03-12 | DDM | 344.11 | RIDF Loan upto 10 crore | Phy pgrs-70%, 5 chambers, Not registered with WDRA, NB Brd not displayed
17 | R172000121 | Godown | Hoshangabad | MPWLC | Godown | 2013-03-12 | DDM | 178.49 | RIDF Loan upto 10 crore | Phy pgrs-30%, Fin pgrs-30%, 3 chambers, Grading & Sorting facilities not envisaged, No tie up arrangements with other Warehouse in project area, Not registered with WDRA, NB Brd not displayed
17 | R172000122 | Godown | Hoshangabad | MPWLC | Godown | 2013-03-12 | DDM | 57.26 | RIDF Loan upto 10 crore | Phy pgrs-0%, Fin pgrs-0%, 3 chambers, Grading & Sorting facilities not envisaged, No tie up arrangements with other Warehouse in project area, NB Brd not displayed
17 | R172000123 | Convertible CAP | Harda | MPWLC | CAP |  |  | 517.79 | RIDF Loan upto 10 crore
17 | R172000124 | Convertibe CAP | Harda | MPWLC | CAP |  |  | 699.72 | RIDF Loan upto 10 crore
17 | R172000125 | Convertibe CAP | Harda | MPWLC | CAP |  |  | 261.9 | RIDF Loan upto 10 crore
17 | R172000126 | Convertibe CAP | Bhopal | MPWLC | CAP |  |  | 425.8 | RIDF Loan upto 10 crore
17 | R172000127 | Convertibe CAP | Sehore | MPWLC | CAP |  |  | 571.44 | RIDF Loan upto 10 crore
17 | R172000128 | Convertibe CAP | Hoshangabad | MPWLC | CAP | 2013-03-15 | RO Official | 1227.08 | RIDF Loan 10.01-24.99 crore | Phy progress-50%, fin progress at site as per dept-33%, NB Brd-No, Suggestions/Action point- Project officers suggestted that warehouse complex may be financed under RIDF, Good quality approach roads may be constructed/maintained
17 | R172000129 | Convertibe CAP | Hoshangabad | MPWLC | CAP |  |  | 183.71 | RIDF Loan upto 10 crore
17 | R172000130 | Convertibe CAP | Hoshangabad | MPWLC | CAP | 2013-03-12 | DDM | 530.2 | RIDF Loan upto 10 crore | Phy pgrs-5%, Fin pgrs- 0.25 Cr, Grading & Sorting facilities not envisaged, No tie up arrangements with other Warehouse in project area, NB Brd not displayed
17 | R172000131 | Convertibe CAP | Vidisha | MPWLC | CAP | 2013-03-26 | DDM | 508.81 | RIDF Loan upto 10 crore | Phy progress-50%, Due to delay in the selection of site & design problem, CAPs have been constructed on the hard rock formation and therefore design had to changed., NB Brd-No, At district level, the impl dept was not aware about NB fin assistance
17 | R172000132 | Convertibe CAP | Vidisha | MPWLC | CAP |  |  | 508.81 | RIDF Loan upto 10 crore
17 | R172000133 | Convertibe CAP | Raisen | MPWLC | CAP |  |  | 257.86 | RIDF Loan upto 10 crore
17 | R172000134 | Conversion of Existing CAP into Godown | Raisen | MPWLC | CAP-Godown |  |  | 372.37 | RIDF Loan upto 10 crore
17 | R172000135 | Conversion of Existing CAP into Godown | Sehore | MPWLC | CAP-Godown | 2014-01-06 | DDM | 123.17 | RIDF Loan upto 10 crore | Phy prgs=90%,(Pending works-Shutters installation,Outer plaster,finishing,Outer whitewash), Internal finishing=100%, Order issued for installation of board acknowledging RIDF/State Govt finance
17 | R172000136 | Conversion of Existing CAP into Godown | Sehore | MPWLC | CAP-Godown |  |  | 245.1 | RIDF Loan upto 10 crore
17 | R172000137 | Godown (Under PEG Scheme) | Seoni | MPWLC | Godown | 2013-03-26 | DDM | 482.63 | RIDF Loan upto 10 crore | Phy prgs-100%. Delay was on a/c of slow progress & limited approach to the site at the time of consuction. NB Brd-not displayed. No tie up facilities with testing Lab is envisaged. 3 Godowns having capacity of 4200MT, 5400MT & 5400 MT constructed
17 | R172000138 | Godown (Under PEG Scheme) | Shivpuri | MPWLC | Godown | 2013-01-10 | DDM | 173.04 | RIDF Loan upto 10 crore | Work order not made available, Phy progress-100%, NB Brd-No, No firefighting arrangement, No grading facility available only storage facility available
17 | R172000139 | Godown (Under PEG Scheme) | Dhar | MPWLC | Godown | 2014-01-07 | DDM | 632.97 | RIDF Loan upto 10 crore | Phy prgs-90%, Phy prgs-Indor 80% & Fin.prgs-92%// NB Brd not displayed/ Delay due to heavy monsoon last year & problem of labourer in harvesting season
17 | R172000140 | Godown (Under PEG Scheme) | Jhabua | MPWLC | Godown | 2013-03-14 | DDM | 223.23 | RIDF Loan upto 10 crore | phy prgs 90%, due to heavy rain work delayed by 6 mths, project board not displayed, WBM road all side of the godown may be completed
17 | R172000141 | Godown (Under PEG Scheme) | Dindori | MPWLC | Godown |  |  | 343.43 | RIDF Loan upto 10 crore
17 | R172000142 | Godown (Under PEG Scheme) | Raisen | MPWLC | Godown |  |  | 621.27 | RIDF Loan upto 10 crore
18 | R182000001 | Thikariya Medium tank Project | Neemuch | WRD | MIP |  |  | 6933.53 | RIDF Loan 25 crore & above
18 | R182000002 | Omkareshwar Phase IV Right Bank Lift Canal | Khargone | NVDA | MJP | 2015-03-24 | RO Official | 7218.7 | RIDF Loan 25 crore & above | Phy prgs-70%(M Canal->76%, Lining/Distributories/Minors&subminors-26-50%, Br canal/CD-51-75%, Watercourse/field channels-<25%), Project encountered some problem of LA due to public agitation. Br displayed but NB RIDF funding not indicated
18 | R182000003 | Gausabas adanwara balaya road | Damoh | PWD | Road |  |  | 735.75 | RIDF Loan upto 10 crore
18 | R182000004 | Dongala to meen & dongala to narayana road | Ujjain | PWD | Road |  |  | 476.63 | RIDF Loan upto 10 crore
18 | R182000005 | Jhitarkhedi to Bichhrod Road | Ujjain | PWD | Road |  |  | 320.88 | RIDF Loan upto 10 crore
18 | R182000006 | Runaheda to gunaai road | Ujjain | PWD | Road |  |  | 162.07 | RIDF Loan upto 10 crore
18 | R182000007 | Madigarda patwarikheda road | Vidisha | PWD | Road |  |  | 224.15 | RIDF Loan upto 10 crore
18 | R182000008 | Anandpur bhagwantapur road to shirajnagar satpada | Vidisha | PWD | Road |  |  | 198.43 | RIDF Loan upto 10 crore
18 | R182000009 | Dehripama raypura to barod road | Vidisha | PWD | Road |  |  | 362.62 | RIDF Loan upto 10 crore
18 | R182000010 | Madipur nandor ambar naulasa road | Vidisha | PWD | Road |  |  | 357.11 | RIDF Loan upto 10 crore
18 | R182000011 | Tarha nitri bhadora teelam mudra ahmedpur road | Vidisha | PWD | Road |  |  | 449.57 | RIDF Loan upto 10 crore
18 | R182000012 | Dayanandpur to boriya via bamankhuda via boriya ka | Vidisha | PWD | Road |  |  | 294.64 | RIDF Loan upto 10 crore
18 | R182000013 | Chatoli to hironda road | Vidisha | PWD | Road |  |  | 323.79 | RIDF Loan upto 10 crore
18 | R182000014 | Naulasa bawariya kheruva road | Vidisha | PWD | Road |  |  | 301.11 | RIDF Loan upto 10 crore
18 | R182000015 | Madiyee makhrar jaldhara road | Jabalpur | PWD | Road |  |  | 265.58 | RIDF Loan upto 10 crore
18 | R182000016 | Jheeriya maheshpur devhara road | Jabalpur | PWD | Road |  |  | 158.1 | RIDF Loan upto 10 crore
18 | R182000017 | Kubarhat babiya road | Jabalpur | PWD | Road |  |  | 163.81 | RIDF Loan upto 10 crore
18 | R182000018 | Savalkheda to jawar road | Khandwa | PWD | Road |  |  | 221.86 | RIDF Loan upto 10 crore
18 | R182000019 | Ashapura betul s.h.no. 25 to kalighodi to mehlu ro | Khandwa | PWD | Road | 2015-01-16 | DDM | 329.66 | RIDF Loan upto 10 crore | Work is incomplete (only E/W & CD has been completed), ToR-due to forest clearance, Problem of Forest clearance has been resolved but written permissino has not given by For. Dept, Out of 8km only 7.7 km work completed,NABARD Brd not displayed
18 | R182000020 | Pandana rustompur road | Khandwa | PWD | Road |  |  | 131.52 | RIDF Loan upto 10 crore
18 | R182000021 | Khandwa hoshangabad s.h. No. 15 to bhawaliya khokl | Khandwa | PWD | Road |  |  | 178.41 | RIDF Loan upto 10 crore
18 | R182000022 | Malhargad to jhamad road | Khandwa | PWD | Road |  |  | 244.53 | RIDF Loan upto 10 crore
18 | R182000023 | Barur to bheelkheda chhirvel road | Khandwa | PWD | Road |  |  | 161.58 | RIDF Loan upto 10 crore
18 | R182000024 | Lakha to rahlee road | Narsingpur | PWD | Road |  |  | 102.1 | RIDF Loan upto 10 crore
18 | R182000025 | Baranj to khulri road | Narsingpur | PWD | Road |  |  | 150.28 | RIDF Loan upto 10 crore
18 | R182000026 | Gundrahi to pathroda road | Narsingpur | PWD | Road |  |  | 153.75 | RIDF Loan upto 10 crore
18 | R182000027 | Kanhadgaon to chinchgaon road | Balaghat | PWD | Road |  |  | 178.49 | RIDF Loan upto 10 crore
18 | R182000028 | Bharweli to bagholi ameda road | Balaghat | PWD | Road |  |  | 126.22 | RIDF Loan upto 10 crore
18 | R182000029 | Vishrampur ghodatola nevargaon road | Balaghat | PWD | Road |  |  | 78.99 | RIDF Loan upto 10 crore
18 | R182000030 | Balaghat town interior road | Balaghat | PWD | Road |  |  | 524.94 | RIDF Loan upto 10 crore
18 | R182000031 | Damkhedi bhatkhedi road | Bhopal | PWD | Road |  |  | 313.26 | RIDF Loan upto 10 crore
18 | R182000032 | Bheelakhedi parkhedi gehukheda to maharishi vidyam | Raisen | PWD | Road |  |  | 267.21 | RIDF Loan upto 10 crore
18 | R182000033 | Kewatpipaliya umraoganj saikheda road | Raisen | PWD | Road |  |  | 167.1 | RIDF Loan upto 10 crore
18 | R182000034 | Amravad sankheda road to gugulwada road | Raisen | PWD | Road |  |  | 57.51 | RIDF Loan upto 10 crore
18 | R182000035 | Devata to barhakalan road | Raisen | PWD | Road |  |  | 124.76 | RIDF Loan upto 10 crore
18 | R182000036 | Kutnaseer to shivtala palkarshi road | Raisen | PWD | Road |  |  | 238.4 | RIDF Loan upto 10 crore
18 | R182000037 | Bamanwada dhandala dehrikala gugalwada sankheda ro | Raisen | PWD | Road |  |  | 247.68 | RIDF Loan upto 10 crore
18 | R182000038 | Chhabara to khetoghan road | Raisen | PWD | Road |  |  | 137.14 | RIDF Loan upto 10 crore
18 | R182000039 | Chhabara to pipariya puvariya road | Raisen | PWD | Road |  |  | 147.42 | RIDF Loan upto 10 crore
18 | R182000040 | Magardha umariya bhilwadiya bugulwada road | Raisen | PWD | Road |  |  | 425.33 | RIDF Loan upto 10 crore
18 | R182000041 | Chaayan to makdi road | Mandsaur | PWD | Road |  |  | 181.46 | RIDF Loan upto 10 crore
18 | R182000042 | Bakhatgad kadmal mathwad road | Alirajpur | PWD | Road |  |  | 554.93 | RIDF Loan upto 10 crore
18 | R182000043 | Deori to kesali road | Sagar | PWD | Road |  |  | 137.71 | RIDF Loan upto 10 crore
18 | R182000044 | Lidhorakhurd to pipariya turn via batallion road | Sagar | PWD | Road |  |  | 223.3 | RIDF Loan upto 10 crore
18 | R182000045 | Tundri to dhooltara road | Sagar | PWD | Road |  |  | 342.69 | RIDF Loan upto 10 crore
18 | R182000046 | Maangad shahpur dhura road | Sagar | PWD | Road |  |  | 386.66 | RIDF Loan upto 10 crore
18 | R182000047 | Bhainswahi chandrapura ballaimafi road | Sagar | PWD | Road |  |  | 236.26 | RIDF Loan upto 10 crore
18 | R182000048 | Ghatampur khand pipariya dhudhoniya road | Sagar | PWD | Road |  |  | 233.19 | RIDF Loan upto 10 crore
18 | R182000049 | Paagara Approach road | Sagar | PWD | Road |  |  | 238.5 | RIDF Loan upto 10 crore
18 | R182000050 | Barapani aapchand gonchi road | Sagar | PWD | Road |  |  | 239.94 | RIDF Loan upto 10 crore
18 | R182000051 | Daana hilgun road to khadaraban pipariya vaid road | Sagar | PWD | Road |  |  | 379.26 | RIDF Loan upto 10 crore
18 | R182000052 | Saloya khadaraban richawar saikheda road | Sagar | PWD | Road |  |  | 383.38 | RIDF Loan upto 10 crore
18 | R182000053 | Tilakheda to chavada road | Sagar | PWD | Road |  |  | 182.02 | RIDF Loan upto 10 crore
18 | R182000054 | Mofadakhedi to aahirbamangaon road | Hoshangabad | PWD | Road |  |  | 223.39 | RIDF Loan upto 10 crore
18 | R182000055 | Palanpur badodiya road | Hoshangabad | PWD | Road |  |  | 87.76 | RIDF Loan upto 10 crore
18 | R182000056 | Dhamsaa datwaasa to shail road | Hoshangabad | PWD | Road |  |  | 271.48 | RIDF Loan upto 10 crore
18 | R182000057 | Bhangiya to lodhadi road | Hoshangabad | PWD | Road |  |  | 127.88 | RIDF Loan upto 10 crore
18 | R182000058 | Kisangad to panth piplodha road | Ratlam | PWD | Road |  |  | 195.76 | RIDF Loan upto 10 crore
18 | R182000059 | Ringnod to hathpipaliya | Ratlam | PWD | Road | 2014-10-08 | DDM | 368.59 | RIDF Loan upto 10 crore | Phy prgs>76%. ToR-due to panchayat interference, Vist book not available, NB brd not displayed. road damaged & broken at some places. Water logging problem due to CC road and CD work not done properly
18 | R182000060 | Dhudhuri gunvad road | Jhabua | PWD | Road |  |  | 78.29 | RIDF Loan upto 10 crore
18 | R182000061 | Thirmau to kharpadakhedi badchowk road | Betul | PWD | Road |  |  | 159.15 | RIDF Loan upto 10 crore
18 | R182000062 | Thaani to dhanori Parsdoh road | Betul | PWD | Road |  |  | 179.5 | RIDF Loan upto 10 crore
18 | R182000063 | Nayapura to ratatlai road | Harda | PWD | Road |  |  | 196.42 | RIDF Loan upto 10 crore
18 | R182000064 | Harai bheda thendni jogiwadi hathikho road | Chindwarha | PWD | Road |  |  | 189.15 | RIDF Loan upto 10 crore
18 | R182000065 | Batkakhapa saaldana chureesajava uttariya dharamkh | Chindwarha | PWD | Road |  |  | 193.25 | RIDF Loan upto 10 crore
18 | R182000066 | Bijori to pandu pipariya chhindi to batkakha harai | Chindwarha | PWD | Road |  |  | 420.56 | RIDF Loan upto 10 crore
18 | R182000067 | Bijori chhindi khapa harai road km 19 to kathotiya | Chhindwara | PWD | Road |  |  | 53.76 | RIDF Loan upto 10 crore
18 | R182000068 | Ghansaur to salahpani road | Seoni | PWD | Road |  |  | 483.15 | RIDF Loan upto 10 crore
18 | R182000069 | Khairi goditola savri road | Balaghat | PWD | Road |  |  | 301.38 | RIDF Loan upto 10 crore
18 | R182000070 | Bahegaon dohra salabari tegnikhurd banjari road | Balaghat | PWD | Road |  |  | 328.82 | RIDF Loan upto 10 crore
18 | R182000071 | Khairlanji ghobadgaundi road | Balaghat | PWD | Road |  |  | 212.81 | RIDF Loan upto 10 crore
18 | R182000072 | Birsola khamariya khursodi road | Balaghat | PWD | Road |  |  | 179.82 | RIDF Loan upto 10 crore
18 | R182000073 | Behrayi landajhari kaydi road | Balaghat | PWD | Road |  |  | 163.62 | RIDF Loan upto 10 crore
18 | R182000074 | Construction of Anganwadi building at various loca | Sehore | W&CD | Anganwadi |  |  | 4252.04 | RIDF Loan 25 crore & above
18 | R182000075 | Construction of Anganwadi building at various loca | Vidisha | W&CD | Anganwadi |  |  | 4239.46 | RIDF Loan 25 crore & above
18 | R182000076 | Indira Sagar Project (Canals ) Phase V Khargone li | Khargone | NVDA | MJP |  |  | 5967.14 | RIDF Loan 25 crore & above
18 | R182000077 | Upper Narmada Project | Dindori | NVDA | MJP |  |  | 5784.11 | RIDF Loan 25 crore & above
18 | R182000078 | Keetkhedi Medium tank Project | Shajapur | WRD | MIP | 2014-10-13 | RO Official | 6045.28 | RIDF Loan 25 crore & above | Phy prgs-75%(HW/Spilways/Head Regulator-98%, Main/Branch canal/lining of canal/distributories/minors&subminors-55%, CD-78%), CWC clearance yet to be obtained, Field channel work should be started, Lining of RBC&LBC maybe completeted,WUA may be completed
18 | R182000079 | Semri Medium Project | Raisen | WRD | MIP | 2015-03-28 | RO Official | 8312.9 | RIDF Loan 25 crore & above | (Phy prgs-H/W,Distributories &Minors&Subminors-51-75%, HR,main canal,>76%)(Remaining excavation/Earthen check point/spill channel/stone patching of remaining work of dam/Down stream & RBC (10 km)work needs to be completed,
18 | R182000080 | Rithouri L.P. R. To Tilgawan Road | Jabalpur | PWD | Road |  |  | 238.5 | RIDF Loan upto 10 crore
18 | R182000081 | Nandni Pipaliya Nagar Road | Shahjapur | PWD | Road |  |  | 359.65 | RIDF Loan upto 10 crore
18 | R182000082 | Padariyiakala to Anuppur District Border Road | Dindori | PWD | Road |  |  | 247.26 | RIDF Loan upto 10 crore
18 | R182000083 | Roosa Barnai Medakhar Pakrisoda Road | Dindori | PWD | Road |  |  | 980.59 | RIDF Loan upto 10 crore
18 | R182000084 | Nangda - Bercha Road | Ujjain | PWD | Road |  |  | 209.38 | RIDF Loan upto 10 crore
18 | R182000085 | Hirapur to Chitawad Road | Khargone | PWD | Road |  |  | 269.18 | RIDF Loan upto 10 crore
18 | R182000086 | Kasdawad to Navdatodi Road | Khargaone | PWD | Road |  |  | 185.53 | RIDF Loan upto 10 crore
18 | R182000087 | Biaora NH 3 to Podonia Road | Rajgarh | PWD | Road |  |  | 131.23 | RIDF Loan upto 10 crore
18 | R182000088 | Suthaliya Mau Lakhanwas Road | Rajgarh | PWD | Road |  |  | 1441.39 | RIDF Loan 10.01-24.99 crore
18 | R182000089 | S.H. 12 to Tumda Road | Sehore | PWD | Road |  |  | 116.36 | RIDF Loan upto 10 crore
18 | R182000090 | Rajgarh Piplodi Road | Rajgarh | PWD | Road | 2015-03-20 | DDM | 498.62 | RIDF Loan upto 10 crore | Phy prgs->76%, Visit book -not available, Benefits -9 villages with population of 4423 benefitted to access medical & education facilities available at district HQ Rajgah, Private bus services has also started between Piploda and Dist HQ
18 | R182000091 | Dhupkhad Duari Road | Sidhi | PWD | Road |  |  | 380.58 | RIDF Loan upto 10 crore
18 | R182000092 | Bedapani to Palasi Road | Sehore | PWD | Road |  |  | 325.62 | RIDF Loan upto 10 crore
18 | R182000093 | Matthagaon to Ranikundi Road | Sehore | PWD | Road |  |  | 192.19 | RIDF Loan upto 10 crore
18 | R182000094 | Pan Guradia to Dhankoat Road | Sehore | PWD | Road |  |  | 98.58 | RIDF Loan upto 10 crore
18 | R182000095 | Silawad to Barwani via Ambapani Road | Barwani | PWD | Road |  |  | 203.55 | RIDF Loan upto 10 crore
18 | R182000096 | Kuthiyana to Rahuapura | Morena | PWD | Road |  |  | 157.69 | RIDF Loan upto 10 crore
18 | R182000097 | Karkeli Raipur Bagdari Bijauri Road | Umaria | PWD | Road |  |  | 647.13 | RIDF Loan upto 10 crore
18 | R182000098 | Kergoan Patadah Kohkatola Chinchgaon Jamgaon Ghat | Mandla | PWD | Road |  |  | 449.92 | RIDF Loan upto 10 crore
18 | R182000099 | Sundar ka pura to Anthiyan ka pura | Bhind | PWD | Road |  |  | 164.49 | RIDF Loan upto 10 crore
18 | R182000100 | Porsa Ater Road | Morena | PWD | Road |  |  | 91.7 | RIDF Loan upto 10 crore
18 | R182000101 | Richora to Damadehi Bahravan Road | Sehore | PWD | Road |  |  | 167.36 | RIDF Loan upto 10 crore
18 | R182000102 | Vitka Pura via Malukapura Kalukapura Betalkapura R | Morena | PWD | Road |  |  | 284.1 | RIDF Loan upto 10 crore
18 | R182000103 | Milanpur Noorabad via Bichola Rethora Road | Morena | PWD | Road | 2015-02-18 | DDM | 505.9 | RIDF Loan upto 10 crore | Phy prgs-100%, ToR-LA problem
18 | R182000104 | Wajidpur to Panwarihat Road | Ashoknagar | PWD | Road |  |  | 449.48 | RIDF Loan upto 10 crore
18 | R182000105 | Pranpur to Nankpura Hirapur Road | Ashoknagar | PWD | Road |  |  | 1029.66 | RIDF Loan 10.01-24.99 crore
18 | R182000106 | Eshagarh to Kadwaya via Devkani Mata Mandir Road | Ashoknagar | PWD | Road |  |  | 105.94 | RIDF Loan upto 10 crore
18 | R182000107 | Pachera Pali Road | Bhind | PWD | Road |  |  | 91.1 | RIDF Loan upto 10 crore
18 | R182000108 | Bahua to Soni via Maharajpura Road | Bhind | PWD | Road |  |  | 153.52 | RIDF Loan upto 10 crore
18 | R182000109 | Alampur to Aagariyakala Road | Raisen | PWD | Road |  |  | 399.53 | RIDF Loan upto 10 crore
18 | R182000110 | Bhopal Sagar Road to Semra Baramad Sounther Road | Raisen | PWD | Road |  |  | 412.64 | RIDF Loan upto 10 crore
18 | R182000111 | Singaldeep Narendrapur Road | Jabalpur | PWD | Road |  |  | 464.73 | RIDF Loan upto 10 crore
18 | R182000112 | Mankhedi Kusumi Road | Jabalpur | PWD | Road |  |  | 289.44 | RIDF Loan upto 10 crore
18 | R182000113 | Suhasa to Kanjhar Road | Ujjain | PWD | Road |  |  | 213.32 | RIDF Loan upto 10 crore
18 | R182000114 | Shamshabad to Motipura Binjha Road | Vidisha | PWD | Road |  |  | 288.25 | RIDF Loan upto 10 crore
18 | R182000115 | Gujarwada-Kirpur Rajon Road | Hoshangabad | PWD | Road |  |  | 277.06 | RIDF Loan upto 10 crore
18 | R182000116 | Aaokodia to Karju Road | Mandsaur | PWD | Road |  |  | 245.84 | RIDF Loan upto 10 crore
18 | R182000117 | Kacharia to Raykheda Road | Mandsaur | PWD | Road |  |  | 155.47 | RIDF Loan upto 10 crore
18 | R182000118 | Nandwel to Mawta Road | Mandsaur | PWD | Road |  |  | 347.94 | RIDF Loan upto 10 crore
18 | R182000119 | Semra Saiyad to Khamkheda Road | Bhopal | PWD | Road |  |  | 363.63 | RIDF Loan upto 10 crore
18 | R182000120 | Ghatkhedi to Sukhi Sevania Road | Bhopal | PWD | Road |  |  | 176.44 | RIDF Loan upto 10 crore
18 | R182000121 | Bhagikheda to Bhadoos Road | Betul | PWD | Road |  |  | 86.56 | RIDF Loan upto 10 crore
18 | R182000122 | Bithli to Manegaon Road | Balaghat | PWD | Road |  |  | 124.62 | RIDF Loan upto 10 crore
18 | R182000123 | Bothli to Behela Road | Balaghat | PWD | Road |  |  | 140.8 | RIDF Loan upto 10 crore
18 | R182000124 | NH 12 to Jhadla Road | Rajgarh | PWD | Road |  |  | 186.23 | RIDF Loan upto 10 crore
18 | R182000125 | NH 12 to Bankpura Road | Rajgarh | PWD | Road |  |  | 180.07 | RIDF Loan upto 10 crore
18 | R182000126 | Boda to Borkheda Road | Rajgarh | PWD | Road |  |  | 1485.78 | RIDF Loan 10.01-24.99 crore
18 | R182000127 | Narsinghgad NH 12 to Bodha Road | Rajgarh | PWD | Road |  |  | 1853.97 | RIDF Loan 10.01-24.99 crore
18 | R182000128 | Taraganj to Babaliya Road | Rajgarh | PWD | Road |  |  | 227.82 | RIDF Loan upto 10 crore
18 | R182000129 | A.B. Road Udankhedi to Sultania Dhamanda Road | Rajgarh | PWD | Road |  |  | 213.58 | RIDF Loan upto 10 crore
18 | R182000130 | A.B. Road Patadia Bulandpur Road | Rajgarh | PWD | Road | 2015-03-20 | DDM | 314.38 | RIDF Loan upto 10 crore | Phy prgs->76%, Visit book -not available, Benefits -7 Revenue villages with population of 8200 benefitted to access medical & education facilities available at district HQ Rajgah, Easily Market access for majorcrops grown inthe area, NB Brd not display
18 | R182000131 | Talen Padana Sarangpur Road | Rajgarh | PWD | Road |  |  | 508.09 | RIDF Loan upto 10 crore
18 | R182000132 | Badagaon Ramgarh Lakhoni Road | Rajgarh | PWD | Road |  |  | 520.94 | RIDF Loan upto 10 crore
18 | R182000133 | Construction of building for I. T. I (convention | Rajgarh | TE&SD | ITI-C |  |  | 297.5 | RIDF Loan upto 10 crore
18 | R182000134 | Construction of building for I. T. I (convention | Mandsaur | TE&SD | ITI-C |  |  | 297.5 | RIDF Loan upto 10 crore
18 | R182000135 | Construction of building for I. T. I (convention | Mandsaur | TE&SD | ITI-C |  |  | 297.5 | RIDF Loan upto 10 crore
18 | R182000136 | Construction of building for I. T. I (convention | Guna | TE&SD | ITI-C |  |  | 297.5 | RIDF Loan upto 10 crore
18 | R182000137 | Construction of building for I. T. I (convention | Guna | TE&SD | ITI-C |  |  | 297.5 | RIDF Loan upto 10 crore
18 | R182000138 | Construction of building for I. T. I (convention | Ashoknagar | TE&SD | ITI-C |  |  | 297.5 | RIDF Loan upto 10 crore
18 | R182000139 | Construction of building for I. T. I (convention | Dewas | TE&SD | ITI-C |  |  | 297.5 | RIDF Loan upto 10 crore
18 | R182000140 | Construction of building for I. T. I (convention | Datia | TE&SD | ITI-C |  |  | 297.5 | RIDF Loan upto 10 crore
18 | R182000141 | Construction of building for I. T. I (convention | Tikamgarh | TE&SD | ITI-C |  |  | 297.5 | RIDF Loan upto 10 crore
18 | R182000142 | Construction of building for I. T. I (convention | Chhatarpur | TE&SD | ITI-C |  |  | 297.5 | RIDF Loan upto 10 crore
18 | R182000143 | Construction of building for I. T. I (convention | Ujjain | TE&SD | ITI-C |  |  | 297.5 | RIDF Loan upto 10 crore
18 | R182000144 | Construction of building for I. T. I (convention | Ujjain | TE&SD | ITI-C |  |  | 297.5 | RIDF Loan upto 10 crore
18 | R182000145 | Construction of building for I. T. I (convention | Sheopur | TE&SD | ITI-C |  |  | 297.5 | RIDF Loan upto 10 crore
18 | R182000146 | Construction of building for I. T. I (convention | Barwani | TE&SD | ITI-C |  |  | 297.5 | RIDF Loan upto 10 crore
18 | R182000147 | Construction of building for I. T. I (convention | Khandwa | TE&SD | ITI-C |  |  | 297.5 | RIDF Loan upto 10 crore
18 | R182000148 | Construction of building for I. T. I (convention | Khandwa | TE&SD | ITI-C |  |  | 297.5 | RIDF Loan upto 10 crore
18 | R182000149 | Construction of building for I. T. I (convention | Barwani | TE&SD | ITI-C |  |  | 297.5 | RIDF Loan upto 10 crore
18 | R182000150 | Construction of building for I. T. I (convention | Shivpuri | TE&SD | ITI-C |  |  | 297.5 | RIDF Loan upto 10 crore
18 | R182000151 | Construction of building for I. T. I (convention | Shivpuri | TE&SD | ITI-C |  |  | 297.5 | RIDF Loan upto 10 crore
18 | R182000152 | Construction of building for I. T. I (convention | Sidhi | TE&SD | ITI-C |  |  | 297.5 | RIDF Loan upto 10 crore
18 | R182000153 | Construction of building for I. T. I (prefabrica | Chhindwara | TE&SD | ITI-P |  |  | 506.23 | RIDF Loan upto 10 crore
18 | R182000154 | Construction of building for I. T. I (prefabrica | Satna | TE&SD | ITI-P |  |  | 506.23 | RIDF Loan upto 10 crore
18 | R182000155 | Construction of building for I. T. I (prefabrica | Rajgarh | TE&SD | ITI-P |  |  | 506.23 | RIDF Loan upto 10 crore
18 | R182000156 | Construction of building for I. T. I (prefabrica | Rajgarh | TE&SD | ITI-P |  |  | 506.23 | RIDF Loan upto 10 crore
18 | R182000157 | Construction of building for I. T. I (prefabrica | vidisha | TE&SD | ITI-P |  |  | 506.23 | RIDF Loan upto 10 crore
18 | R182000158 | Construction of building for I. T. I (prefabrica | vidisha | TE&SD | ITI-P |  |  | 506.23 | RIDF Loan upto 10 crore
18 | R182000159 | Construction of building for I. T. I (prefabrica | bhopal | TE&SD | ITI-P |  |  | 506.23 | RIDF Loan upto 10 crore
18 | R182000160 | Construction of building for I. T. I (prefabrica | umaria | TE&SD | ITI-P |  |  | 506.23 | RIDF Loan upto 10 crore
18 | R182000161 | Construction of building for I. T. I (prefabrica | umaria | TE&SD | ITI-P |  |  | 506.23 | RIDF Loan upto 10 crore
18 | R182000162 | Construction of building for I. T. I (prefabrica | damoh | TE&SD | ITI-P |  |  | 506.23 | RIDF Loan upto 10 crore
18 | R182000163 | Construction of building for I. T. I (prefabrica | burhanpur | TE&SD | ITI-P |  |  | 506.23 | RIDF Loan upto 10 crore
18 | R182000164 | Construction of building for I. T. I (prefabrica | burhanpur | TE&SD | ITI-P |  |  | 506.23 | RIDF Loan upto 10 crore
18 | R182000165 | Construction of building for I. T. I (prefabrica | khargone | TE&SD | ITI-P |  |  | 506.23 | RIDF Loan upto 10 crore
18 | R182000166 | Construction of building for I. T. I (prefabrica | khargone | TE&SD | ITI-P |  |  | 506.23 | RIDF Loan upto 10 crore
18 | R182000167 | Construction of building for I. T. I (prefabrica | hoshangabad | TE&SD | ITI-P |  |  | 506.23 | RIDF Loan upto 10 crore
18 | R182000168 | Construction of building for I. T. I (prefabrica | balaghat | TE&SD | ITI-P |  |  | 506.23 | RIDF Loan upto 10 crore
18 | R182000169 | Construction of building for I. T. I (prefabrica | shahdol | TE&SD | ITI-P |  |  | 506.23 | RIDF Loan upto 10 crore
18 | R182000170 | Construction of building for I. T. I (prefabrica | shahdol | TE&SD | ITI-P |  |  | 506.23 | RIDF Loan upto 10 crore
18 | R182000171 | Construction of building for I. T. I (prefabrica | seoni | TE&SD | ITI-P |  |  | 506.23 | RIDF Loan upto 10 crore
18 | R182000172 | Construction of building for I. T. I (prefabrica | sehore | TE&SD | ITI-P |  |  | 506.32 | RIDF Loan upto 10 crore
18 | R182000173 | Halon Irrigation Project | Mandla | NVDA | MJP |  |  | 3196.8 | RIDF Loan 25 crore & above
18 | R182000174 | BDP-Phase V -Rewa Branch Canal RD KM 24.00 to KM | Rewa | NVDA | MJP |  |  | 31436.21 | RIDF Loan 25 crore & above
18 | R182000175 | Sonpur Medium Tank Project | Sagar | WRD | MIP |  |  | 11309.29 | RIDF Loan 25 crore & above
18 | R182000176 | Godown | Bhopal | MPWLC | Godown |  |  | 720 | RIDF Loan upto 10 crore
18 | R182000177 | Godown | Hoshangabad | MPWLC | Godown |  |  | 247.5 | RIDF Loan upto 10 crore
18 | R182000178 | Godown | Hoshangabad | MPWLC | Godown |  |  | 139.76 | RIDF Loan upto 10 crore
18 | R182000179 | Godown | Hoshangabad | MPWLC | Godown |  |  | 321.24 | RIDF Loan upto 10 crore
18 | R182000180 | Godown | Harda | MPWLC | Godown |  |  | 139.76 | RIDF Loan upto 10 crore
18 | R182000181 | Godown | Harda | MPWLC | Godown |  |  | 788.31 | RIDF Loan upto 10 crore
18 | R182000182 | Godown | Harda | MPWLC | Godown |  |  | 902.1 | RIDF Loan upto 10 crore
18 | R182000183 | Godown | Jabalpur | MPWLC | Godown |  |  | 414.63 | RIDF Loan upto 10 crore
18 | R182000184 | Godown | Bhind | MPWLC | Godown |  |  | 115.67 | RIDF Loan upto 10 crore
18 | R182000185 | Godown | Gwalior | MPWLC | Godown |  |  | 97.38 | RIDF Loan upto 10 crore
18 | R182000186 | Godown | Datia | MPWLC | Godown |  |  | 97.38 | RIDF Loan upto 10 crore
18 | R182000187 | Godown | Morena | MPWLC | Godown |  |  | 99.77 | RIDF Loan upto 10 crore
18 | R182000188 | Godown | Shajapur | MPWLC | Godown |  |  | 27.07 | RIDF Loan upto 10 crore
18 | R182000189 | Godown | Neemuch | MPWLC | Godown |  |  | 49.34 | RIDF Loan upto 10 crore
18 | R182000190 | Godown | Mandsaur | MPWLC | Godown |  |  | 90.43 | RIDF Loan upto 10 crore
18 | R182000191 | Godown | Ratlam | MPWLC | Godown |  |  | 101.27 | RIDF Loan upto 10 crore
18 | R182000192 | Godown | Sagar | MPWLC | Godown |  |  | 125.05 | RIDF Loan upto 10 crore
18 | R182000193 | Godown | Sheopur | MPWLC | Godown |  |  | 347.52 | RIDF Loan upto 10 crore
18 | R182000194 | Godown | Rewa | MPWLC | Godown |  |  | 420 | RIDF Loan upto 10 crore
18 | R182000195 | Godown | Dewas | MPWLC | Godown |  |  | 960 | RIDF Loan upto 10 crore
18 | R182000196 | Godown | Ashoknagar | MPWLC | Godown |  |  | 150 | RIDF Loan upto 10 crore
18 | R182000197 | Godown | Rajgarh | MPWLC | Godown |  |  | 600 | RIDF Loan upto 10 crore
18 | R182000198 | Convertible CAP | Bhopal | MPWLC | CAP |  |  | 665 | RIDF Loan upto 10 crore
18 | R182000199 | Convertibe CAP | Raisen | MPWLC | CAP |  |  | 164.51 | RIDF Loan upto 10 crore
18 | R182000200 | Convertibe CAP | Raisen | MPWLC | CAP |  |  | 730.98 | RIDF Loan upto 10 crore
18 | R182000201 | Convertibe CAP | Harda | MPWLC | CAP |  |  | 197.52 | RIDF Loan upto 10 crore
18 | R182000202 | Convertibe CAP | Rewa | MPWLC | CAP |  |  | 294.51 | RIDF Loan upto 10 crore
18 | R182000203 | Convertibe CAP | Chhatarpur | MPWLC | CAP |  |  | 320.13 | RIDF Loan upto 10 crore
18 | R182000204 | Convertibe CAP | Panna | MPWLC | CAP |  |  | 391.49 | RIDF Loan upto 10 crore
18 | R182000205 | Convertibe CAP | Tikamgarh | MPWLC | CAP |  |  | 115.22 | RIDF Loan upto 10 crore
18 | R182000206 | Conversion of Existing CAP into Godown | Harda | MPWLC | CAP-Godown |  |  | 600 | RIDF Loan upto 10 crore
18 | R182000207 | Conversion of Existing CAP into Godown | Harda | MPWLC | CAP-Godown |  |  | 510 | RIDF Loan upto 10 crore
18 | R182000208 | Conversion of Existing CAP into Godown | Harda | MPWLC | CAP-Godown |  |  | 240 | RIDF Loan upto 10 crore
18 | R182000209 | Conversion of Existing CAP into Godown | Hoshangabad | MPWLC | CAP-Godown |  |  | 61.74 | RIDF Loan upto 10 crore
18 | R182000210 | Conversion of Existing CAP into Godown | Hoshangabad | MPWLC | CAP-Godown |  |  | 18 | RIDF Loan upto 10 crore
18 | R182000211 | Conversion of Existing CAP into Godown | Hoshangabad | MPWLC | CAP-Godown |  |  | 525 | RIDF Loan upto 10 crore
18 | R182000212 | Conversion of Existing CAP into Godown | Seoni | MPWLC | CAP-Godown |  |  | 416.25 | RIDF Loan upto 10 crore
18 | R182000213 | Conversion of Existing CAP into Godown | Sehore | MPWLC | CAP-Godown |  |  | 608.25 | RIDF Loan upto 10 crore
18 | R182000214 | Conversion of Existing CAP into Godown | Hoshangabad | MPWLC | CAP-Godown | 2014-11-29 | RO Official | 1185.99 | RIDF Loan 10.01-24.99 crore | Phy prgs=85%.Fin prgs-65%. Some of existing CAPs had grain stored in them due to mon moving it construction could not taken up simultaneously for all the godowns. NB brd not displayed.Construcion in progress is not as per approved plans
18 | R182000215 | Conversion of Existing CAP into Godown | Seoni | MPWLC | CAP-Godown |  |  | 117.84 | RIDF Loan upto 10 crore
18 | R182000216 | Conversion of Existing CAP into Godown | Balaghat | MPWLC | CAP-Godown |  |  | 113.52 | RIDF Loan upto 10 crore
18 | R182000217 | Conversion of Existing CAP into Godown | Katni | MPWLC | CAP-Godown |  |  | 113.52 | RIDF Loan upto 10 crore
18 | R182000218 | Construction of Pucca CAPs - Rabi | Betul | Markfed | CAP |  |  | 139.86 | RIDF Loan upto 10 crore
18 | R182000219 | Construction of Pucca CAPs - Rabi | Guna | Markfed | CAP |  |  | 326.34 | RIDF Loan upto 10 crore
18 | R182000220 | Construction of Pucca CAPs - Rabi | Ashoknagar | Markfed | CAP |  |  | 839.17 | RIDF Loan upto 10 crore
18 | R182000221 | Construction of Pucca CAPs - Rabi | Jabalpur | Markfed | CAP |  |  | 400.94 | RIDF Loan upto 10 crore
18 | R182000222 | Construction of Pucca CAPs - Rabi | Seoni | Markfed | CAP |  |  | 699.3 | RIDF Loan upto 10 crore
18 | R182000223 | Construction of Pucca CAPs - Rabi | Chhindwara | Markfed | CAP |  |  | 466.2 | RIDF Loan upto 10 crore
18 | R182000224 | Construction of Pucca CAPs - Rabi | Narsinghpur | Markfed | CAP |  |  | 460.61 | RIDF Loan upto 10 crore
18 | R182000225 | Construction of Pucca CAPs - Rabi | Mandla | Markfed | CAP |  |  | 223.78 | RIDF Loan upto 10 crore
18 | R182000226 | Construction of Pucca CAPs - Rabi | Katni | Markfed | CAP |  |  | 279.72 | RIDF Loan upto 10 crore
18 | R182000227 | Construction of Pucca CAPs - Rabi | Dhar | Markfed | CAP |  |  | 391.61 | RIDF Loan upto 10 crore
18 | R182000228 | Construction of Pucca CAPs - Rabi | Indore | Markfed | CAP |  |  | 466.2 | RIDF Loan upto 10 crore
18 | R182000229 | Construction of Pucca CAPs - Rabi | Khargone | Markfed | CAP |  |  | 727.28 | RIDF Loan upto 10 crore
18 | R182000230 | Construction of Pucca CAPs - Rabi | Badwani | Markfed | CAP |  |  | 111.89 | RIDF Loan upto 10 crore
18 | R182000231 | Construction of Pucca CAPs - Rabi | Khandwa | Markfed | CAP |  |  | 699.3 | RIDF Loan upto 10 crore
18 | R182000232 | Construction of Pucca CAPs - Rabi | Rewa | Markfed | CAP |  |  | 186.48 | RIDF Loan upto 10 crore
18 | R182000233 | Construction of Pucca CAPs - Rabi | Sidhi | Markfed | CAP |  |  | 142.54 | RIDF Loan upto 10 crore
18 | R182000234 | Construction of Pucca CAPs - Rabi | Singrauli | Markfed | CAP |  |  | 41.96 | RIDF Loan upto 10 crore
18 | R182000235 | Construction of Pucca CAPs - Rabi | Satna | Markfed | CAP |  |  | 279.72 | RIDF Loan upto 10 crore
18 | R182000236 | Construction of Pucca CAPs - Rabi | Shahdol | Markfed | CAP |  |  | 18.65 | RIDF Loan upto 10 crore
18 | R182000237 | Construction of Pucca CAPs - Rabi | Umariya | Markfed | CAP |  |  | 23.31 | RIDF Loan upto 10 crore
18 | R182000238 | Construction of Pucca CAPs - Rabi | Annupur | Markfed | CAP |  |  | 206.99 | RIDF Loan upto 10 crore
18 | R182000239 | Construction of Pucca CAPs - Kharif | Jabalpur | Markfed | CAP |  |  | 676.4 | RIDF Loan upto 10 crore
18 | R182000240 | Construction of Pucca CAPs - Kharif | Balaghat | Markfed | CAP |  |  | 950 | RIDF Loan upto 10 crore
18 | R182000241 | Construction of Pucca CAPs - Kharif | Seoni | Markfed | CAP |  |  | 380 | RIDF Loan upto 10 crore
18 | R182000242 | Construction of Pucca CAPs - Kharif | katni | Markfed | CAP |  |  | 167.2 | RIDF Loan upto 10 crore
18 | R182000243 | Construction of Pucca CAPs - Kharif | Mandla | Markfed | CAP |  |  | 83.6 | RIDF Loan upto 10 crore
18 | R182000244 | Construction of Pucca CAPs - Kharif | Satna | Markfed | CAP |  |  | 288.8 | RIDF Loan upto 10 crore
18 | R182000245 | Construction of Pucca CAPs - Kharif | Shahdol | Markfed | CAP |  |  | 76 | RIDF Loan upto 10 crore
18 | R182000246 | Construction of Pucca CAPs - Kharif | Umariya | Markfed | CAP |  |  | 98.8 | RIDF Loan upto 10 crore
18 | R182000247 | Construction of Pucca CAPs - Kharif | Singrauli | Markfed | CAP |  |  | 114 | RIDF Loan upto 10 crore
18 | R182000248 | Construction of Pucca CAP - Type A | Raisen | MPWLC | CAP |  |  | 117.25 | RIDF Loan upto 10 crore
18 | R182000249 | Construction of Pucca CAP - Type B | Hoshangabad | MPWLC | CAP |  |  | 106.62 | RIDF Loan upto 10 crore
18 | R182000250 | Construction of Pucca CAP - Type B | Hoshangabad | MPWLC | CAP |  |  | 67.77 | RIDF Loan upto 10 crore
18 | R182000251 | Construction of Pucca CAP - Type B | Hoshangabad | MPWLC | CAP |  |  | 197.15 | RIDF Loan upto 10 crore
18 | R182000252 | Construction of Pucca CAP - Type B | Harda | MPWLC | CAP |  |  | 84.99 | RIDF Loan upto 10 crore
18 | R182000253 | Construction of Pucca CAP - Type B | Bhopal | MPWLC | CAP |  |  | 80.94 | RIDF Loan upto 10 crore
18 | R182000254 | Construction of Pucca CAP - Type B | Hoshangabad | MPWLC | CAP |  |  | 351.6 | RIDF Loan upto 10 crore
18 | R182000255 | Construction of Pucca CAP - Type B | Harda | MPWLC | CAP |  |  | 516.14 | RIDF Loan upto 10 crore
18 | R182000256 | Construction of Pucca CAP - Type C | Raisen | MPWLC | CAP |  |  | 333.74 | RIDF Loan upto 10 crore
18 | R182000257 | Construction of Pucca CAP - Type C | Raisen | MPWLC | CAP |  |  | 199.09 | RIDF Loan upto 10 crore
18 | R182000258 | Construction of Pucca CAP - Type C | Sehore | MPWLC | CAP |  |  | 116.19 | RIDF Loan upto 10 crore
18 | R182000259 | Construction of Pucca CAP - Type C | Rajgarh | MPWLC | CAP |  |  | 227.91 | RIDF Loan upto 10 crore
18 | R182000260 | Construction of Pucca CAP - Type C | Ujjain | MPWLC | CAP |  |  | 347.83 | RIDF Loan upto 10 crore
18 | R182000261 | Construction of Pucca CAP - Type C | Shajapur | MPWLC | CAP |  |  | 351.6 | RIDF Loan upto 10 crore
18 | R182000262 | Construction of Pucca CAP - Type C | Mandsaur | MPWLC | CAP |  |  | 457.07 | RIDF Loan upto 10 crore
18 | R182000263 | Construction of Pucca CAP - Type C | Sheopur | MPWLC | CAP |  |  | 351.6 | RIDF Loan upto 10 crore
19 | R192000001 | Datuni Medium Tank Project | DEWAS |  |  | 2015-02-24 | RO Official |  | RIDF Loan upto 10 crore | Phy prgs-25% (E/W-56%,Const of flanks 2 coffer dams-40%, Nalla closure of main dam-20%), ToR-due to LA, Forest clearance, TSC clearance has not received so far from MOWR, GoI, Visitbook not maintained, NB Brd not displayed, Illegal mining at site
19 | R192000002 | Mardanpur Group Water Supply Project | SEHORE |  |  | 2015-03-13 | RO Official |  | RIDF Loan upto 10 crore | Phy prgs-25%(Intake well-45%,K-9 Raw water pumping main-70%), ToR-in intake well & electrical substation, work behind schedule as per the PERT chart , Forest clearance is needed for laying of pipelines and some elevated service reservoirs
19 | R192000003 | Udaipura Group Water Supply Project | RAISEN | [5 empty] | RIDF Loan upto 10 crore
19 | R192000004 | Talunkhurd Group Water Supply Project | BARWANI | [5 empty] | RIDF Loan upto 10 crore
19 | R192000005 | Bagod, Naadiya, Pipliya Group Water Supply Project | KHARGONE | [5 empty] | RIDF Loan upto 10 crore
19 | R192000006 | Arnia Bahadur Group Water Supply Project | UJAIN | [5 empty] | RIDF Loan upto 10 crore
19 | R192000007 | Majholi Group Water Supply Project | SIDHI | [5 empty] | RIDF Loan upto 10 crore
19 | R192000008 | Bhatera Group Water Supply Project | BALAGHAT | [5 empty] | RIDF Loan upto 10 crore
19 | R192000009 | Manpur Group Water Supply Project | UMARIA | [5 empty] | RIDF Loan upto 10 crore
19 | R192000010 | Devsara Group Water Supply Project | BALAGHAT | [5 empty] | RIDF Loan upto 10 crore
19 | R192000011 | Mehandwani Group Water Supply Project | DINDORI | [5 empty] | RIDF Loan upto 10 crore
19 | R192000012 | Extension Renovation Modernisation of Barna Project | MANY | [5 empty] | RIDF Loan upto 10 crore
19 | R192000013 | DEVLA BAGHADI TO BARSALAY ROAD | BARWANI | [5 empty] | RIDF Loan upto 10 crore
19 | R192000014 | ENKHEDA TO JAWRA ROAD | BETUL | [5 empty] | RIDF Loan upto 10 crore
19 | R192000015 | DHODKHEDA SAWANGI GUNKHED ROAD | BETUL | [5 empty] | RIDF Loan upto 10 crore
19 | R192000016 | KATKUHI JOD MALAJPUR TO JHARKUND ROAD | BETUL | [5 empty] | RIDF Loan upto 10 crore
19 | R192000017 | PARSODI HATHNORA TO BETULBAJAR ROAD | BETUL | [5 empty] | RIDF Loan upto 10 crore
19 | R192000018 | SHAHPUR TO BHAYAWADI ROAD | BETUL | [5 empty] | RIDF Loan upto 10 crore
19 | R192000019 | DHULKOT BORIBUJURG TO PASCHIN NIMAR BORDER ROAD | BURHANPUR | [5 empty] | RIDF Loan upto 10 crore
19 | R192000020 | GANJ JHAMTULI AMROLIYA DEVRA ROAD | CHHATARPUR |  |  | 2015-03-13 | RO Official |  | RIDF Loan upto 10 crore | Phy prgs-98% permission was not given by Forest Dept for widenig the road in some portion, Board displayed but NABARD support clause not indicated.
19 | R192000021 | KANDELA RAMPURGHAT ROAD | CHHATARPUR | [5 empty] | RIDF Loan upto 10 crore
19 | R192000022 | LUGASI JHIJHAN SARDARPUR ROAD | CHHATARPUR | [5 empty] | RIDF Loan upto 10 crore
19 | R192000023 | KANHARGAON MUSADEHI ROHNA ROAD | CHHINDWARA | [5 empty] | RIDF Loan upto 10 crore
19 | R192000024 | RAJEGAON JAMSIMARIYA CHHINDWARA ROAD | CHHINDWARA | [5 empty] | RIDF Loan upto 10 crore
19 | R192000025 | SHIVLALDHANA KUKDA CHIMAN MALHANWARA TO CHHINDWARA CHAND ROAD | CHHINDWARA | [5 empty] | RIDF Loan upto 10 crore
19 | R192000026 | SADIPURA DERIYA SAHU TO KULAWAD ROAD | DEWAS | [5 empty] | RIDF Loan upto 10 crore
19 | R192000027 | BARANGI TO ROLGAON ROAD | HARDA | [5 empty] | RIDF Loan upto 10 crore
19 | R192000028 | BHUVANKHEDI TO BAMHONI VIA BHUNNAS BHAIRONPUR RIJGAON KUJARGAON ROAD | HARDA | [5 empty] | RIDF Loan upto 10 crore
19 | R192000029 | SIGON GAWLA MALPON TO HANDIYA ROAD | HARDA | [5 empty] | RIDF Loan upto 10 crore
19 | R192000030 | SOHAGPUR PANRALAI ROAD | HARDA | [5 empty] | RIDF Loan upto 10 crore
19 | R192000031 | BHAIRONPUR TO GOLGAON ROAD | HOSHANGABAD | [5 empty] | RIDF Loan upto 10 crore
19 | R192000032 | GHUGHWASA TO BORTALAI ROAD | HOSHANGABAD | [5 empty] | RIDF Loan upto 10 crore
19 | R192000033 | SAMON NASIRABAD ROAD TO BHANPUR BAGALKHEDI ROAD | HOSHANGABAD | [5 empty] | RIDF Loan upto 10 crore
19 | R192000034 | TIHARIYA BADSHAH TO INDUSTRIAL AREA SANWER ROAD | INDORE | [5 empty] | RIDF Loan upto 10 crore
19 | R192000035 | GOWARDHAN GAUSHALA TO HINGONIYA JUNCTION ROAD | INDORE | [5 empty] | RIDF Loan upto 10 crore
19 | R192000036 | KODIYA TO CHARHAWAN ROAD | KATNI | [5 empty] | RIDF Loan upto 10 crore
19 | R192000037 | BADOD AHIR TO DEEWAL ROAD | KHANDWA | [5 empty] | RIDF Loan upto 10 crore
19 | R192000038 | BHAKRADA TO BAMHANGAON KHEDIKITTA ROAD | KHANDWA | [5 empty] | RIDF Loan upto 10 crore
19 | R192000039 | KHALWA DONGLIYA ROAD VIA KOTHA ROAD TO KHALWA DEVTALAI ROAD | KHANDWA | [5 empty] | RIDF Loan upto 10 crore
19 | R192000040 | BADI TO MULTHAN ROAD | KHARGONE | [5 empty] | RIDF Loan upto 10 crore
19 | R192000041 | DOLANI TO DABRI ROAD | KHARGONE | [5 empty] | RIDF Loan upto 10 crore
19 | R192000042 | GAWLA TO BAMANDI ROAD | KHARGONE | [5 empty] | RIDF Loan upto 10 crore
19 | R192000043 | KHEDI TO JALJYOTI ROAD | KHARGONE | [5 empty] | RIDF Loan upto 10 crore
19 | R192000044 | KOTHIBUJURG TO KOTHIKHURD ROAD | KHARGONE | [5 empty] | RIDF Loan upto 10 crore
19 | R192000045 | PANWA TO RAGWAN ROAD | KHARGONE | [5 empty] | RIDF Loan upto 10 crore
19 | R192000046 | SATRATHI TO BHOINDA ROAD | KHARGONE | [5 empty] | RIDF Loan upto 10 crore
19 | R192000047 | NARAYANGANJ TO DEVRI MUKAS ROAD | MANDLA | [5 empty] | RIDF Loan upto 10 crore
19 | R192000048 | BOLIYA TO JAIN DIWAKAR (CHAUTHMALJI MAHARAJ DIKSHA STHAL TAK) ROAD | MANDSAUR | [5 empty] | RIDF Loan upto 10 crore
19 | R192000049 | TAKRAWAD TO DEVRI ROAD | MANDSAUR | [5 empty] | RIDF Loan upto 10 crore
19 | R192000050 | RAJORA TO SATHO VIA NAGELA ROAD | MORENA | [5 empty] | RIDF Loan upto 10 crore
19 | R192000051 | MEHGAONTALA TO BHAMA ROAD | NARSIMHAPUR | [5 empty] | RIDF Loan upto 10 crore
19 | R192000052 | N. H. 12 TO BIJORA ROAD | NARSIMHAPUR | [5 empty] | RIDF Loan upto 10 crore
19 | R192000053 | PURGAWAN TO SIHORA ROAD | NARSIMHAPUR | [5 empty] | RIDF Loan upto 10 crore
19 | R192000054 | KUKDESHWAR TO HANUMANTYA BHATKHEDI SUDHI LASODIYA ROAD | NEEMUCH | [5 empty] | RIDF Loan upto 10 crore
19 | R192000055 | SARVANIYA MAHARAJ TO AAKLI MELANKHEDA ROAD | NEEMUCH | [5 empty] | RIDF Loan upto 10 crore
19 | R192000056 | SAVAN TO BHADWAMATA ROAD | NEEMUCH | [5 empty] | RIDF Loan upto 10 crore
19 | R192000057 | AMCHHAKALAN TO UMARIYA ROAD | RAISEN | [5 empty] | RIDF Loan upto 10 crore
19 | R192000058 | BAKTARA TO ARKA ROAD | RAISEN | [5 empty] | RIDF Loan upto 10 crore
19 | R192000059 | BAKTARA TO DIGHWAD ROAD | RAISEN | [5 empty] | RIDF Loan upto 10 crore
19 | R192000060 | BAKTARA TO GUGALWARA MANKAPUR ROAD | RAISEN | [5 empty] | RIDF Loan upto 10 crore
19 | R192000061 | BAKTARA TO MANGROL ROAD | RAISEN | [5 empty] | RIDF Loan upto 10 crore
19 | R192000062 | BAKTARA TO MALJHIR ROAD | RAISEN | [5 empty] | RIDF Loan upto 10 crore
19 | R192000063 | BARELI TO BAGALWARA ROAD | RAISEN | [5 empty] | RIDF Loan upto 10 crore
19 | R192000064 | HIRANIYA TO TIGARIYA ROAD | RAISEN | [5 empty] | RIDF Loan upto 10 crore
19 | R192000065 | JAKHDAPUL TO NANAKHEDI BHADKI SAYA PREM JATAB DIVTIYA ROAD | RAISEN | [5 empty] | RIDF Loan upto 10 crore
19 | R192000066 | LADLI KHUKARIYA TO UMRAOGANJ ROAD | RAISEN | [5 empty] | RIDF Loan upto 10 crore
19 | R192000067 | METHAGAON TO KEKDA ROAD | RAISEN | [5 empty] | RIDF Loan upto 10 crore
19 | R192000068 | KHARWANKALAN APPROACH ROAD | RATLAM | [5 empty] | RIDF Loan upto 10 crore
19 | R192000069 | PANTH PIPLODA ROAD | RATLAM | [5 empty] | RIDF Loan upto 10 crore
19 | R192000070 | MAJHIYAR PATHRI PADRI SIRMAUR ROAD | REWA | [5 empty] | RIDF Loan upto 10 crore
19 | R192000071 | REWA SIRMAUR ROAD TO GARGANTOLA TIWARIAN KA TOLA RAJGARH ROAD | REWA | [5 empty] | RIDF Loan upto 10 crore
19 | R192000072 | UMARIYA GANGEV ROAD VIA GIRUARI ROAD | REWA | [5 empty] | RIDF Loan upto 10 crore
19 | R192000073 | SEHORA NAVALGAON NAGDAHAR PURWA ROAD | SEONI | [5 empty] | RIDF Loan upto 10 crore
19 | R192000074 | BINA RICHHAI ROAD | SAGAR | [5 empty] | RIDF Loan upto 10 crore
19 | R192000075 | BAXWAHA TO NAINAGIR ROAD | SAGAR | [5 empty] | RIDF Loan upto 10 crore
19 | R192000076 | JARARA TO PATAN ROAD | SAGAR | [5 empty] | RIDF Loan upto 10 crore
19 | R192000077 | JAWTI TO NISHOBARRI NAINWASH MANPUR ROAD | VIDISHA | [5 empty] | RIDF Loan upto 10 crore
19 | R192000078 | LATERI SHAMSHABAD ROAD TO NAYAGAON DHOKDA ROAD | VIDISHA | [5 empty] | RIDF Loan upto 10 crore
19 | R192000079 | Datehara Group Water Supply Project | MORENA | [5 empty] | RIDF Loan upto 10 crore
19 | R192000080 | Narhela Group Water Supply Project | MORENA | [5 empty] | RIDF Loan upto 10 crore
19 | R192000081 | Roshni Group Water Supply Project | KHANDWA | [5 empty] | RIDF Loan upto 10 crore
19 | R192000082 | Gangabawdi Group Water Supply Project | NEEMUCH | [5 empty] | RIDF Loan upto 10 crore
19 | R192000083 | Punjapura Group Water Supply Project | DEWAS | [5 empty] | RIDF Loan upto 10 crore
19 | R192000084 | Piparjhari Group Water Supply Project | BALAGHAT | [5 empty] | RIDF Loan upto 10 crore
19 | R192000085 | Dhuti Group Water Supply Project | BALAGHAT | [5 empty] | RIDF Loan upto 10 crore
19 | R192000086 | Jhurki Group Water Supply Project | SEONI | [5 empty] | RIDF Loan upto 10 crore
19 | R192000087 | Kudam Group Water Supply Project | JABALPUR | [5 empty] | RIDF Loan upto 10 crore
19 | R192000088 | Jhagri Karriya Rakh Laxman Kuti Road | Damoh | PWD | Road |  |  | 117.52 | RIDF Loan upto 10 crore
19 | R192000089 | Kaikheda HarizanTola Tigra Road | Damoh | PWD | Road |  |  | 350.59 | RIDF Loan upto 10 crore
19 | R192000090 | Semritala to Purena kalan Road | Hoshangabad | PWD | Road |  |  | 220.43 | RIDF Loan upto 10 crore
19 | R192000091 | Essagarh(Denga Mochar) to Pipariya- Nayagaon Road | Ashoknagar | PWD | Road |  |  | 512.81 | RIDF Loan upto 10 crore
19 | R192000092 | Rijoda Dongar Road | Ashoknagar | PWD | Road |  |  | 836.34 | RIDF Loan upto 10 crore
19 | R192000093 | Karod to Parsoda Road | Guna | PWD | Road |  |  | 176.86 | RIDF Loan upto 10 crore
19 | R192000094 | Parwah to Pipliya Road | Guna | PWD | Road |  |  | 110.46 | RIDF Loan upto 10 crore
19 | R192000095 | Amrod to Nonera Road | Guna | PWD | Road |  |  | 176.9 | RIDF Loan upto 10 crore
19 | R192000096 | Dhanoriya to Ukawadkhurd | Guna | PWD | Road |  |  | 182.05 | RIDF Loan upto 10 crore
19 | R192000097 | Raikwar Nowgawan Road | Satna | PWD | Road |  |  | 106.39 | RIDF Loan upto 10 crore
19 | R192000098 | Badera Ajmain Road | Satna | PWD | Road |  |  | 142.47 | RIDF Loan upto 10 crore
19 | R192000099 | Ramvan Dilaura Road | Satna | PWD | Road |  |  | 145.01 | RIDF Loan upto 10 crore
19 | R192000100 | Bholiya To Kunchrod Road | Mandsaur | PWD | Road |  |  | 149.64 | RIDF Loan upto 10 crore
19 | R192000101 | Pinda to Gujarbardiya Road | Mandsaur | PWD | Road |  |  | 344.99 | RIDF Loan upto 10 crore
19 | R192000102 | Lamgari to Patalwada Road | Mandsaur | PWD | Road |  |  | 239.97 | RIDF Loan upto 10 crore
19 | R192000103 | Sagore to Manpura Road | Mandsaur | PWD | Road |  |  | 84.47 | RIDF Loan upto 10 crore
19 | R192000104 | Malyakhedi to Jamalpura Kochavi Road | Mandsaur | PWD | Road |  |  | 267.94 | RIDF Loan upto 10 crore
19 | R192000105 | Bilkisganj (Pani ki Tank) Bamlagarh via Gadiya Roa | Sehore | PWD | Road |  |  | 407.46 | RIDF Loan upto 10 crore
19 | R192000106 | Ashta Jagananthpura to Anandipura Road | Sehore | PWD | Road |  |  | 136.34 | RIDF Loan upto 10 crore
19 | R192000107 | Gader to Isherpur Road | Sehore | PWD | Road |  |  | 82.99 | RIDF Loan upto 10 crore
19 | R192000108 | Rewgaon to sanwalkheda Road | Sehore | PWD | Road |  |  | 172.42 | RIDF Loan upto 10 crore
19 | R192000109 | Kosmi to Gehukheda to Gondi Gundariya Road | Sehore | PWD | Road |  |  | 158.98 | RIDF Loan upto 10 crore
19 | R192000110 | Bordi to Gondi Guradiya to Jamoniya Bajyafat Road | Sehore | PWD | Road |  |  | 177.29 | RIDF Loan upto 10 crore
19 | R192000111 | Bordhi to Bordha Khela via Narela Jod Road | Sehore | PWD | Road |  |  | 103.1 | RIDF Loan upto 10 crore
19 | R192000112 | Bhadkul to Jamoniya to Bordhi Approach Road | Sehore | PWD | Road |  |  | 277.19 | RIDF Loan upto 10 crore
19 | R192000113 | Bori to Dongri Road | Sehore | PWD | Road |  |  | 68 | RIDF Loan upto 10 crore
19 | R192000114 | Nonbhait to Theekri Road | Sehore | PWD | Road |  |  | 108.73 | RIDF Loan upto 10 crore
19 | R192000115 | Main road Barda to Barda and Main road to Pipaliya | Sehore | PWD | Road |  |  | 136.28 | RIDF Loan upto 10 crore
19 | R192000116 | Jait Sardar Nagar to Netankhedi Surajkund Road | Sehore | PWD | Road |  |  | 320.52 | RIDF Loan upto 10 crore
19 | R192000117 | Approach road to Holipura tappar( from Jait Naraya | Sehore | PWD | Road |  |  | 113.67 | RIDF Loan upto 10 crore
19 | R192000118 | Mogra to Gurusahab Internal Road | Sehore | PWD | Road |  |  | 95.75 | RIDF Loan upto 10 crore
19 | R192000119 | Shyampur to Thikrikheda Road | Sehore | PWD | Road |  |  | 138.98 | RIDF Loan upto 10 crore
19 | R192000120 | Aanwali to Girvanya Road | Dhar | PWD | Road |  |  | 180.74 | RIDF Loan upto 10 crore
19 | R192000121 | Bhimpura to Chikali Road | Dhar | PWD | Road |  |  | 130.41 | RIDF Loan upto 10 crore
19 | R192000122 | Harai Pratap Singh Approach Road i/c improvement o | Rewa | PWD | Road |  |  | 230.32 | RIDF Loan upto 10 crore
19 | R192000123 | Nagai to Atariya Shivprasad Road | Rewa | PWD | Road |  |  | 93.38 | RIDF Loan upto 10 crore
19 | R192000124 | Bichhodna Bagda Road | Datia | PWD | Road |  |  | 101.34 | RIDF Loan upto 10 crore
19 | R192000125 | Sinawal to Gwalior Jhansi via tugyan ka dera Road | Datia | PWD | Road |  |  | 194.46 | RIDF Loan upto 10 crore
19 | R192000126 | Unao Sarsai Road | Datia | PWD | Road |  |  | 190.65 | RIDF Loan upto 10 crore
19 | R192000127 | Salaiya Pawar Road to Taka via Chhata Road | Datia | PWD | Road |  |  | 402.02 | RIDF Loan upto 10 crore
19 | R192000128 | Nagda Bhikampur Road | Ujjain | PWD | Road |  |  | 129.44 | RIDF Loan upto 10 crore
19 | R192000129 | HL bridge across betwa river Ashapuri khasrod Salkani Wardhman factory | Raisen | PWD | Bridge |  |  | 1289.46 | RIDF Loan 10.01-24.99 crore
19 | R192000130 | Upper Tilwara Canal Project | Seoni | WRD | MIP |  |  | 9061.58 | RIDF Loan 25 crore & above
19 | R192000131 | Aamkhut Kaththiwada Road | Alirajpur | PWD | Road |  |  | 777.38 | RIDF Loan upto 10 crore
19 | R192000132 | Sorwa Kel Chandarmeli Phoolmal Road | Alirajpur | PWD | Road |  |  | 385.22 | RIDF Loan upto 10 crore
19 | R192000133 | Parsol Sirni Indar Kadwaya Road | Ashoknagar | PWD | Road |  |  | 367.57 | RIDF Loan upto 10 crore
19 | R192000134 | Shadora Wajidpur road | Ashoknagar | PWD | Road |  |  | 273.97 | RIDF Loan upto 10 crore
19 | R192000135 | Dudwa to Gram Ghat Temni Road | Balaghat | PWD | Road |  |  | 110.84 | RIDF Loan upto 10 crore
19 | R192000136 | Sihora -Sihoratola-Devgaon Road | Balaghat | PWD | Road |  |  | 216.66 | RIDF Loan upto 10 crore
19 | R192000137 | Barwani to Choti kasrawad road | Barwani | PWD | Road |  |  | 126.15 | RIDF Loan upto 10 crore
19 | R192000138 | Lalbagh to Sharda road | Burhanpur | PWD | Road |  |  | 305.38 | RIDF Loan upto 10 crore
19 | R192000139 | Icchapur to Bhota Road | Burhanpur | PWD | Road |  |  | 333.9 | RIDF Loan upto 10 crore
19 | R192000140 | Khajuraho byepass road | Chhatarpur | PWD | Road |  |  | 1128.24 | RIDF Loan 10.01-24.99 crore
19 | R192000141 | Simri Jalamsingh to Chandu Choupra Road | Damoh | PWD | Road |  |  | 104.1 | RIDF Loan upto 10 crore
19 | R192000142 | Patera Raneh Marg | Damoh | PWD | Road |  |  | 278.7 | RIDF Loan upto 10 crore
19 | R192000143 | Kheda Approach Road | Dhar | PWD | Road |  |  | 152.09 | RIDF Loan upto 10 crore
19 | R192000144 | Bilhati Parsen Bahadurpura Road | Gwalior | PWD | Road |  |  | 348.45 | RIDF Loan upto 10 crore
19 | R192000145 | Bhadroli to Dilawar Road | Gwalior | PWD | Road |  |  | 141.6 | RIDF Loan upto 10 crore
19 | R192000146 | New Collectorate to Sirol Thiraha Road | Gwalior | PWD | Road |  |  | 290.21 | RIDF Loan upto 10 crore
19 | R192000147 | Campel Unhel Semria Karadia Road | Indore | PWD | Road |  |  | 699.19 | RIDF Loan upto 10 crore
19 | R192000148 | Khomana Aakya Gangakhedi Road | Indore | PWD | Road |  |  | 414.86 | RIDF Loan upto 10 crore
19 | R192000149 | Khajrana to Jhalriya Road kM.1/2 to 2/6 | Indore | PWD | Road |  |  | 136.43 | RIDF Loan upto 10 crore
19 | R192000150 | A.B to Soya ruchi factory Road | Indore | PWD | Road |  |  | 170.75 | RIDF Loan upto 10 crore
19 | R192000151 | Pipariya to Sonpur beejkendra Road | Jabalpur | PWD | Road |  |  | 282.66 | RIDF Loan upto 10 crore
19 | R192000152 | Sakri bichua nimbori road | Jabalpur | PWD | Road |  |  | 364.43 | RIDF Loan upto 10 crore
19 | R192000153 | Khirhani Sachuli Lamatara Deori Road | Jabalpur | PWD | Road |  |  | 256.09 | RIDF Loan upto 10 crore
19 | R192000154 | Lamkana Majhgawan Bagheli Marg | Jabalpur | PWD | Road |  |  | 310.56 | RIDF Loan upto 10 crore
19 | R192000155 | Khinni Deori Road | Jabalpur | PWD | Road |  |  | 213.32 | RIDF Loan upto 10 crore
19 | R192000156 | Naharpura Khijada to Chaipury Road | Jhabua | PWD | Road |  |  | 219.67 | RIDF Loan upto 10 crore
19 | R192000157 | Roopgarh Mohankot Road | Jhabua | PWD | Road |  |  | 232.25 | RIDF Loan upto 10 crore
19 | R192000158 | Petlawad Roopgarh Hanuman Mandir Road | Jhabua | PWD | Road |  |  | 81.11 | RIDF Loan upto 10 crore
19 | R192000159 | Panki to Jhakela via Rotla Road | Jhabua | PWD | Road |  |  | 145.05 | RIDF Loan upto 10 crore
19 | R192000160 | Pitol Anas Road | Jhabua | PWD | Road |  |  | 111.64 | RIDF Loan upto 10 crore
19 | R192000161 | Ziree Umarkot to Dewali Manasya Road | Jhabua | PWD | Road |  |  | 290.55 | RIDF Loan upto 10 crore
19 | R192000162 | Gangakhedi Mandan Road | Jhabua | PWD | Road |  |  | 175.42 | RIDF Loan upto 10 crore
19 | R192000163 | Pithanpur Dhamou Road | Jhabua | PWD | Road |  |  | 193.56 | RIDF Loan upto 10 crore
19 | R192000164 | Paloha to Katjunagar road | Narsinghpur | PWD | Road |  |  | 151.45 | RIDF Loan upto 10 crore
19 | R192000165 | Narsinghpur Tindani Gargata Road | Narsinghpur | PWD | Road |  |  | 553.87 | RIDF Loan upto 10 crore
19 | R192000166 | Goundi-Dhubghat Road | Narsinghpur | PWD | Road |  |  | 86.92 | RIDF Loan upto 10 crore
19 | R192000167 | Imliya Morach Road | Narsinghpur | PWD | Road |  |  | 203.23 | RIDF Loan upto 10 crore
19 | R192000168 | Athwa Kala to Tokara via Sehana Talal | Neemuch | PWD | Road |  |  | 960.94 | RIDF Loan upto 10 crore
19 | R192000169 | Jeeran Pirana Road | Neemuch | PWD | Road |  |  | 107.43 | RIDF Loan upto 10 crore
19 | R192000170 | Ashapuri murari choupada amarsthon road | Raisen | PWD | Road |  |  | 466.1 | RIDF Loan upto 10 crore
19 | R192000171 | Hardot Pattan neelkantavar mandir to gehuras road | Raisen | PWD | Road |  |  | 242.78 | RIDF Loan upto 10 crore
19 | R192000172 | Palak mati Dam to kara ghati tari road | Raisen | PWD | Road |  |  | 378.42 | RIDF Loan upto 10 crore
19 | R192000173 | Palkashri to ghurela road | Raisen | PWD | Road |  |  | 93.35 | RIDF Loan upto 10 crore
19 | R192000174 | Dhgaon-Bamhori Road | Raisen | PWD | Road |  |  | 798.45 | RIDF Loan upto 10 crore
19 | R192000175 | Begumganj Sagar Marg Jhiriya Mandir | Raisen | PWD | Road |  |  | 597.13 | RIDF Loan upto 10 crore
19 | R192000176 | Construction of Approach Road to Raisen Fort | Raisen | PWD | Road |  |  | 148.22 | RIDF Loan upto 10 crore
19 | R192000177 | Aashapuri Khasrod to Saalkani Vardhman Factory,Salkani Factory upto NH-12 | Raisen | PWD | Road |  |  | 269.94 | RIDF Loan upto 10 crore
19 | R192000178 | Mandideep Dahod to Food Part App Road | Raisen | PWD | Road |  |  | 171.12 | RIDF Loan upto 10 crore
19 | R192000179 | Tilandi parkhedi | Raisen | PWD | Road |  |  | 501.38 | RIDF Loan upto 10 crore
19 | R192000180 | Ganeshganj-Sojnawar Tarha Road | Sagar | PWD | Road |  |  | 404 | RIDF Loan upto 10 crore
19 | R192000181 | Inayatpur to Jholsi Tiggadda Road | Sagar | PWD | Road |  |  | 252 | RIDF Loan upto 10 crore
19 | R192000182 | Garhakota bye pass Road | Sagar | PWD | Road |  |  | 340 | RIDF Loan upto 10 crore
19 | R192000183 | Mara Baroda Kodni Road | Sagar | PWD | Road |  |  | 317.5 | RIDF Loan upto 10 crore
19 | R192000184 | Semrabag-Jinda Forelane Road | Sagar | PWD | Road |  |  | 328.77 | RIDF Loan upto 10 crore
19 | R192000185 | Banda Bara Kerbana Road | Sagar | PWD | Road |  |  | 1109.15 | RIDF Loan 10.01-24.99 crore
19 | R192000186 | Widening and upgradation of rehli road | Sagar | PWD | Road |  |  | 333.92 | RIDF Loan upto 10 crore
19 | R192000187 | Icchawar Ram Nagar Road | Sehore | PWD | Road |  |  | 290.51 | RIDF Loan upto 10 crore
19 | R192000188 | Sakhi to Deovran Road | Shahdol | PWD | Road |  |  | 229.38 | RIDF Loan upto 10 crore
19 | R192000189 | Batura to Sompur vhaya Girva Road | Shahdol | PWD | Road |  |  | 664.28 | RIDF Loan upto 10 crore
19 | R192000190 | Papond to vijaysota road | Shahdol | PWD | Road |  |  | 261.19 | RIDF Loan upto 10 crore
19 | R192000191 | Kharpa to Aakhetpur Road | Shahdol | PWD | Road |  |  | 248.41 | RIDF Loan upto 10 crore
19 | R192000192 | Gahloni to Berja Road | Shivpuri | PWD | Road |  |  | 223.22 | RIDF Loan upto 10 crore
19 | R192000193 | Kakrai to Behrada Road | Shivpuri | PWD | Road |  |  | 459.99 | RIDF Loan upto 10 crore
19 | R192000194 | Sonhar to Shila nagar Road | Shivpuri | PWD | Road |  |  | 283.91 | RIDF Loan upto 10 crore
19 | R192000195 | Amolpatha to Kundalpur vhaya Shankargarh Ganeshkheda Road | Shivpuri | PWD | Road |  |  | 184.81 | RIDF Loan upto 10 crore
19 | R192000196 | Chakra to Jhirki road | Tikamgarh | PWD | Road |  |  | 177.87 | RIDF Loan upto 10 crore
19 | R192000197 | Tikamgarh to Kari vhaya bharatnagar road | Tikamgarh | PWD | Road |  |  | 290.08 | RIDF Loan upto 10 crore
19 | R192000198 | Maalpeetha to Bangaav road | Tikamgarh | PWD | Road |  |  | 589.11 | RIDF Loan upto 10 crore
19 | R192000199 | Nivadi byepass road | Tikamgarh | PWD | Road |  |  | 183.07 | RIDF Loan upto 10 crore
19 | R192000200 | Badnagar bypass road | Ujjain | PWD | Road |  |  | 794.08 | RIDF Loan upto 10 crore
20 | R202000001 | Bridge across Banjar River on Sarekha - Surwahi - | Balaghat | PWD | Bridge |  |  | 334.69
20 | R202000002 | Bridge across Sagar River in KM 1/4 of Keolari-Ugl | Seoni | PWD | Bridge |  |  | 265.42
20 | R202000003 | Bridge across Bebas River on Sinroja Tilakhedi Pip | Sagar | PWD | Bridge |  |  | 243.41
20 | R202000004 | Bebas Bridge on Mailwara Sigon Road Submersible | Damoh | PWD | Bridge |  |  | 343.02
20 | R202000005 | Bridge across Ghodapachhad River in kM 50/4 on Ash | Khandwa | PWD | Bridge |  |  | 861.01
20 | R202000006 | Submersible Bridge across Tapti River in kM 6/4 on | Burhanpur | PWD | Bridge |  |  | 935.37
20 | R202000007 | Bridge across Sindh River on Bhadurpura - Atarsuma | Bhind | PWD | Bridge |  |  | 1949.21
20 | R202000008 | Bridge Asan River Submersible on Ghoogas-Bichpai R | Morena | PWD | Bridge |  |  | 470.52
20 | R202000009 | Bridge across Gopad River across Kusumi Banjari Ro | Singrauli | PWD | Bridge |  |  | 395.91
20 | R202000010 | Bridge across River Samdhin on Beohari-Mau Panch J | Shahdol | PWD | Bridge |  |  | 280.43
20 | R202000011 | Submersible Bridge Across Kewai River on Nigwani K | Annupur | PWD | Bridge |  |  | 261.17
20 | R202000012 | Bridge Across Tem River kM 20/10 & Utawli River kM | Vidisha | PWD | Bridge |  |  | 583.23
20 | R202000013 | Bridge across Shivna River on Acheri Achera Road H | Mandsaur | PWD | Bridge |  |  | 536.17
20 | R202000014 | Hat-Vinati_Madiyado road - Sonar river Bridge Subm | Damoh | PWD | Bridge |  |  | 759.18
20 | R202000015 | Bridge across Sindh river on Jakhmoli Larol Road H | Bhind | PWD | Bridge |  |  | 1440.09
20 | R202000016 | Udaypur to Bamora Road | Vidisha | PWD | Road |  |  | 135.53
20 | R202000017 | Esharwas - Nainwas - Chamar Umariya to Amjhir Ashr | Vidisha | PWD | Road |  |  | 177.43
20 | R202000018 | Puranpura link road no.5 to Ahmadpur Road | Vidisha | PWD | Road |  |  | 201.75
20 | R202000019 | SH-19 to Lashkarpura app Road | Vidisha | PWD | Road |  |  | 452.89
20 | R202000020 | Badoh - Pathari Road | Vidisha | PWD | Road |  |  | 82.76
20 | R202000021 | Ladkui Chowkito Gularpura Road | Sehore | PWD | Road |  |  | 239.38
20 | R202000022 | Approach road in Pandagaon village | Sehore | PWD | Road |  |  | 140.47
20 | R202000023 | Chhech Chameti to Neelkanth Road | Sehore | PWD | Road |  |  | 219.15
20 | R202000024 | KEWAT COLONY ROAD IN PANDAGAON | Sehore | PWD | Road |  |  | 79.34
20 | R202000025 | LADKUI TO SINGPUR TAPPAR ROAD | Sehore | PWD | Road |  |  | 101.21
20 | R202000026 | MAIN ROAD TO SATDEV ASHRAM | Sehore | PWD | Road |  |  | 77.8
20 | R202000027 | LADKUI ROAD TO HABIB NAGAR ROAD | Sehore | PWD | Road |  |  | 120.94
20 | R202000028 | KARJWANI TO PANHAL KHARBAPURA | Dhar | PWD | Road |  |  | 469.46
20 | R202000029 | DHAMI SIRONJ ROAD | Dhar | PWD | Road |  |  | 232.67
20 | R202000030 | Kawda-Nadipura to Shamshan Ghat Road | Dhar | PWD | Road |  |  | 239.22
20 | R202000031 | Valiyakundiya awaliya Navrangpura to chikhalikheda | Khargone | PWD | Road |  |  | 153.2
20 | R202000032 | Bablai Gadariya Road | Khargone | PWD | Road |  |  | 67.07
20 | R202000033 | Bhilat Dev Nandarwada Koyalajhir Salai Parcha Road | Hoshangabad | PWD | Road |  |  | 799.94
20 | R202000034 | Semri harchand to Pathrai Road | Hoshangabad | PWD | Road |  |  | 241.16
20 | R202000035 | Sohagpur Rewabankhedi Road | Hoshangabad | PWD | Road |  |  | 167.4
20 | R202000036 | Babadiya Bhau to amlada Kalan Bhadugaon Road | Hoshangabad | PWD | Road |  |  | 544.8
20 | R202000037 | Khakarapura Bendripura Bairakhedi Kharar to Pipali | Hoshangabad | PWD | Road |  |  | 341.59
20 | R202000038 | Jeeraveh choukigavan Bhaironpur to Nipaniya Road | Hoshangabad | PWD | Road |  |  | 629.34
20 | R202000039 | NIPANIYA KHATKAD JHAKLAY CHATARKHEDA TO SEONI MALW | Hoshangabad | PWD | Road |  |  | 564.2
20 | R202000040 | MHOW NEEMUCH FOURLANE TO GHATLA APPROACH ROAD | Ratlam | PWD | Road |  |  | 168.14
20 | R202000041 | SAKHA PATNA ROAD | Damoh | PWD | Road |  |  | 164.09
20 | R202000042 | RAILA KANPURA TO BETARIYA ROAD | Singrauli | PWD | Road |  |  | 939.23
20 | R202000043 | GATA AMAYAN ROAD | Bhind | PWD | Road |  |  | 135.27
20 | R202000044 | UMARI SAGARA ROAD | Bhind | PWD | Road |  |  | 368.88
20 | R202000045 | Pacholi to Chhtakapura Whaya Bhaikhakapura Road | Morena | PWD | Road |  |  | 200.03
20 | R202000046 | Sheopur - Khatoli Road | Sheopur | PWD | Road |  |  | 1831.73
20 | R202000047 | Rannod to Pachawali Road | Shivpuri | PWD | Road |  |  | 66.61
20 | R202000048 | Daviya Jagan to Devari Road | Shivpuri | PWD | Road |  |  | 146.69
20 | R202000049 | Strengthening of Guna Ashoknagar to Karod Mahur Ro | Guna | PWD | Road |  |  | 86.7
20 | R202000050 | Sirsti to Saretha Road | Guna | PWD | Road |  |  | 683.68
20 | R202000051 | HATWAHA SATAI ROAD | Chattarpur | PWD | Road |  |  | 500.69
20 | R202000052 | RECONSTRUCTION OF DAMAGED PORTION OF BUXWAHA NANAG | Chattarpur | PWD | Road |  |  | 539.38
20 | R202000053 | NOWGONG ISSANAGAR ROAD TO KALAPANI VIA PARAPATTI R | Chattarpur | PWD | Road |  |  | 256
20 | R202000054 | NAUPAHARIYA GALAN LAHADARA ROAD | Chattarpur | PWD | Road |  |  | 139.77
20 | R202000055 | KUSMELI KABADIYA ROAD | Chhindwara | PWD | Road |  |  | 403.21
20 | R202000056 | Bisapur Sailya Road | Chhindwara | PWD | Road |  |  | 134.38
20 | R202000057 | A.B.Road to Kabulpura via Kamardipur | Shajapur | PWD | Road |  |  | 280.44
20 | R202000058 | Baspur Tawa River to Shantipur | Betul | PWD | Road |  |  | 219.84
20 | R202000059 | Betul District to Harda Road | Betul | PWD | Road |  |  | 191.13
20 | R202000060 | Khapa Khateda to Kajli Road | Betul | PWD | Road |  |  | 308.78
20 | R202000061 | Dhodwara Babai to Dabheri Road | Betul | PWD | Road |  |  | 113.24
20 | R202000062 | Construction of Bhanpura to Chhote Mahadev - Bade | Mandsaur | PWD | Road |  |  | 463.52
20 | R202000063 | Bridge across Ken river on Banda Nareni Road | Chattarpur | PWD | Bridge |  |  | 719.06
20 | R202000064 | Bridge across Bairma River on Hardua Ghat Muari Ro | Damoh | PWD | Bridge |  |  | 716.62
20 | R202000065 | Bridge across Bairma River on Bandakpur Balarpur B | Damoh | PWD | Bridge |  |  | 897.27
20 | R202000066 | Bridge across Sonar river on Hata vinati dolee (at | Damoh | PWD | Bridge |  |  | 759.36
20 | R202000067 | Bridge across Narmada river Anwalighat on Salkanpu | Sehore | PWD | Bridge |  |  | 2497.51
20 | R202000068 | Bridge across Narmada river on Chotichipaner to Ba | Harda | PWD | Bridge |  |  | 2234.93
20 | R202000069 | Bridge across Dudhi river on Ganeshganj Khapasani | Chhindwara | PWD | Bridge |  |  | 541.74
20 | R202000070 | Bridge across river Chhapi on Khilchipur Machalpur | Rajgarh | PWD | Bridge |  |  | 680.03
20 | R202000071 | Bridge across chamla river on Khasrod Khurd Kamanp | Ujjain | PWD | Bridge |  |  | 466.25
20 | R202000072 | Bridge across Son River on Rupoula Jai Singh nagar | Shahdol | PWD | Bridge |  |  | 864.51
20 | R202000073 | Ranipindhari Road to Sagouni Road | Narsinghpur | PWD | Road |  |  | 277.24
20 | R202000074 | Sanchi Udaigiri to Basoda | Vidisha | PWD | Road |  |  | 1654.48
20 | R202000075 | Kanari daskhajuri nateran raipur to phupher khusor | Vidisha | PWD | Road |  |  | 797.25
20 | R202000076 | Kumhar Karadiya Digithan Narayanpura Road | Dhar | PWD | Road |  |  | 112.36
20 | R202000077 | Gadhgarha Bolada Road | Dhar | PWD | Road |  |  | 183.07
20 | R202000078 | Dhar Ring Road To Padaliya | Dhar | PWD | Road |  |  | 111.99
20 | R202000079 | Approach Road Zirniya to Damkheda | Khargone | PWD | Road |  |  | 608.3
20 | R202000080 | Amankhedi Sangvi Chhirwa Road | Khargone | PWD | Road |  |  | 234.56
20 | R202000081 | Hingwa-Varla Road | Barwani | PWD | Road |  |  | 200.48
20 | R202000082 | Parsauna To Pondi VIA Rajbandh Luri Padainiya Road | Singrauli | PWD | Road |  |  | 351.44
20 | R202000083 | A.B Road via Dehri Telegaon Suthaliya Road | Guna | PWD | Road |  |  | 81.8
20 | R202000084 | Badagaon Deotha Road | Chattarpur | PWD | Road |  |  | 142.31
20 | R202000085 | Devpur to Mugalsarai Road ( km 6 to km 16) | Vidisha | PWD | Road |  |  | 772.74
20 | R202000086 | Construction of Bourosa to Malhargarh Road | Vidisha | PWD | Road |  |  | 339.16
20 | R202000087 | Widening upgradation of Morena Bypass | Morena | PWD | Road |  |  | 259.46
20 | R202000088 | Maharajpur- Jhamar Road | Sagar | PWD | Road |  |  | 88.98
20 | R202000089 | Dhasaan GWSS | Chattarpur | MPJNM | RDWS |  |  | 6024.54
20 | R202000090 | Indwar GWSS | Umaria | MPJNM | RDWS |  |  | 4511.95
20 | R202000091 | Singhaura GWSS | Panna | MPJNM | RDWS |  |  | 11230.11
20 | R202000092 | Damhedi GWSS | Anuppur | MPJNM | RDWS |  |  | 4311.91
20 | R202000093 | Karanpura GWSS | Umaria and Katni | MPJNM | RDWS |  |  | 6077.61
20 | R202000094 | Gorihar GWSS | Chattarpur | MPJNM | RDWS |  |  | 7258.14
20 | R202000095 | Narmada Malwa-Gambhir Link Project | Khandwa and Khargone | NVDA | MJP |  |  | 103568.05
20 | R202000096 | Construction of 350 bedded Hospital and GNM Traini | Vidisha | DHFW | Health |  |  | 4399.6
20 | R202000097 | Construction of 450 bedded Hospital buildings at D | Ujjain | DHFW | Health |  |  | 2501.56
20 | R202000098 | Construction of 100 bedded Civil Hospital Sarangpu | Rajgarh | DHFW | Health |  |  | 708.9
20 | R202000099 | Construction of 100 bedded Civil Hospital Aagar at | Shajapur | DHFW | Health |  |  | 719.96
20 | R202000100 | Construction of 100 bedded Civil Hospital Barwaha | Khargone | DHFW | Health |  |  | 732.7
20 | R202000101 | Construction of 6-F, 16-G & 16 H Type Quarters at | Khargone | DHFW | Health |  |  | 362.1
20 | R202000102 | Construction of 100 bedded Civil Hospital Badnagar | Ujjain | DHFW | Health |  |  | 977.5
20 | R202000103 | Construction of 6-F, 16-G & 16 H Type Quarters at | Ujjain | DHFW | Health |  |  | 363.8
20 | R202000104 | Contruction of 6-F, 16-G & 16 H Type Quarters at C | Sehore | DHFW | Health |  |  | 363.8
20 | R202000105 | Upgradation of Kailashnath Katju Civil Hospital w | Bhopal | DHFW | Health |  |  | 2070.6
21 | P2016700000000000008 | Construction of building for I. T. I (conventional) | Agar Malwa | TE&SD | School |  |  | 340
21 | P2016700000000000009 | Construction of building for I. T. I (conventional) | Vidisha | TE&SD | School |  |  | 340
21 | P2016700000000000010 | Construction of building for I. T. I (conventional) | Sehore | TE&SD | School |  |  | 340
21 | P2016700000000000011 | Construction of building for I. T. I (conventional) | Hoshangabad | TE&SD | School |  |  | 340
21 | P2016700000000000012 | Construction of building for I. T. I (conventional) | Hoshangabad | TE&SD | School |  |  | 340
21 | P2016700000000000013 | Construction of building for I. T. I (conventional) | Raisen | TE&SD | School |  |  | 340
21 | P2016700000000000014 | Construction of building for I. T. I (conventional) | Betul | TE&SD | School |  |  | 340
21 | P2016700000000000015 | Construction of building for I. T. I (conventional) | Tikamgarh | TE&SD | School |  |  | 340
21 | P2016700000000000016 | Construction of building for I. T. I (conventional) | Chattarpur | TE&SD | School |  |  | 340
21 | P2016700000000000017 | Construction of building for I. T. I (conventional) | Shivpuri | TE&SD | School |  |  | 340
21 | P2016700000000000018 | Construction of building for I. T. I (conventional) | Bhind | TE&SD | School |  |  | 340
21 | P2016700000000000019 | Construction of building for I. T. I (conventional) | Khargone | TE&SD | School |  |  | 340
21 | P2016700000000000020 | Construction of building for I. T. I (conventional) | Ujjain | TE&SD | School |  |  | 340
21 | P2016700000000000021 | Construction of building for I. T. I (conventional) | Khargone | TE&SD | School |  |  | 340
21 | P2016700000000000022 | Construction of building for I. T. I (conventional) | Dewas | TE&SD | School |  |  | 340
21 | P2016700000000000023 | Construction of building for I. T. I (conventional) | Ujjain | TE&SD | School |  |  | 340
21 | P2016700000000000024 | Construction of building for I. T. I (conventional) | Khandwa | TE&SD | School |  |  | 340
21 | P2016700000000000025 | Construction of building for I. T. I (conventional) | Mandsaur | TE&SD | School |  |  | 340
21 | P2016700000000000026 | Construction of building for I. T. I (conventional) | Damoh | TE&SD | School |  |  | 340
21 | P2016700000000000027 | Construction of building for I. T. I (conventional) | Damoh | TE&SD | School |  |  | 340
21 | P2016700000000000028 | Construction of building for I. T. I (conventional) | Sagar | TE&SD | School |  |  | 340
21 | P2016700000000000029 | Construction of building for I. T. I (conventional) | Jabalpur | TE&SD | School |  |  | 340
21 | P2016700000000000030 | Construction of building for I. T. I (conventional) | Jabalpur | TE&SD | School |  |  | 340
21 | P2016700000000000031 | Construction of building for I. T. I (conventional) | Chhindwara | TE&SD | School |  |  | 340
21 | P2016700000000000032 | Construction of building for I. T. I (conventional) | Narsinghpur | TE&SD | School |  |  | 340
21 | P2016700000000000033 | Construction of building for I. T. I (conventional) | Narsinghpur | TE&SD | School |  |  | 340
21 | P2016700000000000034 | Construction of building for I. T. I (conventional) | Satna | TE&SD | School |  |  | 340
21 | P2016700000000000035 | Construction of building for I. T. I (conventional) | Singrauli | TE&SD | School |  |  | 340
21 | P2016700000000000036 | Construction of building for I. T. I (conventional) | Singrauli | TE&SD | School |  |  | 340
21 | P2016700000000000037 | Construction of building for I. T. I (conventional) | Rewa | TE&SD | School |  |  | 340
21 | P2016700000000000039 | Mohanpura Major Multipurpose Irrigation project | Rajgarh | WRD | MIS |  |  | 44151.73
21 | P2016700000000000062 | Antaraliya Jod to Kajlas Road | Agar (Shajapur) | PWD | Road |  |  | 310.66
21 | P2016700000000000063 | Tanodiya to Madkota Road | Agar (Shajapur) | PWD | Road |  |  | 1963.69
21 | P2016700000000000064 | Birulbazar to Rai Amla Road | Betul | PWD | Road |  |  | 365.19
21 | P2016700000000000065 | Kumbhariya Jod to Mathini Road | Betul | PWD | Road |  |  | 115.58
21 | P2016700000000000066 | Simariyajoshi to Sontalai Road | Betul | PWD | Road |  |  | 135.37
21 | P2016700000000000067 | Upgrdation of road from Bilkhiria to Mahakankali Mandir | Bhopal | PWD | Road |  |  | 484.68
21 | P2016700000000000068 | Chandla Bypass Road | Chattarpur | PWD | Road |  |  | 1268.4
21 | P2016700000000000069 | Chandla Hathoha Ajaygarh Road | Chattarpur | PWD | Road |  |  | 2774.81
21 | P2016700000000000070 | Lavkushnagar Bypass Road | Chattarpur | PWD | Road |  |  | 1373.98
21 | P2016700000000000071 | Pipirya Nankar to Moti Nagar Road | Dewas | PWD | Road |  |  | 125.93
21 | P2016700000000000072 | Udaynagar (Sabalgarh Phata) to Kanad Road | Dewas | PWD | Road |  |  | 852.01
21 | P2016700000000000073 | Sandala Tilgara Road | Dhar | PWD | Road |  |  | 116.82
21 | P2016700000000000074 | Kusumkui Jhaklay Gadariya Harpalpur Hathnapur Road | Hoshangabad | PWD | Road |  |  | 793.45
21 | P2016700000000000075 | Sikandari to Mohammadpur Londiya CC Road | Indore | PWD | Road |  |  | 381.86
21 | P2016700000000000076 | Amgawan - Darouli - Keolari - Marha Road | Jabalpur | PWD | Road |  |  | 241.89
21 | P2016700000000000077 | Karhaiya Kurna Tampal Road | Jabalpur | PWD | Road |  |  | 167.01
21 | P2016700000000000078 | Mohankot to Morjhariya via Semalkundia Road | Jhabua | PWD | Road |  |  | 363.65
21 | P2016700000000000079 | Gobaria Sangwada upto Indore ikshapur Highway | Khandwa | PWD | Road |  |  | 359.17
21 | P2016700000000000080 | Panjaria to Chhegaon Devi | Khandwa | PWD | Road |  |  | 536.4
21 | P2016700000000000081 | Katora to Bakawa Road | Khargone | PWD | Road |  |  | 340.38
21 | P2016700000000000082 | Pipri to Machalgaon Road | Khargone | PWD | Road |  |  | 269.24
21 | P2016700000000000083 | Asawati to Haripura Kurawan Ajaypur Road | Mandsaur | PWD | Road |  |  | 1184.42
21 | P2016700000000000084 | Badwan to Akya (via Damnar) road | Mandsaur | PWD | Road |  |  | 673.47
21 | P2016700000000000085 | Guliyana to Ratikhedi (Via Nipniya Jogikheda) Road | Mandsaur | PWD | Road |  |  | 590.12
21 | P2016700000000000086 | Munderi to Nahargarh Road | Mandsaur | PWD | Road |  |  | 796.5
21 | P2016700000000000087 | Bohani to Rehli Road | Narsinghpur | PWD | Road |  |  | 216.33
21 | P2016700000000000088 | Sukha to Jhiriyamata Road | Narsinghpur | PWD | Road |  |  | 249.77
21 | P2016700000000000089 | Umariya to Piparha Road | Narsinghpur | PWD | Road |  |  | 762.39
21 | P2016700000000000090 | Jhantia Govindpura Road (via Saloda) | Neemuch | PWD | Road |  |  | 217.5
21 | P2016700000000000091 | Moriya To Himmatkhedi Road | Ratlam | PWD | Road |  |  | 155.64
21 | P2016700000000000092 | Atariya to Bhitwa Road | Rewa | PWD | Road |  |  | 182.58
21 | P2016700000000000093 | Padari Chiraiya Nalla to Dol approach road | Rewa | PWD | Road |  |  | 269.7
21 | P2016700000000000094 | Rajha Akauri Mauharia Road | Rewa | PWD | Road |  |  | 300.82
21 | P2016700000000000095 | Upgradation of Mauganj Jail approach Road | Rewa | PWD | Road |  |  | 352.23
21 | P2016700000000000096 | Mokalpur Chouraha to Madkhera Jagir Road | Sagar | PWD | Road |  |  | 277.26
21 | P2016700000000000097 | Rakh Besli Road | Sagar | PWD | Road |  |  | 364.08
21 | P2016700000000000098 | Amarpatan Rampur Road | Satna | PWD | Road |  |  | 2865.6
21 | P2016700000000000099 | Delha Karaiya Karoundi Road | Satna | PWD | Road |  |  | 319.12
21 | P2016700000000000100 | Burhar Jaitpur Road (Bhatiya Jaitpur) | Shahdol | PWD | Road |  |  | 198.45
21 | P2016700000000000101 | Bardiyason Railway gate to Palswad-Lalupura-Hanoti-Jhonkar-Jalalpura (AB Road) Road | Shajapur | PWD | Road |  |  | 1384.5
21 | P2016700000000000102 | Tighra to Gorya Road upto Rajashthan Border | Shivpuri | PWD | Road |  |  | 160.8
21 | P2016700000000000103 | Jharda to Mahidpur Road via Tarot-Kachariya-Katariya Khed-Barkheda Khurd-Sipawara-Sagwali-Tarnod-Karnawad-Kanakhedi | Ujjain | PWD | Road |  |  | 1531.5
21 | P2016700000000000104 | NH-86 Dhaturiya Haveli to Sorai Amachhar Chak- Dholkhedi (SH-19) Ring Road | Vidisha | PWD | Road |  |  | 2156.58
21 | P2016700000000000221 | C/o Sub Br Dhoriya Nalla | Balaghat | PWD | Bridge |  |  | 708.82
21 | P2016700000000000222 | C/o Sub Br Bah River | Bhopal | PWD | Bridge |  |  | 632.23
21 | P2016700000000000223 | C/o Sub Br Bah River in KM 5/4 & Nalla in KM 8/4 | Bhopal | PWD | Bridge |  |  | 729.78
21 | P2016700000000000224 | C/o Sub Br Narmada River | Dindori | PWD | Bridge |  |  | 1266.17
21 | P2016700000000000225 | C/o H.L. Sub Br Gambhir River in 135 M | Indore | PWD | Bridge |  |  | 508.78
21 | P2016700000000000226 | C/o H.L Br Kshipra River in KM 5/2-8 | Ratlam | PWD | Bridge |  |  | 563.27
21 | P2016700000000000227 | C/o H.L. Br Bihar River | Rewa | PWD | Bridge |  |  | 584.34
21 | P2016700000000000228 | C/o Sub Br Bewas River in KM 4/6-8 | Sagar | PWD | Bridge |  |  | 784.27
21 | P2016700000000000229 | C/o Sub Br Satna River in KM 6/10 | Satna | PWD | Bridge |  |  | 551.06
21 | P2016700000000000230 | C/o Sub Br Seep River | Sehore | PWD | Bridge |  |  | 672.28
21 | P2016700000000000231 | C/o H.L. Br Gopad River | Sidhi | PWD | Bridge |  |  | 1070.73
21 | P2016700000000000232 | C/o Sub Br Saprar River | Tikamgarh | PWD | Bridge |  |  | 652.06
21 | P2016700000000000233 | C/o Sub Br Kshipra River | Ujjain | PWD | Bridge |  |  | 523.96
21 | P2016700000000000270 | Narmada Malwa Gambhir Link Project - Phase II | Indore | NVDA | MJP |  |  | 93099
22 | P2016700000000000730 | Anuppur - Jaithari Venkatnagar Road | Anuppur | PWD | Road |  |  | 3579.81
22 | P2016700000000000731 | Katedhara Tirodi Khawasa Road | Balaghat | PWD | Road |  |  | 2454.82
22 | P2016700000000000732 | Phanda Tumda Jharkheda Road | Bhopal | PWD | Road |  |  | 2058.41
22 | P2016700000000000733 | Khajuri Sadak Dhamania Bakani Parwalia Road | Bhopal | PWD | Road |  |  | 1543.82
22 | P2016700000000000734 | Upgradation of Dewas to Vijyaganj Mandi Road | Dewas | PWD | Road |  |  | 3731.38
22 | P2016700000000000735 | Jhukehi Kymore Bhatura Road | Katni | PWD | Road |  |  | 4156.86
22 | P2016700000000000736 | Mandsaur to Sanjit Road | Mandsaur | PWD | Road |  |  | 3653.21
22 | P2016700000000000737 | Ratlam - Dhanasuta Road | Ratlam | PWD | Road |  |  | 3680.64
22 | P2016700000000000738 | Gourjhamar - Kesli - Tada -Searmau Road | Sagar & Raisen | PWD | Road |  |  | 5654.63
22 | P2016700000000000739 | Cheech to Kalwana Road | Sehore | PWD | Road |  |  | 4406.01
22 | P2016700000000000740 | Kahani Palari Road | Seoni | PWD | Road |  |  | 6014.07
22 | P2016700000000000741 | Khawasa to Tirodi Road | Seoni | PWD | Road |  |  | 2412.65
22 | P2016700000000000742 | NH-86 Km 66 to Kuakhedi Gulabganj Andia Road | Vidisha | PWD | Road |  |  | 3613.16
22 | P2016700000000001204 | Bridge across Dokariya Nalla on Kochewahi - Botejhari Road | Balaghat | PWD | Bridge |  |  | 450.27
22 | P2016700000000001205 | Bridge across Tawa River on Sarni-Loniya Road | Betul | PWD | Bridge |  |  | 770.7
22 | P2016700000000001206 | Bridge across Tapti River Jainabad village - Rajghat burhanpur | Burhanpur | PWD | Bridge |  |  | 1045.78
22 | P2016700000000001207 | Bridge across Jam river - Sanwari Mohgalon Road | Chhindwara | PWD | Bridge |  |  | 451.5
22 | P2016700000000001208 | Bridge across Katni river of Ganiyari-Ghinochi Road | Katni | PWD | Bridge |  |  | 437.58
22 | P2016700000000001209 | Bridge across Ghogra River - Bareli-Gaganwada Road | Raisen | PWD | Bridge |  |  | 646.78
22 | P2016700000000001210 | Bridge across Tenduni River - Mangrol-Bagalwada Road | Raisen | PWD | Bridge |  |  | 897.18
22 | P2016700000000001211 | Bridge across Bais River - Dhokhedi Road | Vidisha | PWD | Bridge |  |  | 1121.51

## Social Monitoring (hidden)
ग्रामीण आधारभूत विकास निधि / RURAL INFRASTRUCTURE DEVELOPMENT FUND
चालू परियोजनाओं का विवरण / DETAILS OF ONGOING PROJECTS
राज्य/ STATE : MADHYA PRADESH REGIONAL OFFICE
की स्थिति/ POSITION AS ON : 31 DECEMBER 2016
[19 empty] | 0 | 0
Tranche | PIC | Project | District | Block | Activity | Agency | Rv_Balance_Cost | NB sanction | Disbursement | PSC_Dt | PCR recd date | Actual compl_dt | Expected Date of completion | Status | Date of Field Visit | Monitored by | Potential Envisaged | Potential created | Villages | Marketing centres | Remarks
13 | R132000094 | Kanjai - Sakri - Andua - Singaldip | Jabalpur | Nalkheda | Road | PWD | 95.18 | 86.96 | 86.96 | 2007-10-26 | 2008-08-18 | 2008-03-19 | 2010-12-01 | Completed |  |  | 4.56 | 4.56 | 4 | 2 | Cost escalation due to tender percentages and difference of cost of material. 4.56 Km Road was constructed. The said infrastructure connectesd 4 villages with market yards at Budhagar and Indrana
13 | R132000158 | HLB a/c river Bihar in KM 2/10 | Rewa | Manasa- Neemuch | Bridge | PWD | 96.27 | 96.27 | 93.06 | 2007-11-29 | 2008-10-10 | 2008-01-31 | 2010-12-31 | Completed |  | DDM | 90 | 90 | 18 |  | Slight saving on cost; Time over run by three -and -a half month;It generated 25000 non -recurring man days of employment;Connected 18 villages to marketing centre aqt Rewa. reduced travel distance by 12 Km
13 | R132000049 | Saloda Solid Weir | Neemuch | Tikamgrah | MIS | WRD | 18.08 | 18.08 | 17.39 | 2007-09-17 | 2008-11-06 | 2008-03-30 | 2009-10-31 | Completed |  |  | 71 | 71 |  |  | 1 Ha irrigation potential created . WUA is under process
13 | R132000157 | SB a/c Mandha River bridge in KM 19 | Rewa | Babai Chichli | Bridge | PWD | 93.12 | 75.46 | 70.27 | 2007-11-29 | 2008-12-17 | 2008-07-31 | 2010-12-31 | Completed |  |  | 48 | 48 | 16 | 2 | Bridge was executed with a cost of Rs.69.453 Lakh. Cost saving Time over run. 30000 Mandays created, connected 16 villages to 2 marketing centrea at Jawa and Shankargarh. Reduced travelling distance by 20 Km
13 | R132000052 | Kachhala Solid Weir | Neemuch | Nateran | MIS | WRD | 1.86 | 1.86 | 0.43 | 2007-09-17 | 2009-01-07 | 2008-04-30 | 2009-10-31 | Completed |  | DDM | 75 | 75 |  |  | created 75 Ha potential. WUA not formed
13 | R132000086 | Bandakpur Hindoriya Road | Damoh | Nalkheda | Road | PWD | 80.15 | 80.15 | 80.15 | 2007-10-26 | 2009-06-11 | 2008-03-31 | 2010-12-01 | Completed |  | DDM | 8.4 | 8.4 | 4 | 2 | The project resulted in a 8.4 Km road to connect 4 villages to 2 marketing centres
13 | R132000093 | Kudam - Chiraipani road | Jabalpur | Tarana | Road | PWD | 275 | 220 | 220 | 2007-10-26 | 2009-06-11 | 2008-06-24 | 2010-12-01 | Completed |  |  | 11.35 | 11.36 | 8 | 2 | The project resulted in creation of 11.36 Km of road and connected 8 villages to 2 marketing centres.
13 | R132000030 | Palsoda Solid Weir | Neemuch | Harda | MIS | WRD | 47.49 | 45.12 | 45.12 | 2007-09-17 | 2009-06-18 | 2008-05-28 | 2009-10-31 | Completed | 2010-02-25 | DDM | 61 | 61 |  |  | Potential created 61 Ha.WUA not formed. Completed on time COR due to high tender
13 | R132000104 | Suwasra Guradiya Kalan Road | Mandsaur | Damoh | Road | PWD | 236.53 | 236.53 | 186.09 | 2007-10-26 | 2009-07-27 | 2008-03-10 | 2010-12-01 | Completed |  | DDM | 21 | 21 |  |  | The project resulted in 21 Km of Road.
13 | R132000106 | Runija Angari Road | Mandsaur | Harda | Road | PWD | 138.32 | 138.32 | 68.13 | 2007-10-26 | 2009-07-27 | 2007-10-20 | 2010-12-01 | Completed |  | DDM | 10.6 | 10.4 |  |  | The project resulted in 10.40 Km of road.
13 | R132000130 | Gogapur-Bappiya-Zutawad-Ranayarapee | Ujjain | Kirnapur | Road | PWD | 198.37 | 198.37 | 196.59 | 2007-10-26 | 2009-07-27 | 2008-03-31 | 2010-12-01 | Completed |  |  | 17 | 21.5 |  |  | The project resyulted in 21.50 Km of road
13 | R132000031 | Tulsapura Tank | Ujjain | Pandhana | MIS | WRD | 65.85 | 65.85 | 65.85 | 2007-09-17 | 2009-09-06 | 2012-06-30 | 2009-10-31 | Completed |  |  | 115 | 115 |  |  | WUA to be formed, Potential created - 115 Ha
13 | R132000128 | Digora Mohangarh Road | Tikamgarh | Ashoknagar | Road | PWD | 109.66 | 109.66 | 109.66 | 2007-10-26 | 2009-10-29 | 2008-09-14 | 2010-12-01 | Completed |  |  | 19 | 19.2 |  |  | 19.20 Km road implemented
13 | R132000080 | Balai Karaila Mata Mandir Road | Ashoknagar | Mehidpur | Road | PWD | 172.39 | 172.39 | 172.39 | 2007-10-26 | 2010-05-04 | 2009-03-31 | 2010-12-01 | Completed |  |  | 18.4 | 18.4 | 10 | 2 | The project had cretaed 18 40 Km Road. It comnected 10 villages to 2 marketing centres
13 | R132000054 | Luharra-Kandipur-Chainpura-Hindoriy | Damoh | Chourai | Road | PWD | 83.47 | 83.47 | 83.47 | 2007-10-26 | 2010-06-02 | 2008-04-30 | 2010-12-01 | Completed |  |  | 9.6 | 9.6 | 7 |  | road project of 9.6 km is executed. 7 villages are connected
13 | R132000055 | Hindoriya- Pipariya-Ronda Road | Damoh | Badnawar | Road | PWD | 67.39 | 67.39 | 67.39 | 2007-10-26 | 2010-06-02 | 2009-06-30 | 2010-12-01 | Completed |  | DDM | 10 | 10 | 8 |  | road project of 10 km is executed. 8 villages are connected
13 | R132000063 | Bhyana Karlawad Road | Rajgarh | Shajapur | Road | PWD | 410.52 | 342.08 | 342.08 | 2007-10-26 | 2010-06-02 | 2007-06-18 | 2010-12-01 | Completed |  |  | 13.4 | 13.4 | 5 |  | road project of 13.4 km is executed. 5 villages are connected
13 | R132000065 | Bonda Sendri Umari Kandara Kotari R | Rajgarh | Garoth | Road | PWD | 328.86 | 312.69 | 312.69 | 2007-10-26 | 2010-06-02 | 2009-11-30 | 2010-12-01 | Completed |  |  | 11.6 | 11.6 | 10 |  | road project of 11.6 km is executed. 10 villages are connected
13 | R132000071 | Maili - Tikari - Partapur road | Seoni | Bhanpura | Road | PWD | 121.59 | 121.59 | 121.59 | 2007-10-26 | 2010-06-02 | 2009-07-07 | 2010-12-01 | Completed |  |  | 6.7 | 6.7 | 12 |  | road project of 6.7 km is executed. 12 villages are connected
13 | R132000090 | Pondi - Bhita - Kainthra - Khatolid | Jabalpur | Badnagar | Road | PWD | 126 | 100.8 | 100.8 | 2007-10-26 | 2010-06-02 | 2008-10-30 | 2010-12-01 | Completed |  | DDM | 5.4 | 5.4 | 9 |  | road project of 5.4 km is executed. 9 villages are connected
13 | R132000095 | Ponda - Bachaiya Road | Katni | Tarana | Road | PWD | 255 | 255 | 255 | 2007-10-26 | 2010-06-02 | 2008-11-24 | 2010-12-01 | Completed |  | DDM | 14.7 | 14.7 | 18 |  | road project of 14.7 km is executed. 18 villages are connected
13 | R132000096 | Vijayraghavgarh- Kharkhri-Padkhuri | Katni | Badnagar | Road | PWD | 393.37 | 314.7 | 314.7 | 2007-10-26 | 2010-06-02 | 2009-06-25 | 2010-12-01 | Completed |  |  | 14.85 | 14.85 |  |  | road project of 14.85 km is executed.
13 | R132000097 | Sleemnabad Bahoriband Road | Katni | Jawad | Road | PWD | 204.66 | 182.2 | 182.2 | 2007-10-26 | 2010-06-02 | 2008-08-27 | 2010-12-01 | Completed |  | DDM | 9.33 | 9.33 |  |  | road project of 9.33 km is executed.
13 | R132000098 | Katni-Kailwara- Kharkhari -Hathkuri | Katni | Sanwer | Road | PWD | 249.08 | 249.08 | 249.08 | 2007-10-26 | 2010-06-02 | 2008-01-26 | 2010-12-01 | Completed |  | DDM | 22.2 | 22.2 |  |  | road project of 22.2 km is executed.
13 | R132000100 | Bartari- Pakar - Masandha -Bakal ro | Katni | Jawad | Road | PWD | 211.11 | 211.11 | 211.11 | 2007-10-26 | 2010-06-02 | 2008-04-02 | 2010-12-01 | Completed |  | DDM | 20.4 | 20.4 |  |  | road project of 20.4 km is executed.
13 | R132000112 | Talen - Kudlasa Road | Rajgarh | Khilchipur | Road | PWD | 84.02 | 84.02 | 84.02 | 2007-10-26 | 2010-06-02 | 2008-04-30 | 2010-12-01 | Completed |  |  | 6.6 | 6.6 |  |  | road project of 6.6 km is executed.
13 | R132000057 | Sanai Talwada Siganpur Road | Guna | Depalpur | Road | PWD | 122.4 | 122.4 | 122.4 | 2007-10-26 | 2010-08-18 | 2010-03-15 | 2010-12-01 | Completed |  | DDM | 7 | 7 |  |  | 7 km road is constructed.
13 | R132000089 | Ralamandal Tillorekhurd Tillorebuzu | Indore | Mahidpur | Road | PWD | 176.21 | 176.21 | 176.21 | 2007-10-26 | 2010-08-18 | 2008-01-31 | 2010-12-01 | Completed |  |  | 15.6 | 15.35 | 6 | 4 | 15.35 km road was constructed. 6 villages and 4 marketing centres connected.
15 | R152000030 | Dethali-Bujurg-Panwadi road | Mandsaur | Garoth | Road | PWD | 54.55 | 54.55 | 53.86 | 2009-07-23 | 2010-08-18 | 2009-08-04 | 2012-08-31 | Completed |  |  | 7.6 | 5.6 | 4 | 2 | 5.6 km length road is constructed. 4 villages & 2 Marketing centres connected.
13 | R132000038 | Arjun Baroda Tank | Indore | Udaipura | MIS | WRD | 41.69 | 41.69 | 34.21 | 2007-09-17 | 2010-09-03 | 2008-04-12 | 2009-10-31 | Completed |  |  | 100 | 90 |  |  | 90 Ha irrigation potential is created.
13 | R132000050 | Burhi Barlai Tank | Indore | Ujjain | MIS | WRD | 25.51 | 25.51 | 6.72 | 2007-09-17 | 2010-09-03 | 2008-03-31 | 2009-10-31 | Completed |  | DDM | 70 | 70 |  |  | 70 Ha Irrigation potential is created. WUA formation is under progress.
13 | R132000159 | SB a/c Narain river in KM 6/2 | Sagar | Manasa | Bridge | PWD | 68.48 | 54.78 | 54 | 2007-11-29 | 2010-09-22 | 2009-02-25 | 2010-12-31 | Completed |  | DDM | 17.7 | 17.7 | 50 | 2 | bridge of 17.70 m was constructed, which connected 50 villages to 2 marketing centres
13 | R132000162 | SB a/c Sukha Nalla in KM 15/6 | Sagar | Alote | Bridge | PWD | 146.54 | 117.23 | 117.23 | 2007-11-29 | 2010-09-22 | 2009-03-30 | 2010-12-31 | Completed |  |  | 30 | 30 | 50 | 2 | Bridge of 30 m was constructed, which connected 50 villages to 2 marketing centres
13 | R132000008 | Bhokriya Tank Project | Khandwa | Kevalari | MIS | WRD | 144.86 | 144.86 | 144.86 | 2007-09-17 | 2010-09-28 | 2009-03-31 | 2009-10-31 | Completed |  |  | 198 | 198.2 |  |  | Irrigation Potential of 198.20 Ha is created.WUA is not yet formed.
13 | R132000032 | Salakhedi Barrage | Ujjain | Pandhana | MIS | WRD | 57.31 | 54.73 | 54.73 | 2007-09-17 | 2010-10-19 | 2008-12-31 | 2009-10-31 | Completed |  |  | 75 | 70 |  |  | Irrigation potential of 70 Ha is created.WUA is yet to be formed.
13 | R132000035 | Kalukheda Koyalaghat Barragecumcaus | Ujjain | Pandhana | MIS | WRD | 49.98 | 47.77 | 47.77 | 2007-09-17 | 2010-10-19 | 2008-12-31 | 2009-10-31 | Completed |  |  | 65 | 65 |  |  | Irrigation Potential of 65 Ha is created.WUA is yet to be formed.
13 | R132000041 | Shivghat Barrage | Ujjain | Biaora | MIS | WRD | 44.06 | 41.97 | 41.97 | 2007-09-17 | 2010-10-19 | 2009-03-31 | 2009-10-31 | Completed |  |  | 82 | 82 |  |  | 82 Ha irrigation Potential is created.WUA is yet to be formed.
13 | R132000042 | Mahurikhema Barrage | Ujjain | Piploda | MIS | WRD | 18.09 | 17.29 | 17.29 | 2007-09-17 | 2010-10-19 | 2008-12-31 | 2009-10-31 | Completed |  | DDM | 43 | 43 |  |  | Irrigation potential of 43 Ha is created.WUA is yet to be formed.
13 | R132000044 | Arrolia Dewra Barrage | Ujjain | Rewa | MIS | WRD | 27.98 | 26.85 | 26.85 | 2007-09-17 | 2010-10-19 | 2008-12-31 | 2009-10-31 | Completed |  | DDM | 42 | 42 |  |  | Irrigation potential of 42 Ha is created.WUA is yet to be formed.
13 | R132000047 | Gundarlia Barrage | Ujjain | Garhakota | MIS | WRD | 40.11 | 38.31 | 38.31 | 2007-09-17 | 2010-10-19 | 2009-03-31 | 2009-10-31 | Completed |  |  | 53 | 53 |  |  | Irrigation Potential of 53 Ha is created. WUA is yet to be formed.
13 | R132000048 | Bilkeshwar (Dhaturia) Barrage | Ujjain | Malthone | MIS | WRD | 34.49 | 32.99 | 32.99 | 2007-09-17 | 2010-10-19 | 2008-12-31 | 2009-10-31 | Completed |  |  | 57 | 45 |  |  | Irrigation Potential of 45 Ha is created. WUA is yet to be formed.
13 | R132000051 | Shekhpur Barrage | Ujjain | Nateran | MIS | WRD | 33.47 | 32.01 | 32.01 | 2007-09-17 | 2010-10-19 | 2009-03-31 | 2009-10-31 | Completed |  |  | 50 | 50 |  |  | Irrigation Potential of 50 Ha uis created. WUA is yet to be formegd.
13 | R132000006 | Dongargaon Tank Project | Indore | Ichhawar | MIS | WRD | 179.14 | 171.29 | 171.29 | 2007-09-17 | 2010-11-01 | 2009-03-31 | 2009-10-31 | Completed |  | DDM | 210 | 190 |  |  | The project created irrigation potential 190 Ha. WUA is tet to be formed
13 | R132000056 | Anoo- Bandakpur road | Damoh | Mhow | Road | PWD | 91.83 | 91.83 | 65.76 | 2007-10-26 | 2010-11-29 | 2010-06-15 | 2010-12-01 | Completed |  |  | 5.5 | 5.5 | 9 |  | 5.50 km road contructed. 9 villages are connected
13 | R132000064 | Semali Ramgarh Road | Rajgarh | Chourai | Road | PWD | 264.6 | 254.43 | 254.43 | 2007-10-26 | 2010-11-29 | 2008-03-31 | 2010-12-01 | Completed |  |  | 12.8 | 12.8 | 7 | 2 | 12.80 km road constructed.7 villages 2 marketing centres connected
13 | R132000102 | Mandla Pindrai Nainpur Road | Mandla | Damoh | Road | PWD | 213.63 | 213.63 | 213.63 | 2007-10-26 | 2010-11-29 | 2008-05-10 | 2010-12-01 | Completed |  |  | 24.4 | 24.4 | 20 | 3 | 24.4 km road constructed.20 villages & 3 mktg. centres constructed.
13 | R132000113 | Chhapikheda- Nalkheda Road | Rajgarh | Narsinghgarh | Road | PWD | 105.48 | 98.86 | 98.86 | 2007-10-26 | 2010-11-29 | 2009-06-10 | 2010-12-01 | Completed |  | DDM | 12 | 12 | 10 | 1 | 12 km road constructed.10 villages & 1 mktg. centre connected.
15 | R152000002 | Sarai- Ahirganwa road | Anuppur | Pushprajgarh | Road | PWD | 23.22 | 23.22 | 23.22 | 2009-07-23 | 2010-12-22 | 2009-05-20 | 2012-08-31 | Completed |  |  | 10.2 | 10.2 |  |  | 10.2 km length road was constructed.
15 | R152000018 | Vijayganjmandi-Jawasiya road | Dewas | Dewas | Road | PWD | 60.85 | 60.85 | 59.03 | 2009-07-23 | 2010-12-22 | 2009-08-31 | 2012-08-31 | Completed |  |  | 11.4 | 11.4 |  |  | 11.4 km length road was constructed.
13 | R132000124 | Sunwara - Pindrai - Keolari Road | Seoni | Nateran -Lateri | Road | PWD | 32.18 | 32.18 | 32.18 | 2007-10-26 | 2011-06-15 | 2009-09-27 | 2010-12-01 | Completed |  | DDM | 11.6 | 8 | 6 | 3 | 8.00 km length road is constructed. 6 villages & 3 Marketing centres connected.
15 | R152000024 | Sawal Kheda- Palanpur - Talnagri Ro | Hoshangabad | Hoshangabad | Road | PWD | 82.18 | 82.18 | 82.18 | 2009-07-23 | 2011-06-15 | 2009-06-14 | 2012-08-31 | Completed |  |  | 11 | 10.54 | 4 | 1 | 10.54 km length road is constructed. 4 villages & 1 Marketing centres connected. The road connect major crops area.
13 | R132000147 | HLB a/c Karanj Nalla in KM 6/4 | Khandwa | Katni | Bridge | PWD | 66.65 | 66.65 | 66.65 | 2007-11-29 | 2011-08-03 | 2009-08-31 | 2010-12-31 | Completed |  |  | 60 | 60 | 12 | 1 | Bridge of 60 m was constructed, which connected 12 villages to 1 marketing centre. 18 km of distance has been reduced.
13 | R132000149 | HLB a/c Ghorwa river in KM 2/6 | Khandwa | Pandhana | Bridge | PWD | 63.62 | 56.02 | 55.76 | 2007-11-29 | 2011-08-03 | 2009-07-15 | 2010-12-31 | Completed |  |  | 30 | 30 | 8 | 2 | Bridge of 30 m was constructed, which connected 08 villages to 2 marketing centres.
13 | R132000150 | HLB a/c Sukta river in KM 13/6 | Harda | Nainpur | Bridge | PWD | 170.06 | 145.47 | 145.47 | 2007-11-29 | 2011-08-03 | 2009-06-20 | 2010-12-31 | Completed |  |  | 100 | 100 | 12 | 3 | Bridge of 100 m was constructed, which connected 12 villages to 3 marketing centres. 20 km of distance has been reduced.
13 | R132000058 | Ratatalai - Mangrul road | Harda | Khandwa | Road | PWD | 104.38 | 101.18 | 101.18 | 2007-10-26 | 2011-08-05 | 2009-03-31 | 2010-12-01 | Completed |  |  | 5 | 5 | 2 | 2 | 5.0 km length road is constructed. 2 villages & 2 Marketing centres connected.
13 | R132000061 | Seamou-Pipaliya-Tada Road | Raisen | Goharganj | Road | PWD | 159.82 | 151.68 | 151.68 | 2007-10-26 | 2011-08-05 | 2010-05-30 | 2010-12-01 | Completed |  |  | 8 | 8 | 18 | 3 | 8.0 km length road is constructed. 18 villages & 3 Marketing centres connected.
13 | R132000062 | Chandan Pipaliya Pratapgarh Road | Raisen | Gohaganj | Road | PWD | 260.32 | 260.32 | 260.32 | 2007-10-26 | 2011-08-05 | 2009-06-30 | 2010-12-01 | Completed |  | DDM | 13.8 | 13.8 | 11 | 2 | 13.8 km length road is constructed. 18 villages & 3 Marketing centres connected.
13 | R132000066 | Pidarua to Sagar Malthone Approach | Sagar | Mahidpur | Road | PWD | 125.07 | 123.1 | 106.26 | 2007-10-26 | 2011-08-05 | 2008-12-17 | 2010-12-01 | Completed |  |  | 4.5 | 4.27 | 7 | 2 | 4.27 km length road is constructed. 7 villages & 2 Marketing centres connected.
13 | R132000068 | Bilkishganj to Neebukheda Road | Sehore | Barod | Road | PWD | 215.69 | 184.06 | 184.06 | 2007-10-26 | 2011-08-05 |  | 2010-12-01 | Completed |  | RO Official | 10 | 11.2 | 4 | 1 | 11.2 km length road is constructed. 4 villages & 1 Marketing centre connected.
13 | R132000075 | Kodi Mehgaon Sothiya Vidisha Road | Vidisha | Rehli | Road | PWD | 90.36 | 90.36 | 90.36 | 2007-10-26 | 2011-08-05 | 2008-06-30 | 2010-12-01 | Completed |  | DDM | 14.8 | 14.8 | 5 | 4 | The project resulted in creation of 14.80 Km of road and connected 5 villages to 4 marketing centres.
13 | R132000078 | Ashoknagar Thubon Piplod Road | Ashoknagar | Shajapur | Road | PWD | 256.28 | 246.35 | 246.35 | 2007-10-26 | 2011-08-05 | 2007-11-19 | 2010-12-01 | Completed |  |  | 17.6 | 17.6 | 11 | 2 | 17.6 km length road is constructed. 11 villages & 2 Marketing centres connected. 12 km of distance has been reduced.
13 | R132000079 | Sehrai Achalgarh Piprai Road | Ashoknagar | Neemuch | Road | PWD | 180.26 | 180.26 | 180.26 | 2007-10-26 | 2011-08-05 | 2009-03-02 | 2010-12-01 | Completed |  |  | 15.3 | 15.3 | 17 | 3 | 15.3 km length road is constructed. 17 villages & 3 Marketing centres connected. 3 km of distance has been reduced.
13 | R132000091 | Tilsani- Baghraji Road | Jabalpur | Nalkheda | Road | PWD | 425 | 340 | 340 | 2007-10-26 | 2011-08-05 |  | 2010-12-01 | Completed |  | DDM | 16.4 | 16.4 | 26 | 2 | 16.4 km length road is constructed. 26 villages & 2 Marketing centres connected.
13 | R132000114 | Alot-Talode road | Ratlam | Malthown Banda | Road | PWD | 246.89 | 214.7 | 214.7 | 2007-10-26 | 2011-08-05 | 2008-12-31 | 2010-12-01 | Completed |  | DDM | 12.4 | 12.4 | 10 | 3 | 12.4 km length road is constructed. 10 villages & 3 Marketing centres connected.
13 | R132000115 | Dhodhar - Rola road | Ratlam | Khuai | Road | PWD | 37.33 | 37.33 | 37.33 | 2007-10-26 | 2011-08-05 | 2008-06-30 | 2010-12-01 | Completed |  |  | 5.2 | 5.2 | 10 | 3 | 5.2 km length road is constructed. 10 villages & 3 Marketing centres connected.
13 | R132000122 | Ichhawar- Ramnagar Road | Sehore | Vidisha | Road | PWD | 180.4 | 180.4 | 180.4 | 2007-10-26 | 2011-08-05 |  | 2010-12-01 | Completed |  |  | 13.2 | 12 | 6 | 2 | 12.0 km length road is constructed. 6 villages & 2 Marketing centres connected.
13 | R132000123 | Jamoniya- Semradangi Road | Sehore | Vididha -Raisen | Road | PWD | 124.16 | 124.16 | 124.16 | 2007-10-26 | 2011-08-05 |  | 2010-12-01 | Completed |  |  | 8.6 | 8.6 | 10 | 2 | 8.6 km length road is constructed. 10 villages & 2 Marketing centres connected. 15 km of distance has been reduced.
15 | R152000005 | Bhoura- Sataldehi -chopna road | Betul | Ghoradongri | Road | PWD | 39.48 | 39.48 | 39.48 | 2009-07-23 | 2011-08-05 | 2009-04-30 | 2012-08-31 | Completed |  |  | 15 | 15.83 | 11 | 2 | The project resulted in creation of 15.83 Km of road and connected 11 villages to 2 marketing centres.
15 | R152000011 | Gunji-Nonpani-Biltara road | Damoh | Damoh | Road | PWD | 136.34 | 123.47 | 120.7 | 2009-07-23 | 2011-08-05 | 2010-04-30 | 2012-08-31 | Completed |  |  | 5.5 | 5.5 | 4 | 2 | The project resulted in creation of 5.50 Km of road and connected 4 villages to 2 marketing centres.
15 | R152000013 | Rond-Salaiya-Bagalwara road | Damoh | Patera | Road | PWD | 43.04 | 43.04 | 24.7 | 2009-07-23 | 2011-08-05 | 2010-06-17 | 2012-08-31 | Completed |  |  | 15 | 15 | 14 | 2 | The project resulted in creation of 15.00 Km of road and connected 14 villages to 2 marketing centres. 20 km of distance has been reduced.
15 | R152000015 | Manpura-Lidhora-Karaiya-Badoli Sam | Damoh | Damoh | Road | PWD | 312.87 | 250.3 | 233.72 | 2009-07-23 | 2011-08-05 | 2010-06-10 | 2012-08-31 | Completed |  |  | 9.8 | 9.8 | 5 | 1 | The project resulted in creation of 9.80 Km of road and connected 5 villages to 1 marketing centre. 7 km of distance has been reduced.
15 | R152000016 | Hinota- Murachh-Muhrai road | Damoh | Hatta | Road | PWD | 196.51 | 196.51 | 183.97 | 2009-07-23 | 2011-08-05 | 2010-06-30 | 2012-08-31 | Completed |  |  | 12.9 | 12.9 | 7 | 1 | The project resulted in creation of 12.90 Km of road and connected 7 villages to 1 marketing centre. 6 km of distance has been reduced.
15 | R152000017 | Harrai- Ramadehi--Amwahi-Badipura- | Damoh | Tendukheda | Road | PWD | 133.97 | 133.97 | 132.77 | 2009-07-23 | 2011-08-05 | 2010-06-30 | 2012-08-31 | Completed |  |  | 10.2 | 10 | 4 | 2 | The project resulted in creation of 10.00 Km of road and connected 4 villages to 2 marketing centres.
15 | R152000026 | Dhanpuri-Padwar-Imlai- Khandiya roa | Jabalpur | Jabalpur | Road | PWD | 301.54 | 241.23 | 207.68 | 2009-07-23 | 2011-08-05 | 2009-12-31 | 2012-08-31 | Completed |  |  | 7.1 | 7.1 | 4 | 1 | The project resulted in creation of 7.10 Km of road and connected 4 villages to 1 marketing centre.
15 | R152000035 | Sanchi-Gulgaon-Chiroli-Banskheda Ro | Raisen | Sanchi | Road | PWD | 101.9 | 101.9 | 101.9 | 2009-07-23 | 2011-08-05 | 2010-06-30 | 2012-08-31 | Completed |  |  | 13.2 | 13.2 | 6 | 2 | The project resulted in creation of 13.20 Km of road and connected 6 villages to 2 marketing centre.
15 | R152000049 | Mothi-Gadoli-Baheriya Sahani- Barch | Sagar | Rahatgarh | Road | PWD | 122.01 | 122.01 | 118 | 2009-07-23 | 2011-08-05 | 2010-01-31 | 2012-08-31 | Completed |  |  | 22 | 22 | 12 | 3 | The project resulted in creation of 22.00 Km of road and connected 12 villages to 3 marketing centres.
15 | R152000055 | Salkanpur-Mardanpur road | Sehore | Budhni | Road | PWD | 296.64 | 237.31 | 205.65 | 2009-07-23 | 2011-08-05 |  | 2012-08-31 | Completed |  |  | 11.5 | 11.5 | 19 | 2 | The project resulted in creation of 11.50 Km of road and connected 19 villages to 2 marketing centres.
15 | R152000187 | Raheti to Dhamanda- Chichlaha Appro | Sehore | Budani | Road | PWD | 48.21 | 48.21 | 42.78 | 2010-01-25 | 2011-08-05 |  | 2013-03-03 | Completed |  |  | 5 | 5 | 3 | 1 | The project resulted in creation of 5.00 Km of road and connected 3 villages to 1 marketing centre.
15 | R152000188 | Gondi-Guradiya- Chakaldi Rd | Sehore | Budani | Road | PWD | 50.17 | 50.17 | 50.17 | 2010-01-25 | 2011-08-05 |  | 2013-03-03 | Completed |  |  | 5 | 5 | 4 | 1 | The project resulted in creation of 5.00 Km of road and connected 4 villages to 1 marketing centre.
15 | R152000189 | Banya - Jhajpura Rd | Sehore | Budani | Road | PWD | 70.64 | 70.64 | 70.64 | 2010-01-25 | 2011-08-05 |  | 2013-03-03 | Completed |  |  | 5 | 5 | 3 | 1 | The project resulted in creation of 5.00 Km of road and connected 3 villages to 1 marketing centre.
13 | R132000004 | Asrakund Tank Project | Dhar | Rewa | MIS | WRD | 335.57 | 318.79 | 318.79 | 2007-09-17 | 2011-08-11 | 2010-06-10 | 2009-10-31 | Completed |  | DDM | 390 | 375 |  |  | 375 Ha potential created. WUA is yet to be formed.
13 | R132000116 | Bahera Dabar Piparahi Road | Rewa | Sehore | Road | PWD | 440 | 352 | 302.88 | 2007-10-26 | 2011-08-29 | 2009-12-28 | 2010-12-01 | Completed |  |  | 20 | 20 | 11 | 2 | The project resulted in creation of 20.00 Km of road and connected 11 villages to 2 marketing centres.
13 | R132000118 | Deo Talab Naigarhi Road | Rewa | Barghat | Road | PWD | 305.34 | 244.27 | 244.27 | 2007-10-26 | 2011-08-29 | 2009-03-30 | 2010-12-01 | Completed |  |  | 16.2 | 16.2 | 10 | 2 | The project resulted in creation of 16.20 Km of road and connected 10 villages to 2 marketing centres.
13 | R132000119 | Naigarhi Garh road | Rewa | Seoni | Road | PWD | 283.9 | 227.12 | 227.12 | 2007-10-26 | 2011-08-29 | 2010-12-30 | 2010-12-01 | Completed |  |  | 13.6 | 13.6 | 5 |  | The project resulted in creation of 13.60 Km of road and connected 11 villages to 2 marketing centres.
13 | R132000120 | Deotalab- Garh Road | Rewa | Shajapur -M.Barodiya | Road | PWD | 218.24 | 218.02 | 218.02 | 2007-10-26 | 2011-08-29 | 2009-04-30 | 2010-12-01 | Completed |  |  | 14.4 | 14.4 | 10 | 1 | The project resulted in creation of 14.40 Km of road and connected 10 villages to 1 marketing centre.
13 | R132000125 | Gohparu - Rasmohni- Burhar road | Shahdol | Sironj | Road | PWD | 854.67 | 696.92 | 524.59 | 2007-10-26 | 2011-08-29 | 2011-03-31 | 2010-12-01 | Completed |  | DDM | 65 | 68 | 30 | 5 | The project resulted in creation of 68.00 Km of road and connected 30 villages to 5 marketing centres.
13 | R132000143 | SB a/c Bairma river | Damoh | Sihora | Bridge | PWD | 334.42 | 268.2 | 268.2 | 2007-11-29 | 2011-08-29 | 2010-06-14 | 2010-12-31 | Completed |  | OIC | 190 | 180 | 20 | 2 | Bridge of 180 m was constructed, which connected 20 villages to 2 marketing centres. 35 km of distance has been reduced.
15 | R152000033 | Maheba-Kot road | Panna | Gonour | Road | PWD | 86.57 | 86.57 | 86.57 | 2009-07-23 | 2011-08-29 | 2011-03-31 | 2012-08-31 | Completed |  |  | 10.5 | 10.5 | 15 | 2 | The project resulted in creation of 10.50 Km of road and connected 15 villages to 2 marketing centres.
15 | R152000059 | Burhar-Hardi road | Shahdol | Sohagpur | Road | PWD | 221.41 | 221.41 | 209.76 | 2009-07-23 | 2011-08-29 | 2011-03-05 | 2012-08-31 | Completed |  |  | 10.5 | 10.5 | 20 | 3 | The project resulted in creation of 10.50 Km of road and connected 20 villages to 3 marketing centres.
15 | R152000060 | Kanchanpur-Udhiya-Singhpur road | Shahdol | Sohagpur | Road | PWD | 112.2 | 112.2 | 112.2 | 2009-07-23 | 2011-08-29 | 2011-03-26 | 2012-08-31 | Completed |  |  | 10.3 | 8.15 | 7 | 1 | The project resulted in creation of 8.15 Km of road and connected 7 villages to 1 marketing centre. 10.00 km of distance has been reduced
15 | R152000067 | Alampura-Banne Buzurg road | Tikamgarh | Palera | Road | PWD | 110.54 | 110.54 | 110.54 | 2009-07-23 | 2011-08-29 | 2010-03-30 | 2012-08-31 | Completed |  |  | 7.4 | 7.4 | 5 | 3 | The project resulted in creation of 7.40 Km of road and connected 5 villages to 3 marketing centres.
15 | R152000069 | Jawasiyapanth - Narayana road | Ujjain | Mahidpur | Road | PWD | 298.71 | 298.71 | 169.21 | 2009-07-23 | 2011-08-29 | 2010-06-30 | 2012-08-31 | Completed |  |  | 16 | 11 | 7 | 1 | The project resulted in creation of 11.00 Km of road and connected 7 villages to 1 marketing centre.
13 | R132000007 | Khadi Tank Project | Indore | Sehore | MIS | WRD | 296.66 | 283.3 | 283.3 | 2007-09-17 | 2011-09-16 | 2011-03-31 | 2009-10-31 | Completed |  | DDM | 330 | 308 |  |  | 308 Ha potential created. WUA is yet to be formed.
13 | R132000019 | Beejanagaree | Shajapur | Barwani | MIS | WRD | 140.16 | 133.15 | 133.15 | 2007-09-17 | 2011-09-16 | 2010-07-31 | 2009-10-31 | Completed |  |  | 200 | 200 |  |  | 200 Ha potential created. WUA is yet to be formed.
13 | R132000029 | Lahori Tank | Shajapur | Senwada | MIS | WRD | 91.51 | 86.93 | 86.93 | 2007-09-17 | 2011-09-16 | 2010-03-31 | 2009-10-31 | Completed |  | DDM | 90 | 88.46 |  |  | 88.46 Ha potential created. WUA is yet to be formed.
13 | R132000033 | Dongargaon Pickup Weir | Shajapur | Pandhana | MIS | WRD | 70.68 | 67.15 | 67.15 | 2007-09-17 | 2011-09-16 | 2010-07-31 | 2009-10-31 | Completed |  |  | 80 | 90 |  |  | 90 Ha potential created. WUA is yet to be formed.
13 | R132000037 | Bagula Mukhi Pickup Weir | Shajapur | Ajaygarh | MIS | WRD | 58.45 | 55.53 | 55.53 | 2007-09-17 | 2011-09-16 | 2009-03-31 | 2009-10-31 | Completed |  |  | 70 | 70 |  |  | 70 Ha potential created. WUA is yet to be formed.
13 | R132000039 | Dehri Gurjar Pickup Weir | Shajapur | Narsinghgarh | MIS | WRD | 53.81 | 51.12 | 51.12 | 2007-09-17 | 2011-09-16 | 2009-03-31 | 2009-10-31 | Completed |  |  | 75 | 75 |  |  | 75 Ha potential created. WUA is yet to be formed.
13 | R132000043 | Dharola Pick-up Weir | Shajapur | Jawa | MIS | WRD | 49.13 | 46.67 | 46.67 | 2007-09-17 | 2011-09-16 | 2010-03-31 | 2009-10-31 | Completed |  |  | 85 | 85 |  |  | 85 Ha potential created. WUA is yet to be formed.
13 | R132000046 | Bhilkhedi Weir | Shajapur | Banda | MIS | WRD | 46.94 | 44.59 | 44.59 | 2007-09-17 | 2011-09-16 | 2009-03-31 | 2009-10-31 | Completed |  | DDM | 80 | 80 |  |  | 80 Ha potential created. WUA is yet to be formed.
13 | R132000141 | HLB a/c Gouraiya river in KM 79/10 | Damoh | Kundam | Bridge | PWD | 154.19 | 124.72 | 124.72 | 2007-11-29 | 2011-09-19 | 2011-02-14 | 2010-12-31 | Completed |  |  | 115 | 115 | 20 | 2 | Bridge of 115 m was constructed, which connected 20 villages to 2 marketing centres.
13 | R132000163 | HLB a/c Jamni river in KM 6/4 | Tikamgarh | Jaora | Bridge | PWD | 169.66 | 136.36 | 136.36 | 2007-11-29 | 2011-10-19 | 2011-03-18 | 2010-12-31 | Completed |  |  | 126 | 126 | 20 | 2 | Bridge of 126 m was constructed, which connected 20 villages to 2 marketing centres. 20 km of distance has been reduced.
13 | R132000076 | Mudra-Murraiya to Barkheda Jagir ro | Vidisha | Dheemarkheda | Road | PWD | 365.49 | 365.49 | 365.49 | 2007-10-26 | 2011-11-09 | 2009-02-05 | 2010-12-01 | Completed |  | DDM | 25.6 | 25.6 | 9 | 2 | The project resulted in creation of 25.60 Km of road and connected 9 villages to 2 marketing centres.
13 | R132000077 | Madhura Bagal Harukhedi to Basoda S | Vidisha | Dheemarkheda | Road | PWD | 91.19 | 91.19 | 91.19 | 2007-10-26 | 2011-11-09 | 2008-05-20 | 2010-12-01 | Completed |  |  | 6.5 | 6.5 | 6 | 1 | The project resulted in creation of 6.50 Km of road and connected 6 villages to 1 marketing centre.
13 | R132000092 | Sihora - Gourkha - Nandghat Road | Jabalpur | Ghattia | Road | PWD | 329.31 | 329.31 | 329.31 | 2007-10-26 | 2011-11-09 | 2010-11-30 | 2010-12-01 | Completed |  | DDM | 15.6 | 15.6 | 12 | 3 | The project resulted in creation of 15.60 Km of road and connected 12 villages to 3 marketing centres.
13 | R132000107 | Chichli Link road | Narsinghpur | Mhow | Road | PWD | 110.91 | 88.73 | 88.73 | 2007-10-26 | 2011-11-09 | 2008-08-25 | 2010-12-01 | Completed |  | DDM | 3.4 | 3.4 | 2 | 2 | The project resulted in creation of 3.40 Km of road and connected 2 villages to 2 marketing centres.
13 | R132000108 | Narsinghpur Devkachachar Road | Narsinghpur | Manasa- Jawad | Road | PWD | 290.98 | 232.78 | 232.78 | 2007-10-26 | 2011-11-09 | 2009-03-31 | 2010-12-01 | Completed |  |  | 9.6 | 9.6 | 8 | 3 | The project resulted in creation of 9.60 Km of road and connected 8 villages to 3 marketing centres.
13 | R132000109 | Podar - Salichouka- Barha Road | Narsinghpur | Silwani | Road | PWD | 364 | 291.2 | 291.2 | 2007-10-26 | 2011-11-09 | 2010-11-30 | 2010-12-01 | Completed |  |  | 14.6 | 14.6 | 5 | 2 | The project resulted in creation of 14.60 Km of road and connected 5 villages to 2 marketing centres.
15 | R152000019 | Nagda-Kadod-Chirakhan road | Dhar | Badanwar | Road | PWD | 591.39 | 527.79 | 527.7 | 2009-07-23 | 2011-11-09 | 2011-03-20 | 2012-08-31 | Completed |  |  | 14.1 | 19.4 | 8 | 2 | The project resulted in creation of 19.40 Km of road and connected 8 villages having population of about 20678 to 2 marketing centres.
15 | R152000079 | Santoshpur-Bhouriya road | Vidisha | Sironj | Road | PWD | 41.52 | 41.52 | 41.52 | 2009-07-23 | 2011-11-09 | 2010-10-17 | 2012-08-31 | Completed |  |  | 12 | 12 | 15 | 4 | The project resulted in creation of 12.00 Km of road and connected 15 villages to 4 marketing centres.
15 | R152000186 | Upgradation of Satna Dharkundi Rd | Satna | Rampur | Road | PWD | 231.4 | 212.11 | 186.89 | 2010-01-25 | 2011-11-09 | 2011-04-30 | 2013-03-03 | Completed |  |  | 17 | 17 | 10 | 1 | The project resulted in creation of 17.00 Km of road and connected 10 villages to 1 marketing centre.
13 | R132000016 | Panwadi Tank Project | Mandsaur | Zarda | MIS | WRD | 161.02 | 155.34 | 155.34 | 2007-09-17 | 2012-01-18 | 2011-06-30 | 2009-10-31 | Completed |  |  | 180 | 180 |  |  | WUA not formed. potential created 180 Ha
13 | R132000022 | Jaalkhedi Tank | Mandsaur | Gohad | MIS | WRD | 127.28 | 122.3 | 122.3 | 2007-09-17 | 2012-01-18 | 2011-06-30 | 2009-10-31 | Completed |  |  | 150 | 134.4 |  |  | WUA not formed. potential created 134.40
13 | R132000036 | Manasa Pickup Weir | Shajapur | Sitamau | MIS | WRD | 58.8 | 55.86 | 55.86 | 2007-09-17 | 2012-01-18 | 2010-06-30 | 2009-10-31 | Completed |  | DDM | 80 | 88 |  |  | WUA not formed. potential created 88 ha
13 | R132000152 | SB a/c Ken river in KM 15/2 | Panna | Sitamau | Bridge | PWD | 1167.25 | 936.11 | 936.11 | 2007-11-29 | 2012-02-23 | 2011-03-31 | 2010-12-31 | Completed |  |  | 378 | 378 |  |  | Ajaygarh to Chendla Bridge completed (378 mtr)
13 | R132000015 | Jamuniya Tank | Chhindwara | Mahidpur | MIS | WRD | 160.91 | 152.86 | 126.59 | 2007-09-17 | 2012-03-18 | 2011-07-31 | 2009-10-31 | Completed |  |  | 270 | 97 |  |  | WUA to be formed, Potential created- Kharif 81 Ha & Rabi- 97 Ha
13 | R132000017 | Kharela Tank | Ujjain | Karkeli | MIS | WRD | 160.56 | 154.38 | 154.38 | 2007-09-17 | 2012-08-03 | 2012-03-31 | 2009-10-31 | Completed |  |  | 234 | 170 |  |  | WUA - NA. potential created 170 Ha
13 | R132000045 | Malhargarh Barrage | Ujjain | Khurai | MIS | WRD | 26.77 | 25.54 | 25.54 | 2007-09-17 | 2012-08-03 | 2012-03-31 | 2009-10-31 | Completed |  | DDM | 45 | 45 |  |  | WUA -not formed. potential created 45 Ha
15 | R152000153 | C/o Sub Br Kunda Ri in Khargone c | Khargone | Khargone | Bridge | PWD | 398.08 | 318.46 | 299.07 | 2009-12-24 | 2012-08-07 | 2012-03-25 | 2013-01-31 | Completed |  |  | 225 | 225 | 28 | 1 | Bridge completed
16 | R162000015 | brg Abna River in Km 6/6 of Khand | Khandwa | Khandwa | Bridge | PWD | 235.77 | 196.97 | 160.73 | 2010-08-27 | 2012-08-07 | 2012-01-15 | 2013-10-01 | Completed |  |  | 5.6 | 5.6 | 16 | 1 | Khandwa to Abna river bridge completed (5.60km)
16 | R162000016 | brg Veda River in Km 7/10 of Sail | Khargone | Kasrawad | Bridge | PWD | 510.03 | 459.44 | 441.44 | 2010-08-27 | 2012-08-07 | 2011-12-07 | 2013-10-01 | Completed |  |  | 6 | 6 | 19 | 1 | Sailani to to Veda bridge completed (6 km)
13 | R132000161 | HLB a/c Kaith river in KM 8/4 | Sagar | Khilchipur | Bridge | PWD | 169.1 | 135.28 | 135.28 | 2007-11-29 | 2012-09-03 | 2011-07-15 | 2010-12-31 | Completed |  | DDM | 120 | 120 |  |  | Garhakota to Rehli bridge completed.
13 | R132000013 | Kalajhora Tank Project | Raisen | Jatara | MIS | WRD | 270.57 | 270.57 | 270.57 | 2007-09-17 | 2012-11-07 | 2011-03-31 | 2009-10-31 | Completed |  |  | 405 | 405 |  |  | Formation of WUA in progress
13 | R132000027 | Karonda Tank | Katni | Tendukheda | MIS | WRD | 93.08 | 92.4 | 92.4 | 2007-09-17 | 2012-11-07 | 2010-06-30 | 2009-10-31 | Completed |  |  | 200 | 125 |  |  | WUA not formed, Potential created-Rabi 25 Ha & Kharif 100 Ha
13 | R132000028 | Simraha Tank | Katni | Patera | MIS | WRD | 88.09 | 88.09 | 88.09 | 2007-09-17 | 2012-11-07 | 2010-06-30 | 2009-10-31 | Completed |  |  | 121 | 133 |  |  | WUA to be formed, Potential created-Rabi 40 Ha & Kharif 93 Ha
13 | R132000034 | Bijaura Tank | Katni | Pandhana | MIS | WRD | 60.96 | 61.91 | 61.91 | 2007-09-17 | 2012-11-07 | 2008-06-30 | 2009-10-31 | Completed |  |  | 67 | 67 |  |  | WUA to be formed, Potential created-Rabi 10 Ha & Kharif 57 Ha
15 | R152000144 | C/o H.L. Br Chandan Ri in KM 1/8 | Balaghat | Waraseoni | Bridge | PWD | 330.51 | 330.51 | 285.78 | 2009-12-24 | 2013-01-23 | 2011-04-30 | 2013-01-31 | Completed |  |  | 286 |  |  |  | Rs.44.73 - saving due to change in foundation levels, less quantities in approach road as per site condition
15 | R152000145 | C/o H.L.Br Son Ri in KM 7/4 on Bh | Balaghat | Langi | Bridge | PWD | 334.76 | 334.76 | 270.33 | 2009-12-24 | 2013-01-23 | 2011-06-28 | 2013-01-31 | Completed |  |  | 210 |  |  |  | Rs.64.43 - saving due to change in foundation levels, less quantities in approach road as per site condition
13 | R132000009 | Shrinagar Tank Project | Mandsaur | Gohparu Sohagpur Burhar | MIS | WRD | 163.8 | 158.93 | 139.12 | 2007-09-17 | 2013-02-07 | 2012-05-31 | 2009-10-31 | Completed |  |  | 200 | 186.16 |  |  | WUA not formed, Potential created-186.16 Ha
13 | R132000020 | Kunwarpura Tank | Mandsaur | Gohad | MIS | WRD | 124.89 | 120.09 | 120.09 | 2007-09-17 | 2013-02-07 | 2012-12-31 | 2009-10-31 | Completed |  |  | 160 | 143 |  |  | WUA not formed, Potential created - 143 Ha
13 | R132000010 | Hadkho Tank Project | Mandsaur | Agar | MIS | WRD | 207.45 | 201.03 | 200.98 | 2007-09-17 | 2013-05-15 | 2012-12-31 | 2009-10-31 | Completed |  |  | 241 | 268 |  |  | Due to higher tender rates and charge of dam alignment actual exps increased .Potential created-268 Ha. WUA not formed
13 | R132000101 | Dharampuri-Garangaon-Bhagwanpur roa | Khandwa | Many | Road | PWD | 208.27 | 208.27 | 208.27 | 2007-10-26 | 2013-12-09 | 2009-06-29 | 2010-12-01 | Completed |  |  | 14.5 | 14.5
15 | R152000047 | Karrapur-Tinsua- Padwar - Nimon- Ma | Sagar | Sagar | Road | PWD | 390.27 | 390.27 | 390.27 | 2009-07-23 | 2013-12-09 | 2010-05-30 | 2012-08-31 | Completed |  |  | 20
15 | R152000176 | Parwariya-Sonthiya Rd | Raisen | Sanchi | Road | PWD | 131.58 | 131.58 | 131.58 | 2010-01-25 | 2013-12-09 | 2011-11-29 | 2013-03-03 | Completed |  |  | 10 | 10
18 | R182000001 | Thikariya Medium tank Project | Neemuch | Neemuch | MIP | WRD | 7298.45 | 6933.53 | 6933.53 | 2012-09-30 | 2016-03-25 | 2014-06-23 | 2015-10-31 | Completed |  |  | 2050 | 2500
15 | R152000065 | Baldeogarh-Nowgong road | Tikamgarh | Baldevgarh | Road | PWD | 186.66 | 186.66 | 182.61 | 2009-07-23 | 2016-10-18 | 2012-06-25 | 2012-08-31 | Completed |  |  | 13.8 | 13.8 | 3 | 3
15 | R152000066 | Lidhora-Gotet-Chanderaroad | Tikamgarh | Jatara | Road | PWD | 96.64 | 96.64 | 96.64 | 2009-07-23 | 2016-10-18 | 2010-11-19 | 2012-08-31 | Completed |  |  | 13.4 | 13.4 | 5 | 3
15 | R152000068 | Chandra-Mendwara-Jewar road | Tikamgarh | Palera | Road | PWD | 197.57 | 197.57 | 197.57 | 2009-07-23 | 2016-10-18 | 2010-02-25 | 2012-08-31 | Completed |  |  | 21 | 21 | 6 | 2
15 | R152000072 | Mahidpur-Dhablasiya-Ranayrapeer roa | Ujjain | Mahidpur | Road | PWD | 342.5 | 342.5 | 131.71 | 2009-07-23 | 2016-10-18 | 2010-11-30 | 2012-08-31 | Completed |  |  | 15.7 | 12 | 7 | 1
15 | R152000074 | Sagwali-Zutawad Road | Ujjain | Mahidpur | Road | PWD | 101.34 | 101.34 | 37.65 | 2009-07-23 | 2016-10-18 | 2011-03-31 | 2012-08-31 | Completed |  |  | 7.9 | 7.33 | 4 | 1
16 | R162000048 | Construction of Kalagaon selgaon Ba | Betul | Betul | Road | PWD | 310.74 | 248.59 | 214.692 | 2010-08-27 | 2016-10-18 | 2012-12-24 | 2013-10-01 | Completed |  |  | 8.45 | 8.45 | 5 | 1
16 | R162000049 | Bhimpur to Khamapur Gurna | Betul | Chicholi | Road | PWD | 347.33 | 277.86 | 277.858 | 2010-08-27 | 2016-10-18 | 2014-04-30 | 2013-10-01 | Completed |  |  | 5.5 | 5.5 | 3 | 2
16 | R162000074 | Manawar mandi Wayal Jotpur Road | Dhar | Manawar | Road | PWD | 269.94 | 215.95 | 212.09 | 2010-08-27 | 2016-10-18 | 2014-03-27 | 2013-10-01 | Completed |  |  | 8.5 | 8.5 | 3 | 1
16 | R162000123 | Construction of Kalisindh Kulmankhe | Shajapur | Shajapur | Road | PWD | 225.82 | 225.82 | 225.82 | 2010-08-27 | 2016-10-18 | 2012-08-30 | 2013-10-01 | Completed |  |  | 8.8 | 8.8 | 4 | 4
16 | R162000491 | Jaithari to Jhaital Road | Anuppur | Juithari | Road | PWD | 154.01 | 123.21 | 103.38 | 2011-01-31 | 2016-10-18 | 2015-09-29 | 2016-01-31 | Completed |  |  | 3.8 | 3.8 | 2 | 1
16 | R162000492 | Jaithari Kotma Road to Village Pondi Chondi | Anuppur | Anuppur | Road | PWD | 124.63 | 99.7 | 97.72 | 2011-01-31 | 2016-10-18 | 2013-10-15 | 2016-01-31 | Completed |  |  | 3.8 | 3.8 | 2 | 2
16 | R162000494 | Godaru river to Dhumma Deogawan Jogi Tola road | Anuppur | Anuppur | Road | PWD | 131.35 | 105.08 | 105.08 | 2011-01-31 | 2016-10-18 | 2013-04-20 | 2016-01-31 | Completed |  |  | 3.4 | 3.4 | 4 | 7
16 | R162000577 | Luhagar-Nabalpur-Sahua-Hardi Road | Sagar | Rehli | Road | PWD | 127.41 | 127.41 | 127.41 | 2011-01-31 | 2016-10-18 | 2012-05-28 | 2016-01-31 | Completed |  |  | 7.1 | 7.1 | 6 | 1
16 | R162000590 | Gokalpur Shukla ozhatola Road | Seoni | Barght | Road | PWD | 319.2 | 255.36 | 255.36 | 2011-01-31 | 2016-10-18 | 2013-06-28 | 2016-01-31 | Completed |  |  | 9.1 | 9.1 | 0 | 0
16 | R162000591 | Lohara Bamni Road | Seoni | Barghat | Road | PWD | 77.73 | 62.18 | 52.94 | 2011-01-31 | 2016-10-18 | 2012-09-30 | 2016-01-31 | Completed |  |  | 2.425 | 2.425 | 5 | 1
16 | R162000593 | Ishwarpur Pachpedi gungli Road | Seoni | Ghansore | Road | PWD | 277.49 | 221.99 | 171.5 | 2011-01-31 | 2016-10-18 | 2012-03-16 | 2016-01-31 | Completed |  |  | 9.125 | 9.125 | 7 | 2
16 | R162000594 | Khoot Poniya Road | Seoni | Barght | Road | PWD | 186.32 | 149.06 | 94.8 | 2011-01-31 | 2016-10-18 | 2013-04-20 | 2016-01-31 | Completed |  |  | 4.1 | 4.1 | 3 | 2
16 | R162000601 | Jatara Chandera Road | Tikamgarh | Jatara | Road | PWD | 123.2 | 98.56 | 98.17 | 2011-01-31 | 2016-10-18 | 2011-12-19 | 2016-01-31 | Completed |  |  | 2.2 | 2.2 | 1 | 1
17 | R172000021 | Khadakiphata To Chirwali Road | Dhar | Manawar | Road | PWD | 164.16 | 131.33 | 92.53 | 2012-01-20 | 2016-10-18 | 2014-01-30 | 2015-03-03 | Completed |  |  | 4.4 | 4.4 | 8 | 4
17 | R172000026 | Goraiyaghat To Jamtara Narbadaghat Road | Jabalpur | Barela | Road | PWD | 145.12 | 116.1 | 91.6 | 2012-01-20 | 2016-10-18 | 2013-03-16 | 2015-03-03 | Completed |  |  | 2.8 | 2.8 | 3 | 1
17 | R172000081 | Gopalpur To Chandela Road | Shahdol | Gohparu | Road | PWD | 160.76 | 128.61 | 128.61 | 2012-01-20 | 2016-10-18 | 2013-09-30 | 2015-03-03 | Completed |  |  | 4.6 | 4.6 | 5 | 2
18 | R182000021 | Khandwa hoshangabad s.h. No. 15 to bhawaliya khokl | Khandwa | Khandwa | Road | PWD | 223.01 | 178.41 | 140.11 | 2012-11-08 | 2016-10-18 | 2013-09-30 | 2015-12-31 | Completed |  |  | 5.5 | 5.09 | 4 | 2
18 | R182000047 | Bhainswahi chandrapura ballaimafi road | Sagar | Sagar | Road | PWD | 295.33 | 236.26 | 236.26 | 2012-11-08 | 2016-10-18 | 2014-05-20 | 2015-12-31 | Completed |  |  | 10 | 9.1 | 5 | 2
18 | R182000048 | Ghatampur khand pipariya dhudhoniya road | Sagar | Sagar | Road | PWD | 291.49 | 233.19 | 233.19 | 2012-11-08 | 2016-10-18 | 2013-10-30 | 2015-12-31 | Completed |  |  | 9 | 8.55 | 6 | 2
18 | R182000050 | Barapani aapchand gonchi road | Sagar | Sagar | Road | PWD | 299.93 | 239.94 | 153.4 | 2012-11-08 | 2016-10-18 | 2014-05-25 | 2015-12-31 | Completed |  |  | 7.5 | 6.1 | 4 | 2
18 | R182000051 | Daana hilgun road to khadaraban pipariya vaid road | Sagar | Sagar | Road | PWD | 474.07 | 379.26 | 327.51 | 2012-11-08 | 2016-10-18 | 2014-04-10 | 2015-12-31 | Completed |  |  | 10.5 | 10.1 | 5 | 2
18 | R182000052 | Saloya khadaraban richawar saikheda road | Sagar | Sagar | Road | PWD | 479.22 | 383.38 | 379.64 | 2012-11-08 | 2016-10-18 | 2014-05-10 | 2015-12-31 | Completed |  |  | 12 | 11.13 | 6 | 2
18 | R182000068 | Ghansaur to salahpani road | Seoni | Seoni | Road | PWD | 603.94 | 483.15 | 365.74 | 2012-11-08 | 2016-10-18 | 2015-04-28 | 2015-12-31 | Completed |  |  | 11 | 11 | 5 | 1
19 | R192000180 | Ganeshganj-Sojnawar Tarha Road | Sagar | Rehli | Road | PWD | 505 | 404 | 379.56 | 2014-03-24 | 2016-10-18 | 2015-12-29 | 2017-05-01 | Completed |  |  | 9.5 | 8.3 | 5 | 3
19 | R192000186 | Widening and upgradation of rehli road | Sagar | Rehli | Road | PWD | 417.4 | 333.92 | 333.92 | 2014-03-24 | 2016-10-18 | 2014-07-10 | 2017-05-01 | Completed |  |  | 3.5 | 3.7 | 2 | 2
19 | R192000188 | Sakhi to Deovran Road | Shahdol | Beohari | Road | PWD | 229.38 | 229.38 | 229.38 | 2014-03-24 | 2016-10-18 | 2014-07-15 | 2017-05-01 | Completed |  |  | 6.7 | 6.7 | 4 | 3
19 | R192000190 | Papond to vijaysota road | Shahdol | Beohari | Road | PWD | 261.19 | 261.19 | 261.19 | 2014-03-24 | 2016-10-18 | 2013-11-30 | 2017-05-01 | Completed |  |  | 5 | 5 | 3 | 1
15 | R152000170 | Bhagour- Hatyadeli -Petlawad Rd | Jhabua | Meghanagar | Road | PWD | 515.53 | 515.53 | 370.21 | 2010-01-25 | 2016-11-16 | 2010-06-05 | 2013-03-03 | Completed |  |  | 24.52 | 24.52 | 5 | 2
17 | R172000048 | Upgradation Amgaon Baghawar Road | Annupur | MORENA | Road | PWD | 160.82 | 128.66 | 120.16 | 2012-01-20 | 2016-11-16 | 2012-10-20 | 2015-03-03 | Completed |  |  | 3.5 | 3.5 | 5 | 2
17 | R172000050 | Upgradation Of Garha To Ajansara Marka Bohani Road | Narsinghpur | Chawarpatha | Road | PWD | 575.42 | 460.34 | 460.342 | 2012-01-20 | 2016-11-16 | 2016-03-10 | 2015-03-03 | Completed |  |  | 13.8 | 10.24 | 5 | 2
17 | R172000051 | Upgradation Of Khadchari Mehguan Sujwara Bohani Me | Narsinghpur | Chawarpatha | Road | PWD | 457.77 | 366.22 | 298.97 | 2012-01-20 | 2016-11-16 | 2013-11-20 | 2015-03-03 | Completed |  |  | 11.82 | 10.82 | 7 | 1
18 | R182000024 | Lakha to rahlee road | Narsinghpur | Narsingpur | Road | PWD | 127.62 | 102.1 | 96.64 | 2012-11-08 | 2016-11-16 | 2013-05-20 | 2015-12-31 | Completed |  |  | 2.42 | 2.42 | 2 | 0
18 | R182000025 | Baranj to khulri road | Narsinghpur | Narsingpur | Road | PWD | 187.85 | 150.28 | 150.28 | 2012-11-08 | 2016-11-16 | 2013-12-28 | 2015-12-31 | Completed |  |  | 3.8 | 3.8 | 2 | 1
18 | R182000026 | Gundrahi to pathroda road | Narsinghpur | Narsingpur | Road | PWD | 192.19 | 153.75 | 126.64 | 2012-11-08 | 2016-11-16 | 2015-03-27 | 2015-12-31 | Completed |  |  | 4.5 | 4 | 2 | 1
19 | R192000053 | PURGAWAN TO SIHORA ROAD | Narsinghpur | Chawarpatha | Road | PWD | 427.52 | 342.02 | 285.07 | 2013-11-07 | 2016-11-16 | 2015-10-15 | 2016-12-31 | Completed |  |  | 3 | 3 | 2 | 2
19 | R192000156 | Naharpura Khijada to Chaipury Road | Jhabua | Tandla | Road | PWD | 274.59 | 219.67 | 201.26 | 2014-03-24 | 2016-11-16 | 2014-04-13 | 2017-05-01 | Completed |  |  | 4.96 | 4.96 | 3 | 1
19 | R192000157 | Roopgarh Mohankot Road | Jhabua | Petlawad | Road | PWD | 290.31 | 232.25 | 232.18 | 2014-03-24 | 2016-11-16 | 2014-03-16 | 2017-05-01 | Completed |  |  | 5.58 | 5.58 | 7 | 2
19 | R192000158 | Petlawad Roopgarh Hanuman Mandir Road | Jhabua | Petlawad | Road | PWD | 101.39 | 81.11 | 81.11 | 2014-03-24 | 2016-11-16 | 2014-01-01 | 2017-05-01 | Completed |  |  | 2.51 | 2.51 | 3 | 1
19 | R192000159 | Panki to Jhakela via Rotla Road | Jhabua | Rama | Road | PWD | 181.31 | 145.05 | 145.05 | 2014-03-24 | 2016-11-16 | 2014-05-21 | 2017-05-01 | Completed |  |  | 4.32 | 4.32 | 5 | 2
19 | R192000162 | Gangakhedi Mandan Road | Jhabua | Petlawad | Road | PWD | 219.28 | 175.42 | 175.42 | 2014-03-24 | 2016-11-16 | 2014-02-18 | 2017-05-01 | Completed |  |  | 5.48 | 5.48 | 3 | 2
19 | R192000163 | Pithanpur Dhamou Road | Jhabua | Rama | Road | PWD | 241.95 | 193.56 | 191.24 | 2014-03-24 | 2016-11-16 | 2014-07-15 | 2017-05-01 | Completed |  |  | 3.64 | 3.98 | 3 | 3
16 | R162000579 | Hilgan-Bhainswahi Road | Sagar | Sagar | Road | PWD | 54.37 | 54.37 | 54.37 | 2011-01-31 | 2016-11-18 | 2014-07-20 | 2016-01-31 | Completed |  |  | 6.7 | 6.7 | 4 | 2
19 | R192000182 | Garhakota bye pass Road | Sagar | Rehli | Road | PWD | 425 | 340 | 340 | 2014-03-24 | 2016-11-18 | 2014-06-15 | 2017-05-01 | Completed |  |  | 4 | 3.15 | 2 | 2
15 | R152000157 | C/o H.L.Br Naren Ri in KM 5/4 on | Sagar | Malthone | Bridge | PWD | 112.79 | 112.79 | 106.14 | 2009-12-24 | 2016-11-28 | 2012-02-10 | 2013-01-31 | Completed |  |  | 69 | 69 | 25 | 4
15 | R152000171 | Suddi-Rajarwara - Barhata Rd | Katni | Vijayraghavgarh | Road | PWD | 133.45 | 115.84 | 115.84 | 2010-01-25 | 2016-11-28 | 2010-01-28 | 2013-03-03 | Completed |  |  | 5 | 5
16 | R162000007 | High Level brg Shyamri River in Km | Chhatarpur | Bijawar | Bridge | PWD | 276.21 | 276.21 | 260.25 | 2010-08-27 | 2016-11-28 | 2011-03-31 | 2013-10-01 | Completed |  |  | 288 | 288 | 15 | 1 | Krishnagarh to Palkonda bridge completed (288 mtr)
16 | R162000549 | Mohas Kathotia Godana Road | Katni | Rithi | Road | PWD | 378.03 | 302.42 | 202.47 | 2011-01-31 | 2016-11-28 | 2013-03-25 | 2016-01-31 | Completed |  |  | 11 | 11 | 3 | 2
16 | R162000550 | Bhudsa Bhajiya Road | Katni | Badwara | Road | PWD | 148.52 | 118.82 | 99.32 | 2011-01-31 | 2016-11-28 | 2016-02-20 | 2016-01-31 | Completed |  |  | 5.5 | 5.5 | 3 | 1
16 | R162000551 | Mohas Lalpur Pali Road | Katni | Rithi | Road | PWD | 405.68 | 324.54 | 173.76 | 2011-01-31 | 2016-11-28 | 2013-12-20 | 2016-01-31 | Completed |  |  | 10 | 10 | 5 | 1
16 | R162000552 | Deorkala Mehgaon Road | Katni | Vijayraghavgarh | Road | PWD | 94.03 | 75.22 | 52.36 | 2011-01-31 | 2016-11-28 | 2012-03-01 | 2016-01-31 | Completed |  |  | 3.4 | 3.4
16 | R162000553 | Deora Mohas Road | Katni | Vijayraghavgarh | Road | PWD | 111.28 | 89.02 | 60.39 | 2011-01-31 | 2016-11-28 | 2012-03-25 | 2016-01-31 | Completed |  |  | 4.2 | 3.95 | 2 | 0
16 | R162000554 | Sarswahi Surkhi Road | Katni | Katni | Road | PWD | 83.7 | 66.96 | 59.61 | 2011-01-31 | 2016-11-28 | 2014-11-01 | 2016-01-31 | Completed |  |  | 2.8 | 2.8 | 3 | 1
16 | R162000555 | Upgradation Of Tilgawan Bandha Magardha Road | Katni | Rithi | Road | PWD | 236.9 | 189.52 | 142.34 | 2011-01-31 | 2016-11-28 | 2013-01-10 | 2016-01-31 | Completed |  |  | 7 | 7 | 3 | 1
16 | R162000556 | Kanhwara Patwara Kailwara Road | Katni | Vijayraghavgarh | Road | PWD | 100.85 | 80.68 | 69.9 | 2011-01-31 | 2016-11-28 | 2012-03-25 | 2016-01-31 | Completed |  |  | 3 | 3 | 2 | 1
16 | R162000557 | Dhanwahi neemkheda Badkheda Kirhai Pipariy Road | Katni | Bahoribbandh | Road | PWD | 424.39 | 339.51 | 225.05 | 2011-01-31 | 2016-11-28 | 2014-05-01 | 2016-01-31 | Completed |  |  | 10.5 | 10.5 | 4 | 1
16 | R162000558 | Tikuri Barkheda Pahari Road | Katni | Katni | Road | PWD | 423.85 | 339.08 | 178.23 | 2011-01-31 | 2016-11-28 | 2015-11-10 | 2016-01-31 | Completed |  |  | 11.45 | 11.45 | 5 | 1
17 | R172000097 | High Level Bridge across Urmil River on Rajnagar-Bachhon Road | Chattarpur | Rajnagar | Bridge | PWD | 305.92 | 305.92 | 305.92 | 2012-02-24 | 2016-11-28 | 2013-03-26 | 2015-03-31 | Completed |  |  | 139.98 | 164.24 | 15 | 1
17 | R172000110 | Submersible Bridge across Ur River on Khera-Vijaypur Road | Tikamgarh | Palera | Bridge | PWD | 283.07 | 283.07 | 256.5 | 2012-02-24 | 2016-11-28 | 2013-03-26 | 2015-03-31 | Completed |  |  | 165 | 165 | 15 | 1
17 | R172000111 | High Level Bridge across Ur River on Larkhurd-Jarua Road | Tikamgarh | Jatara | Bridge | PWD | 130.7 | 130.7 | 120.05 | 2012-02-24 | 2016-11-28 | 2012-12-30 | 2015-03-31 | Completed |  |  | 120 | 120 | 15 | 1
20 | R202000005 | Bridge across Ghodapachhad River in kM 50/4 on Ash | Khandwa | Chhanera | Bridge | PWD | 861.01 | 861.01 | 302.7 | 2014-11-11 | 2016-11-28 | 2016-01-31 | 2017-12-31 | Completed |  |  | 745 | 745 | 25 | 1
20 | R202000046 | Sheopur - Khatoli Road | Sheopur | Sheopur | Road | PWD | 2191.72 | 1831.73 | 820.36 | 2014-11-11 | 2016-11-28 | 2016-03-15 | 2017-12-31 | Completed |  |  | 19.9 | 19.9 | 10 | 3
15 | R152000021 | Sabramodi-Khiyawada road | Guna | Bamori | Road | PWD | 213.45 | 170.76 | 164.38 | 2009-07-23 | 2016-12-16 | 2010-05-30 | 2012-08-31 | Completed |  |  | 9.6 | 9.6 | 5 | 2
15 | R152000039 | Ghindhorhaat- Bhagora Bilas road | Rajgarh | Biaora | Road | PWD | 122.65 | 122.65 | 117.88 | 2009-07-23 | 2016-12-16 | 2012-03-09 | 2012-08-31 | Completed |  |  | 9 | 9 | 10 | 1
15 | R152000041 | Jhadla-Dhabla road via Hikmi | Rajgarh | Narsingarh | Road | PWD | 80.9 | 80.9 | 80.9 | 2009-07-23 | 2016-12-16 | 2008-03-14 | 2012-08-31 | Completed |  |  | 9.1 | 9.1 | 7 | 3
15 | R152000075 | Kurwai-Barual via Kethora Nahi road | Vidisha | Kurwar | Road | PWD | 131.35 | 131.35 | 131.35 | 2009-07-23 | 2016-12-16 | 2011-12-23 | 2012-08-31 | Completed |  |  | 12.4 | 12.8 | 3 | 1
15 | R152000179 | Goverdhanpura- Nari to Suthaliya- M | Rajgarh | Biaora | Road | PWD | 45.67 | 45.67 | 45.67 | 2010-01-25 | 2016-12-16 | 2010-10-25 | 2013-03-03 | Completed |  |  | 3 | 3 | 5 | 1
15 | R152000196 | Dhudhawari to Chapara Rd | Vidisha | Kurwai | Road | PWD | 94.4 | 94.4 | 94.4 | 2010-01-25 | 2016-12-16 | 2013-02-07 | 2013-03-03 | Completed |  |  | 6 | 6
16 | R162000012 | brg Ashamati River in Km 15/2 of | Indore | Indore | Bridge | PWD | 143.02 | 131.71 | 131.71 | 2010-08-27 | 2016-12-16 | 2012-12-31 | 2013-10-01 | Completed |  |  | 65.2 | 65.2 | 30 | 4
16 | R162000013 | brg Gambhir River on Ajnod - Bana | Indore | Indore | Bridge | PWD | 57.98 | 57.98 | 57.98 | 2010-08-27 | 2016-12-16 | 2012-12-31 | 2013-10-01 | Completed |  |  | 129 | 129 | 20 | 4
16 | R162000077 | Construction of Khamgaon Balagaon r | Harda | Timarni | Road | PWD | 248.25 | 227.83 | 199.7 | 2010-08-27 | 2016-12-16 | 2013-04-30 | 2013-10-01 | Completed |  |  | 8.73 | 8.73 | 4 | 2
16 | R162000078 | Construction of Lokhartalai Dhekna | Hoshangabad | Hoshangabad | Road | PWD | 488.59 | 479.18 | 479.18 | 2010-08-27 | 2016-12-16 | 2015-06-15 | 2013-10-01 | Completed |  |  | 18 | 18 | 12 | 3
16 | R162000079 | Construction Of Sonkhedi Misrod Roa | Hoshangabad | Hoshangabad | Road | PWD | 414.76 | 335.74 | 311.67 | 2010-08-27 | 2016-12-16 | 2013-03-25 | 2013-10-01 | Completed |  |  | 10.5 | 10.5 | 5 | 1
16 | R162000080 | Construction of Hoshangabad Link Ro | Hoshangabad | Hoshangabad | Road | PWD | 273 | 237.58 | 231.96 | 2010-08-27 | 2016-12-16 | 2014-05-14 | 2013-10-01 | Completed |  |  | 6.875 | 6.875 | 5 | 2
16 | R162000081 | Construction of Biora(NH 69) to Roh | Hoshangabad | Hoshangabad | Road | PWD | 299.92 | 239.94 | 219.25 | 2010-08-27 | 2016-12-16 | 2014-05-14 | 2013-10-01 | Completed |  |  | 6.4 | 6.4 | 3 | 1
16 | R162000082 | Construction of Shivpur Talkeshari | Hoshangabad | Babai | Road | PWD | 178.73 | 142.98 | 142.98 | 2010-08-27 | 2016-12-16 | 2010-07-12 | 2013-10-01 | Completed |  |  | 4.98 | 4.98 | 2 | 1
16 | R162000083 | Constructtion of Semari Dobh Road | Hoshangabad | Babai | Road | PWD | 176.07 | 156.74 | 156.74 | 2010-08-27 | 2016-12-16 | 2015-04-15 | 2013-10-01 | Completed |  |  | 6.1 | 6.1 | 4 | 1
16 | R162000092 | Karapgaon Khamariya Amgaon Road | Narsinghpur | Chichli | Road | PWD | 357.64 | 286.11 | 262.19 | 2010-08-27 | 2016-12-16 | 2012-07-02 | 2013-10-01 | Completed |  |  | 8.4 | 8.4 | 5 | 2
16 | R162000094 | Bankpura to Jhadikya Via Lashkarpur | Rajgarh | Narsinghgarh | Road | PWD | 426.17 | 340.94 | 340.94 | 2010-08-27 | 2016-12-16 | 2012-05-30 | 2013-10-01 | Completed |  |  | 12.6 | 12.6 | 6 | 1
16 | R162000095 | Mawasa to Jhalda Road | Rajgarh | Narsinghgarh | Road | PWD | 204.29 | 163.43 | 151.64 | 2010-08-27 | 2016-12-16 | 2013-03-01 | 2013-10-01 | Completed |  |  | 6.5 | 6.5 | 5 | 1
16 | R162000129 | B.T.B. ( Basoda-Tyoda-Bagroda) to G | Vidisha | Ganj basoda | Road | PWD | 318.91 | 318.91 | 318.91 | 2010-08-27 | 2016-12-16 | 2014-06-25 | 2013-10-01 | Completed |  |  | 17.95 | 17.95 | 7 | 1
16 | R162000132 | Pathari Kirarkhedi Batyabda Road | Vidisha | Ganj basoda | Road | PWD | 447.11 | 421.72 | 421.72 | 2010-08-27 | 2016-12-16 | 2015-05-14 | 2013-10-01 | Completed |  |  | 17.32 | 17.32 | 11 | 2
16 | R162000137 | Kethora To barodiya | Vidisha | Kurwai | Road | PWD | 232.64 | 186.11 | 183.11 | 2010-08-27 | 2016-12-16 | 2012-11-22 | 2013-10-01 | Completed |  |  | 7.5 | 7.5 | 4 | 1
16 | R162000547 | Sohagpur Kamtee Madhai Road | Hoshangabad | Sohagpur | Road | PWD | 184.94 | 147.95 | 126.07 | 2011-01-31 | 2016-12-16 | 2013-10-20 | 2016-01-31 | Completed |  |  | 12.5 | 12.5 | 5 | 1
16 | R162000608 | Khiriya to Layra Bothe Jarha Sargoli Akhai Road | Vidisha | Kurwai | Road | PWD | 803.49 | 646.72 | 646.72 | 2011-01-31 | 2016-12-16 | 2012-06-30 | 2016-01-31 | Completed |  |  | 24.6 | 24.6 | 13 | 1
17 | R172000027 | Kundam Biltikuri Road | Jabalpur | Kundam | Road | PWD | 625.78 | 500.62 | 444 | 2012-01-20 | 2016-12-16 | 2011-11-12 | 2015-03-03 | Completed |  |  | 12.7 | 12.7 | 8 | 2
17 | R172000039 | Sadarkheda Manola Via Dasoliber Road | Guna | Zirnia | Road | PWD | 285.11 | 228.09 | 203.19 | 2012-01-20 | 2016-12-16 | 2016-04-30 | 2015-03-03 | Completed |  |  | 8.5 | 8 | 4 | 1
17 | R172000040 | Sirsi To Musaredi Upto Rajasthan Bordar Road | Guna | BAMORI | Road | PWD | 467.47 | 373.98 | 308.87 | 2012-01-20 | 2016-12-16 | 2013-04-10 | 2015-03-03 | Completed |  |  | 13.5 | 11.4 | 5 | 4
17 | R172000082 | Barkheda Bhaurasa Malhargarh Road | Vidisha | Jaisinghnagar | Road | PWD | 81.26 | 65.01 | 65.01 | 2012-01-20 | 2016-12-16 | 2014-03-30 | 2015-03-03 | Completed |  |  | 4 | 4 | 2 | 1
17 | R172000085 | Devli To Bareth Road Via Tharka Tikod Road | Vidisha | Kurwai/Sironj | Road | PWD | 274.93 | 219.94 | 219.94 | 2012-01-20 | 2016-12-16 | 2013-06-29 | 2015-03-03 | Completed |  |  | 11 | 11 | 2 | 1
17 | R172000087 | Gram Imlawada To Chirwata, Sirawali Road | Vidisha | Gyaraspur | Road | PWD | 489.59 | 391.67 | 391.606 | 2012-01-20 | 2016-12-16 | 2015-11-13 | 2015-03-03 | Completed |  |  | 19 | 16.95 | 9 | 0
17 | R172000093 | Sanai To Dankhedi Road | Vidisha | Sironj | Road | PWD | 204.87 | 163.9 | 163.91 | 2012-01-20 | 2016-12-16 | 2013-03-30 | 2015-03-03 | Completed |  |  | 11.8 | 11.8 | 5 | 1
18 | R182000015 | Madiyee makhrar jaldhara road | Jabalpur | Jabalpur | Road | PWD | 331.97 | 265.58 | 265.58 | 2012-11-08 | 2016-12-16 | 2011-11-12 | 2015-12-31 | Completed |  |  | 6.92 | 6.92 | 6 | 2
18 | R182000016 | Jheeriya maheshpur devhara road | Jabalpur | Jabalpur | Road | PWD | 177.63 | 158.1 | 148.04 | 2012-11-08 | 2016-12-16 | 2011-11-12 | 2015-12-31 | Completed |  |  | 4.26 | 4.2 | 5 | 1
18 | R182000054 | Mofadakhedi to aahirbamangaon road | Hoshangabad | Hoshangabad | Road | PWD | 279.24 | 223.39 | 223.39 | 2012-11-08 | 2016-12-16 | 2016-03-30 | 2015-12-31 | Completed |  |  | 4.8 | 4.5 | 3 | 2
18 | R182000055 | Palanpur badodiya road | Hoshangabad | Hoshangabad | Road | PWD | 109.7 | 87.76 | 83.06 | 2012-11-08 | 2016-12-16 | 2013-01-29 | 2015-12-31 | Completed |  |  | 2.9 | 2.9 | 2 | 0
18 | R182000056 | Dhamsaa datwaasa to shail road | Hoshangabad | Hoshangabad | Road | PWD | 339.35 | 271.48 | 271.48 | 2012-11-08 | 2016-12-16 | 2014-10-30 | 2015-12-31 | Completed |  |  | 7.4 | 7.4 | 6 | 1
18 | R182000057 | Bhangiya to lodhadi road | Hoshangabad | Hoshangabad | Road | PWD | 159.85 | 127.88 | 123.73 | 2012-11-08 | 2016-12-16 | 2013-03-25 | 2015-12-31 | Completed |  |  | 3 | 3 | 2 | 0
18 | R182000060 | Ghudhuri gunvad road | Jhabua | Jhabua | Road | PWD | 97.86 | 78.29 | 68.26 | 2012-11-08 | 2016-12-16 | 2012-11-30 | 2015-12-31 | Completed |  |  | 3.2 | 3.2
18 | R182000063 | Nayapura to ratatlai road | Harda | Harda | Road | PWD | 245.52 | 196.42 | 196.41 | 2012-11-08 | 2016-12-16 | 2015-06-29 | 2015-12-31 | Completed |  |  | 6 | 5.8 | 2 | 0
18 | R182000090 | Rajgarh Piplodi Road | Rajgarh | Rajgarh | Road | PWD | 623.28 | 498.62 | 436.24 | 2012-12-20 | 2016-12-16 | 2013-07-17 | 2016-01-31 | Completed |  |  | 18 | 18 | 9 | 2
18 | R182000115 | Gujarwada-Kirpur Rajon Road | Hoshangabad | Babai | Road | PWD | 346.33 | 277.06 | 277.05 | 2012-12-20 | 2016-12-16 | 2015-03-13 | 2016-01-31 | Completed |  |  | 7.5 | 6 | 2 | 1
18 | R182000124 | NH 12 to Jhadla Road | Rajgarh | Narsinghrarh | Road | PWD | 232.79 | 186.23 | 151.88 | 2012-12-20 | 2016-12-16 | 2014-12-27 | 2016-01-31 | Completed |  |  | 5.8 | 5 | 3 | 1
18 | R182000125 | NH 12 to Bankpura Road | Rajgarh | Narsinghrarh | Road | PWD | 225.09 | 180.07 | 169.33 | 2012-12-20 | 2016-12-16 | 2013-07-18 | 2016-01-31 | Completed |  |  | 5.38 | 5.8
18 | R182000126 | Boda to Borkheda Road | Rajgarh | Narsinghrarh | Road | PWD | 1857.23 | 1485.78 | 1352.95 | 2012-12-20 | 2016-12-16 | 2014-06-25 | 2016-01-31 | Completed |  |  | 5.06 | 25.67 | 4 | 2
18 | R182000127 | Narsinghgad NH 12 to Bodha Road | Rajgarh | Narsinghrarh | Road | PWD | 2317.46 | 1853.97 | 1649.21 | 2012-12-20 | 2016-12-16 | 2014-06-25 | 2016-01-31 | Completed |  |  | 25.67 | 25.67 | 7 | 3
18 | R182000131 | Talen Padana Sarangpur Road | Rajgarh | Sarangpur | Road | PWD | 635.11 | 508.09 | 498.45 | 2012-12-20 | 2016-12-16 | 2013-07-22 | 2016-01-31 | Completed |  |  | 15.4 | 11.6 | 5 | 2
19 | R192000032 | GHUGHWASA TO BORTALAI ROAD | Hoshangabad | Hoshangabad | Road | PWD | 129.92 | 115.9 | 115.9 | 2013-11-07 | 2016-12-16 | 2014-12-30 | 2016-12-31 | Completed |  |  | 2.85 | 2.85 | 3 | 1
19 | R192000033 | SAMON NASIRABAD ROAD TO BHANPUR BAGALKHEDI ROAD | Hoshangabad | Hoshangabad | Road | PWD | 50.44 | 50.44 | 50.44 | 2013-11-07 | 2016-12-16 | 2013-09-26 | 2016-12-31 | Completed |  |  | 5 | 5 | 2 | 1
19 | R192000090 | Semritala to Purena kalan Road | Hoshangabad | Pipariya | Road | PWD | 275.54 | 220.43 | 220.43 | 2014-01-30 | 2016-12-16 | 2015-05-29 | 2017-03-03 | Completed |  |  | 5.14 | 4.604 | 2 | 1
19 | R192000093 | Karod to Parsoda Road | Guna | Guna | Road | PWD | 221.08 | 176.86 | 176.86 | 2014-01-30 | 2016-12-16 | 2014-02-15 | 2017-03-03 | Completed |  |  | 5.34 | 5.35 | 5 | 0
19 | R192000094 | Parwah to Pipliya Road | Guna | Bamori | Road | PWD | 138.07 | 110.46 | 109.87 | 2014-01-30 | 2016-12-16 | 2014-06-20 | 2017-03-03 | Completed |  |  | 3.74 | 3.74 | 2 | 3
19 | R192000095 | Amrod to Nonera Road | Guna | Bamori | Road | PWD | 221.12 | 176.9 | 176.9 | 2014-01-30 | 2016-12-16 | 2014-07-17 | 2017-03-03 | Completed |  |  | 5.94 | 6.36 | 2 | 3
19 | R192000096 | Dhanoriya to Ukawadkhurd | Guna | Bamori | Road | PWD | 227.56 | 182.05 | 182.05 | 2014-01-30 | 2016-12-16 | 2014-02-22 | 2017-03-03 | Completed |  |  | 5.4 | 5.4 | 4 | 2
20 | R202000020 | Badoh - Pathari Road | Vidisha | Kurwai | Road | PWD | 82.76 | 82.76 | 66.21 | 2014-11-11 | 2016-12-16 | 2015-02-28 | 2017-12-31 | Completed |  |  | 3 | 3 | 5 | 2
20 | R202000049 | Strengthening of Guna Ashoknagar to Karod Mahur Ro | Guna | Guna | Road | PWD | 94.05 | 86.7 | 15.51 | 2014-11-11 | 2016-12-16 | 2015-10-16 | 2017-12-31 | Completed |  |  | 3.4 | 3.83 | 6 | 1
20 | R202000083 | A.B Road via Dehri Telegaon Suthaliya Road | Guna | Maksudangorh | Road | PWD | 102.25 | 81.8 | 0 | 2015-01-16 | 2016-12-16 | 2014-01-09 | 2018-03-03 | Completed |  |  | 3.8 | 4.65 | 6 | 2
20 | R202000011 | Submersible Bridge Across Kewai River on Nigwani K | Annupur | Kotma | Bridge | PWD | 311.9 | 261.17 | 114.15 | 2014-11-11 | 2017-01-12 | 2016-03-31 | 2017-12-31 | Completed |  |  | 120 | 120 | 17 | 3
13 | R132000002 | Bohna Nalla Tank Project | Chhindwara | Mauganj | MIS | WRD | 1418.26 | 1347.35 | 542.3 | 2007-09-17 |  |  | 2009-10-31 | Ongoing |  |  | 1995
13 | R132000003 | Likhari Tank Project | Chhindwara | Naigarhi | MIS | WRD | 163.47 | 155.3 | 155.3 | 2007-09-17 |  |  | 2009-10-31 | Ongoing |  |  | 182
13 | R132000012 | Shahbad Tilendi Tank | Raisen | Shajapur-Shujalpur | MIS | WRD | 455.31 | 432.54 | 432.54 | 2007-09-17 |  |  | 2009-10-31 | Ongoing |  | RO Officer | 496
13 | R132000014 | Hanoti Tank | Shajapur | Ghattia | MIS | WRD | 243.84 | 234.41 | 234.41 | 2007-09-17 |  |  | 2009-10-31 | Ongoing |  |  | 268
13 | R132000018 | Gureha Pipra Tank | Katni | Manpur | MIS | WRD | 142.71 | 135.57 | 135.57 | 2007-09-17 |  |  | 2009-10-31 | Ongoing |  |  | 180
13 | R132000021 | Imlia Nala Closure Scheme | Sagar | Gohad | MIS | WRD | 121.81 | 116.93 | 85.75 | 2007-09-17 |  |  | 2009-10-31 | Completed |  |  | 242
13 | R132000023 | Nayapura Tank | Raisen | Gohad | MIS | WRD | 106.09 | 103.05 | 103.05 | 2007-09-17 |  |  | 2009-10-31 | Completed |  | DDM | 121
13 | R132000024 | Bichhiya Weir | Sagar | Ater | MIS | WRD | 85.71 | 85.71 | 79.07 | 2007-09-17 |  |  | 2009-10-31 | Completed |  |  | 248
13 | R132000025 | Vijaypur Weir | Sagar | Gohad | MIS | WRD | 83.24 | 83.24 | 83.24 | 2007-09-17 |  |  | 2009-10-31 | Ongoing |  | DDM | 212
13 | R132000026 | Duttapura Nalla Closure Scheme | Sagar | Tendukheda | MIS | WRD | 78.76 | 78.76 | 78.76 | 2007-09-17 |  |  | 2009-10-31 | Ongoing |  |  | 248
13 | R132000053 | Indira Sagar Proj Phi &II | Khandwa | Chhindwara | MJP | NVDA | 47163 | 4480.48 | 4480.48 | 2007-09-17 |  |  | 2012-10-31 | Ongoing |  |  | 62220
13 | R132000059 | Kamadpur- Chainpura- Khedi- Sihod R | Indore | Bhanpura | Road | PWD | 63.94 | 63.94 | 63.94 | 2007-10-26 |  |  | 2010-12-01 | Completed |  |  | 8
13 | R132000060 | Kanjarda - Diken Road | Neemuch | Bhanpura | Road | PWD | 308.53 | 291.98 | 291.98 | 2007-10-26 |  |  | 2010-12-01 | Ongoing |  |  | 15
13 | R132000067 | Longar-Semra-Lodhi-Parson-Madiya-Ro | Sagar | Vijayraghavgarh | Road | PWD | 198.75 | 198.75 | 198.75 | 2007-10-26 |  |  | 2010-12-01 | Ongoing |  | RO Official | 16
13 | R132000069 | Charnal-Chadwad- Gawa-Parasone Road | Sehore | Bhanpura | Road | PWD | 498.36 | 398.69 | 398.69 | 2007-10-26 |  |  | 2010-12-01 | Ongoing |  |  | 20
13 | R132000070 | Nandi - Shaila - Umarwada Road | Seoni | Rehli | Road | PWD | 231.66 | 185.33 | 185.33 | 2007-10-26 |  |  | 2010-12-01 | Ongoing |  |  | 8.5
13 | R132000072 | Gulana -Sakatkhedi-Nichma-Bumtalai | Shajapur | Obaidullaganj | Road | PWD | 124.22 | 116.28 | 116.28 | 2007-10-26 |  |  | 2010-12-01 | Completed |  |  | 6.9
13 | R132000073 | Bachchukheda Runaheda Road | Ujjain | Rehli | Road | PWD | 289.9 | 231.92 | 231.92 | 2007-10-26 |  |  | 2010-12-01 | Ongoing |  | DDM | 10
13 | R132000074 | Chheerkheda To Nimkheda Road | Vidisha | Rehli | Road | PWD | 39.74 | 39.74 | 39.74 | 2007-10-26 |  |  | 2010-12-01 | Completed |  |  | 4
13 | R132000081 | Katedara - Tirodi -Khawasa Road | Balaghat | Ghattia | Road | PWD | 246.49 | 197.19 | 197.19 | 2007-10-26 |  |  | 2010-12-01 | Ongoing |  |  | 13
13 | R132000082 | Halditola -Badgaon -Dahedi- Mate - | Balaghat | Susner | Road | PWD | 273.56 | 218.85 | 218.85 | 2007-10-26 |  |  | 2010-12-01 | Ongoing |  | DDM | 14.8
13 | R132000083 | Gohad- Dhamasha-Dhanulli Road | Bhind | Dheemarkheda | Road | PWD | 334.02 | 267.22 | 267.22 | 2007-10-26 |  |  | 2010-12-01 | Ongoing |  |  | 20
13 | R132000084 | Newton Mayavadi Road | Chhindwara | Ghattia | Road | PWD | 26.26 | 26.26 | 18.45 | 2007-10-26 |  |  | 2010-12-01 | Completed |  |  | 2.3
13 | R132000085 | Bansa - Deoran- Bhouransa Road | Damoh | Nalkheda | Road | PWD | 85.97 | 85.97 | 85.97 | 2007-10-26 |  |  | 2010-12-01 | Completed |  |  | 6.5
13 | R132000087 | Bhander - Sarsai - Dhamna Road | Datia | Sanwer | Road | PWD | 422.17 | 337.74 | 175.78 | 2007-10-26 |  |  | 2010-12-01 | Ongoing |  | DDM | 21.1
13 | R132000088 | Kuda-Chandrani Road | Dindori | Nalkheda | Road | PWD | 221.34 | 201.07 | 201.07 | 2007-10-26 |  |  | 2010-12-01 | Completed |  |  | 9.6
13 | R132000099 | Vilayatkalan Ganeshpur Salhna Road | Katni | Tarana | Road | PWD | 526.93 | 421.54 | 421.54 | 2007-10-26 |  |  | 2010-12-01 | Ongoing |  |  | 21.43
13 | R132000103 | Bichhiya Danitola Ghughri Road | Mandla | Damoh | Road | PWD | 156.36 | 156.36 | 156.36 | 2007-10-26 |  |  | 2010-12-01 | Ongoing |  |  | 26.6
13 | R132000105 | Malhargarh Narayangarh Road | Mandsaur | Chanchowda | Road | PWD | 82.78 | 66.55 | 66.55 | 2007-10-26 |  |  | 2010-12-01 | Completed |  |  | 7
13 | R132000110 | Manasa - Arniamali - Bordiakala Roa | Neemuch | Silwani | Road | PWD | 196.6 | 196.6 | 196.6 | 2007-10-26 |  |  | 2010-12-01 | Completed |  |  | 12
13 | R132000111 | Bhatkhedi - Jamunia Rao Ji - Lasoor | Neemuch | Sarangpur | Road | PWD | 162.65 | 162.65 | 162.65 | 2007-10-26 |  |  | 2010-12-01 | Completed |  | DDM | 10.5
13 | R132000117 | Pratapganj Hata Road | Rewa | Sehore | Road | PWD | 356.23 | 284.98 | 284.98 | 2007-10-26 |  |  | 2010-12-01 | Ongoing |  | DDM | 17.2
13 | R132000121 | Kuthuliya Hardi Road | Rewa | Ghattia | Road | PWD | 226.66 | 181.33 | 178.14 | 2007-10-26 |  |  | 2010-12-01 | Ongoing |  |  | 11
13 | R132000126 | Kanad-Pachlana Road | Shajapur | Ashoknagar | Road | PWD | 68.36 | 68.36 | 68.36 | 2007-10-26 |  |  | 2010-12-01 | Completed |  |  | 7.4
13 | R132000127 | Sundarsi-Khadi- Polay -Piparanva Ro | Shajapur | Mungaoli | Road | PWD | 316.19 | 255.58 | 255.58 | 2007-10-26 |  |  | 2010-12-01 | Completed |  |  | 18.1
13 | R132000129 | Dablafanth - Sipawara Road | Ujjain | Katangi | Road | PWD | 178.04 | 178.04 | 178.04 | 2007-10-26 |  |  | 2010-12-01 | Ongoing |  |  | 16.2
13 | R132000131 | Zarda- Gelakhedi Nagpura Road | Ujjain | Gohad | Road | PWD | 89.22 | 89.22 | 65.65 | 2007-10-26 |  |  | 2010-12-01 | Ongoing |  |  | 9.85
13 | R132000132 | Sasstra Kathotiya Road | Umaria | Parasia | Road | PWD | 73.73 | 73.73 | 73.73 | 2007-10-26 |  |  | 2010-12-01 | Ongoing |  |  | 30
13 | R132000133 | Barhi Singroli Manpur Road | Umaria | Pathriya | Road | PWD | 178.78 | 178.78 | 161.9 | 2007-10-26 |  |  | 2010-12-01 | Ongoing |  |  | 20.4
13 | R132000134 | HLB A/C Goi River In KM 1/6 | Badwani | Hindoria | Bridge | PWD | 291.45 | 233.16 | 233.16 | 2007-11-29 |  |  | 2010-12-31 | Ongoing |  |  | 196
13 | R132000135 | HLB A/C Khar Nala In KM 2/2 | Bhind | Bhander | Bridge | PWD | 49.07 | 49.07 | 49.07 | 2007-11-29 |  |  | 2010-12-31 | Ongoing |  | DDM | 36
13 | R132000136 | SB A/C Morar River In KM 2/2 | Bhind | Samnapur | Bridge | PWD | 54.87 | 51.82 | 47.53 | 2007-11-29 |  |  | 2010-12-31 | Ongoing |  | DDM | 30
13 | R132000137 | SB A/C Vasily River In KM 1/2 | Bhind | Indore | Bridge | PWD | 44.16 | 40 | 40 | 2007-11-29 |  |  | 2010-12-31 | Ongoing |  |  | 16
13 | R132000138 | HLB A/C Vasily River In KM 1/2 | Bhind | Jabalpur | Bridge | PWD | 96.39 | 91.7 | 91.7 | 2007-11-29 |  |  | 2010-12-31 | Ongoing |  | DDM | 54
13 | R132000139 | HLB A/C Kunwari River In KM 2/2 | Bhind | Kundam | Bridge | PWD | 1029.6 | 823.68 | 823.68 | 2007-11-29 |  |  | 2010-12-31 | Ongoing |  |  | 200
13 | R132000140 | HLB A/C Vasily River In KM 1/4-6 | Bhind | Sihora | Bridge | PWD | 90.76 | 90.76 | 90.76 | 2007-11-29 |  |  | 2010-12-31 | Ongoing |  |  | 45
13 | R132000142 | HLB A/C Gouraiya River In KM 71/10 | Damoh | Majholi | Bridge | PWD | 114.43 | 106.03 | 106.03 | 2007-11-29 |  |  | 2010-12-31 | Ongoing |  | DDM | 80
13 | R132000144 | HLB A/C Sindh River In KM 2/2 | Datia | Katni | Bridge | PWD | 608.44 | 486.75 | 486.75 | 2007-11-29 |  |  | 2010-12-31 | Ongoing |  |  | 275
13 | R132000145 | HLB A/C Sukni River In KM 6/6 | Harda | Katni | Bridge | PWD | 89.88 | 77.23 | 77.23 | 2007-11-29 |  |  | 2010-12-31 | Ongoing |  |  | 45
13 | R132000146 | HLB A/C Abna River In KM 3/8 | Khandwa | Katni - Rithi | Bridge | PWD | 59.8 | 51.06 | 51.06 | 2007-11-29 |  |  | 2010-12-31 | Ongoing |  |  | 24
13 | R132000148 | HLB A/C Siltiya Nalla In KM 3/2 | Khandwa | Bahoriband | Bridge | PWD | 44.62 | 38.84 | 38.84 | 2007-11-29 |  |  | 2010-12-31 | Ongoing |  |  | 24
13 | R132000151 | HLB A/C Lasudia Nallah In KM 18/10 | Mandsaur | Bichiya Ghughari | Bridge | PWD | 83.05 | 67.12 | 61.28 | 2007-11-29 |  |  | 2010-12-31 | Ongoing |  | DDM | 52
13 | R132000153 | HLB A/C Khand River In KM4 | Raisen | Malhargarh | Bridge | PWD | 87.06 | 87.06 | 87.06 | 2007-11-29 |  |  | 2010-12-31 | Ongoing |  | DDM | 45
13 | R132000154 | HLB A/C Ugal River In KM 22/10 | Rajgarh | Sitamau | Bridge | PWD | 159.64 | 128.61 | 128.61 | 2007-11-29 |  |  | 2010-12-31 | Ongoing |  | DDM | 105
13 | R132000155 | SB A/C Parvati River | Rajgarh | Chichli | Bridge | PWD | 425.42 | 341.34 | 341.34 | 2007-11-29 |  |  | 2010-12-31 | Ongoing |  | DDM | 210
13 | R132000156 | HLB A/C Rojar River In KM 18/10 | Ratlam | Narsinghpur | Bridge | PWD | 120.12 | 97.5 | 95.76 | 2007-11-29 |  |  | 2010-12-31 | Ongoing |  |  | 45
13 | R132000160 | HLB A/C Dhasan River In KM 25/8 | Sagar | Sarangpur | Bridge | PWD | 170.27 | 136.22 | 94.28 | 2007-11-29 |  |  | 2010-12-31 | Ongoing |  | DDM | 150
13 | R132000164 | SB A/C Piliya Khal Nalla In KM 3/4 | Ujjain | Hanumana | Bridge | PWD | 118.74 | 96.58 | 96.58 | 2007-11-29 |  |  | 2010-12-31 | Ongoing |  |  | 60
13 | R132000165 | HLB A/C Sagad River In KM 2/6 | Vidisha | Hanumana | Bridge | PWD | 155.86 | 126.03 | 126.03 | 2007-11-29 |  |  | 2010-12-31 | Ongoing |  |  | 100
13 | R132000166 | HLB A/C Sapan River In KM 38/10 | Vidisha | Naigarhi | Bridge | PWD | 263.81 | 213.8 | 213.8 | 2007-11-29 |  |  | 2010-12-31 | Ongoing |  | DDM | 100
13 | R132000167 | Bansagar MJP Unitiicanals | Rewa | Many | MJP | WRD | 132433 | 94358.75 | 94217.42 | 2007-11-29 |  |  | 2012-12-31 | Ongoing |  | OIC | 154687
14 | R142000001 | Sindh Phase Ii | Shivpuri | Many | MJP | WRD | 120797 | 86067.86 | 61776.47 | 2008-04-25 |  |  | 2013-05-31 | Ongoing |  |  | 138251
14 | R142000002 | Bariyarpur Lbc Canals Pro | Chattarpur | Many | MJP | WRD | 16034 | 11424.23 | 4794.87 | 2008-11-29 |  |  | 2013-12-31 | Ongoing |  |  | 47814
15 | R152000001 | Bargi Di-Iii (Rbc104-154km) | Katni | Many | MJP | NVDA | 112082.33 | 79859.22 | 34911.64 | 2009-04-24 |  |  | 2014-05-31 | ongoing |  |  | 26000
15 | R152000003 | Gram Parmandal-Sarra Hety Khedly Ba | Betul | Multai | Road | PWD | 253.45 | 253.45 | 253.45 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 21.7
15 | R152000004 | Nasirabad Via Ratanpur-Alampur Road | Betul | Chicholi | Road | PWD | 376.92 | 367.22 | 367.21 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 18.2
15 | R152000006 | Masod-Wandly-Tiwarkhed Road | Betul | Prabhapattan | Road | PWD | 24.24 | 24.24 | 24.24 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 12.4
15 | R152000007 | Mau-Chhekuri-Karoli-Kanathar Road | Bhind | Gohud | Road | PWD | 200.4 | 192.04 | 121.75 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 10.5
15 | R152000008 | Bijawar-Mankari-Badamalehra Road | Chattarpur | Badamalehra | Road | PWD | 108.09 | 108.09 | 108.09 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 10
15 | R152000009 | Sahu Junction- Itava-Hirdepur Road | Damoh | Damoh | Road | PWD | 152.68 | 122.14 | 122.14 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 5.5
15 | R152000010 | Hatta-Subjail-Khari-Jamunia-Ronda-B | Damoh | Hatta | Road | PWD | 405 | 324 | 295.46 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 11.5
15 | R152000012 | Bangaun-Rewjha Kala- Bamhori- Mango | Damoh | Patera | Road | PWD | 552.53 | 442.02 | 442.02 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 16.5
15 | R152000014 | Sakore-Puraina Road | Damoh | Hatta | Road | PWD | 188.43 | 150.74 | 145.23 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 6
15 | R152000020 | Sakka-Amarpur Road | Dindori | Amarpur | Road | PWD | 137.84 | 137.84 | 132.42 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 9.6
15 | R152000022 | Rangawa - Deagarh - Jigania Road | Gwalior | Dabra | Road | PWD | 309.15 | 255.31 | 236.03 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 9.6
15 | R152000023 | Danda Khirak-Tighra Road | Gwalior | Ghatigaon | Road | PWD | 330.33 | 330.33 | 217.35 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 34.2
15 | R152000025 | Yashwant Sagar-Mirjapur-Arniya-Baro | Indore | Depalpur | Road | PWD | 147.83 | 147.83 | 147.83 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 15.92
15 | R152000027 | Tilwara-Chargawan-Gotegaon Road | Jabalpur | Shahpura | Road | PWD | 81.18 | 81.18 | 70.68 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 8
15 | R152000028 | Barwaha-Katkut-Udaya Nagar Road | Khargone | Barwaha | Road | PWD | 93.9 | 75.12 | 64.36 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 6.38
15 | R152000029 | Surva-Sagur-Rahgaon Road | Khargone | Bhikangaon | Road | PWD | 85.15 | 85.15 | 85.15 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 7.4
15 | R152000031 | Noorabad Padawali -Sanichara Road | Morena | Morena | Road | PWD | 257.59 | 206.07 | 164.82 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 7
15 | R152000032 | Bichola Rithora To Bhensora App. Ro | Morena | Morena | Road | PWD | 93.24 | 93.24 | 93.24 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 5.7
15 | R152000034 | Umraoganj-Rojorachak Road | Raisen | Obedullaganj | Road | PWD | 135.2 | 108.16 | 108.16 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 11.4
15 | R152000036 | Nh12-Kingi-Baniyakhedi-Khairwada-Ma | Raisen | Bari | Road | PWD | 161.35 | 161.35 | 102.17 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 18
15 | R152000037 | Simrai Berasia- Hazli Khasrod Road | Raisen | Obedullaganj | Road | PWD | 125.87 | 125.87 | 125.87 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 7
15 | R152000038 | Datagram-Patrikala-Kila Amergarh Ra | Rajgarh | Rajgarh | Road | PWD | 375.27 | 374.09 | 374.09 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 18.6
15 | R152000040 | Lhodipura- Padli Maharaj Road | Rajgarh | Biaora | Road | PWD | 110.76 | 105.7 | 103.3 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 3.02
15 | R152000042 | Biaora Sujhaliya Road -Nariyabay Ka | Rajgarh | Biaora | Road | PWD | 98.4 | 98.4 | 98.4 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 6.8
15 | R152000043 | Gangeo-Tikuri Road | Rewa | Gangeo | Road | PWD | 133.28 | 109.48 | 25.87 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 7.2
15 | R152000044 | Saw-Hardi-Rahat-Dadar Road | Rewa | Rewa | Road | PWD | 275.27 | 220.22 | 27.95 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 7.92
15 | R152000045 | Piparahi-Jadkund Road | Rewa | Hanumna | Road | PWD | 581.65 | 509.54 | 408.81 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 25
15 | R152000046 | Lalgaon-Mangawan Road | Rewa | Gangeo | Road | PWD | 279.67 | 237.63 | 237.63 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 14.6
15 | R152000048 | Ujnethi-Patan Road | Sagar | Banda | Road | PWD | 164.02 | 163.82 | 163.82 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 8
15 | R152000050 | Pajnari-Kandari Tigadda Road | Sagar | Banda | Road | PWD | 153.65 | 153.65 | 146.01 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 6
15 | R152000051 | Satna-Bardadih Siding-Dagdiha Road | Satna | Sohawal | Road | PWD | 132.93 | 132.93 | 132.93 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 19.8
15 | R152000052 | Shyamnagar-Jarkhi-Lalpur Road | Satna | Nagod | Road | PWD | 215.39 | 202.27 | 161.5 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 8.44
15 | R152000053 | Bhaukhedi-Dhamanda-Amalaha Road | Sehore | Ichhawar | Road | PWD | 186.06 | 186.06 | 186.06 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 17.6
15 | R152000054 | Neelbad Approach Road | Sehore | Ashta | Road | PWD | 93.83 | 93.83 | 53.06 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 7
15 | R152000056 | Gopalpur-Seegaon-Narayanpura Road | Sehore | Nasrullaganj | Road | PWD | 555.44 | 444.35 | 215.42 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 10
15 | R152000057 | Rala-Tiladiya Road | Sehore | Nasrullaganj | Road | PWD | 247.07 | 197.66 | 166.02 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 7.18
15 | R152000058 | O'ganj To Shahganj Road | Sehore | Budhni | Road | PWD | 548.95 | 439.16 | 314.41 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 18
15 | R152000061 | Tanodiya-Madkota Road | Shajapur | Agar | Road | PWD | 139.54 | 139.54 | 139.54 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 20.8
15 | R152000062 | Bhasoda-Badagaon Road | Shajapur | Nalkheda | Road | PWD | 86.08 | 86.08 | 86.08 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 9
15 | R152000063 | Bjarlle-Makra Wala Road | Sheopur | Sheopur | Road | PWD | 286 | 228.8 | 223.67 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 20.5
15 | R152000064 | Badagong-Baldeogarh | Tikamgarh | Baldevgarh | Road | PWD | 209.83 | 167.86 | 147.41 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 24.2
15 | R152000070 | Lalpur- Biyvara Road | Ujjain | Ujjain | Road | PWD | 374.11 | 366.34 | 366.34 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 16
15 | R152000071 | Zarda-Tarot-Dhablasiya- Gogakheda R | Ujjain | Mahidpur | Road | PWD | 261.06 | 261.06 | 124.41 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 11.8
15 | R152000073 | Narsingha - Pirzhalar Road | Ujjain | Badnagar | Road | PWD | 150.59 | 150.59 | 150.6 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 6.9
15 | R152000076 | Daynandpur-Badanpur-Bhiyakhedi-Gang | Vidisha | Vidisha | Road | PWD | 95.31 | 95.31 | 95.31 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 6
15 | R152000077 | Sanchi-Udaygiri-Vidisha-Gulabganj B | Vidisha | Sanchi | Road | PWD | 1045.69 | 1045.69 | 1001.69 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 83.2
15 | R152000078 | Hausua - Katsara Road | Vidisha | Vidisha | Road | PWD | 40.01 | 40.01 | 40.01 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 5.5
15 | R152000080 | Gyaraspur-Inderwas Road | Vidisha | Gyaraspur | Road | PWD | 185.12 | 185.12 | 185.12 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 11
15 | R152000081 | Hatkheda - Tarawali Approach Road | Vidisha | Gyaraspur | Road | PWD | 45.19 | 45.19 | 45.19 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 5.5
15 | R152000082 | Laharpur-Pepaldhar Road | Vidisha | Vidisha | Road | PWD | 115.68 | 115.68 | 115.68 | 2009-07-23 |  |  | 2012-08-31 |  |  |  | 8
15 | R152000083 | Pry Health Centre Sakra | Annupur | Jatehri | Health | DHFW | 65 | 55.25 | 51.48 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000084 | Pry Health Centre Cholna | Annupur | Jatehri | Health | DHFW | 65 | 55.25 | 53.64 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000085 | Pry Health Centre Raipur | Ashoknagar | Ashoknagar | Health | DHFW | 65 | 55.25 | 46.97 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000086 | Pry Health Centre Babdad | Badwani | Sendhwa | Health | DHFW | 65 | 55.25 | 54.73 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000087 | Pry Health Centre Rajegaon | Balaghat | Kirnapur | Health | DHFW | 65 | 55.25 | 50.43 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000088 | Pry Health Centre Jaam | Balaghat | Lalbarra | Health | DHFW | 65 | 55.25 | 46.8 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000089 | Pry Health Centre Mohgaon | Balahgat | Katangi | Health | DHFW | 65 | 55.25 | 46.59 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000090 | Pry Health Centre Borgaon | Betul | Betul | Health | DHFW | 65 | 55.25 | 48.03 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000091 | Pry Health Centre Bamnora | Chattarpur | Rajnagar | Health | DHFW | 65 | 55.25 | 55.25 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000092 | Pry Health Centre Bajna | Chattarpur | Malhara | Health | DHFW | 65 | 55.25 | 55.25 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000093 | Pry Health Centre Geldubba | Chhindwara | Tamia | Health | DHFW | 65 | 55.25 | 55.24 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000094 | Pry Health Centre Nohta | Damoh | Jabera | Health | DHFW | 65 | 55.25 | 51.39 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000095 | Pry Health Centre Sadguva | Damoh | Pathariya | Health | DHFW | 65 | 55.25 | 55.25 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000096 | Pry Health Centre Jerath | Damoh | Pathariya | Health | DHFW | 65 | 55.25 | 55.25 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000097 | Pry Health Centre Imaliyaghat | Damoh | Damoh | Health | DHFW | 65 | 55.25 | 55.25 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000098 | Pry Health Centre Gondal | Datiya | Bhander | Health | DHFW | 65 | 55.25 | 55.25 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000099 | Pry Health Centre Satipura | Dhar | Manavar | Health | DHFW | 65 | 55.25 | 55.26 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000100 | Pry Health Centre Rusha | Dindori | Karanjiya | Health | DHFW | 65 | 55.25 | 53.93 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000101 | Pry Health Centre Bamhani | Dindori | Samnapur | Health | DHFW | 65 | 55.25 | 47.43 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000102 | Pry Health Centre Sontalai | Harda | Harda | Health | DHFW | 65 | 55.25 | 26.77 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000103 | Pry Health Centre Singod | Jabalpur | Panagar | Health | DHFW | 65 | 55.25 | 22.63 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000104 | Pry Health Centre Boriya | Jabalpur | Patan | Health | DHFW | 65 | 55.25 | 15.83 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000105 | Pry Health Centre Padwar | Jabalpur | Majholi | Health | DHFW | 65 | 55.25 | 22.24 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000106 | Pry Health Centre Belkhadu | Jabalpur | Bargi | Health | DHFW | 65 | 55.25 | 26.08 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000107 | Pry Health Centre Indana | Jabalpur | Majholi | Health | DHFW | 65 | 55.25 | 46.04 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000108 | Pry Health Centre Bhidki | Jabalpur | Shahpura | Health | DHFW | 65 | 55.25 | 42.65 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000109 | Pry Health Centre Ublad | Jhabua | Jobat | Health | DHFW | 65 | 55.25 | 51 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000110 | Pry Health Centre Sobhavade | Jhbua | Babhra | Health | DHFW | 65 | 55.25 | 32.33 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000111 | Pry Health Centre Umrath | Jhbua | Sondwa | Health | DHFW | 65 | 55.25 | 34.32 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000112 | Pry Health Centre Phulmal | Jhbua | Katthiwada | Health | DHFW | 65 | 55.25 | 29.53 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000113 | Pry Health Centre Katkut | Khargone | Baswa | Health | DHFW | 65 | 55.25 | 55.25 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000114 | Pry Health Centre Guradiya | Khargone | Barwaha | Health | DHFW | 65 | 55.25 | 55.25 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000115 | Pry Health Centre Kabadiya | Khargone | Maheshwar | Health | DHFW | 65 | 55.25 | 55.26 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000116 | Pry Health Centre Helabdava | Khargone | Kasrawad | Health | DHFW | 65 | 55.25 | 55.25 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000117 | Pry Health Centre Pipariya | Mandla | Niwas | Health | DHFW | 65 | 55.25 | 32.71 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000118 | Pry Health Centre Davla Mahesh | Mandsour | Sitamau | Health | DHFW | 65 | 55.25 | 37.69 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000119 | Pry Health Centre Ridhora | Morena | Morena | Health | DHFW | 65 | 55.25 | 55.25 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000120 | Pry Health Centre Bhangroll | Morena | Sabalgadh | Health | DHFW | 65 | 55.25 | 55.25 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000121 | Pry Health Centre Jodori | Rewa | Gangew | Health | DHFW | 65 | 55.25 | 55.25 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000122 | Pry Health Centre Khannodi | Shahdol | Pali(Gohparu) | Health | DHFW | 65 | 55.25 | 55.25 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000123 | Pry Health Centre Avanitpur Badotiy | Shajapur | Shujalpur | Health | DHFW | 65 | 55.25 | 42.17 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000124 | Pry Health Centre Premsar | Sheopur | Sheopur | Health | DHFW | 65 | 55.25 | 50.94 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000125 | Pry Health Centre Dantardakla | Sheopur | Sheopur | Health | DHFW | 65 | 55.25 | 51.45 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000126 | Pry Health Centre Sirsod | Shivpuri | Karera | Health | DHFW | 65 | 55.25 | 39.76 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000127 | Pry Health Centre Chhapara | Seoni | Barghat | Health | DHFW | 65 | 55.25 | 41.34 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000128 | Pry Health Centre Chandera | Tikamgarh | Jatara | Health | DHFW | 65 | 55.25 | 36.92 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000129 | Pry Health Centre Kachhora | Tikamgarh | Palera | Health | DHFW | 65 | 55.25 | 36.95 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000130 | Pry Health Centre Jaruaa | Tikamgarh | Jatara | Health | DHFW | 65 | 55.25 | 32.3 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000131 | Pry Health Centre Luharguvan | Tikamgarh | Prathvipur | Health | DHFW | 65 | 55.25 | 30.65 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000132 | Pry Health Centre Rupakhedi | Ujjain | Tarana | Health | DHFW | 65 | 55.25 | 40.97 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000133 | Pry Health Centre Panth Pipalai | Ujjain | Ujjain | Health | DHFW | 65 | 55.25 | 49.12 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000134 | Pry Health Centre Chintaman Javasiy | Ujjain | Tarana | Health | DHFW | 65 | 55.25 | 0 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000135 | Pry Health Centre Kaytha | Ujjain | Tarana | Health | DHFW | 65 | 55.25 | 29.29 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000136 | Pry Health Centre Bizori | Umariya | Manpur | Health | DHFW | 65 | 55.25 | 44.33 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000137 | Pry Health Centre Dhamokhar | Umariya | Manpur | Health | DHFW | 65 | 55.25 | 45.75 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000138 | Pry Health Centre Nourozabad | Umariya | Karkeli | Health | DHFW | 65 | 55.25 | 47.85 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000139 | Pry Health Centre Bardha | Vidisha | Nateran | Health | DHFW | 65 | 55.25 | 15.77 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000140 | Pry Health Centre Sayar | Vidisha | Vidisha | Health | DHFW | 65 | 55.25 | 42.65 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000141 | Pry Health Centre Ahmadpur | Vidisha | Vidisha | Health | DHFW | 65 | 55.25 | 42.64 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000142 | Pry Health Centre Udaipur | Vidisha | Ganjbasoda | Health | DHFW | 65 | 55.25 | 41.74 | 2009-11-23 |  |  | 2012-12-31 |  |  |  | 1
15 | R152000143 | H.L. Br Wainganga Ri In KM 7/ | Balaghat | Lalbarra | Bridge | PWD | 1391.33 | 1127.34 | 1062.18 | 2009-12-24 |  |  | 2013-01-31 |  |  |  | 420
15 | R152000146 | Sub Br Machana Ri In KM 2/8 O | Betul | Betul | Bridge | PWD | 186.31 | 151.46 | 151.43 | 2009-12-24 |  |  | 2013-01-31 |  |  |  | 90
15 | R152000147 | Sub Br Tawa Ri In KM 1/6 On B | Betul | Ghodadongari | Bridge | PWD | 529.13 | 433.7 | 408.97 | 2009-12-24 |  |  | 2013-01-31 |  |  |  | 220
15 | R152000148 | H.L. Br Tapti Ri In KM 16/4 | Betul | Prabhat-pattan | Bridge | PWD | 369.35 | 297.46 | 248.75 | 2009-12-24 |  |  | 2013-01-31 |  |  |  | 195
15 | R152000149 | H.L. Br Tapti Ri In KM 31/10 | Betul | Bhimpur | Bridge | PWD | 487.2 | 391.37 | 272.36 | 2009-12-24 |  |  | 2013-01-31 |  |  |  | 210
15 | R152000150 | Sub Br Pench Ri On Top - Bans | Chhindwara | Chourai | Bridge | PWD | 297.59 | 239.87 | 216.43 | 2009-12-24 |  |  | 2013-01-31 |  |  |  | 150
15 | R152000151 | H.L.Br Kanhan Ri In Km 12/4 | Chhindwara | Saunsar | Bridge | PWD | 724.98 | 602.9 | 593.24 | 2009-12-24 |  |  | 2013-01-31 |  |  |  | 180
15 | R152000152 | Sub Br Bairma Ri In KM 9/2 On | Damoh | Damoh | Bridge | PWD | 593.81 | 475.05 | 709.47 | 2009-12-24 |  |  | 2013-01-31 |  |  |  | 330
15 | R152000154 | Sub Br Burarewa Ri In KM 119/ | Narsinghpur | Narsinghpur | Bridge | PWD | 159.42 | 141.97 | 137.75 | 2009-12-24 |  |  | 2013-01-31 |  |  |  | 45
15 | R152000155 | Sub Br Maleni Ri In KM 9/2 O | Ratlam | Jaora | Bridge | PWD | 357.46 | 290.42 | 58.98 | 2009-12-24 |  |  | 2013-01-31 |  |  |  | 225
15 | R152000156 | H.L.Br Tons Ri In KM 1/2 On | Rewa | Teonthar | Bridge | PWD | 1378.99 | 1253.14 | 2490.92 | 2009-12-24 |  |  | 2013-01-31 |  |  |  | 200
15 | R152000158 | H.L.Br Tons Ri In Km 22/2-4 O | Satna | Rampur | Bridge | PWD | 358.1 | 358.1 | 358.1 | 2009-12-24 |  |  | 2013-01-31 |  |  |  | 288
15 | R152000159 | Sub Br Pahari Khera Nalla In | Satna | Majgawa | Bridge | PWD | 25.52 | 25.52 | 25.48 | 2009-12-24 |  |  | 2013-01-31 |  |  |  | 75
15 | R152000160 | Sub Br Kolar Ri In KM 11/2 On | Sehore | Rehti | Bridge | PWD | 199.58 | 199.58 | 170.35 | 2009-12-24 |  |  | 2013-01-31 |  |  |  | 150
15 | R152000161 | H.L. Br Jamni Ri In KM 74/6 O | Tikamgarh | Prathvipur | Bridge | PWD | 1607.08 | 1287.15 | 4.63 | 2009-12-24 |  |  | 2013-01-31 |  |  |  | 810
15 | R152000162 | Sub Br Betwa Ri In KM 81/2 On | Tikamgarh | Niwari | Bridge | PWD | 580.13 | 464.1 | 2.42 | 2009-12-24 |  |  | 2013-01-31 |  |  |  | 260
15 | R152000163 | H.L.Br Johilla Ri In KM 12/1 | Umariya | Pali | Bridge | PWD | 579.3 | 469.3 | 324.22 | 2009-12-24 |  |  | 2013-01-31 |  |  |  | 160
15 | R152000164 | Sub Br Bais Ri In KM 3/2 On C | Vidisha | Vidisha | Bridge | PWD | 224.83 | 196.97 | 171.82 | 2009-12-24 |  |  | 2013-01-31 |  |  |  | 192
15 | R152000165 | Hamlapur- Malkapur To Barsali Rd | Betul | Betul | Road | PWD | 183.01 | 183.01 | 183.01 | 2010-01-25 |  |  | 2013-03-03 |  |  |  | 12
15 | R152000166 | Patpada-Moredongari Rd | Chhindwara | Parasiya | Road | PWD | 161.52 | 161.52 | 145.65 | 2010-01-25 |  |  | 2013-03-03 |  |  |  | 11.2
15 | R152000167 | Bamanpura-Nadia-Kudai Rd | Damoh | Patera | Road | PWD | 76.99 | 76.99 | 76.65 | 2010-01-25 |  |  | 2013-03-03 |  |  |  | 6
15 | R152000168 | Amjhar-Padwar Rd | Jabalpur | Kundam | Road | PWD | 219.4 | 175.52 | 173.58 | 2010-01-25 |  |  | 2013-03-03 |  |  |  | 10.8
15 | R152000169 | Baghraji-Badua-Patnakala Rd | Jabalpur | Kundam | Road | PWD | 339.98 | 271.98 | 247.32 | 2010-01-25 |  |  | 2013-03-03 |  |  |  | 13.6
15 | R152000172 | Upgradation Of Kasrawad-Pipalgone-L | Khargone | Kasrawad | Road | PWD | 909.69 | 727.75 | 721.02 | 2010-01-25 |  |  | 2013-03-03 |  |  |  | 22.8
15 | R152000173 | Bajitpura- Umariya Rd | Khargone | Barwaha | Road | PWD | 401.65 | 345.32 | 345.32 | 2010-01-25 |  |  | 2013-03-03 |  |  |  | 18.26
15 | R152000174 | Ghata- Chapartala- Bhadagi - Gaitra | Mandla | Mawai | Road | PWD | 153.43 | 153.43 | 153.43 | 2010-01-25 |  |  | 2013-03-03 |  |  |  | 13.9
15 | R152000175 | Jawad-Modi-Semli-Chandrawat Rd | Neemuch | Jawad | Road | PWD | 131.32 | 131.32 | 131.32 | 2010-01-25 |  |  | 2013-03-03 |  |  |  | 10
15 | R152000177 | Napanera-Newali Rd | Rajgarh | Biaora | Road | PWD | 64.82 | 64.82 | 64.82 | 2010-01-25 |  |  | 2013-03-03 |  |  |  | 3.35
15 | R152000178 | Bhatkhedi To Shilwadiya Rd | Rajgarh | Biaora | Road | PWD | 50.62 | 50.62 | 50.62 | 2010-01-25 |  |  | 2013-03-03 |  |  |  | 3.75
15 | R152000180 | Shutaliya To Ghograghat Rd | Rajgarh | Biaora | Road | PWD | 44.05 | 44.05 | 44.05 | 2010-01-25 |  |  | 2013-03-03 |  |  |  | 3.5
15 | R152000181 | Lakhanwas To Tumdia Khedi Rd | Rajgarh | Biaora | Road | PWD | 73.21 | 58.57 | 58.57 | 2010-01-25 |  |  | 2013-03-03 |  |  |  | 3.5
15 | R152000182 | Dabdiya-Talod Rd | Ratlam | Alote | Road | PWD | 89.89 | 79.83 | 74.56 | 2010-01-25 |  |  | 2013-03-03 |  |  |  | 3
15 | R152000183 | Alot- Sherpurkhurd Via Malya Rd | Ratlam | Alote | Road | PWD | 196.55 | 175.64 | 164.15 | 2010-01-25 |  |  | 2013-03-03 |  |  |  | 7.5
15 | R152000184 | Sihora-Lotna-Lotni-Ramchhayari-Heer | Sagar | Sagar | Road | PWD | 674.64 | 539.71 | 308.72 | 2010-01-25 |  |  | 2013-03-03 |  |  |  | 17
15 | R152000185 | Khurai-Nagna-Dhonga-Kanera-Barodiya | Sagar | Sagar | Road | PWD | 639.37 | 511.5 | 431.84 | 2010-01-25 |  |  | 2013-03-03 |  |  |  | 16
15 | R152000190 | Maksi-Jhonkar Rd | Shajapur | Shajapur | Road | PWD | 55.51 | 55.51 | 55.51 | 2010-01-25 |  |  | 2013-03-03 |  |  |  | 5
15 | R152000191 | Nanawad To Gurdha Via Amalda Rd | Sheopur | Sheopur | Road | PWD | 98.56 | 78.85 | 78.85 | 2010-01-25 |  |  | 2013-03-03 |  |  |  | 7.05
15 | R152000192 | Upgradation Of Goverdhan Umari Rd | Shivpuri | Pohari | Road | PWD | 166.2 | 160.08 | 140.9 | 2010-01-25 |  |  | 2013-03-03 |  |  |  | 13.5
15 | R152000193 | Kundhikheda To Khedakhajuriya Rd | Ujjain | Mahidpur | Road | PWD | 327.79 | 327.79 | 305.03 | 2010-01-25 |  |  | 2013-03-03 |  |  |  | 18
15 | R152000194 | Nagda Gogapur Rd | Ujjain | Nagda | Road | PWD | 280.41 | 224.33 | 107.2 | 2010-01-25 |  |  | 2013-03-03 |  |  |  | 8.8
15 | R152000195 | Eklod-Sironj To Vidisha-Ashoknagar | Vidisha | Sironj | Road | PWD | 484.2 | 484.2 | 484.2 | 2010-01-25 |  |  | 2013-03-03 |  |  |  | 24.8
15 | R152000197 | Berasiya Rd To Bagri Jamber Chhirkh | Vidisha | Vidisha | Road | PWD | 38.89 | 38.89 | 38.9 | 2010-01-25 |  |  | 2013-03-03 |  |  |  | 4
15 | R152000198 | Lower Goi Irrigation Proj | Barwani | Many Blocks | MJP | NVDA | 33482 | 3180.6 | 3180.6 | 2010-01-25 |  |  | 2015-03-03 |  |  |  | 13760
16 | R162000001 | Brg Kewai River At Gulidand - Pac | Anuppur | Kotma | Bridge | PWD | 390.78 | 313.35 | 235.06 | 2010-08-27 |  |  | 2013-10-01
16 | R162000002 | Brg Choti Bagh River On Ghansa Na | Balaghat | Lanjhi | Bridge | PWD | 309.5 | 247.6 | 231.06 | 2010-08-27 |  |  | 2013-10-01
16 | R162000003 | High Level Brg Bagh River In Km. 2 | Balaghat | Kirnapur | Bridge | PWD | 950.41 | 762 | 534.62 | 2010-08-27 |  |  | 2013-10-01
16 | R162000004 | High Level Brg Maru River On Gond | Betul | Athner | Bridge | PWD | 117.15 | 94.14 | 81.25 | 2010-08-27 |  |  | 2013-10-01
16 | R162000005 | Brg UD-Nalla On Sonora Sopai Ro | Betul | Prabhat Pattan | Bridge | PWD | 94.93 | 75.96 | 75.96 | 2010-08-27 |  |  | 2013-10-01
16 | R162000006 | High Level Brg Semri Nalla On Bhop | Bhopal | Berasia | Bridge | PWD | 56.98 | 45.58 | 0 | 2010-08-27 |  |  | 2013-10-01
16 | R162000008 | Brg Narmada River On Shahpur - Ba | Dindori | Dindori | Bridge | PWD | 481.7 | 385.36 | 287.02 | 2010-08-27 |  |  | 2013-10-01
16 | R162000009 | Construction Of High Level Brg Nal | Harda | Khirkiya | Bridge | PWD | 142.68 | 114.14 | 106.66 | 2010-08-27 |  |  | 2013-10-01
16 | R162000010 | Brg Machak River On Sirali- Daga | Harda | Khirkiya | Bridge | PWD | 217.65 | 174.62 | 144.86 | 2010-08-27 |  |  | 2013-10-01
16 | R162000011 | Brg Machak River On Mahendragaon | Harda | Khirkiya | Bridge | PWD | 201.33 | 161.91 | 161.91 | 2010-08-27 |  |  | 2013-10-01
16 | R162000014 | High Level Brg Katkala Nallah At B | Indore | Sanwer | Bridge | PWD | 88.68 | 70.94 | 70.94 | 2010-08-27 |  |  | 2013-10-01
16 | R162000017 | Brg Budner River On Alahi - Mehli | Mandla | Ghughri | Bridge | PWD | 316.26 | 253.01 | 186.52 | 2010-08-27 |  |  | 2013-10-01
16 | R162000018 | Brg Shivna River On Mandsaur - Pr | Mandsaur | Mandsaur | Bridge | PWD | 562.58 | 451.31 | 433.3 | 2010-08-27 |  |  | 2013-10-01
16 | R162000019 | Brg Shakkar River On Kalyanpur - | Narsinghpur | Chichli | Bridge | PWD | 614.8 | 491.84 | 491.84 | 2010-08-27 |  |  | 2013-10-01
16 | R162000020 | High Level Brg Tenduni River On G | Raisen | Silwani | Bridge | PWD | 166.66 | 133.33 | 90.2 | 2010-08-27 |  |  | 2013-10-01
16 | R162000021 | High Level Brg Gahara Nalla On Sul | Raisen | Silwani | Bridge | PWD | 103.98 | 83.18 | 57.14 | 2010-08-27 |  |  | 2013-10-01
16 | R162000022 | Brg Sindoorkiya Nallah On Jaora - | Ratlam | Jaora | Bridge | PWD | 130.98 | 106.5 | 106.03 | 2010-08-27 |  |  | 2013-10-01
16 | R162000023 | High Level Brg At Paisuni River On | Satna | Majhgawan | Bridge | PWD | 516.15 | 413.46 | 413.46 | 2010-08-27 |  |  | 2013-10-01
16 | R162000024 | Brg Satna River On Satna - Jiganh | Satna | Suhawal | Bridge | PWD | 382.86 | 306.29 | 176.2 | 2010-08-27 |  |  | 2013-10-01
16 | R162000025 | Brg Kunuk River At Jaitpur - Jhee | Shahdol | Burhar | Bridge | PWD | 169.13 | 136 | 103.29 | 2010-08-27 |  |  | 2013-10-01
16 | R162000026 | Brg Kunuk River At Jaitpur - Jhee | Shahdol | Burhar | Bridge | PWD | 138.29 | 111.31 | 99.22 | 2010-08-27 |  |  | 2013-10-01
16 | R162000027 | Brg Kunuk River At Jaitpur - Jhee | Shahdol | Burhar | Bridge | PWD | 139.09 | 111.96 | 103.11 | 2010-08-27 |  |  | 2013-10-01
16 | R162000028 | Brg Kunuk River At Bhatia Bhagora | Shahdol | Burhar | Bridge | PWD | 174.16 | 139.33 | 127.47 | 2010-08-27 |  |  | 2013-10-01
16 | R162000029 | Brg Newaj River On Devli - Saliya | Shajapur | Kalapipal | Bridge | PWD | 301.71 | 241.56 | 234.94 | 2010-08-27 |  |  | 2013-10-01
16 | R162000030 | Brg Jamdhad River On Jamner Khed | Shajapur | Shujalpur | Bridge | PWD | 64.81 | 51.85 | 51.85 | 2010-08-27 |  |  | 2013-10-01
16 | R162000031 | High Level Brg Newaj River On Pola | Shajapur | Kalapipal | Bridge | PWD | 253.53 | 203.11 | 194.91 | 2010-08-27 |  |  | 2013-10-01
16 | R162000032 | Brg Mahan River At Deosar - Puran | Singrauli | Deosar | Bridge | PWD | 322.28 | 257.82 | 257.82 | 2010-08-27 |  |  | 2013-10-01
16 | R162000033 | Deharda Rajgha To Budhi Chanderi Rd | Ashoknagar | Chanderi | Road | PWD | 419.48 | 335.58 | 0 | 2010-08-27 |  |  | 2013-10-01
16 | R162000034 | Chanderi To Budhi Chanderi Road | Ashoknagar | Chanderi | Road | PWD | 142 | 113.6 | 92.74 | 2010-08-27 |  |  | 2013-10-01
16 | R162000035 | Bamuriya Chhevlai Tamasha Piprai Ro | Ashoknagar | Mungaoli | Road | PWD | 288.9 | 231.12 | 228.15 | 2010-08-27 |  |  | 2013-10-01
16 | R162000036 | Ashoknagar Piprai Road To Kukaoli J | Ashoknagar | Mungaoli | Road | PWD | 437.96 | 350.37 | 350.37 | 2010-08-27 |  |  | 2013-10-01
16 | R162000037 | Bharroli To Ajileshwar Via Bhagwanp | Ashoknagar | Essagarh | Road | PWD | 438.83 | 351.06 | 320.51 | 2010-08-27 |  |  | 2013-10-01
16 | R162000038 | Khajuriyakala To Mahualampur Road | Ashoknagar | Ashoknagar | Road | PWD | 345.63 | 276.5 | 209.69 | 2010-08-27 |  |  | 2013-10-01
16 | R162000039 | Mathner To Semrahat Road | Ashoknagar | Ashoknagar | Road | PWD | 315.33 | 252.26 | 252.26 | 2010-08-27 |  |  | 2013-10-01
16 | R162000040 | Mata Mandir(Ashoknagar) Sirsi Pipra | Ashoknagar | Ashoknagar | Road | PWD | 394.05 | 315.24 | 293.9 | 2010-08-27 |  |  | 2013-10-01
16 | R162000041 | Rijoda To Kukreta Road | Ashoknagar | Ashoknagar | Road | PWD | 75.02 | 75.02 | 75.02 | 2010-08-27 |  |  | 2013-10-01
16 | R162000042 | Shadora To Kundora Road | Ashoknagar | Ashoknagar | Road | PWD | 358.08 | 286.46 | 286.46 | 2010-08-27 |  |  | 2013-10-01
16 | R162000043 | Tirodi Chakaheti Bamhni Road | Balaghat | Katangi | Road | PWD | 173.1 | 173.1 | 173.1 | 2010-08-27 |  |  | 2013-10-01
16 | R162000044 | Badpani Bhondki Goreghat | Balaghat | Katangi | Road | PWD | 133.53 | 133.53 | 87.62 | 2010-08-27 |  |  | 2013-10-01
16 | R162000045 | Sadara Bhanegaon Road | Balaghat | Lanji | Road | PWD | 71.12 | 60.9 | 60.9 | 2010-08-27 |  |  | 2013-10-01
16 | R162000046 | Upgradation Of Sadra Maneri Road | Balaghat | Lanji | Road | PWD | 171.55 | 161.24 | 107.8 | 2010-08-27 |  |  | 2013-10-01
16 | R162000047 | Morkha To Nagdeo Road | Betul | Multal | Road | PWD | 70.47 | 56.38 | 50.99 | 2010-08-27 |  |  | 2013-10-01
16 | R162000050 | Berasia Sironj Road To Megra Kalan | Bhopal | Berasia | Road | PWD | 749.57 | 672.92 | 635.15 | 2010-08-27 |  |  | 2013-10-01
16 | R162000051 | Berasia To Garah Kalan | Bhopal | Berasia | Road | PWD | 548.6 | 488.65 | 471.35 | 2010-08-27 |  |  | 2013-10-01
16 | R162000052 | Construction Of Chichkheda Nandanwa | Chhindwara | Pardhurna | Road | PWD | 276.23 | 276.23 | 276.23 | 2010-08-27 |  |  | 2013-10-01
16 | R162000053 | Construction Of Badchicholidhana Sa | Chhindwara | Sausar | Road | PWD | 139.47 | 139.47 | 139.466 | 2010-08-27 |  |  | 2013-10-01
16 | R162000054 | Construction Of Sawajpani Pandhari | Chhindwara | Sausar | Road | PWD | 181.04 | 156.45 | 155.08 | 2010-08-27 |  |  | 2013-10-01
16 | R162000055 | Waghoda Lodhikheda Road | Chhindwara | Sausar | Road | PWD | 160.88 | 160.88 | 160.88 | 2010-08-27 |  |  | 2013-10-01
16 | R162000056 | Construction Of Wadegaon Kalamgaon | Chhindwara | Pardhurna | Road | PWD | 95 | 88.85 | 88.57 | 2010-08-27 |  |  | 2013-10-01
16 | R162000057 | Karanpipariya To Guddam Road | Chhindwara | Jamai | Road | PWD | 162.71 | 152.38 | 148.64 | 2010-08-27 |  |  | 2013-10-01
16 | R162000058 | Sonakhar Khutiya Road | Chhindwara | Chhindwara | Road | PWD | 296.51 | 237.21 | 237.208 | 2010-08-27 |  |  | 2013-10-01
16 | R162000059 | Construction Of Chhinda(Chhindwara | Chhindwara | Amarwara | Road | PWD | 128.59 | 108.96 | 91.96 | 2010-08-27 |  |  | 2013-10-01
16 | R162000060 | Garreh Basan Harduwa Road | Damoh | Hatta | Road | PWD | 230.2 | 184.16 | 165.03 | 2010-08-27 |  |  | 2013-10-01
16 | R162000061 | Construction Of Ajitpur Khamaria Ro | Damoh | Tendukheda | Road | PWD | 97.78 | 97.78 | 86.94 | 2010-08-27 |  |  | 2013-10-01
16 | R162000062 | Construction Of Rusalli Sojna Shika | Damoh | Patera | Road | PWD | 233.08 | 233.08 | 233.084 | 2010-08-27 |  |  | 2013-10-01
16 | R162000063 | Rajpura Chouraiya Shahgarh Road | Damoh | Hatta | Road | PWD | 669.07 | 535.26 | 321.03 | 2010-08-27 |  |  | 2013-10-01
16 | R162000064 | Construction Of Talgaon Hardwani Ma | Damoh | Hatta | Road | PWD | 171.39 | 171.39 | 171.39 | 2010-08-27 |  |  | 2013-10-01
16 | R162000065 | Construction Of Shajapur Imlidol Ro | Damoh | Tendukheda | Road | PWD | 176.9 | 167.12 | 167.116 | 2010-08-27 |  |  | 2013-10-01
16 | R162000066 | Balakot Chairai Manka Road | Damoh | Damoh | Road | PWD | 376.34 | 341.07 | 337.97 | 2010-08-27 |  |  | 2013-10-01
16 | R162000067 | Hatta Ghuraghat Pandajhir Road | Damoh | Batiagarh | Road | PWD | 109.51 | 109.51 | 109.51 | 2010-08-27 |  |  | 2013-10-01
16 | R162000068 | Halgaj Hinota Barkhera Ballarpur Ro | Damoh | Damoh | Road | PWD | 409.11 | 346.09 | 317.12 | 2010-08-27 |  |  | 2013-10-01
16 | R162000069 | Bakayan Piprodha Sakatpur Riyana Sa | Damoh | Batiyagarh | Road | PWD | 472.96 | 390.37 | 365.65 | 2010-08-27 |  |  | 2013-10-01
16 | R162000070 | Bansa Tarkheda Basni Road | Damoh | Damoh | Road | PWD | 139.37 | 128.66 | 111.65 | 2010-08-27 |  |  | 2013-10-01
16 | R162000071 | Hathna Sihora Padaria Road | Damoh | Damoh | Road | PWD | 33.77 | 33.77 | 33.77 | 2010-08-27 |  |  | 2013-10-01
16 | R162000072 | Tanda Bori Road | Dhar | Bagh | Road | PWD | 959.31 | 767.45 | 623.54 | 2010-08-27 |  |  | 2013-10-01
16 | R162000073 | Bakaner Ajanda Jotpur Karoli Ganpur | Dhar | Manawar | Road | PWD | 850.17 | 680.14 | 491.52 | 2010-08-27 |  |  | 2013-10-01
16 | R162000075 | Karhiya To Aron Via Gilarghati Road | Gwalior | Bhitarwar | Road | PWD | 586.51 | 469.21 | 155.81 | 2010-08-27 |  |  | 2013-10-01
16 | R162000076 | Construction Of Deogarh To Ratangar | Gwalior | Dabra | Road | PWD | 379.5 | 303.6 | 0 | 2010-08-27 |  |  | 2013-10-01
16 | R162000084 | Semiiya Chau Power Grid To Jalode R | Indore | Indore | Road | PWD | 47.41 | 47.41 | 47.41 | 2010-08-27 |  |  | 2013-10-01
16 | R162000085 | Malipura To Hasalpur Road | Indore | Mhow | Road | PWD | 169.61 | 135.69 | 135.69 | 2010-08-27 |  |  | 2013-10-01
16 | R162000086 | Laxmi Bai Nagar Chota Bangarda Bada | Indore | Debalpur | Road | PWD | 776.42 | 621.14 | 461.59 | 2010-08-27 |  |  | 2013-10-01
16 | R162000087 | Chouhan Khedi Khemna Road | Indore | Indore | Road | PWD | 93.83 | 93.83 | 93.83 | 2010-08-27 |  |  | 2013-10-01
16 | R162000088 | Attayana Kungara Jalodiya Par Limbo | Indore | Depalpur | Road | PWD | 262.19 | 209.75 | 209.75 | 2010-08-27 |  |  | 2013-10-01
16 | R162000089 | Agra Nevri Junction To Piploda Jalo | Indore | Depalpur | Road | PWD | 362.6 | 290.08 | 252.01 | 2010-08-27 |  |  | 2013-10-01
16 | R162000090 | Gangajakhedi Chimankhedi Banediya R | Indore | Depalpur | Road | PWD | 282.31 | 225.85 | 157.78 | 2010-08-27 |  |  | 2013-10-01
16 | R162000091 | Semda Renganwas Arodakot Pemalpur T | Indore | Depalpur | Road | PWD | 422.6 | 338.08 | 245.2 | 2010-08-27 |  |  | 2013-10-01
16 | R162000093 | Neemuch Singouli Road(Pipalikheda) | Neemuch | Javad | Road | PWD | 413.19 | 413.19 | 413.19 | 2010-08-27 |  |  | 2013-10-01
16 | R162000096 | Pachoremachalpur Road To Raipuriya | Rajgarh | Sarangpur | Road | PWD | 209.18 | 209.18 | 209.18 | 2010-08-27 |  |  | 2013-10-01
16 | R162000097 | Chikli Sakad Road | Ratlam | Bajna | Road | PWD | 165.62 | 137.3 | 98.45 | 2010-08-27 |  |  | 2013-10-01
16 | R162000098 | Deori - Raisen Road | Sagar | Deori | Road | PWD | 359.86 | 359.86 | 359.858 | 2010-08-27 |  |  | 2013-10-01
16 | R162000099 | Sanjay Drive Kanera Dev Road | Sagar | Sagar | Road | PWD | 103.99 | 103.99 | 103.99 | 2010-08-27 |  |  | 2013-10-01
16 | R162000100 | NH 26 To Devri Road | Sagar | Sagar | Road | PWD | 314.53 | 314.53 | 340.53 | 2010-08-27 |  |  | 2013-10-01
16 | R162000101 | Sagar Bye Pass Road Gadoli Bangwan | Sagar | Sagar | Road | PWD | 186.61 | 173.34 | 144.04 | 2010-08-27 |  |  | 2013-10-01
16 | R162000102 | Bamnora Tigadda Ramchhayari Person | Sagar | Malthone | Road | PWD | 139.31 | 139.31 | 139.31 | 2010-08-27 |  |  | 2013-10-01
16 | R162000103 | Missing Link Shahpur To Pathariya R | Sagar | Sagar | Road | PWD | 91.31 | 76.25 | 63.26 | 2010-08-27 |  |  | 2013-10-01
16 | R162000104 | Sadar Gayaganj Shyampura Garpehara | Sagar | Sagar | Road | PWD | 311.05 | 274.73 | 274.73 | 2010-08-27 |  |  | 2013-10-01
16 | R162000105 | Aamet Rajuya Badona Road | Sagar | Sagar | Road | PWD | 243.25 | 243.16 | 198.42 | 2010-08-27 |  |  | 2013-10-01
16 | R162000106 | Berkheri Mohali Tinsua Road | Sagar | Sagar | Road | PWD | 254.5 | 241.29 | 184.6 | 2010-08-27 |  |  | 2013-10-01
16 | R162000107 | Makronia 10th Batalian Narwani Bamh | Sagar | Naryawali | Road | PWD | 212.97 | 212.97 | 212.97 | 2010-08-27 |  |  | 2013-10-01
16 | R162000108 | Padrai Bansa Mahukheda Karhad Road | Sagar | Jaisingar | Road | PWD | 472.24 | 393.79 | 295.73 | 2010-08-27 |  |  | 2013-10-01
16 | R162000109 | Khurai Thwari App. Road | Sagar | Jaisingar | Road | PWD | 238.7 | 238.7 | 189.31 | 2010-08-27 |  |  | 2013-10-01
16 | R162000110 | Bansa Singarchori Dhakari Road | Sagar | Jaisingar | Road | PWD | 240.44 | 240.44 | 240.44 | 2010-08-27 |  |  | 2013-10-01
16 | R162000111 | Semradangi To Atraliya Jetli Baradi | Sehore | Sehore | Road | PWD | 372.12 | 309.27 | 239.61 | 2010-08-27 |  |  | 2013-10-01
16 | R162000112 | Thikari To Kusumkheda Road | Sehore | Budni | Road | PWD | 113.89 | 91.11 | 91.11 | 2010-08-27 |  |  | 2013-10-01
16 | R162000113 | Mandi Neelkanth Road | Sehore | Nasrulganj | Road | PWD | 152.5 | 122 | 122 | 2010-08-27 |  |  | 2013-10-01
16 | R162000114 | Dova To Vashudev Road | Sehore | Najrullaganj | Road | PWD | 132.35 | 105.88 | 54.23 | 2010-08-27 |  |  | 2013-10-01
16 | R162000115 | Kalwana Canal To Jholiyapur Via Nar | Sehore | Budni | Road | PWD | 295.52 | 295.52 | 295.52 | 2010-08-27 |  |  | 2013-10-01
16 | R162000116 | Amon To Silgena Road | Sehore | Budni | Road | PWD | 55.2 | 44.16 | 44.16 | 2010-08-27 |  |  | 2013-10-01
16 | R162000117 | Amon To Sagpur Road | Sehore | Budni | Road | PWD | 116.35 | 93.08 | 93.08 | 2010-08-27 |  |  | 2013-10-01
16 | R162000118 | Aroliya To Kurawar Road | Sehore | Ashta | Road | PWD | 180.07 | 180.07 | 180.07 | 2010-08-27 |  |  | 2013-10-01
16 | R162000119 | Construction Of Saliya Devli Road I | Shajapur | Shujalpur | Road | PWD | 80.44 | 80.44 | 78.07 | 2010-08-27 |  |  | 2013-10-01
16 | R162000120 | Construction Of Mansaya Semliya Bad | Shajapur | Kalapipal | Road | PWD | 151.75 | 151.75 | 151.75 | 2010-08-27 |  |  | 2013-10-01
16 | R162000121 | Construction Of Barod Susner Road | Shajapur | Barod | Road | PWD | 357.62 | 357.62 | 214.24 | 2010-08-27 |  |  | 2013-10-01
16 | R162000122 | Construction Of Takhla Payali Mana | Shajapur | Nalkheda | Road | PWD | 166.84 | 154.52 | 154.52 | 2010-08-27 |  |  | 2013-10-01
16 | R162000124 | Construction Of Poaykala To Khatsoo | Shajapur | Shujalpur | Road | PWD | 94.83 | 94.83 | 94.83 | 2010-08-27 |  |  | 2013-10-01
16 | R162000125 | Construction Of Kalapipal Kurawar R | Shajapur | Shujalpur | Road | PWD | 160.23 | 160.23 | 145.62 | 2010-08-27 |  |  | 2013-10-01
16 | R162000126 | Saint Pal Convent School Kanipura T | Ujjain | Ghatia | Road | PWD | 583.3 | 583.3 | 583.3 | 2010-08-27 |  |  | 2013-10-01
16 | R162000127 | Bisalkhedi App. Road | Ujjain | Badnagar | Road | PWD | 207.87 | 166.3 | 116.93 | 2010-08-27 |  |  | 2013-10-01
16 | R162000128 | Kiloli To Lakhesara Road | Ujjain | Badnagar | Road | PWD | 318.36 | 254.69 | 201.66 | 2010-08-27 |  |  | 2013-10-01
16 | R162000130 | Sothiya Ahmadpur Road Via Pasora Ro | Vidisha | Vidisha | Road | PWD | 291.08 | 241.9 | 133.96 | 2010-08-27 |  |  | 2013-10-01
16 | R162000131 | Construction Of Durang Dhamaukhedi | Vidisha | Sironj | Road | PWD | 576.41 | 461.13 | 278.64 | 2010-08-27 |  |  | 2013-10-01
16 | R162000133 | Badi Ukawat To Mundela Road | Vidisha | Lateri | Road | PWD | 226.32 | 214.22 | 214.216 | 2010-08-27 |  |  | 2013-10-01
16 | R162000134 | Mahoti Jhukerumaria Jarsena Dugraua | Vidisha | Lateri | Road | PWD | 646.42 | 517.14 | 318.26 | 2010-08-27 |  |  | 2013-10-01
16 | R162000135 | Construction Of Puragusai Ghatera P | Vidisha | Gyaraspur | Road | PWD | 286.53 | 262.42 | 183.22 | 2010-08-27 |  |  | 2013-10-01
16 | R162000136 | Berkhedi Approach Road | Vidisha | Ganj basoda | Road | PWD | 125.08 | 125.08 | 125.08 | 2010-08-27 |  |  | 2013-10-01
16 | R162000138 | Pench Diiversion Project (Unit-I-H/W) | Chindwara | Chourai | MJP | WRD | 59313.86 | 42261.12 | 42261.12 | 2010-11-08 |  |  | 2015-12-31 | ongoing
16 | R162000139 | Primary Health Centre | Badwani | Silawad | Health | DHFW | 70 | 59.5 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000140 | Primary Health Centre | Betul | Athner | Health | DHFW | 70 | 59.5 | 59.5 | 2011-01-31 |  |  | 2014-03-03
16 | R162000141 | Primary Health Centre | Betul | Ghodadongri | Health | DHFW | 70 | 59.5 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000142 | Primary Health Centre | Betul | Ghodadongri | Health | DHFW | 70 | 59.5 | 59.5 | 2011-01-31 |  |  | 2014-03-03
16 | R162000143 | Primary Health Centre | Betul | Bhimpur | Health | DHFW | 70 | 59.5 | 38.9 | 2011-01-31 |  |  | 2014-03-03
16 | R162000144 | Primary Health Centre | Dhar | Naalcha | Health | DHFW | 70 | 59.5 | 59.5 | 2011-01-31 |  |  | 2014-03-03
16 | R162000145 | Primary Health Centre | Dhar | Badnawar | Health | DHFW | 70 | 59.5 | 48.76 | 2011-01-31 |  |  | 2014-03-03
16 | R162000146 | Primary Health Centre | Dindori | Bajag | Health | DHFW | 70 | 59.5 | 10.12 | 2011-01-31 |  |  | 2014-03-03
16 | R162000147 | Primary Health Centre | Katni | Rithi | Health | DHFW | 70 | 59.5 | 33.75 | 2011-01-31 |  |  | 2014-03-03
16 | R162000148 | Primary Health Centre | Katni | Umariapaan | Health | DHFW | 70 | 59.5 | 32.39 | 2011-01-31 |  |  | 2014-03-03
16 | R162000149 | Primary Health Centre | Katni | Umariapaan | Health | DHFW | 70 | 59.5 | 20.02 | 2011-01-31 |  |  | 2014-03-03
16 | R162000150 | Primary Health Centre | Khandwa | Khandwa | Health | DHFW | 70 | 59.5 | 38.87 | 2011-01-31 |  |  | 2014-03-03
16 | R162000151 | Primary Health Centre | Khandwa | Chhaigaonmakh | Health | DHFW | 70 | 59.5 | 59.5 | 2011-01-31 |  |  | 2014-03-03
16 | R162000152 | Primary Health Centre | Khandwa | Khandwa | Health | DHFW | 70 | 59.5 | 58.19 | 2011-01-31 |  |  | 2014-03-03
16 | R162000153 | Primary Health Centre | Khargone | Bhagwanpura | Health | DHFW | 70 | 59.5 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000154 | Primary Health Centre | Khargone | Maheshwar | Health | DHFW | 70 | 59.5 | 59.5 | 2011-01-31 |  |  | 2014-03-03
16 | R162000155 | Primary Health Centre | Khargone | Segaon | Health | DHFW | 70 | 59.5 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000156 | Primary Health Centre | Khargone | Maheshwar | Health | DHFW | 70 | 59.5 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000157 | Primary Health Centre | Khargone | Bhagwanpura | Health | DHFW | 70 | 59.5 | 59.5 | 2011-01-31 |  |  | 2014-03-03
16 | R162000158 | Primary Health Centre | Mandsaur | Garoth | Health | DHFW | 70 | 59.5 | 59.51 | 2011-01-31 |  |  | 2014-03-03
16 | R162000159 | Primary Health Centre | Mandsaur | Malhargadh | Health | DHFW | 70 | 59.5 | 59.51 | 2011-01-31 |  |  | 2014-03-03
16 | R162000160 | Primary Health Centre | Mandsaur | Malhargadh | Health | DHFW | 70 | 59.5 | 59.51 | 2011-01-31 |  |  | 2014-03-03
16 | R162000161 | Primary Health Centre | Mandsaur | Malhargadh | Health | DHFW | 70 | 59.5 | 59.51 | 2011-01-31 |  |  | 2014-03-03
16 | R162000162 | Primary Health Centre | Panna | Pawai | Health | DHFW | 70 | 59.5 | 52.41 | 2011-01-31 |  |  | 2014-03-03
16 | R162000163 | Primary Health Centre | Panna | Pawai | Health | DHFW | 70 | 59.5 | 59.5 | 2011-01-31 |  |  | 2014-03-03
16 | R162000164 | Primary Health Centre | Satna | Amarpatan | Health | DHFW | 70 | 59.5 | 59.49 | 2011-01-31 |  |  | 2014-03-03
16 | R162000165 | Primary Health Centre | Satna | Amarpatan | Health | DHFW | 70 | 59.5 | 40.98 | 2011-01-31 |  |  | 2014-03-03
16 | R162000166 | Primary Health Centre | Sehore | Ichhawar | Health | DHFW | 70 | 59.5 | 59.5 | 2011-01-31 |  |  | 2014-03-03
16 | R162000167 | Primary Health Centre | Shahdol | Beohari | Health | DHFW | 70 | 59.5 | 59.5 | 2011-01-31 |  |  | 2014-03-03
16 | R162000168 | Primary Health Centre | Shajapur | Moman Badodia | Health | DHFW | 70 | 59.5 | 59.5 | 2011-01-31 |  |  | 2014-03-03
16 | R162000169 | Primary Health Centre | Shajapur | Shajapur | Health | DHFW | 70 | 59.5 | 59.5 | 2011-01-31 |  |  | 2014-03-03
16 | R162000170 | Sub Health Centre | Badwani | Sendhva | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000171 | Sub Health Centre | Badwani | Sendhva | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000172 | Sub Health Centre | Badwani | Sendhva | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000173 | Sub Health Centre | Badwani | Sendhva | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000174 | Sub Health Centre | Badwani | Sendhva | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000175 | Sub Health Centre | Badwani | Sendhva | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000176 | Sub Health Centre | Badwani | Sendhva | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000177 | Sub Health Centre | Badwani | Sendhva | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000178 | Sub Health Centre | Badwani | Sendhva | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000179 | Sub Health Centre | Badwani | Sendhva | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000180 | Sub Health Centre | Balaghat | Balaghat | Health | DHFW | 12 | 10.2 | 7.25 | 2011-01-31 |  |  | 2014-03-03
16 | R162000181 | Sub Health Centre | Balaghat | Balghat | Health | DHFW | 12 | 10.2 | 8.19 | 2011-01-31 |  |  | 2014-03-03
16 | R162000182 | Sub Health Centre | Balaghat | Kirnapur | Health | DHFW | 12 | 10.2 | 5.79 | 2011-01-31 |  |  | 2014-03-03
16 | R162000183 | Sub Health Centre | Balaghat | Kirnapur | Health | DHFW | 12 | 10.2 | 8.61 | 2011-01-31 |  |  | 2014-03-03
16 | R162000184 | Sub Health Centre | Balaghat | Kirnapur | Health | DHFW | 12 | 10.2 | 10 | 2011-01-31 |  |  | 2014-03-03
16 | R162000185 | Sub Health Centre | Balaghat | Katangi | Health | DHFW | 12 | 10.2 | 6.51 | 2011-01-31 |  |  | 2014-03-03
16 | R162000186 | Sub Health Centre | Balaghat | Katangi | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000187 | Sub Health Centre | Balaghat | Katangi | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000188 | Sub Health Centre | Balaghat | Katangi | Health | DHFW | 12 | 10.2 | 5.53 | 2011-01-31 |  |  | 2014-03-03
16 | R162000189 | Sub Health Centre | Balaghat | Katangi | Health | DHFW | 12 | 10.2 | 9.12 | 2011-01-31 |  |  | 2014-03-03
16 | R162000190 | Sub Health Centre | Tikamgarh | Tikamgarh | Health | DHFW | 12 | 10.2 | 4.74 | 2011-01-31 |  |  | 2014-03-03
16 | R162000191 | Sub Health Centre | Tikamgarh | Baldevgarh | Health | DHFW | 12 | 10.2 | 9.22 | 2011-01-31 |  |  | 2014-03-03
16 | R162000192 | Sub Health Centre | Tikamgarh | Nivadi | Health | DHFW | 12 | 10.2 | 5.32 | 2011-01-31 |  |  | 2014-03-03
16 | R162000193 | Sub Health Centre | Tikamgarh | Prithvipur | Health | DHFW | 12 | 10.2 | 9.62 | 2011-01-31 |  |  | 2014-03-03
16 | R162000194 | Sub Health Centre | Tikamgarh | Jatara | Health | DHFW | 12 | 10.2 | 7.99 | 2011-01-31 |  |  | 2014-03-03
16 | R162000195 | Sub Health Centre | Tikamgarh | Palera | Health | DHFW | 12 | 10.2 | 9.55 | 2011-01-31 |  |  | 2014-03-03
16 | R162000196 | Sub Health Centre | Burhanpur | Burhanpur | Health | DHFW | 12 | 10.2 | 9.82 | 2011-01-31 |  |  | 2014-03-03
16 | R162000197 | Sub Health Centre | Burhanpur | Burhanpur | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000198 | Sub Health Centre | Burhanpur | Khaknar | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000199 | Sub Health Centre | Burhanpur | Khaknar | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000200 | Sub Health Centre | Burhanpur | Khaknar | Health | DHFW | 12 | 10.2 | 9.14 | 2011-01-31 |  |  | 2014-03-03
16 | R162000201 | Sub Health Centre | Burhanpur | Khaknar | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000202 | Sub Health Centre | Burhanpur | Khaknar | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000203 | Sub Health Centre | Burhanpur | Khaknar | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000204 | Sub Health Centre | Burhanpur | Khaknar | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000205 | Sub Health Centre | Burhanpur | Khaknar | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000206 | Sub Health Centre | Chhindwara | Mohkheda | Health | DHFW | 12 | 10.2 | 10.2 | 2011-01-31 |  |  | 2014-03-03
16 | R162000207 | Sub Health Centre | Chhindwara | Mohkheda | Health | DHFW | 12 | 10.2 | 8.92 | 2011-01-31 |  |  | 2014-03-03
16 | R162000208 | Sub Health Centre | Chhindwara | Pandurna | Health | DHFW | 12 | 10.2 | 9.9 | 2011-01-31 |  |  | 2014-03-03
16 | R162000209 | Sub Health Centre | Chhindwara | Pandurna | Health | DHFW | 12 | 10.2 | 5.66 | 2011-01-31 |  |  | 2014-03-03
16 | R162000210 | Sub Health Centre | Chhindwara | Pandurna | Health | DHFW | 12 | 10.2 | 9.88 | 2011-01-31 |  |  | 2014-03-03
16 | R162000211 | Sub Health Centre | Chhindwara | Parasiya | Health | DHFW | 12 | 10.2 | 9.76 | 2011-01-31 |  |  | 2014-03-03
16 | R162000212 | Sub Health Centre | Chhindwara | Parasiya | Health | DHFW | 12 | 10.2 | 10.2 | 2011-01-31 |  |  | 2014-03-03
16 | R162000213 | Sub Health Centre | Chhindwara | Parasiya | Health | DHFW | 12 | 10.2 | 9.64 | 2011-01-31 |  |  | 2014-03-03
16 | R162000214 | Sub Health Centre | Chhindwara | Parasiya | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000215 | Sub Health Centre | Chhindwara | Parasiya | Health | DHFW | 12 | 10.2 | 9.28 | 2011-01-31 |  |  | 2014-03-03
16 | R162000216 | Sub Health Centre | Dewas | Barotha | Health | DHFW | 12 | 10.2 | 10.2 | 2011-01-31 |  |  | 2014-03-03
16 | R162000217 | Sub Health Centre | Dewas | Barotha | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000218 | Sub Health Centre | Dewas | Barotha | Health | DHFW | 12 | 10.2 | 10.2 | 2011-01-31 |  |  | 2014-03-03
16 | R162000219 | Sub Health Centre | Dewas | Barotha | Health | DHFW | 12 | 10.2 | 9.44 | 2011-01-31 |  |  | 2014-03-03
16 | R162000220 | Sub Health Centre | Dewas | Kannod | Health | DHFW | 12 | 10.2 | 10.2 | 2011-01-31 |  |  | 2014-03-03
16 | R162000221 | Sub Health Centre | Dewas | Kannod | Health | DHFW | 12 | 10.2 | 10.18 | 2011-01-31 |  |  | 2014-03-03
16 | R162000222 | Sub Health Centre | Dewas | Kannod | Health | DHFW | 12 | 10.2 | 4.25 | 2011-01-31 |  |  | 2014-03-03
16 | R162000223 | Sub Health Centre | Dewas | Kannod | Health | DHFW | 12 | 10.2 | 10.2 | 2011-01-31 |  |  | 2014-03-03
16 | R162000224 | Sub Health Centre | Dewas | Kannod | Health | DHFW | 12 | 10.2 | 7.37 | 2011-01-31 |  |  | 2014-03-03
16 | R162000225 | Sub Health Centre | Dewas | Bagli | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000226 | Sub Health Centre | Dewas | Bagli | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000227 | Sub Health Centre | Dewas | Bagli | Health | DHFW | 12 | 10.2 | 10.2 | 2011-01-31 |  |  | 2014-03-03
16 | R162000228 | Sub Health Centre | Dewas | Bagli | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000229 | Sub Health Centre | Dewas | Khategaon | Health | DHFW | 12 | 10.2 | 8.74 | 2011-01-31 |  |  | 2014-03-03
16 | R162000230 | Sub Health Centre | Dindori | Dindori | Health | DHFW | 12 | 10.2 | 9.49 | 2011-01-31 |  |  | 2014-03-03
16 | R162000231 | Sub Health Centre | Dindori | Dindori | Health | DHFW | 12 | 10.2 | 9.38 | 2011-01-31 |  |  | 2014-03-03
16 | R162000232 | Sub Health Centre | Dindori | Dindori | Health | DHFW | 12 | 10.2 | 9.15 | 2011-01-31 |  |  | 2014-03-03
16 | R162000233 | Sub Health Centre | Dindori | Dindori | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000234 | Sub Health Centre | Dindori | Dindori | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000235 | Sub Health Centre | Dindori | Kranjiya | Health | DHFW | 12 | 10.2 | 7.19 | 2011-01-31 |  |  | 2014-03-03
16 | R162000236 | Sub Health Centre | Dindori | Kranjiya | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000237 | Sub Health Centre | Dindori | Kranjiya | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000238 | Sub Health Centre | Dindori | Kranjiya | Health | DHFW | 12 | 10.2 | 7.52 | 2011-01-31 |  |  | 2014-03-03
16 | R162000239 | Sub Health Centre | Dindori | Kranjiya | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000240 | Sub Health Centre | Jhabua | Petlavad | Health | DHFW | 12 | 10.2 | 9.16 | 2011-01-31 |  |  | 2014-03-03
16 | R162000241 | Sub Health Centre | Jhabua | Petlavad | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000242 | Sub Health Centre | Jhabua | Petlavad | Health | DHFW | 12 | 10.2 | 8.63 | 2011-01-31 |  |  | 2014-03-03
16 | R162000243 | Sub Health Centre | Jhabua | Petlavad | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000244 | Sub Health Centre | Jhabua | Petlavad | Health | DHFW | 12 | 10.2 | 8.35 | 2011-01-31 |  |  | 2014-03-03
16 | R162000245 | Sub Health Centre | Jhabua | Petlavad | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000246 | Sub Health Centre | Jhabua | Thandla | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000247 | Sub Health Centre | Jhabua | Thandla | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000248 | Sub Health Centre | Jhabua | Thandla | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000249 | Sub Health Centre | Jhabua | Thandla | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000250 | Sub Health Centre | Katni | Umariyapan | Health | DHFW | 12 | 10.2 | 8.34 | 2011-01-31 |  |  | 2014-03-03
16 | R162000251 | Sub Health Centre | Katni | Umariyapan | Health | DHFW | 12 | 10.2 | 8.2 | 2011-01-31 |  |  | 2014-03-03
16 | R162000252 | Sub Health Centre | Katni | Umariyapan | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000253 | Sub Health Centre | Katni | Umariyapan | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000254 | Sub Health Centre | Katni | Umariyapan | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000255 | Sub Health Centre | Katni | Rithi | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000256 | Sub Health Centre | Katni | Rithi | Health | DHFW | 12 | 10.2 | 8.62 | 2011-01-31 |  |  | 2014-03-03
16 | R162000257 | Sub Health Centre | Katni | Rithi | Health | DHFW | 12 | 10.2 | 8 | 2011-01-31 |  |  | 2014-03-03
16 | R162000258 | Sub Health Centre | Katni | Kanhvara | Health | DHFW | 12 | 10.2 | 8.55 | 2011-01-31 |  |  | 2014-03-03
16 | R162000259 | Sub Health Centre | Katni | Kanhvara | Health | DHFW | 12 | 10.2 | 8.08 | 2011-01-31 |  |  | 2014-03-03
16 | R162000260 | Sub Health Centre | Khargone | Maheshwar | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000261 | Sub Health Centre | Khargone | Maheshwar | Health | DHFW | 12 | 10.2 | 8.85 | 2011-01-31 |  |  | 2014-03-03
16 | R162000262 | Sub Health Centre | Khargone | Maheshwar | Health | DHFW | 12 | 10.2 | 8.72 | 2011-01-31 |  |  | 2014-03-03
16 | R162000263 | Sub Health Centre | Khargone | Maheshwar | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000264 | Sub Health Centre | Khargone | Jhiranya | Health | DHFW | 12 | 10.2 | 9.13 | 2011-01-31 |  |  | 2014-03-03
16 | R162000265 | Sub Health Centre | Khargone | Seganwa | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000266 | Sub Health Centre | Khargone | Seganwa | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000267 | Sub Health Centre | Khargone | Seganwa | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000268 | Sub Health Centre | Khargone | Seganwa | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000269 | Sub Health Centre | Khargone | Seganwa | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000270 | Sub Health Centre | Mandsaur | Mandsaur | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000271 | Sub Health Centre | Mandsaur | Mandsaur | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000272 | Sub Health Centre | Mandsaur | Mandsaur | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000273 | Sub Health Centre | Mandsaur | Mandsaur | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000274 | Sub Health Centre | Mandsaur | Mandsaur | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000275 | Sub Health Centre | Mandsaur | Malhargad | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000276 | Sub Health Centre | Mandsaur | Malhargad | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000277 | Sub Health Centre | Mandsaur | Malhargad | Health | DHFW | 12 | 10.2 | 8.05 | 2011-01-31 |  |  | 2014-03-03
16 | R162000278 | Sub Health Centre | Mandsaur | Malhargad | Health | DHFW | 12 | 10.2 | 8.98 | 2011-01-31 |  |  | 2014-03-03
16 | R162000279 | Sub Health Centre | Mandsaur | Malhargad | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000280 | Sub Health Centre | Mandla | Bichhiya | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000281 | Sub Health Centre | Mandla | Bichhiya | Health | DHFW | 12 | 10.2 | 9.95 | 2011-01-31 |  |  | 2014-03-03
16 | R162000282 | Sub Health Centre | Mandla | Bichhiya | Health | DHFW | 12 | 10.2 | 9.28 | 2011-01-31 |  |  | 2014-03-03
16 | R162000283 | Sub Health Centre | Mandla | Bichhiya | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000284 | Sub Health Centre | Mandla | Bichhiya | Health | DHFW | 12 | 10.2 | 9.31 | 2011-01-31 |  |  | 2014-03-03
16 | R162000285 | Sub Health Centre | Mandla | Bamhani | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000286 | Sub Health Centre | Mandla | Bamhani | Health | DHFW | 12 | 10.2 | 5.76 | 2011-01-31 |  |  | 2014-03-03
16 | R162000287 | Sub Health Centre | Mandla | Bamhani | Health | DHFW | 12 | 10.2 | 6.43 | 2011-01-31 |  |  | 2014-03-03
16 | R162000288 | Sub Health Centre | Mandla | Bamhani | Health | DHFW | 12 | 10.2 | 5.56 | 2011-01-31 |  |  | 2014-03-03
16 | R162000289 | Sub Health Centre | Mandla | Bamhani | Health | DHFW | 12 | 10.2 | 6.31 | 2011-01-31 |  |  | 2014-03-03
16 | R162000290 | Sub Health Centre | Ashoknagar | Ashoknagar | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000291 | Sub Health Centre | Ashoknagar | Ashoknagar | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000292 | Sub Health Centre | Ashoknagar | Ashoknagar | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000293 | Sub Health Centre | Ashoknagar | Ashoknagar | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000294 | Sub Health Centre | Ashoknagar | Ashoknagar | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000295 | Sub Health Centre | Ashoknagar | Ashoknagar | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000296 | Sub Health Centre | Ashoknagar | Ashoknagar | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000297 | Sub Health Centre | Ashoknagar | Ashoknagar | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000298 | Sub Health Centre | Ashoknagar | Ashoknagar | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000299 | Sub Health Centre | Ashoknagar | Ashoknagar | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000300 | Sub Health Centre | Ashoknagar | Mungoli | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000301 | Sub Health Centre | Ashoknagar | Mungoli | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000302 | Sub Health Centre | Ashoknagar | Mungoli | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000303 | Sub Health Centre | Bhind | Bhind | Health | DHFW | 12 | 10.2 | 9.21 | 2011-01-31 |  |  | 2014-03-03
16 | R162000304 | Sub Health Centre | Bhind | Bhind | Health | DHFW | 12 | 10.2 | 5.1 | 2011-01-31 |  |  | 2014-03-03
16 | R162000305 | Sub Health Centre | Bhind | Bhind | Health | DHFW | 12 | 10.2 | 7.94 | 2011-01-31 |  |  | 2014-03-03
16 | R162000306 | Sub Health Centre | Bhind | Bhind | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000307 | Sub Health Centre | Bhind | Bhind | Health | DHFW | 12 | 10.2 | 9.95 | 2011-01-31 |  |  | 2014-03-03
16 | R162000308 | Sub Health Centre | Bhind | Bhind | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000309 | Sub Health Centre | Bhind | Bhind | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000310 | Sub Health Centre | Bhind | Bhind | Health | DHFW | 12 | 10.2 | 9.38 | 2011-01-31 |  |  | 2014-03-03
16 | R162000311 | Sub Health Centre | Bhind | Bhind | Health | DHFW | 12 | 10.2 | 5.1 | 2011-01-31 |  |  | 2014-03-03
16 | R162000312 | Sub Health Centre | Bhind | Lahaar | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000313 | Sub Health Centre | Bhind | Ater | Health | DHFW | 12 | 10.2 | 10.11 | 2011-01-31 |  |  | 2014-03-03
16 | R162000314 | Sub Health Centre | Bhind | Ater | Health | DHFW | 12 | 10.2 | 9.43 | 2011-01-31 |  |  | 2014-03-03
16 | R162000315 | Sub Health Centre | Bhind | Ater | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000316 | Sub Health Centre | Bhind | Ater | Health | DHFW | 12 | 10.2 | 9.82 | 2011-01-31 |  |  | 2014-03-03
16 | R162000317 | Sub Health Centre | Bhind | Ater | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000318 | Sub Health Centre | Panna | Ajaygad | Health | DHFW | 12 | 10.2 | 9.54 | 2011-01-31 |  |  | 2014-03-03
16 | R162000319 | Sub Health Centre | Panna | Devendragad | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000320 | Sub Health Centre | Panna | Amangunj | Health | DHFW | 12 | 10.2 | 9.38 | 2011-01-31 |  |  | 2014-03-03
16 | R162000321 | Sub Health Centre | Panna | Pawai | Health | DHFW | 12 | 10.2 | 9.41 | 2011-01-31 |  |  | 2014-03-03
16 | R162000322 | Sub Health Centre | Panna | Shahnagar | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000323 | Sub Health Centre | Datia | Indrergad | Health | DHFW | 12 | 10.2 | 10.2 | 2011-01-31 |  |  | 2014-03-03
16 | R162000324 | Sub Health Centre | Datia | Indrergad | Health | DHFW | 12 | 10.2 | 10.2 | 2011-01-31 |  |  | 2014-03-03
16 | R162000325 | Sub Health Centre | Datia | Indrergad | Health | DHFW | 12 | 10.2 | 10.2 | 2011-01-31 |  |  | 2014-03-03
16 | R162000326 | Sub Health Centre | Datia | Indrergad | Health | DHFW | 12 | 10.2 | 10.06 | 2011-01-31 |  |  | 2014-03-03
16 | R162000327 | Sub Health Centre | Datia | Indrergad | Health | DHFW | 12 | 10.2 | 10.2 | 2011-01-31 |  |  | 2014-03-03
16 | R162000328 | Sub Health Centre | Datia | Bhander | Health | DHFW | 12 | 10.2 | 9.89 | 2011-01-31 |  |  | 2014-03-03
16 | R162000329 | Sub Health Centre | Datia | Bhander | Health | DHFW | 12 | 10.2 | 10.2 | 2011-01-31 |  |  | 2014-03-03
16 | R162000330 | Sub Health Centre | Datia | Bhander | Health | DHFW | 12 | 10.2 | 9.61 | 2011-01-31 |  |  | 2014-03-03
16 | R162000331 | Sub Health Centre | Datia | Bhander | Health | DHFW | 12 | 10.2 | 10.2 | 2011-01-31 |  |  | 2014-03-03
16 | R162000332 | Sub Health Centre | Datia | Bhander | Health | DHFW | 12 | 10.2 | 10.2 | 2011-01-31 |  |  | 2014-03-03
16 | R162000333 | Sub Health Centre | Dhar | Dahi | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000334 | Sub Health Centre | Dhar | Dahi | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000335 | Sub Health Centre | Dhar | Kukasi | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000336 | Sub Health Centre | Dhar | Manawar | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000337 | Sub Health Centre | Dhar | Manawar | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000338 | Sub Health Centre | Dhar | Nalchha | Health | DHFW | 12 | 10.2 | 7.43 | 2011-01-31 |  |  | 2014-03-03
16 | R162000339 | Sub Health Centre | Dhar | Bakaner | Health | DHFW | 12 | 10.2 | 10.2 | 2011-01-31 |  |  | 2014-03-03
16 | R162000340 | Sub Health Centre | Dhar | Manavar | Health | DHFW | 12 | 10.2 | 8.68 | 2011-01-31 |  |  | 2014-03-03
16 | R162000341 | Sub Health Centre | Dhar | Tirala | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000342 | Sub Health Centre | Dhar | Nalchha | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000343 | Sub Health Centre | Morena | Porsa | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000344 | Sub Health Centre | Morena | Khadiyar | Health | DHFW | 12 | 10.2 | 8.61 | 2011-01-31 |  |  | 2014-03-03
16 | R162000345 | Sub Health Centre | Morena | Jura | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000346 | Sub Health Centre | Morena | Kailarus | Health | DHFW | 12 | 10.2 | 8.53 | 2011-01-31 |  |  | 2014-03-03
16 | R162000347 | Sub Health Centre | Morena | Pahadgad | Health | DHFW | 12 | 10.2 | 7.08 | 2011-01-31 |  |  | 2014-03-03
16 | R162000348 | Sub Health Centre | Narsinghpur | Narsinghpur | Health | DHFW | 12 | 10.2 | 8.61 | 2011-01-31 |  |  | 2014-03-03
16 | R162000349 | Sub Health Centre | Narsinghpur | Narsinghpur | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000350 | Sub Health Centre | Narsinghpur | Narsinghpur | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000351 | Sub Health Centre | Narsinghpur | Narsinghpur | Health | DHFW | 12 | 10.2 | 9.04 | 2011-01-31 |  |  | 2014-03-03
16 | R162000352 | Sub Health Centre | Narsinghpur | Narsinghpur | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000353 | Sub Health Centre | Narsinghpur | Gotegaon | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000354 | Sub Health Centre | Narsinghpur | Gotegaon | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000355 | Sub Health Centre | Narsinghpur | Gotegaon | Health | DHFW | 12 | 10.2 | 9.89 | 2011-01-31 |  |  | 2014-03-03
16 | R162000356 | Sub Health Centre | Ratlam | Ratlam | Health | DHFW | 12 | 10.2 | 0.01 | 2011-01-31 |  |  | 2014-03-03
16 | R162000357 | Sub Health Centre | Ratlam | Ratlam | Health | DHFW | 12 | 10.2 | 0.01 | 2011-01-31 |  |  | 2014-03-03
16 | R162000358 | Sub Health Centre | Ratlam | Ratlam | Health | DHFW | 12 | 10.2 | 9.8 | 2011-01-31 |  |  | 2014-03-03
16 | R162000359 | Sub Health Centre | Ratlam | Ratlam | Health | DHFW | 12 | 10.2 | 9.05 | 2011-01-31 |  |  | 2014-03-03
16 | R162000360 | Sub Health Centre | Ratlam | Ratlam | Health | DHFW | 12 | 10.2 | 9.38 | 2011-01-31 |  |  | 2014-03-03
16 | R162000361 | Sub Health Centre | Ratlam | Jawara | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000362 | Sub Health Centre | Ratlam | Jawara | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000363 | Sub Health Centre | Ratlam | Jawara | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000364 | Sub Health Centre | Ratlam | Jawara | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000365 | Sub Health Centre | Ratlam | Bajna | Health | DHFW | 12 | 10.2 | 10.2 | 2011-01-31 |  |  | 2014-03-03
16 | R162000366 | Sub Health Centre | Shajapur | Shajapur | Health | DHFW | 12 | 10.2 | 9.97 | 2011-01-31 |  |  | 2014-03-03
16 | R162000367 | Sub Health Centre | Shajapur | Shajapur | Health | DHFW | 12 | 10.2 | 9.87 | 2011-01-31 |  |  | 2014-03-03
16 | R162000368 | Sub Health Centre | Shajapur | Shajapur | Health | DHFW | 12 | 10.2 | 5.87 | 2011-01-31 |  |  | 2014-03-03
16 | R162000369 | Sub Health Centre | Shajapur | Shajapur | Health | DHFW | 12 | 10.2 | 9.8 | 2011-01-31 |  |  | 2014-03-03
16 | R162000370 | Sub Health Centre | Shajapur | Kalapipal | Health | DHFW | 12 | 10.2 | 9.9 | 2011-01-31 |  |  | 2014-03-03
16 | R162000371 | Sub Health Centre | Shajapur | Shajapur | Health | DHFW | 12 | 10.2 | 10.2 | 2011-01-31 |  |  | 2014-03-03
16 | R162000372 | Sub Health Centre | Shajapur | Shajapur | Health | DHFW | 12 | 10.2 | 10.2 | 2011-01-31 |  |  | 2014-03-03
16 | R162000373 | Sub Health Centre | Shajapur | Shajapur | Health | DHFW | 12 | 10.2 | 9.49 | 2011-01-31 |  |  | 2014-03-03
16 | R162000374 | Sub Health Centre | Shajapur | Shajapur | Health | DHFW | 12 | 10.2 | 9.66 | 2011-01-31 |  |  | 2014-03-03
16 | R162000375 | Sub Health Centre | Shajapur | Shajapur | Health | DHFW | 12 | 10.2 | 7.6 | 2011-01-31 |  |  | 2014-03-03
16 | R162000376 | Sub Health Centre | Shajapur | Shajapur | Health | DHFW | 12 | 10.2 | 8.99 | 2011-01-31 |  |  | 2014-03-03
16 | R162000377 | Sub Health Centre | Shajapur | Shajapur | Health | DHFW | 12 | 10.2 | 10.2 | 2011-01-31 |  |  | 2014-03-03
16 | R162000378 | Sub Health Centre | Shajapur | Shujalpur | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000379 | Sub Health Centre | Shajapur | Shujalpur | Health | DHFW | 12 | 10.2 | 9.6 | 2011-01-31 |  |  | 2014-03-03
16 | R162000380 | Sub Health Centre | Ujjain | Ghatiya | Health | DHFW | 12 | 10.2 | 10.2 | 2011-01-31 |  |  | 2014-03-03
16 | R162000381 | Sub Health Centre | Ujjain | Ghatiya | Health | DHFW | 12 | 10.2 | 10.2 | 2011-01-31 |  |  | 2014-03-03
16 | R162000382 | Sub Health Centre | Ujjain | Ghatiya | Health | DHFW | 12 | 10.2 | 10.06 | 2011-01-31 |  |  | 2014-03-03
16 | R162000383 | Sub Health Centre | Ujjain | Ghatiya | Health | DHFW | 12 | 10.2 | 10.2 | 2011-01-31 |  |  | 2014-03-03
16 | R162000384 | Sub Health Centre | Ujjain | Ghatiya | Health | DHFW | 12 | 10.2 | 10.19 | 2011-01-31 |  |  | 2014-03-03
16 | R162000385 | Sub Health Centre | Ujjain | Ghatiya | Health | DHFW | 12 | 10.2 | 10.2 | 2011-01-31 |  |  | 2014-03-03
16 | R162000386 | Sub Health Centre | Ujjain | Ghatiya | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000387 | Sub Health Centre | Ujjain | Tarana | Health | DHFW | 12 | 10.2 | 10.15 | 2011-01-31 |  |  | 2014-03-03
16 | R162000388 | Sub Health Centre | Ujjain | Tarana | Health | DHFW | 12 | 10.2 | 10.2 | 2011-01-31 |  |  | 2014-03-03
16 | R162000389 | Sub Health Centre | Ujjain | Mahitpur | Health | DHFW | 12 | 10.2 | 10.2 | 2011-01-31 |  |  | 2014-03-03
16 | R162000390 | Sub Health Centre | Ujjain | Mahitpur | Health | DHFW | 12 | 10.2 | 10.2 | 2011-01-31 |  |  | 2014-03-03
16 | R162000391 | Sub Health Centre | Ujjain | Mahitpur | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000392 | Sub Health Centre | Ujjain | Mahitpur | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000393 | Sub Health Centre | Ujjain | Ujjain | Health | DHFW | 12 | 10.2 | 10.2 | 2011-01-31 |  |  | 2014-03-03
16 | R162000394 | Sub Health Centre | Ujjain | Ujjain | Health | DHFW | 12 | 10.2 | 10.2 | 2011-01-31 |  |  | 2014-03-03
16 | R162000395 | Sub Health Centre | Ujjain | Ujjain | Health | DHFW | 12 | 10.2 | 10.2 | 2011-01-31 |  |  | 2014-03-03
16 | R162000396 | Sub Health Centre | Ujjain | Ujjain | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000397 | Sub Health Centre | Seoni | Gopalganj | Health | DHFW | 12 | 10.2 | 9.87 | 2011-01-31 |  |  | 2014-03-03
16 | R162000398 | Sub Health Centre | Seoni | Gopalganj | Health | DHFW | 12 | 10.2 | 9.79 | 2011-01-31 |  |  | 2014-03-03
16 | R162000399 | Sub Health Centre | Seoni | Gopalganj | Health | DHFW | 12 | 10.2 | 8.79 | 2011-01-31 |  |  | 2014-03-03
16 | R162000400 | Sub Health Centre | Seoni | Gopalganj | Health | DHFW | 12 | 10.2 | 8.21 | 2011-01-31 |  |  | 2014-03-03
16 | R162000401 | Sub Health Centre | Seoni | Gopalganj | Health | DHFW | 12 | 10.2 | 8.63 | 2011-01-31 |  |  | 2014-03-03
16 | R162000402 | Sub Health Centre | Seoni | Gopalganj | Health | DHFW | 12 | 10.2 | 9.13 | 2011-01-31 |  |  | 2014-03-03
16 | R162000403 | Sub Health Centre | Seoni | Kurai | Health | DHFW | 12 | 10.2 | 4.05 | 2011-01-31 |  |  | 2014-03-03
16 | R162000404 | Sub Health Centre | Seoni | Kurai | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000405 | Sub Health Centre | Seoni | Berghat | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000406 | Sub Health Centre | Seoni | Berghat | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000407 | Sub Health Centre | Seoni | Dhansour | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000408 | Sub Health Centre | Seoni | Dhansour | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000409 | Sub Health Centre | Seoni | Dhansour | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000410 | Sub Health Centre | Seoni | Dhansour | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000411 | Sub Health Centre | Seoni | Dhansour | Health | DHFW | 12 | 10.2 | 9.55 | 2011-01-31 |  |  | 2014-03-03
16 | R162000412 | Sub Health Centre | Seoni | Dhansour | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000413 | Sub Health Centre | Seoni | Dhansour | Health | DHFW | 12 | 10.2 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000414 | Sub Health Centre | Rajgarh | Khichalipur | Health | DHFW | 12 | 10.2 | 9.29 | 2011-01-31 |  |  | 2014-03-03
16 | R162000415 | Sub Health Centre | Rajgarh | Ramgad | Health | DHFW | 12 | 10.2 | 9.23 | 2011-01-31 |  |  | 2014-03-03
16 | R162000416 | Sub Health Centre | Rajgarh | Ramgad | Health | DHFW | 12 | 10.2 | 9.33 | 2011-01-31 |  |  | 2014-03-03
16 | R162000417 | Sub Health Centre | Rajgarh | Karedi | Health | DHFW | 12 | 10.2 | 9.16 | 2011-01-31 |  |  | 2014-03-03
16 | R162000418 | Sub Health Centre | Rajgarh | Dhavla | Health | DHFW | 12 | 10.2 | 9.24 | 2011-01-31 |  |  | 2014-03-03
16 | R162000419 | Sub Health Centre | Rajgarh | Dhavla | Health | DHFW | 12 | 10.2 | 9.72 | 2011-01-31 |  |  | 2014-03-03
16 | R162000420 | Community Health Center | Anuppur | Pushprajgadh | Health | DHFW | 187.02 | 158.97 | 158.97 | 2011-01-31 |  |  | 2014-03-03
16 | R162000421 | Community Health Center | Ashoknagar | Shadora | Health | DHFW | 199.59 | 169.65 | 126.87 | 2011-01-31 |  |  | 2014-03-03
16 | R162000422 | Community Health Center | Badwani | Rajpur | Health | DHFW | 167.94 | 142.75 | 71.17 | 2011-01-31 |  |  | 2014-03-03
16 | R162000423 | Community Health Center | Badwani | Sendhwa | Health | DHFW | 196.42 | 166.96 | 81.59 | 2011-01-31 |  |  | 2014-03-03
16 | R162000424 | Community Health Center | Badwani | Silawad | Health | DHFW | 172.3 | 146.46 | 75.02 | 2011-01-31 |  |  | 2014-03-03
16 | R162000425 | Community Health Center | Balaghat | Waraseoni | Health | DHFW | 149.6 | 127.16 | 108.39 | 2011-01-31 |  |  | 2014-03-03
16 | R162000426 | Community Health Center | Betul | Betul | Health | DHFW | 184.37 | 156.71 | 156.7 | 2011-01-31 |  |  | 2014-03-03
16 | R162000427 | Community Health Center | Chhatarpur | Chhatarpur | Health | DHFW | 176.3 | 149.86 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000428 | Community Health Center | Chhatarpur | Bijawar | Health | DHFW | 180.13 | 153.11 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000429 | Community Health Center | Datia | Seondha | Health | DHFW | 181.25 | 154.06 | 106.23 | 2011-01-31 |  |  | 2014-03-03
16 | R162000430 | Community Health Center | Datia | Datia | Health | DHFW | 152.95 | 130.01 | 130.01 | 2011-01-31 |  |  | 2014-03-03
16 | R162000431 | Community Health Center | Damoh | Damoh | Health | DHFW | 169.11 | 143.74 | 143.19 | 2011-01-31 |  |  | 2014-03-03
16 | R162000432 | Community Health Center | Dewas | Kannod | Health | DHFW | 216.16 | 183.74 | 183.72 | 2011-01-31 |  |  | 2014-03-03
16 | R162000433 | Community Health Center | Dhar | Sardarpur | Health | DHFW | 146.76 | 124.75 | 124.75 | 2011-01-31 |  |  | 2014-03-03
16 | R162000434 | Community Health Center | Dhar | Dharampuri | Health | DHFW | 144.72 | 123.01 | 38.36 | 2011-01-31 |  |  | 2014-03-03
16 | R162000435 | Community Health Center | Dindori | Dindori | Health | DHFW | 176.04 | 149.63 | 146.38 | 2011-01-31 |  |  | 2014-03-03
16 | R162000436 | Community Health Center | Guna | Guna | Health | DHFW | 71.83 | 61.06 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000437 | Community Health Center | Harda | Handia | Health | DHFW | 189.24 | 160.85 | 160.85 | 2011-01-31 |  |  | 2014-03-03
16 | R162000438 | Community Health Center | Harda | Khirkiya | Health | DHFW | 182.31 | 154.96 | 67.3 | 2011-01-31 |  |  | 2014-03-03
16 | R162000439 | Community Health Center | Hoshangabad | Piparia | Health | DHFW | 118.61 | 100.82 | 68.94 | 2011-01-31 |  |  | 2014-03-03
16 | R162000440 | Community Health Center | Indore | Depalpur | Health | DHFW | 152.87 | 129.94 | 129.94 | 2011-01-31 |  |  | 2014-03-03
16 | R162000441 | Community Health Center | Jhabua | Jhabua | Health | DHFW | 178.9 | 152.07 | 137.96 | 2011-01-31 |  |  | 2014-03-03
16 | R162000442 | Community Health Center | Katni | Badwara | Health | DHFW | 186.84 | 158.81 | 158.81 | 2011-01-31 |  |  | 2014-03-03
16 | R162000443 | Community Health Center | Mandla | Mandla | Health | DHFW | 170.05 | 144.54 | 138.02 | 2011-01-31 |  |  | 2014-03-03
16 | R162000444 | Community Health Center | Morena | Ambha | Health | DHFW | 164.86 | 140.13 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000445 | Community Health Center | Morena | Sabalgadh | Health | DHFW | 55.51 | 47.18 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000446 | Community Health Center | Neemuch | Ratangadh | Health | DHFW | 96.56 | 82.08 | 0.01 | 2011-01-31 |  |  | 2014-03-03
16 | R162000447 | Community Health Center | Panna | Panna | Health | DHFW | 172.68 | 146.78 | 70.25 | 2011-01-31 |  |  | 2014-03-03
16 | R162000448 | Community Health Center | Raisen | Badi Barli | Health | DHFW | 180.13 | 153.11 | 153.1 | 2011-01-31 |  |  | 2014-03-03
16 | R162000449 | Community Health Center | Rajgarh | Rajgarh | Health | DHFW | 175.45 | 149.13 | 149.13 | 2011-01-31 |  |  | 2014-03-03
16 | R162000450 | Community Health Center | Rajgarh | Beoawra | Health | DHFW | 121.03 | 102.88 | 102.88 | 2011-01-31 |  |  | 2014-03-03
16 | R162000451 | Community Health Center | Ratlam | Alot | Health | DHFW | 102.93 | 87.49 | 87.49 | 2011-01-31 |  |  | 2014-03-03
16 | R162000452 | Community Health Center | Rewa | Tyonthar | Health | DHFW | 143.12 | 121.65 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000453 | Community Health Center | Rewa | Semaria | Health | DHFW | 162.03 | 137.73 | 137.73 | 2011-01-31 |  |  | 2014-03-03
16 | R162000454 | Community Health Center | Sagar | Bina | Health | DHFW | 174.93 | 148.69 | 104.78 | 2011-01-31 |  |  | 2014-03-03
16 | R162000455 | Community Health Center | Satna | Ramnagar | Health | DHFW | 29.8 | 25.33 | 25.33 | 2011-01-31 |  |  | 2014-03-03
16 | R162000456 | Community Health Center | Satna | Maihar | Health | DHFW | 159.22 | 135.34 | 135.34 | 2011-01-31 |  |  | 2014-03-03
16 | R162000457 | Community Health Center | Satna | Shohawal | Health | DHFW | 214.21 | 182.08 | 86.83 | 2011-01-31 |  |  | 2014-03-03
16 | R162000458 | Community Health Center | Sehore | Astha | Health | DHFW | 172.15 | 146.33 | 146.33 | 2011-01-31 |  |  | 2014-03-03
16 | R162000459 | Community Health Center | Sehore | Budni | Health | DHFW | 182.31 | 154.96 | 154.96 | 2011-01-31 |  |  | 2014-03-03
16 | R162000460 | Community Health Center | Shajapur | Shujalpur | Health | DHFW | 178.88 | 152.05 | 149.15 | 2011-01-31 |  |  | 2014-03-03
16 | R162000461 | Community Health Center | Shivpuri | Shivpuri | Health | DHFW | 180.19 | 153.16 | 92.34 | 2011-01-31 |  |  | 2014-03-03
16 | R162000462 | Community Health Center | Singhroli | Devsar | Health | DHFW | 183.64 | 156.09 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000463 | Community Health Center | Tikamgarh | Baldevgadh | Health | DHFW | 175.51 | 149.18 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000464 | Community Health Center | Tikamgarh | Tikamgarh | Health | DHFW | 252.51 | 214.63 | 58.25 | 2011-01-31 |  |  | 2014-03-03
16 | R162000465 | Community Health Center | Ujjain | Ujjain | Health | DHFW | 173.83 | 147.76 | 147.75 | 2011-01-31 |  |  | 2014-03-03
16 | R162000466 | Community Health Center | Ujjain | Mahidpur | Health | DHFW | 211.97 | 180.17 | 180.16 | 2011-01-31 |  |  | 2014-03-03
16 | R162000467 | Community Health Center | Umaria | Umaria (Karkeli) | Health | DHFW | 170.13 | 144.61 | 104.98 | 2011-01-31 |  |  | 2014-03-03
16 | R162000468 | Community Health Center | Vidisha | Vidisha | Health | DHFW | 197.48 | 167.86 | 47.78 | 2011-01-31 |  |  | 2014-03-03
16 | R162000469 | Community Health Center | Shahdol | Burhar | Health | DHFW | 178.9 | 152.07 | 152.07 | 2011-01-31 |  |  | 2014-03-03
16 | R162000470 | Community Health Center | Anuppur | Jatahri | Health | DHFW | 200.11 | 170.09 | 170.09 | 2011-01-31 |  |  | 2014-03-03
16 | R162000471 | Community Health Center | Anuppur | Anuppur | Health | DHFW | 183.58 | 156.04 | 156.04 | 2011-01-31 |  |  | 2014-03-03
16 | R162000472 | Community Health Center | Bhopal | Fanda | Health | DHFW | 200.11 | 170.09 | 170.09 | 2011-01-31 |  |  | 2014-03-03
16 | R162000473 | Community Health Center | Chhatarpur | Badamalahra | Health | DHFW | 183.58 | 156.04 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000474 | Community Health Center | Dewas | Dewas | Health | DHFW | 183.58 | 156.04 | 156.04 | 2011-01-31 |  |  | 2014-03-03
16 | R162000475 | Community Health Center | Katani | Badwara | Health | DHFW | 200.11 | 170.09 | 170.09 | 2011-01-31 |  |  | 2014-03-03
16 | R162000476 | Community Health Center | Khargone | Khargone (Oon) | Health | DHFW | 200.11 | 170.09 | 146.9 | 2011-01-31 |  |  | 2014-03-03
16 | R162000477 | Community Health Center | Khargone | Barwah | Health | DHFW | 200.11 | 170.09 | 113.63 | 2011-01-31 |  |  | 2014-03-03
16 | R162000478 | Community Health Center | Mandsaur | Mandsaur | Health | DHFW | 200.11 | 170.09 | 162.17 | 2011-01-31 |  |  | 2014-03-03
16 | R162000479 | Community Health Center | Narsinghpur | Narsinghpur | Health | DHFW | 183.58 | 156.04 | 144.01 | 2011-01-31 |  |  | 2014-03-03
16 | R162000480 | Community Health Center | Neemuch | Neemuch | Health | DHFW | 200.11 | 170.09 | 170.1 | 2011-01-31 |  |  | 2014-03-03
16 | R162000481 | Community Health Center | Raisen | Abdullaganj | Health | DHFW | 200.11 | 170.09 | 170.08 | 2011-01-31 |  |  | 2014-03-03
16 | R162000482 | Community Health Center | Rewa | Raipur | Health | DHFW | 200.11 | 170.09 | 170.09 | 2011-01-31 |  |  | 2014-03-03
16 | R162000483 | Community Health Center | Sehore | Nasrullaganj | Health | DHFW | 183.58 | 156.04 | 156.04 | 2011-01-31 |  |  | 2014-03-03
16 | R162000484 | Community Health Center | Shajapur | Shajapur | Health | DHFW | 200.11 | 170.09 | 166.76 | 2011-01-31 |  |  | 2014-03-03
16 | R162000485 | Community Health Center | Shahdol | Jaisinghnagar | Health | DHFW | 200.11 | 170.09 | 170.09 | 2011-01-31 |  |  | 2014-03-03
16 | R162000486 | Community Health Center | Singhroli | Baidhan | Health | DHFW | 200.11 | 170.09 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000487 | Community Health Center | Singhroli | Chitrangi | Health | DHFW | 200.11 | 170.09 | 0 | 2011-01-31 |  |  | 2014-03-03
16 | R162000488 | Community Health Center | Ujjain | Badnagar | Health | DHFW | 200.11 | 170.09 | 170.1 | 2011-01-31 |  |  | 2014-03-03
16 | R162000489 | Amgawa To Podi Road | Anuppur | Pushparajgarh | Road | PWD | 384.32 | 307.46 | 245.81 | 2011-01-31 |  |  | 2014-03-03
16 | R162000490 | Nigwani Kothi Road | Anuppur | Anuppur | Road | PWD | 189.47 | 151.58 | 140.68 | 2011-01-31 |  |  | 2016-01-31
16 | R162000493 | Kotma Nigwani Road To Village Pathroud | Anuppur | Kotma | Road | PWD | 102.99 | 82.39 | 81.22 | 2011-01-31 |  |  | 2016-01-31
16 | R162000495 | Katha,Hirapura Sikri To Lahar Road | Bhind | Lahar | Road | PWD | 185.77 | 148.62 | 148.62 | 2011-01-31 |  |  | 2016-01-31
16 | R162000496 | Narol To Mihoni Mata Road | Bhind | Lahar | Road | PWD | 153.78 | 123.02 | 118.82 | 2011-01-31 |  |  | 2016-01-31
16 | R162000497 | Shayampura To Rahawali Uwari Road | Bhind | Lahar | Road | PWD | 184.04 | 147.23 | 147.23 | 2011-01-31 |  |  | 2016-01-31
16 | R162000498 | Alipura Churwani Road | Chhatarpur | Nowgong | Road | PWD | 183.03 | 146.42 | 146.42 | 2011-01-31 |  |  | 2016-01-31
16 | R162000499 | Upgrading Of Girdhouri Aktoha Road | Chhatrapur | Laundi | Road | PWD | 59.09 | 47.27 | 43.61 | 2011-01-31 |  |  | 2016-01-31
16 | R162000500 | Syami Nalla Lahar Main Road To Balaji Mandir App. Road | Chhatrapur | Bijawar | Road | PWD | 74.78 | 59.82 | 57.44 | 2011-01-31 |  |  | 2016-01-31
16 | R162000501 | CC Road Of Prakrima Road At Chhatrapur | Chhatrapur | Chhatrapur | Road | PWD | 212.94 | 170.35 | 153.41 | 2011-01-31 |  |  | 2016-01-31
16 | R162000502 | Karaboh To Khajri Road | Chhindwara | Chhindwara | Road | PWD | 62.87 | 50.3 | 30.862 | 2011-01-31 |  |  | 2016-01-31
16 | R162000503 | Morli Junction To Jhanda Kudwari Rohna Khurd Roa | Chhindwara | Chhindwara | Road | PWD | 219.61 | 175.69 | 125.03 | 2011-01-31 |  |  | 2016-01-31
16 | R162000504 | Bomaliya Hirawadi Road | Chhindwara | Mohked | Road | PWD | 211.95 | 169.56 | 123.75 | 2011-01-31 |  |  | 2016-01-31
16 | R162000505 | Narsala Dighori Road | Chhindwara | Pandhurna | Road | PWD | 34.12 | 27.3 | 27.3 | 2011-01-31 |  |  | 2016-01-31
16 | R162000506 | Guddam Mankadehi Road | Chhindwara | Jamai | Road | PWD | 102.81 | 82.25 | 58.29 | 2011-01-31 |  |  | 2016-01-31
16 | R162000507 | Bijagora Bhavari Road | Chhindwara | Mohked | Road | PWD | 173.19 | 138.55 | 138.55 | 2011-01-31 |  |  | 2016-01-31
16 | R162000508 | Ponia Penchpul To Top Pipria Khati | Chhindwara | Chourai | Road | PWD | 144.08 | 115.26 | 97.68 | 2011-01-31 |  |  | 2016-01-31
16 | R162000509 | Tighara Pounhara Road | Chhindwara | Mohkhed | Road | PWD | 105.19 | 84.15 | 84.15 | 2011-01-31 |  |  | 2016-01-31
16 | R162000510 | Babai Palatwada Road | Chhindwara | Parasiya | Road | PWD | 78.61 | 62.89 | 53.35 | 2011-01-31 |  |  | 2016-01-31
16 | R162000511 | Kothar Machighat Road | Chhindwara | Jamai | Road | PWD | 57.11 | 45.69 | 45.69 | 2011-01-31 |  |  | 2016-01-31
16 | R162000512 | Lingapani Umariya Road | Chhindwara | Amarwara | Road | PWD | 85.88 | 68.7 | 65.79 | 2011-01-31 |  |  | 2016-01-31
16 | R162000513 | Kuajhiri To Girjamai Swam Road | Chhindwara | Jamai | Road | PWD | 100.68 | 80.54 | 0 | 2011-01-31 |  |  | 2016-01-31
16 | R162000514 | Pindraikala Kotalbarri Bijapani Road | Chhindwara | Chhindwara | Road | PWD | 179.82 | 143.86 | 97.66 | 2011-01-31 |  |  | 2016-01-31
16 | R162000515 | Bareghat Devgarh Road | Chhindwara | Mohked | Road | PWD | 162.73 | 130.18 | 130.18 | 2011-01-31 |  |  | 2016-01-31
16 | R162000516 | Bhaisadand Payali Road | Chhindwara | Parasiya | Road | PWD | 57.49 | 45.99 | 30.99 | 2011-01-31 |  |  | 2016-01-31
16 | R162000517 | Loniyamaru Bilwa Road | Chhindwara | Chhindwara | Road | PWD | 90.59 | 72.47 | 72 | 2011-01-31 |  |  | 2016-01-31
16 | R162000518 | Gumtara-Jamtara Road | Chhindwara | Chourai | Road | PWD | 198.76 | 159.01 | 79.44 | 2011-01-31 |  |  | 2016-01-31
16 | R162000519 | Chhabra To Gorakhghat Road | Chhindwara | Tamiya | Road | PWD | 169.09 | 135.27 | 128.91 | 2011-01-31 |  |  | 2016-01-31
16 | R162000520 | Sheeladehi-Moary-Ghoghry-Ambada Road | Chhindwara | Parasiya | Road | PWD | 229.65 | 183.72 | 166.53 | 2011-01-31 |  |  | 2016-01-31
16 | R162000521 | Bhandai Ghogra Road | Chhindwara | Chhindwara | Road | PWD | 144.48 | 115.58 | 115.58 | 2011-01-31 |  |  | 2016-01-31
16 | R162000522 | Kedarpur Jamuniya Road | Chhindwara | Chourai | Road | PWD | 111.12 | 88.9 | 75.66 | 2011-01-31 |  |  | 2016-01-31
16 | R162000523 | Chargaon Bhajipani Road | Chhindwara | Amarwara | Road | PWD | 135.78 | 108.62 | 95.93 | 2011-01-31 |  |  | 2016-01-31
16 | R162000524 | Chargaon Bandra Road | Chhindwara | Chourai | Road | PWD | 129 | 103.2 | 103.2 | 2011-01-31 |  |  | 2016-01-31
16 | R162000525 | Kuabadlanandiya To Khutty Road | Chhindwara | Tamiya | Road | PWD | 145.08 | 116.06 | 116.06 | 2011-01-31 |  |  | 2016-01-31
16 | R162000526 | Siras Dhamnia Road | Chhindwara | Chourai | Road | PWD | 133.32 | 106.66 | 95.52 | 2011-01-31 |  |  | 2016-01-31
16 | R162000527 | Jhouth Kalan To Ghatiya Road | Chhindwara | Tamiya | Road | PWD | 100.68 | 80.54 | 80.54 | 2011-01-31 |  |  | 2016-01-31
16 | R162000528 | Chhindi Jogimouar Road | Chhindwara | Tamiya | Road | PWD | 203.55 | 162.84 | 131.3 | 2011-01-31 |  |  | 2016-01-31
16 | R162000529 | Jamuniya Hirripathar Bijoripathar Road | Chhindwara | Tamiya | Road | PWD | 402.83 | 322.26 | 320.37 | 2011-01-31 |  |  | 2016-01-31
16 | R162000530 | Damkhoh Jhirapani Road | Chhindwara | Tamiya | Road | PWD | 105.82 | 84.66 | 76.94 | 2011-01-31 |  |  | 2016-01-31
16 | R162000531 | Ekelkhera Richheda Dhanshiya Hevrad Maduua Road | Chhindwara | Parasia | Road | PWD | 379.2 | 303.36 | 260.32 | 2011-01-31 |  |  | 2016-01-31
16 | R162000532 | Koudiya Ghoghara Road | Chhindwara | Pandhurna | Road | PWD | 140.14 | 112.11 | 107.71 | 2011-01-31 |  |  | 2016-01-31
16 | R162000533 | Goraghat Indargarh Road To Bhadol Via Senpura Rooran Village | Datia | Seondha | Road | PWD | 185 | 148 | 148 | 2011-01-31 |  |  | 2016-01-31
16 | R162000534 | Seondha Chungi To Gwalior Jhansi Bye Pass Road | Datia | Datia | Road | PWD | 118.13 | 94.5 | 94.5 | 2011-01-31 |  |  | 2016-01-31
16 | R162000535 | Hinotiya To Chirol Village | Datia | Datia | Road | PWD | 158.93 | 127.14 | 127.14 | 2011-01-31 |  |  | 2016-01-31
16 | R162000536 | Baroni Sonagir Approach Road | Datia | Datia | Road | PWD | 125.96 | 100.77 | 100.77 | 2011-01-31 |  |  | 2016-01-31
16 | R162000537 | Goraghat To Indargarh Via Khajoori Village | Datia | Datia | Road | PWD | 217.16 | 173.73 | 139.1 | 2011-01-31 |  |  | 2016-01-31
16 | R162000538 | Construction Of Ramgarh Approach Road | Datia | Bhander | Road | PWD | 67.44 | 53.95 | 47.31 | 2011-01-31 |  |  | 2016-01-31
16 | R162000539 | Kitiya To Siraliya Road | Dewas | Kannod | Road | PWD | 204.82 | 163.86 | 124.7 | 2011-01-31 |  |  | 2016-01-31
16 | R162000540 | Kitiya To Siya Road | Dewas | Kannod | Road | PWD | 116.04 | 92.83 | 92.83 | 2011-01-31 |  |  | 2016-01-31
16 | R162000541 | Kantaphod To Singladesh (Bairagarah To Singladeh Road) | Dewas | Satwas | Road | PWD | 610.93 | 488.74 | 360.46 | 2011-01-31 |  |  | 2016-01-31
16 | R162000542 | Umeda To Harangaon Road | Dewas | Khategaon | Road | PWD | 193.93 | 155.14 | 141.36 | 2011-01-31 |  |  | 2016-01-31
16 | R162000543 | Sundrel To Hirapur | Dewas | Satwas | Road | PWD | 67.73 | 54.18 | 39.02 | 2011-01-31 |  |  | 2016-01-31
16 | R162000544 | Samgi Kamalpur Via Kailod Road | Dewas | Bagli | Road | PWD | 128.66 | 102.93 | 47.69 | 2011-01-31 |  |  | 2016-01-31
16 | R162000545 | Bangar Beragarh Hirli Road | Dewas | Dewas | Road | PWD | 306.12 | 244.9 | 195.2 | 2011-01-31 |  |  | 2016-01-31
16 | R162000546 | Rabdiya Sidni Fatehpur Phata Road | Dewas | Sonkatch | Road | PWD | 243.25 | 194.6 | 116.09 | 2011-01-31 |  |  | 2016-01-31
16 | R162000548 | Samadhi Bamhnoda Road | Jabalpur | Jabalpur | Road | PWD | 152.32 | 121.86 | 100.36 | 2011-01-31 |  |  | 2016-01-31
16 | R162000559 | Amadi To Gulzera Road | Khargone | Jhirniya | Road | PWD | 293.85 | 235.08 | 201.86 | 2011-01-31 |  |  | 2016-01-31
16 | R162000560 | Nimrani To Satkut Road | Khargone | Kasrawad | Road | PWD | 408.95 | 327.16 | 231.3 | 2011-01-31 |  |  | 2016-01-31
16 | R162000561 | Khargone Mangrool Road | Khargone | Khargone | Road | PWD | 104.28 | 83.42 | 71.52 | 2011-01-31 |  |  | 2016-01-31
16 | R162000562 | Mohgaon Basgadhi Road | Mandla | Niwas | Road | PWD | 188.04 | 150.43 | 142.22 | 2011-01-31 |  |  | 2016-01-31
16 | R162000563 | Surajpura Kanhargaon Dobhi Daitpura Tumergaon Khirkhiny Chhatrwada Road | Mandla | Nainpur | Road | PWD | 283.35 | 226.68 | 164.36 | 2011-01-31 |  |  | 2016-01-31
16 | R162000564 | Niwari Mohgaon Gaurachhaper Saguriya Bandha Road | Mandla | Nainpur | Road | PWD | 346.35 | 277.08 | 277.08 | 2011-01-31 |  |  | 2016-01-31
16 | R162000565 | Gonjhi Keregaon Chichgaon Duddum Chiraldongwi Road | Mandla | Nainpur | Road | PWD | 407.26 | 325.81 | 206.81 | 2011-01-31 |  |  | 2016-01-31
16 | R162000566 | Beejegaon Bharveli Putaarra Lutmara Khursipar Road | Mandla | Nainpur | Road | PWD | 440.82 | 352.66 | 340.59 | 2011-01-31 |  |  | 2016-01-31
16 | R162000567 | Manipura Road To Ishwara Mahadev Mandir Road | Morena | Phadgarh | Road | PWD | 64.99 | 51.99 | 16.71 | 2011-01-31 |  |  | 2016-01-31
16 | R162000568 | Rai Ka Pura To Bahadurpur Road | Morena | Ambah | Road | PWD | 96.37 | 77.1 | 57.31 | 2011-01-31 |  |  | 2016-01-31
16 | R162000569 | Palpura To Pachoripura Road (Via Dugsingh Ka Pura Phatak Ka Pura ) | Morena | Morena | Road | PWD | 437.85 | 350.28 | 222 | 2011-01-31 |  |  | 2016-01-31
16 | R162000570 | Barroli To Ummedgarh Bansi Road | Morena | Joura | Road | PWD | 113 | 90.4 | 58.39 | 2011-01-31 |  |  | 2016-01-31
16 | R162000571 | Bhadbhadiya Jawad Athana Sukhanand Road | Neemuch | Jawad | Road | PWD | 722.58 | 578.06 | 514.03 | 2011-01-31 |  |  | 2016-01-31
16 | R162000572 | Char Gaon To Salaiya Kanwar Samnapur Kachhi Road | Raisen | Bari | Road | PWD | 219.75 | 175.8 | 145.48 | 2011-01-31 |  |  | 2016-01-31
16 | R162000573 | Khandawar Sultannagar Jontala Nan Bhet Road | Raisen | Bari | Road | PWD | 127.81 | 102.25 | 76.29 | 2011-01-31 |  |  | 2016-01-31
16 | R162000574 | Nayapura To Gokula Kundi Road | Raisen | Obedullah gunj | Road | PWD | 152.62 | 122.1 | 122.1 | 2011-01-31 |  |  | 2016-01-31
16 | R162000575 | N-12 To Barodiya Khurd Gehalpur Chooupan Marhaiya Kanwar Road | Raisen | Bari | Road | PWD | 255.85 | 204.68 | 192.68 | 2011-01-31 |  |  | 2016-01-31
16 | R162000576 | Chandrapur Turnig To Baraun Market | Rewa | Sirmour | Road | PWD | 129.87 | 103.9 | 86.2 | 2011-01-31 |  |  | 2016-01-31
16 | R162000578 | Rajkhedi Sagar Bye Pass Road | Sagar | Sagar | Road | PWD | 109.9 | 109.9 | 109.9 | 2011-01-31 |  |  | 2016-01-31
16 | R162000580 | Bhapson To Satoriya Road | Sagar | Bina | Road | PWD | 69.1 | 69.1 | 69.1 | 2011-01-31 |  |  | 2016-01-31
16 | R162000581 | Hiroundi Koldari Road | Satna | Majhgawan | Road | PWD | 129.76 | 103.81 | 75.51 | 2011-01-31 |  |  | 2016-01-31
16 | R162000582 | Kordarnath Kulhariya Bhakul Baba Road | Satna | Unchehara | Road | PWD | 119.62 | 95.7 | 42.47 | 2011-01-31 |  |  | 2016-01-31
16 | R162000583 | Jamuniya Kalan To Bagwada Road | Sehore | Nasrulaganj | Road | PWD | 121.19 | 96.95 | 85.96 | 2011-01-31 |  |  | 2016-01-31
16 | R162000584 | Dholpura To Bolagaon Road | Sehore | Nasrulaganj | Road | PWD | 140.25 | 112.2 | 98.91 | 2011-01-31 |  |  | 2016-01-31
16 | R162000585 | Jamuniya Kalan To Ranipura Road | Sehore | Nasrulaganj | Road | PWD | 138.65 | 110.92 | 109.23 | 2011-01-31 |  |  | 2016-01-31
16 | R162000586 | Basaniya Khurd To Dhankot Road | Sehore | Rehti | Road | PWD | 104.94 | 83.95 | 83.95 | 2011-01-31 |  |  | 2016-01-31
16 | R162000587 | Basaniya Khurd To Basaniya Kalan Road | Sehore | Rehti | Road | PWD | 71.45 | 57.16 | 57.16 | 2011-01-31 |  |  | 2016-01-31
16 | R162000588 | Dholpur To Bagwada Road | Sehore | Nasrulaganj | Road | PWD | 167.6 | 134.08 | 85.82 | 2011-01-31 |  |  | 2016-01-31
16 | R162000589 | Pipariya Dhapara Road | Seoni | Barghat | Road | PWD | 188.23 | 150.58 | 114.16 | 2011-01-31 |  |  | 2016-01-31
16 | R162000592 | Sarra Hirri To Sagar Road | Seoni | Kurai | Road | PWD | 195.15 | 156.12 | 156.12 | 2011-01-31 |  |  | 2016-01-31
16 | R162000595 | Beelwara(Mata) To Berja Road | Shivpuri | Pohari | Road | PWD | 185.92 | 148.74 | 102.07 | 2011-01-31 |  |  | 2016-01-31
16 | R162000596 | Bharota To Deharda (Ganesh) Road | Shivpuri | Kolaras | Road | PWD | 146.47 | 117.18 | 79.64 | 2011-01-31 |  |  | 2016-01-31
16 | R162000597 | Saparwada To Dulhara | Shivpuri | Pohari | Road | PWD | 174.25 | 139.4 | 109.77 | 2011-01-31 |  |  | 2016-01-31
16 | R162000598 | Purail Chhanda To Deora Railway Station Road | Singrauli | Purail | Road | PWD | 458.4 | 366.72 | 336.59 | 2011-01-31 |  |  | 2016-01-31
16 | R162000599 | Gadhor Pondi Road | Singrauli | Chitrangi | Road | PWD | 572.6 | 458.08 | 372.52 | 2011-01-31 |  |  | 2016-01-31
16 | R162000600 | Bairdah Sakariya Road | Singrauli | Chitrangi | Road | PWD | 210.3 | 168.24 | 168.24 | 2011-01-31 |  |  | 2016-01-31
16 | R162000602 | Tikamgarh Sudha Sagar Ahar Road | Tikamgarh | Tikamgarh | Road | PWD | 199.47 | 159.58 | 159.58 | 2011-01-31 |  |  | 2016-01-31
16 | R162000603 | Construction Of Approach Road For Village Panjh | Vidisha | Vidisha | Road | PWD | 143 | 114.4 | 70.59 | 2011-01-31 |  |  | 2016-01-31
16 | R162000604 | Sumer Hathiyakhedi Khiriya Suakhedi Atarikhejra Road | Vidisha | Vidisha | Road | PWD | 328.27 | 328.27 | 328.27 | 2011-01-31 |  |  | 2016-01-31
16 | R162000605 | Durga Nagar Saraswati School To Guraiya Chidoriya Bhoriya Road | Vidisha | Vidisha | Road | PWD | 294.99 | 235.99 | 204.01 | 2011-01-31 |  |  | 2016-01-31
16 | R162000606 | Jhirniya-Karhiya-Saunthor-Andiya-Suraud-Khejra-Adampur-Goberhela-Devrajpur | Vidisha | Vidisha | Road | PWD | 948.52 | 758.82 | 431.32 | 2011-01-31 |  |  | 2016-01-31
16 | R162000607 | Berkheda Sagoda Ghatkhedi Satdhara Bhopal Road | Vidisha | Shamshabad | Road | PWD | 930.77 | 772.48 | 366.6 | 2011-01-31 |  |  | 2016-01-31
16 | R162000609 | Submersible Bridge Across Kanhan River On Berdi- Sayra-Partapur Road | Chhindwara | Sousor | Bridge | PWD | 761.55 | 609.24 | 609.24 | 2011-01-31 |  |  | 2016-01-31
16 | R162000610 | H L Bridge Across Ghissari Rive In Km 21/2 | Balaghat | Kirnapur | Bridge | PWD | 525.7 | 420.56 | 420.56 | 2011-01-31 |  |  | 2016-01-31
16 | R162000611 | Bridge Across Pandajhir Nalla | Narsinghpur | Tendhukhedha | Bridge | PWD | 159.12 | 127.3 | 88.99 | 2011-01-31 |  |  | 2016-01-31
16 | R162000612 | Submer Bridge Across Wainganag River In Km 3/10 | Seoni | Keolari | Bridge | PWD | 265.64 | 212.51 | 212.51 | 2011-01-31 |  |  | 2016-01-31
16 | R162000613 | Indira Sagar Proj Can Pii | Barwani | Many Blocks | MJP | NVDA | 54055.13 | 5135.24 | 5135.23 | 2011-02-25 |  |  | 2016-03-02
16 | R162000614 | Omkareswar Pro Canal | Dhar | Many Blocks | MJP | NVDA | 35415 | 3364.43 | 3241.07 | 2011-02-25 |  |  | 2016-03-02
17 | R172000001 | Sagad MIP | Vidisha | Shamshabad | MIP | WRD | 10384.09 | 9864.89 | 9865.12 | 2011-08-25 |  |  | 2016-08-31 |  |  |  | 9478
17 | R172000002 | Pench Diversion Project Unit Ii Canal | Chhindwara | Chourai | MJP | WRD | 37745.47 | 35858.2 | 35858.2 | 2011-12-05 |  |  | 2016-12-31 |  |  |  | 70918
17 | R172000003 | Mahuar MIP | Shivpuri | Pichhore | MIP | WRD | 12853.99 | 12853.99 | 12853.99 | 2011-12-22 |  |  | 2016-12-31 |  |  |  | 9500
17 | R172000004 | Sip-Kolar Link Mip | Sehore | Ichhawar | MIP | WRD | 13381.93 | 7659.87 | 6974.79 | 2012-01-20 |  |  | 2017-01-31 |  |  |  | 6100
17 | R172000005 | Balwadi - Deoli - Dhawali Road | Barwani | SENDHWA | Road | PWD | 733.64 | 586.91 | 455.26 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 19.8
17 | R172000006 | Barwani Bhagwati Morkatta Borkhedi | Balaghat | BARWANI | Road | PWD | 1116.02 | 892.82 | 885.62 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 22.7
17 | R172000007 | Bawadiyaphata To Lohara Road | Barwani | THIKRI | Road | PWD | 181.08 | 144.86 | 122.27 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 4.65
17 | R172000008 | Birulbazar To Sawalmenda Ghana Road | Betul | PRABHAT PATTAN | Road | PWD | 216.94 | 173.55 | 153.74 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 6
17 | R172000009 | Bisalkhedi To Beelkheda Road | Bhopal | Phanda | Road | PWD | 197.27 | 157.82 | 157.816 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 3.5
17 | R172000010 | Bisalkhedi To Millenium College Via Shuting Renge | Bhopal | Bhopal | Road | PWD | 334.95 | 267.96 | 195.99 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 3.7
17 | R172000011 | Hathnoor To Badkhedi Road | Burhanpur | BURHANPUR | Road | PWD | 142.71 | 114.17 | 100.71 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 2.12
17 | R172000012 | Nawla Ghagharla Road | Burhanpur | Khaknar | Road | PWD | 179.88 | 143.9 | 104.13 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 3.58
17 | R172000013 | Shahpur Dhamangaon Road | Burhanpur | BURHANPUR | Road | PWD | 398.78 | 319.02 | 270.11 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 8.2
17 | R172000014 | Jaitpur To Vardha Road | Chattarpur | Badamalehra | Road | PWD | 76.51 | 61.21 | 60.44 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 8.6
17 | R172000015 | Pathapur To Hathna Road | Chattarpur | Chhatarpur | Road | PWD | 125.3 | 100.24 | 0 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 3.7
17 | R172000016 | Rajnagar Road To Sarani Via Radhepur | Chattarpur | Chhatarpur | Road | PWD | 129.44 | 103.55 | 102.49 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 4.4
17 | R172000017 | Malapodi To Bhangarh Road | Damoh | Jabera | Road | PWD | 975.12 | 780.1 | 780.1 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 13.7
17 | R172000018 | Batiagarh To Kerwana Road | Damoh | Batiyagarh | Road | PWD | 1267.22 | 1013.78 | 680.86 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 21
17 | R172000019 | Mehguon To Kauwakhoh Road | Damoh | Patera | Road | PWD | 452.4 | 361.92 | 234.6 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 7.64
17 | R172000020 | Balwari Gandhwani Road | Dhar | Gandhwani | Road | PWD | 260.29 | 208.23 | 181.17 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 9.4
17 | R172000022 | Kod To Bhansola Chaupati Road | Dhar | BADNAWAR | Road | PWD | 951.94 | 761.55 | 761.55 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 20.22
17 | R172000023 | Nisarpur To Koteshwar Road | Dhar | Nisarpur | Road | PWD | 238.4 | 190.72 | 137.01 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 4.8
17 | R172000024 | Kumthi To Kamadpura Road | Indore | Mhow | Road | PWD | 275.17 | 220.14 | 182.25 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 6.5
17 | R172000025 | Bharda (Sharda) Nipaniya Madhai Road | Jabalpur | Panagar | Road | PWD | 294.23 | 235.38 | 139.83 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 4.5
17 | R172000028 | Narlai Imlai Nargawan Road | Jabalpur | Panagar | Road | PWD | 251.45 | 201.16 | 138.88 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 4.5
17 | R172000029 | Sihora Sarda Madai Road | Jabalpur | SIHORA | Road | PWD | 528.09 | 422.47 | 343.93 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 9.1
17 | R172000030 | Talad To Padwar Road | Jabalpur | Majholi | Road | PWD | 346.02 | 276.82 | 225.03 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 8.7
17 | R172000031 | Sailwara Bhandra Kachhargaon Road | Katni | Dheemarkheda, | Road | PWD | 354.07 | 283.26 | 228.19 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 16
17 | R172000032 | Kehlari To Phatehpur Road | Katni | Sihora | Road | PWD | 91.1 | 72.88 | 62.85 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 2.5
17 | R172000033 | Surgaon To Nipani Bijori Road | Khandwa | KHANDWA | Road | PWD | 123.29 | 98.63 | 76.26 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 3.7
17 | R172000034 | Bablai To Somekhedi Karai Kodiakhedi To Pipaliaph | Khargone | KHANDWA | Road | PWD | 283.53 | 226.82 | 140.89 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 6.94
17 | R172000035 | Choli To Bablai Road | Khargone | Maheshwar | Road | PWD | 196.96 | 157.57 | 118.89 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 5.43
17 | R172000036 | Maheshwar To Marmur Road | Khargone | Maheshwar | Road | PWD | 259.6 | 207.68 | 203.31 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 4.58
17 | R172000037 | Maheshwar To Mehatwara Road | Khargone | Maheshwar | Road | PWD | 320.74 | 256.59 | 171.23 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 7.1
17 | R172000038 | Mudia To Dhasalgon Road | Khargone | Maheshwar | Road | PWD | 326.28 | 261.02 | 211.66 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 9.5
17 | R172000041 | Sirsi To Sadarkheda Road | Guna | BAMORI | Road | PWD | 261.74 | 209.39 | 84.88 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 6
17 | R172000042 | Bhagore To Barkhedakalan Road | Mandsaur | BAMORI | Road | PWD | 155.57 | 124.46 | 82.97 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 4.3
17 | R172000043 | Jharda To Irli Road | Mandsaur | Sitamau | Road | PWD | 332.19 | 265.75 | 191.9 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 6.3
17 | R172000044 | Katia Raghunathpura Road | Mandsaur | Malhargarh | Road | PWD | 237.16 | 189.73 | 142.28 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 3.8
17 | R172000045 | Mundadi To Narayangarh Road | Mandsaur | Sitamau | Road | PWD | 194.45 | 155.56 | 109.18 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 4.1
17 | R172000046 | Narayangarh Bajrua Raod | Mandsaur | Malhargarh | Road | PWD | 212.88 | 170.3 | 101.03 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 4
17 | R172000047 | Khera To Datera Road | Morena | Malhargarh | Road | PWD | 353.37 | 282.7 | 231.64 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 9.6
17 | R172000049 | Upgradatin Of Chargawan Gundarai Road | Narsinghpur | Kareli | Road | PWD | 128.21 | 102.57 | 102.566 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 2.55
17 | R172000052 | Hinotiya Mahalpur Ghatkhedi Road | Raisen | Chawarpatha | Road | PWD | 344.62 | 275.7 | 218.09 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 8.8
17 | R172000053 | Amajhir To Lasudiya Ram Road | Sehore | Sanchi | Road | PWD | 246.17 | 196.94 | 161.49 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 4.2
17 | R172000054 | Bai To Bori To Berkhedi Road | Sehore | Ichhawar | Road | PWD | 165.21 | 132.17 | 129.62 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 4
17 | R172000055 | Barkheda Hasan To Dehri Road | Sehore | Nasrullaganj | Road | PWD | 164.1 | 131.28 | 120.17 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 3.56
17 | R172000056 | Barkhedahasan To Naikhedi Road | Sehore | Sehore | Road | PWD | 159.13 | 127.3 | 126.75 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 3.56
17 | R172000057 | Barkheda Hasan To Suakhedi Road | Sehore | Sehore | Road | PWD | 118.93 | 95.14 | 91.11 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 2.6
17 | R172000058 | Beebda Satmundi Jahajpura Road | Sehore | Sehore | Road | PWD | 216.53 | 173.22 | 110.05 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 6
17 | R172000059 | Bodra Babdi To Samnapur Road | Sehore | Budni | Road | PWD | 286.3 | 229.04 | 189 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 6
17 | R172000060 | Chhaparikhurd Via Chhaparikalan Road | Sehore | Budni | Road | PWD | 112.87 | 90.3 | 89.98 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 2.31
17 | R172000061 | Dudlai To Rupadeh To Rupadi Road | Sehore | Sehore | Road | PWD | 115.87 | 92.7 | 92.7 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 2.12
17 | R172000062 | Dupadiya Chachakhedi Road | Sehore | Ichhawar | Road | PWD | 250.3 | 200.24 | 174.71 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 3.6
17 | R172000063 | Gilehari To Vasudev Road | Sehore | Ashta | Road | PWD | 177.61 | 142.09 | 109.62 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 4
17 | R172000064 | Hathlewa, Chachmau, Nayapura To Shahganj Road | Sehore | Nasrullaganj | Road | PWD | 234.26 | 187.41 | 187.38 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 5
17 | R172000065 | Jahangirpura To Devsthan Dargah Road | Sehore | Budni | Road | PWD | 180.75 | 144.6 | 130.88 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 3.7
17 | R172000066 | Jontala To Baktara Road | Sehore | Sehore | Road | PWD | 227.99 | 182.39 | 181.01 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 5
17 | R172000067 | Jontala To Silgena Road | Sehore | Budni | Road | PWD | 237.28 | 189.82 | 189.82 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 6
17 | R172000068 | Kharpa To Hedarganj Road | Sehore | Budni | Road | PWD | 100.12 | 80.1 | 72.88 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 2.35
17 | R172000069 | Kulashkala To Barvakhedi Road | Sehore | Ichhawar | Road | PWD | 241.57 | 193.26 | 193.258 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 4.2
17 | R172000070 | Kuri To Nayapura Road | Sehore | Sehore | Road | PWD | 292.08 | 233.66 | 175.34 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 8
17 | R172000071 | Mograram To Gudvela Road | Sehore | Nasrullaganj | Road | PWD | 182.79 | 146.23 | 90.95 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 3.4
17 | R172000072 | Rupadeh To Gadiya Road | Sehore | Ichhawar | Road | PWD | 285.77 | 228.62 | 200.64 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 4.86
17 | R172000073 | Silgena To Nandner Road | Sehore | Ichhawar | Road | PWD | 279.31 | 223.45 | 179.44 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 4.7
17 | R172000074 | Semri - Khanpura To Ratanpur Road | Sehore | Budni | Road | PWD | 332.53 | 266.02 | 142.636 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 5.2
17 | R172000075 | Sh - 18 To Ataraliya To Khejdakheda Road | Sehore | Ashta | Road | PWD | 224.3 | 179.44 | 134.064 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 5
17 | R172000076 | Sonkhedi To Seelkanth Road | Sehore | Budni | Road | PWD | 189.75 | 151.8 | 151.8 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 4.4
17 | R172000077 | Teekmod To Mangrol Road | Sehore | Nasrullaganj | Road | PWD | 143.65 | 114.92 | 105.48 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 2.5
17 | R172000078 | Tumda Marg To Taj Via Amrod Road | Sehore | Nasrullaganj | Road | PWD | 145.86 | 116.69 | 101.79 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 3.14
17 | R172000079 | Udaypura Patariya Via Patariya Singha Road | Sehore | Sehore | Road | PWD | 250.05 | 200.04 | 152.1 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 4.9
17 | R172000080 | Bhursi To Mahroi Bela Road | Shahdol | Ichhawar | Road | PWD | 219.82 | 175.86 | 161.38 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 6
17 | R172000083 | Barej To Akabarpur Bamuriyatal Road | Vidisha | Kurwai | Road | PWD | 91.09 | 72.87 | 72.866 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 4.5
17 | R172000084 | Barwai To Kaswatal Road | Vidisha | Sironj | Road | PWD | 377.12 | 301.69 | 297.082 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 14.5
17 | R172000086 | Dhamnod To Dasipur Road | Vidisha | Ganjbasoda | Road | PWD | 142.78 | 114.22 | 114.22 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 7
17 | R172000088 | Imlani Khamkhera To Sironj Berasia Road Via Tiliya | Vidisha | Ganjbasoda/Gyaraspur | Road | PWD | 309.62 | 247.7 | 169.41 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 10.8
17 | R172000089 | Mundra Ganeshpur To Nipaniya Bhadar Road | Vidisha | Sironj | Road | PWD | 185.72 | 148.58 | 148.58 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 8
17 | R172000090 | N. H. 86 To Suwakhedi Sonthiya Road | Vidisha | Vidisha/ Gyaraspur | Road | PWD | 131.77 | 105.42 | 82.98 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 4.4
17 | R172000091 | Nolasa Lakholi Dargawan Tilak Road | Vidisha | Vidisha | Road | PWD | 418.95 | 335.16 | 335.158 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 21
17 | R172000092 | Pipaliyahat - Bamankhedi To Khiriyadangi Road | Vidisha | Vidisha | Road | PWD | 287.77 | 230.22 | 230.216 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 13.6
17 | R172000094 | Shamshabad Road To Katara Namakhedi Kothicharkalan | Vidisha | Kurwai | Road | PWD | 564.78 | 451.82 | 451.82 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 21
17 | R172000095 | Vidisha Lashkarpur To Kothichar Gulabganj Road To | Vidisha | Vidisha | Road | PWD | 142.76 | 114.21 | 114.21 | 2012-01-20 |  |  | 2015-03-03 |  |  |  | 7
17 | R172000096 | Highlevel Bridge Across SON RIVER In K.M. 3/2 Of Kadta Sarra | Balaghat | Lanji | Bridge | PWD | 713.39 | 670.33 | 1186.76 | 2012-02-24 |  |  | 2015-03-31 |  |  |  | 150
17 | R172000098 | Highlevel Bridge Across SINDH RIVER In K.M. 10/4-6 | Datia | Seondha | Bridge | PWD | 838.02 | 838.02 | 838.02 | 2012-02-24 |  |  | 2015-03-31 |  |  |  | 320
17 | R172000099 | Submersible Bridge On Hanumantia Nallah | Neemuch | Jawad | Bridge | PWD | 144.83 | 116.36 | 116.05 | 2012-02-24 |  |  | 2015-03-31 |  |  |  | 45
17 | R172000100 | Submersible Bridge Across Gambhiri River | Neemuch | Jawad | Bridge | PWD | 137.66 | 110.13 | 110.13 | 2012-02-24 |  |  | 2015-03-31 |  |  |  | 70
17 | R172000101 | Submersible Bridge On Harkiyakhal River | Neemuch | Neemuch | Bridge | PWD | 113.29 | 98.02 | 88.16 | 2012-02-24 |  |  | 2015-03-31 |  |  |  | 75
17 | R172000102 | High Level Across Bhadaksanawad Nallah | Neemuch | Neemuch | Bridge | PWD | 121.35 | 97.08 | 68.48 | 2012-02-24 |  |  | 2015-03-31 |  |  |  | 45
17 | R172000103 | High Level Bridge Across Ken River On Bishani | Panna | Shahnagar | Bridge | PWD | 330.79 | 272.77 | 69.39 | 2012-02-24 |  |  | 2015-03-31 |  |  |  | 180
17 | R172000104 | Submersible Bridge On Tikod-Ninor- | Rajgarh | Sarangpur | Bridge | PWD | 307.09 | 303.06 | 303.06 | 2012-02-24 |  |  | 2015-03-31 |  |  |  | 150
17 | R172000105 | Submersible Bridge Across Narmada | Raisen | Badi | Bridge | PWD | 1635.39 | 1635.39 | 1635.39 | 2012-02-24 |  |  | 2015-03-31 |  |  |  | 455
17 | R172000106 | High Level Bridge Across Sonar River On | Sagar | Rehli | Bridge | PWD | 192.11 | 157.3 | 150.18 | 2012-02-24 |  |  | 2015-03-31 |  |  |  | 62
17 | R172000107 | Submersible Bridge Across Waingang | Seoni | Chhapara | Bridge | PWD | 337.72 | 337.72 | 575.3 | 2012-02-24 |  |  | 2015-03-31 |  |  |  | 150
17 | R172000108 | High Level Bridge On Chillar River | Shajapur | Shajapur | Bridge | PWD | 412.18 | 330.1 | 542.84 | 2012-02-24 |  |  | 2015-03-31 |  |  |  | 210
17 | R172000109 | High Level Bridge Across Sheep River-Sheopur | Sheopur | Sheopur | Bridge | PWD | 278.5 | 277.42 | 276.92 | 2012-02-24 |  |  | 2015-03-31 |  |  |  | 125
17 | R172000112 | Submersible Bridge On Kshipra River Alot-Jharda | Ujjain | Mahidpur | Bridge | PWD | 411.45 | 329.94 | 297.22 | 2012-02-24 |  |  | 2015-03-31 |  |  |  | 250
17 | R172000113 | Submersible Bridge On Bagedi River | Ujjain | Badnagar | Bridge | PWD | 126.18 | 108.02 | 84.81 | 2012-02-24 |  |  | 2015-03-31 |  |  |  | 45
17 | R172000114 | Submersible Bridge Across Chhoti Kalisindh | Ujjain | Mahidpur | Bridge | PWD | 207.23 | 207.23 | 207.23 | 2012-02-24 |  |  | 2015-03-31 |  |  |  | 150
17 | R172000115 | Submersible Bridge Across Kshipra-Panbihar Road | Ujjain | Ghatia | Bridge | PWD | 233.86 | 233.86 | 209.43 | 2012-02-24 |  |  | 2015-03-31 |  |  |  | 210
17 | R172000116 | High Level Bridge Across Kethan River On Pamakhedi | Vidisha | Sironj | Bridge | PWD | 133.25 | 123.18 | 119.96 | 2012-02-24 |  |  | 2015-03-31 |  |  |  | 60
17 | R172000117 | Bargi Diversion Project Phase Iv Right Bank Canal | Katni | Many Blocks | MJP | NVDA | 43124 | 43124 | 28531.37 | 2012-02-24 |  |  | 2017-03-31 |  |  |  | 34000
17 | R172000118 | Kushalpura MIP | Rajgarh | Biaora | MIP | WRD | 3516.66 | 2878.86 | 2878.86 | 2012-02-24 |  |  | 2017-03-31 |  |  |  | 7540
17 | R172000119 | Rehti MIP | Vidisha | Kurwai | MIP | WRD | 2152.29 | 1914.28 | 1914.05 | 2012-03-06 |  |  | 2017-05-01 |  |  |  | 1975
17 | R172000120 | Godown | Hoshangabad | Macherakala | Godown | MPWLC | 362.22 | 344.11 | 344.12 | 2012-03-06 |  |  | 2015-05-01 |  |  |  | 10000
17 | R172000121 | Godown | Hoshangabad | Umardha | Godown | MPWLC | 187.88 | 178.49 | 178.49 | 2012-03-06 |  |  | 2015-05-01 |  |  |  | 5000
17 | R172000122 | Godown | Hoshangabad | Bankhedi | Godown | MPWLC | 60.27 | 57.26 | 57.27 | 2012-03-06 |  |  | 2015-05-01 |  |  |  | 1800
17 | R172000123 | Convertible CAP | Harda | Kheda | CAP | MPWLC | 545.04 | 517.79 | 451.71 | 2012-03-06 |  |  | 2015-05-01 |  |  |  | 30000
17 | R172000124 | Convertibe CAP | Harda | Ajnas | CAP | MPWLC | 736.55 | 699.72 | 612.42 | 2012-03-06 |  |  | 2015-05-01 |  |  |  | 40000
17 | R172000125 | Convertibe CAP | Harda | Sultanpur | CAP | MPWLC | 275.68 | 261.9 | 162.72 | 2012-03-06 |  |  | 2015-05-01 |  |  |  | 10000
17 | R172000126 | Convertibe CAP | Bhopal | Hinotia Alam | CAP | MPWLC | 448.21 | 425.8 | 0 | 2012-03-06 |  |  | 2015-05-01 |  |  |  | 21600
17 | R172000127 | Convertibe CAP | Sehore | Takipur | CAP | MPWLC | 601.52 | 571.44 | 571.44 | 2012-03-06 |  |  | 2015-05-01 |  |  |  | 37800
17 | R172000128 | Convertibe CAP | Hoshangabad | Samnapur | CAP | MPWLC | 1291.66 | 1227.08 | 441.97 | 2012-03-06 |  |  | 2015-05-01 |  |  |  | 75000
17 | R172000129 | Convertibe CAP | Hoshangabad | Dhikwada | CAP | MPWLC | 193.38 | 183.71 | 99.75 | 2012-03-06 |  |  | 2015-05-01 |  |  |  | 10000
17 | R172000130 | Convertibe CAP | Hoshangabad | Umaradha | CAP | MPWLC | 558.1 | 530.2 | 288.45 | 2012-03-06 |  |  | 2015-05-01 |  |  |  | 30000
17 | R172000131 | Convertibe CAP | Vidisha | Vidisha | CAP | MPWLC | 535.59 | 508.81 | 508.81 | 2012-03-06 |  |  | 2015-05-01 |  |  |  | 32400
17 | R172000132 | Convertibe CAP | Vidisha | Ganjbasoda | CAP | MPWLC | 535.59 | 508.81 | 494 | 2012-03-06 |  |  | 2015-05-01 |  |  |  | 32400
17 | R172000133 | Convertibe CAP | Raisen | Dibatiya | CAP | MPWLC | 271.43 | 257.86 | 228.83 | 2012-03-06 |  |  | 2015-05-01 |  |  |  | 20000
17 | R172000134 | Conversion Of Existing CAP Into Godown | Raisen | Bamhori | CAP-Godown | MPWLC | 391.97 | 372.37 | 372.37 | 2012-03-06 |  |  | 2015-05-01 |  |  |  | 20000
17 | R172000135 | Conversion Of Existing CAP Into Godown | Sehore | Rehati | CAP-Godown | MPWLC | 129.66 | 123.17 | 117.82 | 2012-03-06 |  |  | 2015-05-01 |  |  |  | 5000
17 | R172000136 | Conversion Of Existing CAP Into Godown | Sehore | Takipur | CAP-Godown | MPWLC | 258 | 245.1 | 245.1 | 2012-03-06 |  |  | 2015-05-01 |  |  |  | 11800
17 | R172000137 | Godown (Under Peg Scheme) | Seoni | Seoni | Godown | MPWLC | 508.03 | 482.63 | 482.63 | 2012-03-06 |  |  | 2015-05-01 |  |  |  | 15000
17 | R172000138 | Godown (Under Peg Scheme) | Shivpuri | Shivpuri | Godown | MPWLC | 182.15 | 173.04 | 140.94 | 2012-03-06 |  |  | 2015-05-01 |  |  |  | 5000
17 | R172000139 | Godown (Under Peg Scheme) | Dhar | Dhar | Godown | MPWLC | 666.29 | 632.97 | 632.98 | 2012-03-06 |  |  | 2015-05-01 |  |  |  | 20000
17 | R172000140 | Godown (Under Peg Scheme) | Jhabua | Meghnagar | Godown | MPWLC | 234.98 | 223.23 | 223.23 | 2012-03-06 |  |  | 2015-05-01 |  |  |  | 8000
17 | R172000141 | Godown (Under Peg Scheme) | Dindori | Dindori | Godown | MPWLC | 361.5 | 343.43 | 343.43 | 2012-03-06 |  |  | 2015-05-01 |  |  |  | 10000
17 | R172000142 | Godown (Under Peg Scheme) | Raisen | Dibatia | Godown | MPWLC | 653.97 | 621.27 | 621.26 | 2012-03-06 |  |  | 2015-05-01 |  |  |  | 20000
18 | R182000002 | Omkareshwar Phase Iv Right Bank Lift Canal | Khargone | Khargone & Dhar | MJP | NVDA | 7218.7 | 7218.7 | 6604.16 | 2012-11-08 |  |  | 2017-12-31 |  |  |  | 54630
18 | R182000003 | Gausabas Adanwara Balaya Road | Damoh | Damoh | Road | PWD | 919.69 | 735.75 | 688.99 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 23.6
18 | R182000004 | Dongala To Meen & Dongala To Narayana Road | Ujjain | Ujjain | Road | PWD | 595.79 | 476.63 | 244.14 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 14.9
18 | R182000005 | Jhitarkhedi To Bichhrod Road | Ujjain | Ujjain | Road | PWD | 401.1 | 320.88 | 223.65 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 7.8
18 | R182000006 | Runaheda To Gunaai Road | Ujjain | Ujjain | Road | PWD | 202.59 | 162.07 | 162.07 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 5.9
18 | R182000007 | Madigarda Patwarikheda Road | Vidisha | Vidisha | Road | PWD | 280.19 | 224.15 | 224.15 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 6.6
18 | R182000008 | Anandpur Bhagwantapur Road To Shirajnagar Satpada | Vidisha | Vidisha | Road | PWD | 248.04 | 198.43 | 190.99 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 6
18 | R182000009 | Dehripama Raypura To Barod Road | Vidisha | Vidisha | Road | PWD | 453.28 | 362.62 | 204 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 11.5
18 | R182000010 | Madipur Nandor Ambar Naulasa Road | Vidisha | Vidisha | Road | PWD | 446.39 | 357.11 | 319.58 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 12
18 | R182000011 | Tarha Nitri Bhadora Teelam Mudra Ahmedpur Road | Vidisha | Vidisha | Road | PWD | 561.96 | 449.57 | 278.87 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 14.2
18 | R182000012 | Dayanandpur To Boriya Via Bamankhuda Via Boriya Ka | Vidisha | Vidisha | Road | PWD | 368.3 | 294.64 | 191.54 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 9.65
18 | R182000013 | Chatoli To Hironda Road | Vidisha | Vidisha | Road | PWD | 404.74 | 323.79 | 244.83 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 8.06
18 | R182000014 | Naulasa Bawariya Kheruva Road | Vidisha | Vidisha | Road | PWD | 376.39 | 301.11 | 198.88 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 7.5
18 | R182000017 | Kubarhat Babiya Road | Jabalpur | Jabalpur | Road | PWD | 204.76 | 163.81 | 163.81 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 4.02
18 | R182000018 | Savalkheda To Jawar Road | Khandwa | Khandwa | Road | PWD | 277.32 | 221.86 | 221.86 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 5.8
18 | R182000019 | Ashapura Betul S.H.No. 25 To Kalighodi To Mehlu Ro | Khandwa | Khandwa | Road | PWD | 412.08 | 329.66 | 294.55 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 8
18 | R182000020 | Pandana Rustompur Road | Khandwa | Khandwa | Road | PWD | 164.4 | 131.52 | 110.79 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 4.7
18 | R182000022 | Malhargad To Jhamad Road | Khandwa | Khandwa | Road | PWD | 305.66 | 244.53 | 183.81 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 5
18 | R182000023 | Barur To Bheelkheda Chhirvel Road | Khandwa | Khandwa | Road | PWD | 201.98 | 161.58 | 140.98 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 6.2
18 | R182000027 | Kanhadgaon To Chinchgaon Road | Balaghat | Balaghat | Road | PWD | 223.11 | 178.49 | 178.49 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 6.1
18 | R182000028 | Bharweli To Bagholi Ameda Road | Balaghat | Balaghat | Road | PWD | 157.78 | 126.22 | 118.79 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 4.2
18 | R182000029 | Vishrampur Ghodatola Nevargaon Road | Balaghat | Balaghat | Road | PWD | 98.74 | 78.99 | 78.99 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 3.2
18 | R182000030 | Balaghat Town Interior Road | Balaghat | Balaghat | Road | PWD | 656.17 | 524.94 | 506.65 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 10.2
18 | R182000031 | Damkhedi Bhatkhedi Road | Bhopal | Bhopal | Road | PWD | 391.57 | 313.26 | 259.51 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 9.3
18 | R182000032 | Bheelakhedi Parkhedi Gehukheda To Maharishi Vidyam | Raisen | Raisen | Road | PWD | 334.01 | 267.21 | 90.92 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 7.1
18 | R182000033 | Kewatpipaliya Umraoganj Saikheda Road | Raisen | Raisen | Road | PWD | 208.87 | 167.1 | 140.61 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 4.3
18 | R182000034 | Amravad Sankheda Road To Gugulwada Road | Raisen | Raisen | Road | PWD | 71.89 | 57.51 | 43 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 0.8
18 | R182000035 | Devata To Barhakalan Road | Raisen | Raisen | Road | PWD | 155.95 | 124.76 | 95.98 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 3.86
18 | R182000036 | Kutnaseer To Shivtala Palkarshi Road | Raisen | Raisen | Road | PWD | 298 | 238.4 | 238.4 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 7.7
18 | R182000037 | Bamanwada Dhandala Dehrikala Gugalwada Sankheda Ro | Raisen | Raisen | Road | PWD | 309.6 | 247.68 | 247.68 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 7.76
18 | R182000038 | Chhabara To Khetoghan Road | Raisen | Raisen | Road | PWD | 171.43 | 137.14 | 108.41 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 4.7
18 | R182000039 | Chhabara To Pipariya Puvariya Road | Raisen | Raisen | Road | PWD | 184.28 | 147.42 | 147.42 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 4.02
18 | R182000040 | Magardha Umariya Bhilwadiya Bugulwada Road | Raisen | Raisen | Road | PWD | 531.66 | 425.33 | 425.33 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 11.44
18 | R182000041 | Chaayan To Makdi Road | Mandsaur | Mandsaur | Road | PWD | 226.83 | 181.46 | 140.39 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 4.5
18 | R182000042 | Bakhatgad Kadmal Mathwad Road | Alirajpur | Alirajpur | Road | PWD | 693.66 | 554.93 | 312.97 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 12.34
18 | R182000043 | Deori To Kesali Road | Sagar | Sagar | Road | PWD | 172.14 | 137.71 | 137.71 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 6.2
18 | R182000044 | Lidhorakhurd To Pipariya Turn Via Batallion Road | Sagar | Sagar | Road | PWD | 279.13 | 223.3 | 146.21 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 4.2
18 | R182000045 | Tundri To Dhooltara Road | Sagar | Sagar | Road | PWD | 342.69 | 342.69 | 317.26 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 8.5
18 | R182000046 | Maangad Shahpur Dhura Road | Sagar | Sagar | Road | PWD | 394.07 | 386.66 | 386.66 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 10.5
18 | R182000049 | Paagara Approach Road | Sagar | Sagar | Road | PWD | 298.12 | 238.5 | 238.5 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 5.5
18 | R182000053 | Tilakheda To Chavada Road | Sagar | Sagar | Road | PWD | 227.52 | 182.02 | 118.79 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 3.65
18 | R182000058 | Kisangad To Panth Piplodha Road | Ratlam | Ratlam | Road | PWD | 244.7 | 195.76 | 195.76 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 5.5
18 | R182000059 | Ringnod To Hathpipaliya | Ratlam | Ratlam | Road | PWD | 460.74 | 368.59 | 298.59 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 14.5
18 | R182000061 | Thirmau To Kharpadakhedi Badchowk Road | Betul | Betul | Road | PWD | 198.94 | 159.15 | 152.92 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 5
18 | R182000062 | Thaani To Dhanori Parsdoh Road | Betul | Betul | Road | PWD | 224.38 | 179.5 | 152.36 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 6
18 | R182000064 | Harai Bheda Thendni Jogiwadi Hathikho Road | Chhindwara | Chhindwara | Road | PWD | 236.44 | 189.15 | 182.95 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 6.2
18 | R182000065 | Batkakhapa Saaldana Chureesajava Uttariya Dharamkh | Chhindwara | Chhindwara | Road | PWD | 241.56 | 193.25 | 193.25 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 6.6
18 | R182000066 | Bijori To Pandu Pipariya Chhindi To Batkakha Harai | Chhindwara | Chhindwara | Road | PWD | 525.7 | 420.56 | 0 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 7
18 | R182000067 | Bijori Chhindi Khapa Harai Road Km 19 To Kathotiya | Chhindwara | Chindwarha | Road | PWD | 67.2 | 53.76 | 0 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 3
18 | R182000069 | Khairi Goditola Savri Road | Balaghat | Balaghat | Road | PWD | 376.73 | 301.38 | 301.38 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 7.34
18 | R182000070 | Bahegaon Dohra Salabari Tegnikhurd Banjari Road | Balaghat | Balaghat | Road | PWD | 411.02 | 328.82 | 264.78 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 7.4
18 | R182000071 | Khairlanji Ghobadgaundi Road | Balaghat | Balaghat | Road | PWD | 266.01 | 212.81 | 202.12 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 4.52
18 | R182000072 | Birsola Khamariya Khursodi Road | Balaghat | Balaghat | Road | PWD | 224.77 | 179.82 | 156.14 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 7.84
18 | R182000073 | Behrayi Landajhari Kaydi Road | Balaghat | Balaghat | Road | PWD | 204.52 | 163.62 | 158.66 | 2012-11-08 |  |  | 2015-12-31 |  |  |  | 6.1
18 | R182000074 | Construction Of Anganwadi Building At Various Loca | Sehore | various places | Anganwadi | W&CD | 5002.4 | 4252.04 | 1281.663 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 368
18 | R182000075 | Construction Of Anganwadi Building At Various Loca | Vidisha | various places | Anganwadi | W&CD | 4987.6 | 4239.46 | 908.737 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 307
18 | R182000076 | Indira Sagar Project (Canals ) Phase V Khargone Li | Khargone | Khargone | MJP | NVDA | 5967.14 | 5967.14 | 5363.1 | 2012-12-20 |  |  | 2018-01-31 |  |  |  | 33140
18 | R182000077 | Upper Narmada Project | Dindori | Dindori, Anuppur | MJP | NVDA | 57841.1 | 5784.11 | 1612.7 | 2012-12-20 |  |  | 2018-01-31 |  |  |  | 18616
18 | R182000078 | Keetkhedi Medium Tank Project | Shajapur | Shajapur | MIP | WRD | 6647 | 6045.28 | 5758.28 | 2012-12-20 |  |  | 2018-01-31 |  |  |  | 3480
18 | R182000079 | Semri Medium Project | Raisen | Raisen | MIP | WRD | 8312.9 | 8312.9 | 8312.9 | 2012-12-20 |  |  | 2018-01-31 |  |  |  | 11090.82
18 | R182000080 | Rithouri L.P. R. To Tilgawan Road | Jabalpur | Panagar | Road | PWD | 298.12 | 238.5 | 238.5 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 7.1
18 | R182000081 | Nandni Pipaliya Nagar Road | Shajapur | Kalapipal | Road | PWD | 449.56 | 359.65 | 242.56 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 6.6
18 | R182000082 | Padariyiakala To Anuppur District Border Road | Dindori | Dindori | Road | PWD | 309.08 | 247.26 | 239.5 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 4.25
18 | R182000083 | Roosa Barnai Medakhar Pakrisoda Road | Dindori | Karanjia | Road | PWD | 1225.74 | 980.59 | 447.79 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 20.31
18 | R182000084 | Nangda - Bercha Road | Ujjain | Khachrod | Road | PWD | 261.73 | 209.38 | 206.03 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 7.8
18 | R182000085 | Hirapur To Chitawad Road | Khargone | Badwah | Road | PWD | 336.47 | 269.18 | 269.18 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 10.46
18 | R182000086 | Kasdawad To Navdatodi Road | Khargone | Maheshwar | Road | PWD | 231.91 | 185.53 | 185.52 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 4.8
18 | R182000087 | Biaora NH 3 To Podonia Road | Rajgarh | Biaora | Road | PWD | 164.04 | 131.23 | 125.79 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 4
18 | R182000088 | Suthaliya Mau Lakhanwas Road | Rajgarh | Biaora | Road | PWD | 1801.74 | 1441.39 | 1261.31 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 25.6
18 | R182000089 | S.H. 12 To Tumda Road | Sehore | Sehore | Road | PWD | 145.45 | 116.36 | 85.64 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 2
18 | R182000091 | Dhupkhad Duari Road | Sidhi | Kusumi | Road | PWD | 475.72 | 380.58 | 241.65 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 9.48
18 | R182000092 | Bedapani To Palasi Road | Sehore | Narsulaganj | Road | PWD | 407.03 | 325.62 | 309.88 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 8
18 | R182000093 | Matthagaon To Ranikundi Road | Sehore | Budhni | Road | PWD | 240.24 | 192.19 | 163.23 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 3.3
18 | R182000094 | Pan Guradia To Dhankoat Road | Sehore | Budhni | Road | PWD | 123.22 | 98.58 | 92.79 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 2.2
18 | R182000095 | Silawad To Barwani Via Ambapani Road | Barwani | Barwani | Road | PWD | 254.44 | 203.55 | 156.42 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 6.14
18 | R182000096 | Kuthiyana To Rahuapura | Morena | Amban | Road | PWD | 197.11 | 157.69 | 112.68 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 4.5
18 | R182000097 | Karkeli Raipur Bagdari Bijauri Road | Umaria | Kerkeli | Road | PWD | 808.91 | 647.13 | 474.68 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 12
18 | R182000098 | Kergoan Patadah Kohkatola Chinchgaon Jamgaon Ghat | Mandla | Naipur | Road | PWD | 562.4 | 449.92 | 448.86 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 15.5
18 | R182000099 | Sundar Ka Pura To Anthiyan Ka Pura | Bhind | Lahar | Road | PWD | 205.61 | 164.49 | 158.95 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 9
18 | R182000100 | Porsa Ater Road | Morena | Porsa | Road | PWD | 114.63 | 91.7 | 86.33 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 3.45
18 | R182000101 | Richora To Damadehi Bahravan Road | Sehore | Budhni | Road | PWD | 209.2 | 167.36 | 126.56 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 3.7
18 | R182000102 | Vitka Pura Via Malukapura Kalukapura Betalkapura R | Morena | Amban | Road | PWD | 355.13 | 284.1 | 176.34 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 7.5
18 | R182000103 | Milanpur Noorabad Via Bichola Rethora Road | Morena | Morena | Road | PWD | 632.38 | 505.9 | 460.45 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 17.5
18 | R182000104 | Wajidpur To Panwarihat Road | Ashoknagar | Asoknagar | Road | PWD | 561.85 | 449.48 | 423.26 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 14.5
18 | R182000105 | Pranpur To Nankpura Hirapur Road | Ashoknagar | Chanderi | Road | PWD | 1287.08 | 1029.66 | 1029.66 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 19.18
18 | R182000106 | Eshagarh To Kadwaya Via Devkani Mata Mandir Road | Ashoknagar | Eshagarh | Road | PWD | 132.43 | 105.94 | 105.94 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 3.8
18 | R182000107 | Pachera Pali Road | Bhind | Mehgaon | Road | PWD | 113.88 | 91.1 | 77.05 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 2.4
18 | R182000108 | Bahua To Soni Via Maharajpura Road | Bhind | Bhind | Road | PWD | 191.9 | 153.52 | 75.34 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 5.4
18 | R182000109 | Alampur To Aagariyakala Road | Raisen | Gairatganj | Road | PWD | 499.41 | 399.53 | 304.59 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 12.75
18 | R182000110 | Bhopal Sagar Road To Semra Baramad Sounther Road | Raisen | Sanchi | Road | PWD | 515.8 | 412.64 | 360.61 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 9.8
18 | R182000111 | Singaldeep Narendrapur Road | Jabalpur | Panagar | Road | PWD | 580.91 | 464.73 | 464.73 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 8.4
18 | R182000112 | Mankhedi Kusumi Road | Jabalpur | Shahpura | Road | PWD | 361.8 | 289.44 | 289.42 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 7.68
18 | R182000113 | Suhasa To Kanjhar Road | Ujjain | Badnagar | Road | PWD | 266.65 | 213.32 | 213.31 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 11.6
18 | R182000114 | Shamshabad To Motipura Binjha Road | Vidisha | Shamsadabad | Road | PWD | 360.31 | 288.25 | 218.28 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 3.68
18 | R182000116 | Aaokodia To Karju Road | Mandsaur | Mandsaur | Road | PWD | 307.3 | 245.84 | 163.35 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 6.5
18 | R182000117 | Kacharia To Raykheda Road | Mandsaur | Sitamau | Road | PWD | 194.34 | 155.47 | 86.74 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 6.4
18 | R182000118 | Nandwel To Mawta Road | Mandsaur | Mandsaur | Road | PWD | 434.93 | 347.94 | 265.96 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 3.8
18 | R182000119 | Semra Saiyad To Khamkheda Road | Bhopal | Fanda | Road | PWD | 454.54 | 363.63 | 244.72 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 9.6
18 | R182000120 | Ghatkhedi To Sukhi Sevania Road | Bhopal | Fanda | Road | PWD | 220.55 | 176.44 | 133.88 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 8
18 | R182000121 | Bhagikheda To Bhadoos Road | Betul | Betul | Road | PWD | 108.2 | 86.56 | 86.56 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 4
18 | R182000122 | Bithli To Manegaon Road | Balaghat | Birsa | Road | PWD | 155.78 | 124.62 | 91.16 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 2.5
18 | R182000123 | Bothli To Behela Road | Balaghat | Lanji | Road | PWD | 176 | 140.8 | 136.35 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 5.5
18 | R182000128 | Taraganj To Babaliya Road | Rajgarh | Sarangpur | Road | PWD | 242.63 | 227.82 | 227.81 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 28
18 | R182000129 | A.B. Road Udankhedi To Sultania Dhamanda Road | Rajgarh | Sarangpur | Road | PWD | 266.97 | 213.58 | 162.91 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 7.2
18 | R182000130 | A.B. Road Patadia Bulandpur Road | Rajgarh | Sarangpur | Road | PWD | 392.98 | 314.38 | 249.93 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 8.7
18 | R182000132 | Badagaon Ramgarh Lakhoni Road | Rajgarh | Zirapur | Road | PWD | 651.17 | 520.94 | 104.18 | 2012-12-20 |  |  | 2016-01-31 |  |  |  | 11.6
18 | R182000133 | Construction Of Building For I. T. I (Convention | Rajgarh | Khujner | ITI-C | TE&SD | 350 | 297.5 | 260.99 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000134 | Construction Of Building For I. T. I (Convention | Mandsaur | shaamgarh | ITI-C | TE&SD | 350 | 297.5 | 288.09 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000135 | Construction Of Building For I. T. I (Convention | Mandsaur | Mandsaur | ITI-C | TE&SD | 350 | 297.5 | 297.3 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000136 | Construction Of Building For I. T. I (Convention | Guna | Kumbhraj | ITI-C | TE&SD | 350 | 297.5 | 123.96 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000137 | Construction Of Building For I. T. I (Convention | Guna | Chachoda | ITI-C | TE&SD | 350 | 297.5 | 82.18 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000138 | Construction Of Building For I. T. I (Convention | Ashoknagar | Ashoknagar | ITI-C | TE&SD | 350 | 297.5 | 197.2 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000139 | Construction Of Building For I. T. I (Convention | Dewas | Kannod | ITI-C | TE&SD | 350 | 297.5 | 131.37 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000140 | Construction Of Building For I. T. I (Convention | Datia | Datia | ITI-C | TE&SD | 350 | 297.5 | 297.5 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000141 | Construction Of Building For I. T. I (Convention | Tikamgarh | Tikamgarh | ITI-C | TE&SD | 350 | 297.5 | 289.68 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000142 | Construction Of Building For I. T. I (Convention | Chattarpur | Chhatarpur | ITI-C | TE&SD | 350 | 297.5 | 274.16 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000143 | Construction Of Building For I. T. I (Convention | Ujjain | Badnagar | ITI-C | TE&SD | 350 | 297.5 | 92.92 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000144 | Construction Of Building For I. T. I (Convention | Ujjain | Shujalpur | ITI-C | TE&SD | 350 | 297.5 | 116.78 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000145 | Construction Of Building For I. T. I (Convention | Sheopur | Sheopur | ITI-C | TE&SD | 350 | 297.5 | 250.38 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000146 | Construction Of Building For I. T. I (Convention | Barwani | Barwani | ITI-C | TE&SD | 350 | 297.5 | 213.76 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000147 | Construction Of Building For I. T. I (Convention | Khandwa | Mundi | ITI-C | TE&SD | 350 | 297.5 | 270.91 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000148 | Construction Of Building For I. T. I (Convention | Khandwa | Bhagwanpura | ITI-C | TE&SD | 350 | 297.5 | 204.84 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000149 | Construction Of Building For I. T. I (Convention | Barwani | Pati | ITI-C | TE&SD | 350 | 297.5 | 105.31 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000150 | Construction Of Building For I. T. I (Convention | Shivpuri | Kolaras | ITI-C | TE&SD | 350 | 297.5 | 207.63 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000151 | Construction Of Building For I. T. I (Convention | Shivpuri | pohari | ITI-C | TE&SD | 350 | 297.5 | 226.98 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000152 | Construction Of Building For I. T. I (Convention | Sidhi | Kusumi | ITI-C | TE&SD | 350 | 297.5 | 158 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000153 | Construction Of Building For I. T. I (Prefabrica | Chhindwara | Junardev | ITI-P | TE&SD | 595.57 | 506.23 | 154.63 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000154 | Construction Of Building For I. T. I (Prefabrica | Satna | Uchera | ITI-P | TE&SD | 595.57 | 506.23 | 123.93 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000155 | Construction Of Building For I. T. I (Prefabrica | Rajgarh | Biora | ITI-P | TE&SD | 595.57 | 506.23 | 439.51 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000156 | Construction Of Building For I. T. I (Prefabrica | Rajgarh | Rajgarh | ITI-P | TE&SD | 595.57 | 506.23 | 439.53 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000157 | Construction Of Building For I. T. I (Prefabrica | Vidisha | Ganjbasoda | ITI-P | TE&SD | 595.57 | 506.23 | 439.32 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000158 | Construction Of Building For I. T. I (Prefabrica | Vidisha | lateri | ITI-P | TE&SD | 595.57 | 506.23 | 439.44 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000159 | Construction Of Building For I. T. I (Prefabrica | bhopal | baresia | ITI-P | TE&SD | 595.57 | 506.23 | 506.23 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000160 | Construction Of Building For I. T. I (Prefabrica | Umaria | umaria | ITI-P | TE&SD | 595.57 | 506.23 | 412.22 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000161 | Construction Of Building For I. T. I (Prefabrica | Umaria | kohoka | ITI-P | TE&SD | 595.57 | 506.23 | 411.49 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000162 | Construction Of Building For I. T. I (Prefabrica | damoh | tendukheda | ITI-P | TE&SD | 595.57 | 506.23 | 112.47 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000163 | Construction Of Building For I. T. I (Prefabrica | Burhanpur | burhanpur | ITI-P | TE&SD | 595.57 | 506.23 | 107.03 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000164 | Construction Of Building For I. T. I (Prefabrica | Burhanpur | nepanagar | ITI-P | TE&SD | 595.57 | 506.23 | 124.43 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000165 | Construction Of Building For I. T. I (Prefabrica | Khargone | bhagwanpura | ITI-P | TE&SD | 595.57 | 506.23 | 144.57 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000166 | Construction Of Building For I. T. I (Prefabrica | Khargone | jeernia | ITI-P | TE&SD | 595.57 | 506.23 | 232.4 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000167 | Construction Of Building For I. T. I (Prefabrica | Hoshangabad | sohagpur | ITI-P | TE&SD | 595.57 | 506.23 | 431.65 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000168 | Construction Of Building For I. T. I (Prefabrica | balaghat | malajkhand | ITI-P | TE&SD | 595.57 | 506.23 | 213.21 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000169 | Construction Of Building For I. T. I (Prefabrica | Shahdol | jaitpur | ITI-P | TE&SD | 595.57 | 506.23 | 413.48 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000170 | Construction Of Building For I. T. I (Prefabrica | Shahdol | jaisinghpur | ITI-P | TE&SD | 595.57 | 506.23 | 409.99 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000171 | Construction Of Building For I. T. I (Prefabrica | Seoni | lucknadown | ITI-P | TE&SD | 595.57 | 506.23 | 117.23 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000172 | Construction Of Building For I. T. I (Prefabrica | Sehore | shahaganj | ITI-P | TE&SD | 595.57 | 506.32 | 439.36 | 2013-02-08 |  |  | 2016-03-31 |  |  |  | 2468.6
18 | R182000173 | Halon Irrigation Project | Mandla | Mandla | MJP | NVDA | 31968 | 3196.8 | 1459.28 | 2013-02-08 |  |  | 2018-03-03 |  |  |  | 13040
18 | R182000174 | Bargi-BDP-Phase V -Rewa Branch Canal RD KM 24.00 To KM | Rewa | Rewa | MJP | NVDA | 33090.75 | 31436.21 | 10344.11 | 2013-02-08 |  |  | 2018-03-03 |  |  |  | 34800
18 | R182000175 | Sonpur Medium Tank Project | Sagar | Sagar | MIP | WRD | 12746.45 | 11309.29 | 7633.64 | 2013-02-08 |  |  | 2018-03-03 |  |  |  | 7000
18 | R182000176 | Godown | Bhopal | Mungalia Khurd | Godown | MPWLC | 960 | 720 | 0 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 24000
18 | R182000177 | Godown | Hoshangabad | Hathnapur | Godown | MPWLC | 330.61 | 247.5 | 247.51 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 10800
18 | R182000178 | Godown | Hoshangabad | Macherakala | Godown | MPWLC | 186.34 | 139.76 | 129.75 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 5400
18 | R182000179 | Godown | Hoshangabad | Dhikwada | Godown | MPWLC | 428.32 | 321.24 | 0 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 10000
18 | R182000180 | Godown | Harda | Bagwad | Godown | MPWLC | 186.34 | 139.76 | 139.76 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 5400
18 | R182000181 | Godown | Harda | Kheda | Godown | MPWLC | 1051.08 | 788.31 | 788.34 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 30000
18 | R182000182 | Godown | Harda | Saktapur | Godown | MPWLC | 1202.8 | 902.1 | 199.05 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 30000
18 | R182000183 | Godown | Jabalpur | Barkheda (Panagar) | Godown | MPWLC | 552.84 | 414.63 | 414.62 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 16200
18 | R182000184 | Godown | Bhind | Ghohad | Godown | MPWLC | 154.22 | 115.67 | 115.05 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 4800
18 | R182000185 | Godown | Gwalior | Dabra | Godown | MPWLC | 129.84 | 97.38 | 93.17 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 3600
18 | R182000186 | Godown | Datia | Datia | Godown | MPWLC | 129.84 | 97.38 | 97.39 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 6600
18 | R182000187 | Godown | Morena | Morena | Godown | MPWLC | 133.03 | 99.77 | 83.23 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 3600
18 | R182000188 | Godown | Shajapur | Momanbadodia | Godown | MPWLC | 36.09 | 27.07 | 27.07 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 1200
18 | R182000189 | Godown | Neemuch | Neemuch | Godown | MPWLC | 65.79 | 49.34 | 49.34 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 1800
18 | R182000190 | Godown | Mandsaur | Mandsaur | Godown | MPWLC | 120.58 | 90.43 | 90.43 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 3600
18 | R182000191 | Godown | Ratlam | Ratlam | Godown | MPWLC | 135.03 | 101.27 | 92.01 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 3600
18 | R182000192 | Godown | Sagar | Pagara | Godown | MPWLC | 166.74 | 125.05 | 123.51 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 5400
18 | R182000193 | Godown | Sheopur | Sheopur | Godown | MPWLC | 463.37 | 347.52 | 347.52 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 12000
18 | R182000194 | Godown | Rewa | Sirmar | Godown | MPWLC | 560 | 420 | 353.57 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 14000
18 | R182000195 | Godown | Dewas | Dewas | Godown | MPWLC | 1280 | 960 | 0 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 32000
18 | R182000196 | Godown | Ashoknagar | Ashoknagar | Godown | MPWLC | 200 | 150 | 139.27 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 5000
18 | R182000197 | Godown | Rajgarh | Rajgarh | Godown | MPWLC | 800 | 600 | 600 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 20000
18 | R182000198 | Convertible CAP | Bhopal | Mugalia Khurd | CAP | MPWLC | 700 | 665 | 0 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 48000
18 | R182000199 | Convertibe CAP | Raisen | Dibatia | CAP | MPWLC | 173.17 | 164.51 | 90.93 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 10000
18 | R182000200 | Convertibe CAP | Raisen | Noorganj | CAP | MPWLC | 769.45 | 730.98 | 683.61 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 50000
18 | R182000201 | Convertibe CAP | Harda | Sultanpur | CAP | MPWLC | 207.92 | 197.52 | 162.72 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 10000
18 | R182000202 | Convertibe CAP | Rewa | Sirmor | CAP | MPWLC | 310.01 | 294.51 | 294.52 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 30000
18 | R182000203 | Convertibe CAP | Chattarpur | Ramgarh | CAP | MPWLC | 336.98 | 320.13 | 247.29 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 15000
18 | R182000204 | Convertibe CAP | Panna | Gunnor | CAP | MPWLC | 412.09 | 391.49 | 334.33 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 20000
18 | R182000205 | Convertibe CAP | Tikamgarh | Niwari | CAP | MPWLC | 121.28 | 115.22 | 82.96 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 5400
18 | R182000206 | Conversion Of Existing CAP Into Godown | Harda | Kheda | CAP-Godown | MPWLC | 800 | 600 | 600.01 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 40000
18 | R182000207 | Conversion Of Existing CAP Into Godown | Harda | Sultanpur | CAP-Godown | MPWLC | 680 | 510 | 510.01 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 34000
18 | R182000208 | Conversion Of Existing CAP Into Godown | Harda | Sultanpur | CAP-Godown | MPWLC | 320 | 240 | 240 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 16000
18 | R182000209 | Conversion Of Existing CAP Into Godown | Hoshangabad | Semriharchand | CAP-Godown | MPWLC | 82.32 | 61.74 | 44.84 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 3000
18 | R182000210 | Conversion Of Existing CAP Into Godown | Hoshangabad | Banapura | CAP-Godown | MPWLC | 24 | 18 | 18.01 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 1200
18 | R182000211 | Conversion Of Existing CAP Into Godown | Hoshangabad | Samnapur | CAP-Godown | MPWLC | 700 | 525 | 525 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 35000
18 | R182000212 | Conversion Of Existing CAP Into Godown | Seoni | Narela | CAP-Godown | MPWLC | 555.3 | 416.25 | 416.25 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 25000
18 | R182000213 | Conversion Of Existing CAP Into Godown | Sehore | Takipur | CAP-Godown | MPWLC | 811.06 | 608.25 | 608.25 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 37800
18 | R182000214 | Conversion Of Existing CAP Into Godown | Hoshangabad | Pawarkheda | CAP-Godown | MPWLC | 1581.32 | 1185.99 | 1186 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 56500
18 | R182000215 | Conversion Of Existing CAP Into Godown | Seoni | Seoni | CAP-Godown | MPWLC | 157.12 | 117.84 | 109.93 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 5400
18 | R182000216 | Conversion Of Existing CAP Into Godown | Balaghat | Balaghat | CAP-Godown | MPWLC | 151.36 | 113.52 | 110.17 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 5400
18 | R182000217 | Conversion Of Existing CAP Into Godown | Katni | Katni | CAP-Godown | MPWLC | 151.36 | 113.52 | 111.24 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 5400
18 | R182000218 | Construction Of Pucca Caps - Rabi | Betul | Betul/ Nos-3 | CAP | Markfed | 147.22 | 139.86 | 104.96 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 15000
18 | R182000219 | Construction Of Pucca Caps - Rabi | Guna | Guna/ Nos-7 | CAP | Markfed | 343.52 | 326.34 | 147.3 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 35000
18 | R182000220 | Construction Of Pucca Caps - Rabi | Ashoknagar | Ashoknagar/ Nos-18 | CAP | Markfed | 883.33 | 839.17 | 619.68 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 90000
18 | R182000221 | Construction Of Pucca Caps - Rabi | Jabalpur | Jabalpur /Nos-9 | CAP | Markfed | 422.04 | 400.94 | 317.81 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 43000
18 | R182000222 | Construction Of Pucca Caps - Rabi | Seoni | Seoni/Nos-15 | CAP | Markfed | 736.11 | 699.3 | 572.6 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 75000
18 | R182000223 | Construction Of Pucca Caps - Rabi | Chhindwara | Chhindwara/Nos-10 | CAP | Markfed | 490.74 | 466.2 | 392.26 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 50000
18 | R182000224 | Construction Of Pucca Caps - Rabi | Narsinghpur | Narsinghpur/ Nos-10 | CAP | Markfed | 484.85 | 460.61 | 407.54 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 49400
18 | R182000225 | Construction Of Pucca Caps - Rabi | Mandla | Mandla/Nos-5 | CAP | Markfed | 235.56 | 223.78 | 182.73 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 24000
18 | R182000226 | Construction Of Pucca Caps - Rabi | Katni | Katni/Nos-6 | CAP | Markfed | 294.44 | 279.72 | 223.12 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 30000
18 | R182000227 | Construction Of Pucca Caps - Rabi | Dhar | Dhar/Nos-9 | CAP | Markfed | 412.22 | 391.61 | 185.5 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 42000
18 | R182000228 | Construction Of Pucca Caps - Rabi | Indore | Indore/Nos-10 | CAP | Markfed | 490.74 | 466.2 | 0 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 50000
18 | R182000229 | Construction Of Pucca Caps - Rabi | Khargone | Khargone/Nos-16 | CAP | Markfed | 765.56 | 727.28 | 397.37 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 78000
18 | R182000230 | Construction Of Pucca Caps - Rabi | Badwani | Badwani/Nos-3 | CAP | Markfed | 117.78 | 111.89 | 0 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 12000
18 | R182000231 | Construction Of Pucca Caps - Rabi | Khandwa | khandwa/Nos-15 | CAP | Markfed | 736.11 | 699.3 | 576.09 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 75000
18 | R182000232 | Construction Of Pucca Caps - Rabi | Rewa | Rewa/Nos-4 | CAP | Markfed | 196.3 | 186.48 | 186.48 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 20000
18 | R182000233 | Construction Of Pucca Caps - Rabi | Sidhi | Sidhi/Nos-4 | CAP | Markfed | 150.04 | 142.54 | 142.55 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 16000
18 | R182000234 | Construction Of Pucca Caps - Rabi | Singrauli | Singrauli/Nos-1 | CAP | Markfed | 44.17 | 41.96 | 41.62 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 4500
18 | R182000235 | Construction Of Pucca Caps - Rabi | Satna | Satna/Nos-6 | CAP | Markfed | 294.44 | 279.72 | 279.72 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 28000
18 | R182000236 | Construction Of Pucca Caps - Rabi | Shahdol | Shahdol/Nos-1 | CAP | Markfed | 19.63 | 18.65 | 18.54 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 2000
18 | R182000237 | Construction Of Pucca Caps - Rabi | Umaria | Umariya/Nos-1 | CAP | Markfed | 24.54 | 23.31 | 23.31 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 2500
18 | R182000238 | Construction Of Pucca Caps - Rabi | Annupur | Anuppur/Nos-5 | CAP | Markfed | 217.89 | 206.99 | 20.13 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 22200
18 | R182000239 | Construction Of Pucca Caps - Kharif | Jabalpur | Jabalpur/Nos-19 | CAP | Markfed | 712 | 676.4 | 661.2 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 89000
18 | R182000240 | Construction Of Pucca Caps - Kharif | Balaghat | Balaghat / Nos-25 | CAP | Markfed | 1000 | 950 | 921.05 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 125000
18 | R182000241 | Construction Of Pucca Caps - Kharif | Seoni | Seoni /Nos-10 | CAP | Markfed | 400 | 380 | 380 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 50000
18 | R182000242 | Construction Of Pucca Caps - Kharif | katni | Katni /Nos-5 | CAP | Markfed | 176 | 167.2 | 165.01 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 22000
18 | R182000243 | Construction Of Pucca Caps - Kharif | Mandla | Mandla /Nos-3 | CAP | Markfed | 88 | 83.6 | 64.39 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 11000
18 | R182000244 | Construction Of Pucca Caps - Kharif | Satna | Satna /Nos-8 | CAP | Markfed | 304 | 288.8 | 274.49 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 38000
18 | R182000245 | Construction Of Pucca Caps - Kharif | Shahdol | Shahdol /Nos-2 | CAP | Markfed | 80 | 76 | 68.64 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 10000
18 | R182000246 | Construction Of Pucca Caps - Kharif | Umaria | Umariya /Nos-3 | CAP | Markfed | 104 | 98.8 | 98.8 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 13000
18 | R182000247 | Construction Of Pucca Caps - Kharif | Singrauli | Singrauli /Nos-3 | CAP | Markfed | 120 | 114 | 95.3 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 15000
18 | R182000248 | Construction Of Pucca CAP - Type A | Raisen | Noorganj | CAP | MPWLC | 123.42 | 117.25 | 10.08 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 50000
18 | R182000249 | Construction Of Pucca CAP - Type B | Hoshangabad | Babai | CAP | MPWLC | 112.23 | 106.62 | 0 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 30000
18 | R182000250 | Construction Of Pucca CAP - Type B | Hoshangabad | Dokrikheda | CAP | MPWLC | 207.53 | 197.15 | 44.97 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 60000
18 | R182000251 | Construction Of Pucca CAP - Type B | Hoshangabad | Hathnapur | CAP | MPWLC | 85.2 | 80.94 | 161.88 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 20000
18 | R182000252 | Construction Of Pucca CAP - Type B | Harda | Bagwad | CAP | MPWLC | 543.3 | 516.14 | 36.28 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 73400
18 | R182000253 | Construction Of Pucca CAP - Type B | Bhopal | Mungaliakot | CAP | MPWLC | 209.57 | 199.09 | 28.91 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 30000
18 | R182000254 | Construction Of Pucca CAP - Type B | Hoshangabad | Various places | CAP | MPWLC | 239.91 | 227.91 | 287.33 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 30000
18 | R182000255 | Construction Of Pucca CAP - Type B | Harda | Various places | CAP | MPWLC | 370.1 | 351.6 | 0 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 50000
18 | R182000256 | Construction Of Pucca CAP - Type C | Raisen | Noorganj | CAP | MPWLC | 370.1 | 351.6 | 0 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 50000
18 | R182000257 | Construction Of Pucca CAP - Type C | Raisen | Goharganj | CAP | MPWLC | 209.57 | 199.09 | 10.29 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 30000
18 | R182000258 | Construction Of Pucca CAP - Type C | Sehore | Takipur | CAP | MPWLC | 122.31 | 116.19 | 116.19 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 20000
18 | R182000259 | Construction Of Pucca CAP - Type C | Rajgarh | Khujner road | CAP | MPWLC | 239.91 | 227.91 | 53.88 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 30000
18 | R182000260 | Construction Of Pucca CAP - Type C | Ujjain | Nagda Gram Pipaliyamolu | CAP | MPWLC | 366.14 | 347.83 | 106.86 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 45000
18 | R182000261 | Construction Of Pucca CAP - Type C | Shajapur | Makshi Gram Jhonker | CAP | MPWLC | 370.1 | 351.6 | 259.28 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 50000
18 | R182000262 | Construction Of Pucca CAP - Type C | Mandsaur | Mandsaur Gram Malyakhev Kheda | CAP | MPWLC | 481.13 | 457.07 | 0 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 65000
18 | R182000263 | Construction Of Pucca CAP - Type C | Sheopur | Sheopur | CAP | MPWLC | 370.1 | 351.6 | 351.6 | 2013-03-22 |  |  | 2016-05-01 |  |  |  | 50000
19 | R192000001 | Datuni Medium Tank Project | Dewas | Dewas | MIP | WRD | 15398.11 | 13774.74 | 13747.8 | 2013-07-19 |  |  | 2018-07-31 |  |  |  | 8800
19 | R192000002 | Mardanpur Group Water Supply Project | Sehore | Many | RDWS | MPJNM | 27467 | 23346 | 18453.35 | 2013-08-23 |  |  | 2018-08-31 |  |  |  | 25.65
19 | R192000003 | Udaipura Group Water Supply Project | Raisen | Many | RDWS | MPJNM | 15572 | 13235 | 11775.76 | 2013-08-23 |  |  | 2018-08-31 |  |  |  | 20.17
19 | R192000004 | Talunkhurd Group Water Supply Project | Barwani | Many | RDWS | MPJNM | 5188 | 4410 | 4283.91 | 2013-08-23 |  |  | 2018-08-31 |  |  |  | 6.6
19 | R192000005 | Bagod, Naadiya, Pipliya Group Water Supply Project | Khargone | Many | RDWS | MPJNM | 6753 | 5740 | 5394.52 | 2013-08-23 |  |  | 2018-08-31 |  |  |  | 7.95
19 | R192000006 | Arnia Bahadur Group Water Supply Project | Ujjain | Many | RDWS | MPJNM | 1252 | 1064 | 784.75 | 2013-08-23 |  |  | 2018-08-31 |  |  |  | 1.35
19 | R192000007 | Majholi Group Water Supply Project | Sidhi | Many | RDWS | MPJNM | 8166 | 6941 | 3103.66 | 2013-08-23 |  |  | 2018-08-31 |  |  |  | 10.3
19 | R192000008 | Bhatera Group Water Supply Project | Balaghat | Many | RDWS | MPJNM | 4111 | 3494 | 2652.51 | 2013-08-23 |  |  | 2018-08-31 |  |  |  | 18.23
19 | R192000009 | Manpur Group Water Supply Project | Umaria | Many | RDWS | MPJNM | 3810 | 3239 | 2362.54 | 2013-08-23 |  |  | 2018-08-31 |  |  |  | 7.6
19 | R192000010 | Devsara Group Water Supply Project | Balaghat | Many | RDWS | MPJNM | 3160 | 2686 | 1882.7 | 2013-08-23 |  |  | 2018-08-31 |  |  |  | 1.35
19 | R192000011 | Mehandwani Group Water Supply Project | Dindori | Many | RDWS | MPJNM | 4616 | 3924 | 0 | 2013-08-23 |  |  | 2018-08-31 |  |  |  | 2.59
19 | R192000012 | Extension Renovation Modernisation Of Barna Project | Raisen | Udayapura and Bari | MJP | WRD | 43688.58 | 41504.15 | 23538.94 | 2013-11-07 |  |  | 2018-12-01 |  |  |  | 70000
19 | R192000013 | Devla Baghadi To Barsalay Road | Barwani | Rajpur | Road | PWD | 380.08 | 304.06 | 304.06 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 9.73
19 | R192000014 | Enkheda To Jawra Road | Betul | Betul | Road | PWD | 124.57 | 124.57 | 124.57 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 4.48
19 | R192000015 | Dhodkheda Sawangi Gunkhed Road | Betul | Athner | Road | PWD | 139.73 | 139.73 | 139.73 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 6.44
19 | R192000016 | Katkuhi Jod Malajpur To Jharkund Road | Betul | CHICHOLI | Road | PWD | 198.63 | 198.63 | 198.63 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 7.3
19 | R192000017 | Parsodi Hathnora To Betulbajar Road | Betul | Betul | Road | PWD | 295.42 | 295.42 | 295.42 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 7.3
19 | R192000018 | Shahpur To Bhayawadi Road | Betul | Betul | Road | PWD | 516.23 | 516.23 | 516.23 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 11.6
19 | R192000019 | Dhulkot Boribujurg To Paschin Nimar Border Road | Burhanpur | Burhanpur | Road | PWD | 342.54 | 274.03 | 259.27 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 6.3
19 | R192000020 | Ganj Jhamtuli Amroliya Devra Road | Chattarpur | Bijawar | Road | PWD | 3270.76 | 2616.61 | 2309.7 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 30
19 | R192000021 | Kandela Rampurghat Road | Chattarpur | Barigarh | Road | PWD | 408.58 | 392.57 | 392.56 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 6
19 | R192000022 | Lugasi Jhijhan Sardarpur Road | Chattarpur | Nowgong | Road | PWD | 523.3 | 438.27 | 364.99 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 11
19 | R192000023 | Kanhargaon Musadehi Rohna Road | Chhindwara | Chhindwara | Road | PWD | 379.7 | 335.76 | 335.758 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 7.7
19 | R192000024 | Rajegaon Jamsimariya Chhindwara Road | Chhindwara | Mokhed | Road | PWD | 254.45 | 241.26 | 241.258 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 6.5
19 | R192000025 | Shivlaldhana Kukda Chiman Malhanwara To Chhindwara Chand Road | Chhindwara | Mohkhed | Road | PWD | 393.68 | 360.05 | 322.27 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 9.3
19 | R192000026 | Sadipura Deriya Sahu To Kulawad Road | Dewas | Bagli | Road | PWD | 62.82 | 62.82 | 62.82 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 1.9
19 | R192000027 | Barangi To Rolgaon Road | Harda | Harda | Road | PWD | 835.31 | 668.25 | 368.852 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 13.65
19 | R192000028 | Bhuvankhedi To Bamhoni Via Bhunnas Bhaironpur Rijgaon Kujargaon Road | Harda | Harda | Road | PWD | 962.91 | 770.33 | 432.264 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 16
19 | R192000029 | Sigon Gawla Malpon To Handiya Road | Harda | Handia | Road | PWD | 596.63 | 477.3 | 313.86 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 9
19 | R192000030 | Sohagpur Panralai Road | Harda | Timarni | Road | PWD | 286.73 | 229.38 | 204.3 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 4.2
19 | R192000031 | Bhaironpur To Golgaon Road | Hoshangabad | Seoni Malwa | Road | PWD | 140.2 | 112.16 | 106.52 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 3.04
19 | R192000034 | Tihariya Badshah To Industrial Area Sanwer Road | Indore | Depalpur | Road | PWD | 108.28 | 108.28 | 108.28 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 2.4
19 | R192000035 | Gowardhan Gaushala To Hingoniya Junction Road | Indore | Depalpur | Road | PWD | 146.69 | 146.69 | 125 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 5.5
19 | R192000036 | Kodiya To Charhawan Road | Katni | Bahoriband | Road | PWD | 445.06 | 356.05 | 251.66 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 7
19 | R192000037 | Badod Ahir To Deewal Road | Khandwa | Pandhana | Road | PWD | 270.95 | 236.26 | 236.258 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 5.47
19 | R192000038 | Bhakrada To Bamhangaon Khedikitta Road | Khandwa | Khandwa | Road | PWD | 222.51 | 222.51 | 222.508 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 6.42
19 | R192000039 | Khalwa Dongliya Road Via Kotha Road To Khalwa Devtalai Road | Khandwa | Khalwa | Road | PWD | 360.06 | 329.1 | 181.88 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 7.4
19 | R192000040 | Badi To Multhan Road | Khargone | Kasrawad | Road | PWD | 848.3 | 678.64 | 448.12 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 8.86
19 | R192000041 | Dolani To Dabri Road | Khargone | Kasrawad | Road | PWD | 450.67 | 360.54 | 360.54 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 8.61
19 | R192000042 | Gawla To Bamandi Road | Khargone | Kasrawad | Road | PWD | 138.29 | 110.63 | 110.63 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 4
19 | R192000043 | Khedi To Jaljyoti Road | Khargone | Kasrawad | Road | PWD | 233.17 | 193.61 | 193.61 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 6.62
19 | R192000044 | Kothibujurg To Kothikhurd Road | Khargone | Kasrawad | Road | PWD | 39.7 | 39.7 | 39.7 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 2.6
19 | R192000045 | Panwa To Ragwan Road | Khargone | Kasrawad | Road | PWD | 158.88 | 158.88 | 158.88 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 5.52
19 | R192000046 | Satrathi To Bhoinda Road | Khargone | Kasrawad | Road | PWD | 261.32 | 261.32 | 261.32 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 8.8
19 | R192000047 | Narayanganj To Devri Mukas Road | Mandla | Narayanganj | Road | PWD | 1681.69 | 1345.35 | 1233.79 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 21.5
19 | R192000048 | Boliya To Jain Diwakar (Chauthmalji Maharaj Diksha Sthal Tak) Road | Mandsaur | Garoth | Road | PWD | 180.97 | 144.78 | 118.74 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 3
19 | R192000049 | Takrawad To Devri Road | Mandsaur | Garoth | Road | PWD | 291.31 | 233.05 | 179.98 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 5
19 | R192000050 | Rajora To Satho Via Nagela Road | Morena | Porsa | Road | PWD | 224.84 | 179.87 | 179.87 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 6
19 | R192000051 | Mehgaontala To Bhama Road | Narsinghpur | Chawarphata | Road | PWD | 1215.62 | 972.5 | 358.92 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 20.3
19 | R192000052 | N. H. 12 To Bijora Road | Narsinghpur | Handia | Road | PWD | 354.18 | 283.34 | 283.462 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 5
19 | R192000054 | Kukdeshwar To Hanumantya Bhatkhedi Sudhi Lasodiya Road | Neemuch | Manasa | Road | PWD | 574.93 | 460.54 | 239.56 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 8.65
19 | R192000055 | Sarvaniya Maharaj To Aakli Melankheda Road | Neemuch | Neemuch | Road | PWD | 226.72 | 197.15 | 145.9 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 5.54
19 | R192000056 | Savan To Bhadwamata Road | Neemuch | Neemuch | Road | PWD | 238.49 | 209.2 | 185.86 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 4.42
19 | R192000057 | Amchhakalan To Umariya Road | Raisen | Goharganj | Road | PWD | 142.39 | 113.91 | 99.68 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 2.85
19 | R192000058 | Baktara To Arka Road | Raisen | Badi | Road | PWD | 317.55 | 254.04 | 87.2 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 5
19 | R192000059 | Baktara To Dighwad Road | Raisen | Badi | Road | PWD | 142.46 | 113.97 | 27.33 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 2.5
19 | R192000060 | Baktara To Gugalwara Mankapur Road | Raisen | Badi | Road | PWD | 517.03 | 413.62 | 413.616 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 11.2
19 | R192000061 | Baktara To Mangrol Road | Raisen | Badi | Road | PWD | 324.65 | 259.72 | 56.07 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 4.5
19 | R192000062 | Baktara To Maljhir Road | Raisen | Badi | Road | PWD | 388.62 | 310.9 | 117.48 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 7.06
19 | R192000063 | Bareli To Bagalwara Road | Raisen | Badi | Road | PWD | 1024.92 | 952.07 | 912.32 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 10.52
19 | R192000064 | Hiraniya To Tigariya Road | Raisen | Goharganj | Road | PWD | 227.32 | 181.86 | 122.35 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 4.5
19 | R192000065 | Jakhdapul To Nanakhedi Bhadki Saya Prem Jatab Divtiya Road | Raisen | Goharganj | Road | PWD | 419.68 | 335.74 | 247.57 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 8.5
19 | R192000066 | Ladli Khukariya To Umraoganj Road | Raisen | Obedullaganj | Road | PWD | 184.46 | 147.57 | 147.566 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 4.7
19 | R192000067 | Methagaon To Kekda Road | Raisen | Udaipura | Road | PWD | 57.91 | 57.91 | 57.91 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 2.4
19 | R192000068 | Kharwankalan Approach Road | Ratlam | A lot | Road | PWD | 32.8 | 32.8 | 32.8 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 3.64
19 | R192000069 | Panth Piploda Road | Ratlam | A lot | Road | PWD | 47.9 | 47.9 | 47.9 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 5.7
19 | R192000070 | Majhiyar Pathri Padri Sirmaur Road | Rewa | Sirmour | Road | PWD | 161.08 | 161.08 | 161.08 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 7.05
19 | R192000071 | Rewa Sirmaur Road To Gargantola Tiwarian Ka Tola Rajgarh Road | Rewa | Sirmour | Road | PWD | 506.23 | 404.98 | 293.46 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 9.35
19 | R192000072 | Umariya Gangev Road Via Giruari Road | Rewa | Gangeo | Road | PWD | 206.54 | 206.54 | 206.54 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 5.8
19 | R192000073 | Sehora Navalgaon Nagdahar Purwa Road | Seoni | Lakhnadon | Road | PWD | 253.69 | 223.71 | 166.48 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 5.64
19 | R192000074 | Bina Richhai Road | Sagar | Deori | Road | PWD | 235.16 | 235.16 | 235.16 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 8
19 | R192000075 | Baxwaha To Nainagir Road | Sagar | Banda | Road | PWD | 1108.51 | 886.81 | 863.3 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 13.2
19 | R192000076 | Jarara To Patan Road | Sagar | Sagar | Road | PWD | 138.07 | 110.46 | 76.07 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 2.38
19 | R192000077 | Jawti To Nishobarri Nainwash Manpur Road | Vidisha | Lateri | Road | PWD | 558.34 | 446.67 | 302.27 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 12.24
19 | R192000078 | Lateri Shamshabad Road To Nayagaon Dhokda Road | Vidisha | Lateri | Road | PWD | 484.45 | 387.56 | 236.29 | 2013-11-07 |  |  | 2016-12-31 |  |  |  | 10
19 | R192000079 | Datehara Group Water Supply Project | Morena | Many | RDWS | MPJNM | 2698.53 | 2293.75 | 0 | 2013-11-07 |  |  | 2018-12-31 |  |  |  | 4.8
19 | R192000080 | Narhela Group Water Supply Project | Morena | Many | RDWS | MPJNM | 6116.7 | 5199.2 | 3225.79 | 2013-11-07 |  |  | 2018-12-31 |  |  |  | 11.1
19 | R192000081 | Roshni Group Water Supply Project | Khandwa | Many | RDWS | MPJNM | 2714.83 | 2307.6 | 1055.47 | 2013-11-07 |  |  | 2018-12-31 |  |  |  | 2.15
19 | R192000082 | Gangabawdi Group Water Supply Project | Neemuch | Many | RDWS | MPJNM | 3887.62 | 3304.48 | 2694.77 | 2013-11-07 |  |  | 2018-12-31 |  |  |  | 4.55
19 | R192000083 | Punjapura Group Water Supply Project | Dewas | Many | RDWS | MPJNM | 1904.39 | 1618.74 | 1618.74 | 2013-11-07 |  |  | 2018-12-31 |  |  |  | 1.07
19 | R192000084 | Piparjhari Group Water Supply Project | balaghat | Many | RDWS | MPJNM | 1749.15 | 1486.78 | 1017.58 | 2013-11-07 |  |  | 2018-12-31 |  |  |  | 25.65
19 | R192000085 | Dhuti Group Water Supply Project | Balaghat | Many | RDWS | MPJNM | 2673.78 | 2272.71 | 1644.91 | 2013-11-07 |  |  | 2018-12-31 |  |  |  | 11.11
19 | R192000086 | Jhurki Group Water Supply Project | Seoni | Many | RDWS | MPJNM | 1109.03 | 942.67 | 810.7 | 2013-11-07 |  |  | 2018-12-31 |  |  |  | 6.47
19 | R192000087 | Kudam Group Water Supply Project | Jabalpur | Many | RDWS | MPJNM | 3566.49 | 3031.51 | 406.3 | 2013-11-07 |  |  | 2018-12-31 |  |  |  | 4.51
19 | R192000088 | Jhagri Karriya Rakh Laxman Kuti Road | Damoh | Damoh | Road | PWD | 117.52 | 117.52 | 106.8 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 4
19 | R192000089 | Kaikheda Harizantola Tigra Road | Damoh | Hatta | Road | PWD | 350.59 | 350.59 | 348.99 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 7.1
19 | R192000091 | Essagarh(Denga Mochar) To Pipariya- Nayagaon Road | Ashoknagar | Esagarh | Road | PWD | 641.01 | 512.81 | 102.56 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 8.46
19 | R192000092 | Rijoda Dongar Road | Ashoknagar | Mungaoli | Road | PWD | 1045.42 | 836.34 | 821.81 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 13.9
19 | R192000097 | Raikwar Nowgawan Road | Satna | Amarpatan | Road | PWD | 106.39 | 106.39 | 94.7 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 5.1
19 | R192000098 | Badera Ajmain Road | Satna | Maihar | Road | PWD | 142.47 | 142.47 | 109.36 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 5
19 | R192000099 | Ramvan Dilaura Road | Satna | Rampur Baghelon | Road | PWD | 145.01 | 145.01 | 138.33 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 3
19 | R192000100 | Bholiya To Kunchrod Road | Mandsaur | Mandsaur | Road | PWD | 187.05 | 149.64 | 109.83 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 4
19 | R192000101 | Pinda To Gujarbardiya Road | Mandsaur | Mandsaur | Road | PWD | 431.24 | 344.99 | 259.34 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 9.5
19 | R192000102 | Lamgari To Patalwada Road | Mandsaur | Mandsaur | Road | PWD | 299.96 | 239.97 | 192.48 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 6
19 | R192000103 | Sagore To Manpura Road | Mandsaur | Sitamau | Road | PWD | 84.54 | 84.47 | 77.12 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 2
19 | R192000104 | Malyakhedi To Jamalpura Kochavi Road | Mandsaur | Mandsaur | Road | PWD | 307.44 | 267.94 | 198.14 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 6.6
19 | R192000105 | Bilkisganj (Pani Ki Tank) Bamlagarh Via Gadiya Roa | Sehore | Icchawar | Road | PWD | 459.24 | 407.46 | 377.63 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 8.9
19 | R192000106 | Ashta Jagananthpura To Anandipura Road | Sehore | Ashta | Road | PWD | 140.03 | 136.34 | 136.34 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 3.6
19 | R192000107 | Gader To Isherpur Road | Sehore | Budni | Road | PWD | 103.74 | 82.99 | 82.99 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 1.7
19 | R192000108 | Rewgaon To Sanwalkheda Road | Sehore | Budni | Road | PWD | 215.52 | 172.42 | 34.48 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 3.1
19 | R192000109 | Kosmi To Gehukheda To Gondi Gundariya Road | Sehore | Budni | Road | PWD | 198.73 | 158.98 | 158.98 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 4
19 | R192000110 | Bordi To Gondi Guradiya To Jamoniya Bajyafat Road | Sehore | Budni | Road | PWD | 221.61 | 177.29 | 167.32 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 4.62
19 | R192000111 | Bordhi To Bordha Khela Via Narela Jod Road | Sehore | Budni | Road | PWD | 128.87 | 103.1 | 29.58 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 3
19 | R192000112 | Bhadkul To Jamoniya To Bordhi Approach Road | Sehore | Budni | Road | PWD | 346.49 | 277.19 | 154.66 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 7
19 | R192000113 | Bori To Dongri Road | Sehore | Budni | Road | PWD | 85 | 68 | 58.7 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 1.5
19 | R192000114 | Nonbhait To Theekri Road | Sehore | Budni | Road | PWD | 135.91 | 108.73 | 90.19 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 3.2
19 | R192000115 | Main Road Barda To Barda And Main Road To Pipaliya | Sehore | Budni | Road | PWD | 170.35 | 136.28 | 46.78 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 2.3
19 | R192000116 | Jait Sardar Nagar To Netankhedi Surajkund Road | Sehore | Budni | Road | PWD | 400.65 | 320.52 | 320.52 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 6.3
19 | R192000117 | Approach Road To Holipura Tappar( From Jait Naraya | Sehore | Budni | Road | PWD | 142.09 | 113.67 | 113.67 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 3
19 | R192000118 | Mogra To Gurusahab Internal Road | Sehore | Budni | Road | PWD | 119.69 | 95.75 | 85.85 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 1.06
19 | R192000119 | Shyampur To Thikrikheda Road | Sehore | Nasrullaganj | Road | PWD | 173.73 | 138.98 | 131.98 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 3
19 | R192000120 | Aanwali To Girvanya Road | Dhar | Kukshi | Road | PWD | 180.74 | 180.74 | 180.74 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 4.86
19 | R192000121 | Bhimpura To Chikali Road | Dhar | Kukshi | Road | PWD | 154.69 | 130.41 | 108.71 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 3.12
19 | R192000122 | Harai Pratap Singh Approach Road I/C Improvement O | Rewa | Hanumana | Road | PWD | 230.32 | 230.32 | 230.32 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 4
19 | R192000123 | Nagai To Atariya Shivprasad Road | Rewa | Mauganj | Road | PWD | 116.73 | 93.38 | 18.68 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 2.6
19 | R192000124 | Bichhodna Bagda Road | Datia | Bhander | Road | PWD | 106.68 | 101.34 | 97.6 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 3
19 | R192000125 | Sinawal To Gwalior Jhansi Via Tugyan Ka Dera Road | Datia | Datia | Road | PWD | 243.08 | 194.46 | 194.46 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 5.7
19 | R192000126 | Unao Sarsai Road | Datia | Datia | Road | PWD | 226.89 | 190.65 | 189.83 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 7.08
19 | R192000127 | Salaiya Pawar Road To Taka Via Chhata Road | Datia | Datia | Road | PWD | 502.53 | 402.02 | 312.22 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 14.31
19 | R192000128 | Nagda Bhikampur Road | Ujjain | Khachrod | Road | PWD | 129.44 | 129.44 | 25.89 | 2014-01-30 |  |  | 2017-03-03 |  |  |  | 10.48
19 | R192000129 | HL Bridge Across Betwa River Ashapuri Khasrod Salkani Wardhman Factory | Raisen | Obedullahganj | Bridge | PWD | 1611.83 | 1289.46 | 257.89 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 200
19 | R192000130 | Upper Tilwara Canal Project | Seoni | Dhanora | MIP | WRD | 9538.5 | 9061.58 | 8402.59 | 2014-03-24 |  |  | 2019-03-31 |  |  |  | 7950
19 | R192000131 | Aamkhut Kaththiwada Road | Alirajpur | Katthiwada | Road | PWD | 971.72 | 777.38 | 355.47 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 9.2
19 | R192000132 | Sorwa Kel Chandarmeli Phoolmal Road | Alirajpur | Katthiwada | Road | PWD | 481.53 | 385.22 | 202.51 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 6.99
19 | R192000133 | Parsol Sirni Indar Kadwaya Road | Ashoknagar | Esagarh | Road | PWD | 459.46 | 367.57 | 286.97 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 8
19 | R192000134 | Shadora Wajidpur Road | Ashoknagar | Ashoknagar | Road | PWD | 342.46 | 273.97 | 248.01 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 7
19 | R192000135 | Dudwa To Gram Ghat Temni Road | Balaghat | Langi | Road | PWD | 138.55 | 110.84 | 87.71 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 5.58
19 | R192000136 | Sihora -Sihoratola-Devgaon Road | Balaghat | Lalburra | Road | PWD | 270.82 | 216.66 | 146.97 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 3.5
19 | R192000137 | Barwani To Choti Kasrawad Road | Barwani | Barwani | Road | PWD | 157.69 | 126.15 | 126.15 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 2.48
19 | R192000138 | Lalbagh To Sharda Road | Burhanpur | Burhanpur | Road | PWD | 381.72 | 305.38 | 197.18 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 3.74
19 | R192000139 | Icchapur To Bhota Road | Burhanpur | Burhanpur | Road | PWD | 417.37 | 333.9 | 210.58 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 3.7
19 | R192000140 | Khajuraho Byepass Road | Chattarpur | Rajnagar | Road | PWD | 1410.3 | 1128.24 | 883.72 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 5
19 | R192000141 | Simri Jalamsingh To Chandu Choupra Road | Damoh | Jabera | Road | PWD | 130.12 | 104.1 | 82.72 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 2.8
19 | R192000142 | Patera Raneh Marg | Damoh | Patera | Road | PWD | 348.37 | 278.7 | 278.7 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 8
19 | R192000143 | Kheda Approach Road | Dhar | Dhar | Road | PWD | 152.09 | 152.09 | 115.97 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 1.5
19 | R192000144 | Bilhati Parsen Bahadurpura Road | Gwalior | Morar | Road | PWD | 348.45 | 348.45 | 296.84 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 9.9
19 | R192000145 | Bhadroli To Dilawar Road | Gwalior | Morar | Road | PWD | 177 | 141.6 | 107.96 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 5.2
19 | R192000146 | New Collectorate To Sirol Thiraha Road | Gwalior | Morar | Road | PWD | 305.67 | 290.21 | 256.7 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 1.73
19 | R192000147 | Campel Unhel Semria Karadia Road | Indore | Indore | Road | PWD | 873.99 | 699.19 | 651.81 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 12
19 | R192000148 | Khomana Aakya Gangakhedi Road | Indore | Indore | Road | PWD | 518.57 | 414.86 | 414.86 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 7.31
19 | R192000149 | Khajrana To Jhalriya Road Km.1/2 To 2/6 | Indore | Indore | Road | PWD | 170.54 | 136.43 | 96.3 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 1.5
19 | R192000150 | A.B To Soya Ruchi Factory Road | Indore | Indore | Road | PWD | 213.44 | 170.75 | 146.56 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 2.5
19 | R192000151 | Pipariya To Sonpur Beejkendra Road | Jabalpur | Panagar | Road | PWD | 353.32 | 282.66 | 83.23 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 3.3
19 | R192000152 | Sakri Bichua Nimbori Road | Jabalpur | Panagar | Road | PWD | 455.54 | 364.43 | 364.43 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 9
19 | R192000153 | Khirhani Sachuli Lamatara Deori Road | Jabalpur | Sihora | Road | PWD | 320.11 | 256.09 | 149.4 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 5
19 | R192000154 | Lamkana Majhgawan Bagheli Marg | Jabalpur | Majholi | Road | PWD | 388.2 | 310.56 | 196.02 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 4
19 | R192000155 | Khinni Deori Road | Jabalpur | Majholi | Road | PWD | 266.65 | 213.32 | 168.12 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 2.5
19 | R192000160 | Pitol Anas Road | Jhabua | Jhabua | Road | PWD | 139.55 | 111.64 | 93.63 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 2.76
19 | R192000161 | Ziree Umarkot To Dewali Manasya Road | Jhabua | Rama | Road | PWD | 363.19 | 290.55 | 244.29 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 9.94
19 | R192000164 | Paloha To Katjunagar Road | Narsinghpur | Sainkheda | Road | PWD | 189.31 | 151.45 | 100.9 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 3.1
19 | R192000165 | Narsinghpur Tindani Gargata Road | Narsinghpur | Narsinghpur | Road | PWD | 692.34 | 553.87 | 386.76 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 8
19 | R192000166 | Goundi-Dhubghat Road | Narsinghpur | Narsinghpur | Road | PWD | 108.65 | 86.92 | 69.53 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 1.2
19 | R192000167 | Imliya Morach Road | Narsinghpur | Narsinghpur | Road | PWD | 254.04 | 203.23 | 164.23 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 3.4
19 | R192000168 | Athwa Kala To Tokara Via Sehana Talal | Neemuch | Jawad | Road | PWD | 1201.18 | 960.94 | 899.38 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 16.62
19 | R192000169 | Jeeran Pirana Road | Neemuch | neemuch | Road | PWD | 134.29 | 107.43 | 101.51 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 2.7
19 | R192000170 | Ashapuri Murari Choupada Amarsthon Road | Raisen | Obedullaganj | Road | PWD | 582.63 | 466.1 | 210.834 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 10.8
19 | R192000171 | Hardot Pattan Neelkantavar Mandir To Gehuras Road | Raisen | gairatganj | Road | PWD | 303.48 | 242.78 | 139.614 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 5
19 | R192000172 | Palak Mati Dam To Kara Ghati Tari Road | Raisen | Obedullaganj | Road | PWD | 473.03 | 378.42 | 229.58 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 6.5
19 | R192000173 | Palkashri To Ghurela Road | Raisen | Bari | Road | PWD | 116.69 | 93.35 | 82.73 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 2.8
19 | R192000174 | Dhgaon-Bamhori Road | Raisen | Silwani | Road | PWD | 998.06 | 798.45 | 798.45 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 27
19 | R192000175 | Begumganj Sagar Marg Jhiriya Mandir | Raisen | Begumganj | Road | PWD | 746.41 | 597.13 | 500.57 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 13
19 | R192000176 | Construction Of Approach Road To Raisen Fort | Raisen | Raisen | Road | PWD | 185.28 | 148.22 | 136.26 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 1.8
19 | R192000177 | Aashapuri Khasrod To Saalkani Vardhman Factory,Salkani Factory Upto NH-12 | Raisen | Obedullahganj | Road | PWD | 337.42 | 269.94 | 182.11 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 4.62
19 | R192000178 | Mandideep Dahod To Food Part App Road | Raisen | Obedullahganj | Road | PWD | 213.9 | 171.12 | 171.12 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 1.9
19 | R192000179 | Tilandi Parkhedi | Raisen | Raisen | Road | PWD | 626.73 | 501.38 | 379.3 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 9.2
19 | R192000181 | Inayatpur To Jholsi Tiggadda Road | Sagar | Khurai | Road | PWD | 315 | 252 | 78.78 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 5.2
19 | R192000183 | Mara Baroda Kodni Road | Sagar | Rahatgarh | Road | PWD | 396.88 | 317.5 | 190.08 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 4.5
19 | R192000184 | Semrabag-Jinda Forelane Road | Sagar | Sagar | Road | PWD | 410.96 | 328.77 | 328.77 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 6.6
19 | R192000185 | Banda Bara Kerbana Road | Sagar | Banda | Road | PWD | 1386.44 | 1109.15 | 1109.15 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 27
19 | R192000187 | Icchawar Ram Nagar Road | Sehore | Ichhawar | Road | PWD | 363.14 | 290.51 | 290.51 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 10.6
19 | R192000189 | Batura To Sompur Vhaya Girva Road | Shahdol | Burhar | Road | PWD | 711.45 | 664.28 | 664.28 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 15.4
19 | R192000191 | Kharpa To Aakhetpur Road | Shahdol | Beohari | Road | PWD | 248.41 | 248.41 | 248.41 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 6.95
19 | R192000192 | Gahloni To Berja Road | Shivpuri | Pohari | Road | PWD | 259.51 | 223.22 | 223.22 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 5
19 | R192000193 | Kakrai To Behrada Road | Shivpuri | Pohari | Road | PWD | 557.89 | 459.99 | 190.14 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 11
19 | R192000194 | Sonhar To Shila Nagar Road | Shivpuri | Karera | Road | PWD | 283.91 | 283.91 | 283.91 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 10.2
19 | R192000195 | Amolpatha To Kundalpur Vhaya Shankargarh Ganeshkheda Road | Shivpuri | Karera | Road | PWD | 221.22 | 184.81 | 117.93 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 4.8
19 | R192000196 | Chakra To Jhirki Road | Tikamgarh | Tikamgarh | Road | PWD | 177.87 | 177.87 | 177.87 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 3.5
19 | R192000197 | Tikamgarh To Kari Vhaya Bharatnagar Road | Tikamgarh | Tikamgarh | Road | PWD | 306.07 | 290.08 | 272.24 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 7.5
19 | R192000198 | Maalpeetha To Bangaav Road | Tikamgarh | Jatara | Road | PWD | 736.39 | 589.11 | 543.1 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 13.6
19 | R192000199 | Nivadi Byepass Road | Tikamgarh | Nivari | Road | PWD | 183.07 | 183.07 | 183.07 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 1.8
19 | R192000200 | Badnagar Bypass Road | Ujjain | Badnagar | Road | PWD | 809.97 | 794.08 | 765.69 | 2014-03-24 |  |  | 2017-05-01 |  |  |  | 6.12
20 | R202000001 | Bridge Across Banjar River On Sarekha - Surwahi - | Balaghat | Paraswada | Bridge | PWD | 418.36 | 334.69 | 127.25 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 150
20 | R202000002 | Bridge Across Sagar River In KM 1/4 Of Keolari-Ugl | Seoni | Keolari | Bridge | PWD | 318.99 | 265.42 | 144.22 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 135
20 | R202000003 | Bridge Across Bebas River On Sinroja Tilakhedi Pip | Sagar | Sagar | Bridge | PWD | 298.85 | 243.41 | 19.54 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 105
20 | R202000004 | Bebas Bridge On Mailwara Sigon Road Submersible | Damoh | Patharia | Bridge | PWD | 360.32 | 343.02 | 168.39 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 170
20 | R202000006 | Submersible Bridge Across Tapti River In Km 6/4 On | Burhanpur | Khaknar | Bridge | PWD | 1124.87 | 935.37 | 245.89 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 280
20 | R202000007 | Bridge Across Sindh River On Bhadurpura - Atarsuma | Bhind | Raun | Bridge | PWD | 2436.51 | 1949.21 | 389.15 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 455
20 | R202000008 | Bridge Asan River Submersible On Ghoogas-Bichpai R | Morena | Joura | Bridge | PWD | 587.15 | 470.52 | 68.86 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 90
20 | R202000009 | Bridge Across Gopad River Across Kusumi Banjari Ro | Singrauli | Kusumi | Bridge | PWD | 407.27 | 395.91 | 43.25 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 300
20 | R202000010 | Bridge Across River Samdhin On Beohari-Mau Panch J | Shahdol | Beohari | Bridge | PWD | 280.43 | 280.43 | 120.24 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 70
20 | R202000012 | Bridge Across Tem River Km 20/10 & Utawli River Km | Vidisha | Lateri | Bridge | PWD | 710.95 | 583.23 | 329.9 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 135
20 | R202000013 | Bridge Across Shivna River On Acheri Achera Road H | Mandsaur | Mandsaur | Bridge | PWD | 536.17 | 536.17 | 218.96 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 225
20 | R202000014 | Hat-Vinati_Madiyado Road - Sonar River Bridge Subm | Damoh | Hatta | Bridge | PWD | 776.7 | 759.18 | 311.01 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 250
20 | R202000015 | Bridge Across Sindh River On Jakhmoli Larol Road H | Bhind | Raun | Bridge | PWD | 1440.09 | 1440.09 | 668.18 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 455
20 | R202000016 | Udaypur To Bamora Road | Vidisha | Kurwai | Road | PWD | 135.53 | 135.53 | 84.32 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 3
20 | R202000017 | Esharwas - Nainwas - Chamar Umariya To Amjhir Ashr | Vidisha | Lateri | Road | PWD | 221.79 | 177.43 | 94.07 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 4.48
20 | R202000018 | Puranpura Link Road No.5 To Ahmadpur Road | Vidisha | Vidisha | Road | PWD | 201.75 | 201.75 | 111.86 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 3.3
20 | R202000019 | SH-19 To Lashkarpura App Road | Vidisha | Vidisha | Road | PWD | 508.31 | 452.89 | 239.61 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 8.02
20 | R202000021 | Ladkui Chowkito Gularpura Road | Sehore | Narsullaganj | Road | PWD | 299.23 | 239.38 | 78.63 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 4.6
20 | R202000022 | Approach Road In Pandagaon Village | Sehore | Narsullaganj | Road | PWD | 175.59 | 140.47 | 0 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 2
20 | R202000023 | Chhech Chameti To Neelkanth Road | Sehore | Narsullaganj | Road | PWD | 273.94 | 219.15 | 0 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 4
20 | R202000024 | Kewat Colony Road In Pandagaon | Sehore | Narsullaganj | Road | PWD | 99.17 | 79.34 | 23.66 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 0.8
20 | R202000025 | Ladkui To Singpur Tappar Road | Sehore | Narsullaganj | Road | PWD | 126.51 | 101.21 | 53.19 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 1.9
20 | R202000026 | Main Road To Satdev Ashram | Sehore | Narsullaganj | Road | PWD | 97.25 | 77.8 | 0 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 0.9
20 | R202000027 | Ladkui Road To Habib Nagar Road | Sehore | Narsullaganj | Road | PWD | 151.17 | 120.94 | 56.76 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 2.6
20 | R202000028 | Karjwani To Panhal Kharbapura | Dhar | Kukshi | Road | PWD | 537.67 | 469.46 | 359.43 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 6
20 | R202000029 | Dhami Sironj Road | Dhar | Gandhwani | Road | PWD | 290.84 | 232.67 | 0 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 3.6
20 | R202000030 | Kawda-Nadipura To Shamshan Ghat Road | Dhar | Kukshi | Road | PWD | 285.72 | 239.22 | 19.75 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 3.8
20 | R202000031 | Valiyakundiya Awaliya Navrangpura To Chikhalikheda | Khargone | Maheshwar | Road | PWD | 153.2 | 153.2 | 60.99 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 5.12
20 | R202000032 | Bablai Gadariya Road | Khargone | Maheshwar | Road | PWD | 67.07 | 67.07 | 0 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 2.82
20 | R202000033 | Bhilat Dev Nandarwada Koyalajhir Salai Parcha Road | Hoshangabad | Seoni Malwa | Road | PWD | 999.92 | 799.94 | 639.95 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 18.12
20 | R202000034 | Semri Harchand To Pathrai Road | Hoshangabad | Sohagpur | Road | PWD | 301.45 | 241.16 | 138.95 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 4.5
20 | R202000035 | Sohagpur Rewabankhedi Road | Hoshangabad | Sohagpur | Road | PWD | 193.51 | 167.4 | 133.92 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 4.5
20 | R202000036 | Babadiya Bhau To Amlada Kalan Bhadugaon Road | Hoshangabad | Seoni Malwa | Road | PWD | 681 | 544.8 | 435.84 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 11
20 | R202000037 | Khakarapura Bendripura Bairakhedi Kharar To Pipali | Hoshangabad | Seoni Malwa | Road | PWD | 426.99 | 341.59 | 273.27 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 7.28
20 | R202000038 | Jeeraveh Choukigavan Bhaironpur To Nipaniya Road | Hoshangabad | Seoni Malwa | Road | PWD | 786.68 | 629.34 | 395.82 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 11.7
20 | R202000039 | Nipaniya Khatkad Jhaklay Chatarkheda To Seoni Malw | Hoshangabad | Seoni Malwa | Road | PWD | 705.25 | 564.2 | 362.63 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 12.32
20 | R202000040 | Mhow Neemuch Fourlane To Ghatla Approach Road | Ratlam | Ratlam | Road | PWD | 210.17 | 168.14 | 0 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 3.4
20 | R202000041 | Sakha Patna Road | Damoh | Jabera | Road | PWD | 164.09 | 164.09 | 131.27 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 6.6
20 | R202000042 | Raila Kanpura To Betariya Road | Singrauli | Waidhan | Road | PWD | 1174.04 | 939.23 | 691.85 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 15
20 | R202000043 | Gata Amayan Road | Bhind | Mehgaon | Road | PWD | 169.09 | 135.27 | 0 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 3.2
20 | R202000044 | Umari Sagara Road | Bhind | Bhind | Road | PWD | 461.1 | 368.88 | 0 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 11.2
20 | R202000045 | Pacholi To Chhtakapura Whaya Bhaikhakapura Road | Morena | Morena | Road | PWD | 217.96 | 200.03 | 96.25 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 4.2
20 | R202000047 | Rannod To Pachawali Road | Shivpuri | badarwas | Road | PWD | 66.61 | 66.61 | 53.29 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 4
20 | R202000048 | Daviya Jagan To Devari Road | Shivpuri | Khaniyadhana | Road | PWD | 183.36 | 146.69 | 0 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 3.6
20 | R202000050 | Sirsti To Saretha Road | Guna | Bamori | Road | PWD | 766.57 | 683.68 | 39.48 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 12.24
20 | R202000051 | Hatwaha Satai Road | Chattarpur | Bijawar | Road | PWD | 500.69 | 500.69 | 0 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 13.2
20 | R202000052 | Reconstruction Of Damaged Portion Of Buxwaha Nanag | Chattarpur | Buxwaha | Road | PWD | 579.9 | 539.38 | 0 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 16
20 | R202000053 | Nowgong Issanagar Road To Kalapani Via Parapatti R | Chattarpur | Chhatarpur | Road | PWD | 302.31 | 256 | 114.22 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 5.3
20 | R202000054 | Naupahariya Galan Lahadara Road | Chattarpur | Nawgong | Road | PWD | 174.71 | 139.77 | 38.23 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 5.15
20 | R202000055 | Kusmeli Kabadiya Road | Chhindwara | Chhindwara | Road | PWD | 403.21 | 403.21 | 322.57 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 5
20 | R202000056 | Bisapur Sailya Road | Chhindwara | Chhindwara | Road | PWD | 167.98 | 134.38 | 28.53 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 5.2
20 | R202000057 | A.B.Road To Kabulpura Via Kamardipur | Shajapur | Mohan Badodiya | Road | PWD | 280.44 | 280.44 | 136.65 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 5.2
20 | R202000058 | Baspur Tawa River To Shantipur | Betul | Ghodadongri | Road | PWD | 219.84 | 219.84 | 175.87 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 5.52
20 | R202000059 | Betul District To Harda Road | Betul | Bhimpur | Road | PWD | 211.08 | 191.13 | 129.56 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 2.8
20 | R202000060 | Khapa Khateda To Kajli Road | Betul | Amla | Road | PWD | 308.78 | 308.78 | 86.43 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 5
20 | R202000061 | Dhodwara Babai To Dabheri Road | Betul | Betul | Road | PWD | 141.55 | 113.24 | 65.31 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 1.88
20 | R202000062 | Construction Of Bhanpura To Chhote Mahadev - Bade | Mandsaur | Garoth | Road | PWD | 579.4 | 463.52 | 285.38 | 2014-11-11 |  |  | 2017-12-31 |  |  |  | 4
20 | R202000063 | Bridge Across Ken River On Banda Nareni Road | Chattarpur | Gaurihar | Bridge | PWD | 898.83 | 719.06 | 63.85 | 2014-12-19 |  |  | 2018-01-31 |  |  |  | 190
20 | R202000064 | Bridge Across Bairma River On Hardua Ghat Muari Ro | Damoh | Hatta | Bridge | PWD | 747.38 | 716.62 | 284.5 | 2014-12-19 |  |  | 2018-01-31 |  |  |  | 250
20 | R202000065 | Bridge Across Bairma River On Bandakpur Balarpur B | Damoh | Damoh | Bridge | PWD | 1017.9 | 897.27 | 232.18 | 2014-12-19 |  |  | 2018-01-31 |  |  |  | 350
20 | R202000066 | Bridge Across Sonar River On Hata Vinati Dolee (At | Damoh | Hatta | Bridge | PWD | 776.93 | 759.36 | 244.76 | 2014-12-19 |  |  | 2018-01-31 |  |  |  | 240
20 | R202000067 | Bridge Across Narmada River Anwalighat On Salkanpu | Sehore | Budhni | Bridge | PWD | 2497.51 | 2497.51 | 475.06 | 2014-12-19 |  |  | 2018-01-31 |  |  |  | 630
20 | R202000068 | Bridge Across Narmada River On Chotichipaner To Ba | Harda | Harda | Bridge | PWD | 2234.93 | 2234.93 | 347.48 | 2014-12-19 |  |  | 2018-01-31 |  |  |  | 840
20 | R202000069 | Bridge Across Dudhi River On Ganeshganj Khapasani | Chhindwara | Tamia/Chichli | Bridge | PWD | 674.02 | 541.74 | 127.2 | 2014-12-19 |  |  | 2018-01-31 |  |  |  | 165
20 | R202000070 | Bridge Across River Chhapi On Khilchipur Machalpur | Rajgarh | Khilchipur | Bridge | PWD | 796.24 | 680.03 | 382.42 | 2014-12-19 |  |  | 2018-01-31 |  |  |  | 90
20 | R202000071 | Bridge Across Chamla River On Khasrod Khurd Kamanp | Ujjain | Badnagar | Bridge | PWD | 466.25 | 466.25 | 264.78 | 2014-12-19 |  |  | 2018-01-31 |  |  |  | 140
20 | R202000072 | Bridge Across Son River On Rupoula Jai Singh Nagar | Shahdol | Beohari | Bridge | PWD | 864.51 | 864.51 | 360.96 | 2014-12-19 |  |  | 2018-01-31 |  |  |  | 245
20 | R202000073 | Ranipindhari Road To Sagouni Road | Narsinghpur | Kurwai | Road | PWD | 346.55 | 277.24 | 150.25 | 2015-01-16 |  |  | 2018-03-03 |  |  |  | 4.3
20 | R202000074 | Sanchi Udaigiri To Basoda | Vidisha | Sanchi | Road | PWD | 2068.1 | 1654.48 | 383.31 | 2015-01-16 |  |  | 2018-03-03 |  |  |  | 14
20 | R202000075 | Kanari Daskhajuri Nateran Raipur To Phupher Khusor | Vidisha | Nateran | Road | PWD | 996.56 | 797.25 | 132.41 | 2015-01-16 |  |  | 2018-03-03 |  |  |  | 15.5
20 | R202000076 | Kumhar Karadiya Digithan Narayanpura Road | Dhar | Dhar | Road | PWD | 112.36 | 112.36 | 0 | 2015-01-16 |  |  | 2018-03-03 |  |  |  | 3.82
20 | R202000077 | Gadhgarha Bolada Road | Dhar | Badnawar | Road | PWD | 228.84 | 183.07 | 146.46 | 2015-01-16 |  |  | 2018-03-03 |  |  |  | 5
20 | R202000078 | Dhar Ring Road To Padaliya | Dhar | Dhar | Road | PWD | 111.99 | 111.99 | 0 | 2015-01-16 |  |  | 2018-03-03 |  |  |  | 3.42
20 | R202000079 | Approach Road Zirniya To Damkheda | Khargone | Bhikangaon | Road | PWD | 760.37 | 608.3 | 0 | 2015-01-16 |  |  | 2018-03-03 |  |  |  | 13.13
20 | R202000080 | Amankhedi Sangvi Chhirwa Road | Khargone | Bhikangaon | Road | PWD | 293.2 | 234.56 | 0 | 2015-01-16 |  |  | 2018-03-03 |  |  |  | 7.58
20 | R202000081 | Hingwa-Varla Road | Barwani | Sendhwa | Road | PWD | 250.6 | 200.48 | 133.93 | 2015-01-16 |  |  | 2018-03-03 |  |  |  | 4.97
20 | R202000082 | Parsauna To Pondi Via Rajbandh Luri Padainiya Road | Singrauli | Waidhan | Road | PWD | 439.3 | 351.44 | 281.15 | 2015-01-16 |  |  | 2018-03-03 |  |  |  | 5
20 | R202000084 | Badagaon Deotha Road | Chattarpur | Nowgong | Road | PWD | 177.89 | 142.31 | 74.66 | 2015-01-16 |  |  | 2018-03-03 |  |  |  | 5
20 | R202000085 | Devpur To Mugalsarai Road ( Km 6 To Km 16) | Vidisha | Sironj | Road | PWD | 965.93 | 772.74 | 25.35 | 2015-01-16 |  |  | 2018-03-03 |  |  |  | 11
20 | R202000086 | Construction Of Bourosa To Malhargarh Road | Vidisha | Kurwai | Road | PWD | 423.95 | 339.16 | 104.05 | 2015-01-16 |  |  | 2018-03-03 |  |  |  | 8.4
20 | R202000087 | Widening Upgradation Of Morena Bypass | Morena | Morena | Road | PWD | 324.32 | 259.46 | 207.57 | 2015-01-16 |  |  | 2018-03-03 |  |  |  | 6.48
20 | R202000088 | Maharajpur- Jhamar Road | Sagar | Deori | Road | PWD | 88.98 | 88.98 | 0 | 2015-01-16 |  |  | 2018-03-03 |  |  |  | 4
20 | R202000089 | Dhasaan GWSS | Chattarpur | Many | RDWS | MPJNM | 7087.69 | 6024.54 | 1204.91 | 2015-01-16 |  |  | 2018-03-03 |  |  |  | 72284
20 | R202000090 | Indwar GWSS | Umaria | Many | RDWS | MPJNM | 5308.17 | 4511.95 | 902.39 | 2015-01-16 |  |  | 2018-03-03 |  |  |  | 68025
20 | R202000091 | Singhaura GWSS | Panna | Many | RDWS | MPJNM | 13211.9 | 11230.11 | 2246.02 | 2015-01-16 |  |  | 2018-03-03 |  |  |  | 114715
20 | R202000092 | Damhedi GWSS | Anuppur | Many | RDWS | MPJNM | 5072.84 | 4311.91 | 862.38 | 2015-01-16 |  |  | 2018-03-03 |  |  |  | 90805
20 | R202000093 | Karanpura GWSS | Umaria and Katni | Many | RDWS | MPJNM | 7150.14 | 6077.61 | 1215.52 | 2015-01-16 |  |  | 2018-03-03 |  |  |  | 56533
20 | R202000094 | Gorihar GWSS | Chattarpur | Many | RDWS | MPJNM | 8538.98 | 7258.14 | 1451.63 | 2015-01-16 |  |  | 2018-03-03 |  |  |  | 90805
20 | R202000095 | Narmada Malwa-Gambhir Link Project | Khandwa and Khargone | Khandwa Khargone Indore Ujjain | MJP | NVDA | 109019 | 103568.05 | 65635.02 | 2015-02-20 |  |  | 2020-03-02 |  |  |  | 50000
20 | R202000096 | Construction Of 350 Bedded Hospital And GNM Traini | Vidisha | vidisha | Health | DHFW | 5176 | 4399.6 | 2223.08 | 2015-02-20 |  |  | 2018-03-31 |  |  |  | 1
20 | R202000097 | Construction Of 450 Bedded Hospital Buildings At D | Ujjain | Ujjain | Health | DHFW | 2943 | 2501.56 | 1604.76 | 2015-02-20 |  |  | 2018-03-31 |  |  |  | 1
20 | R202000098 | Construction Of 100 Bedded Civil Hospital Sarangpu | Rajgarh | Sarangpur | Health | DHFW | 834 | 708.9 | 389.05 | 2015-02-20 |  |  | 2018-03-31 |  |  |  | 1
20 | R202000099 | Construction Of 100 Bedded Civil Hospital Aagar At | Shajapur | Aagar | Health | DHFW | 847 | 719.96 | 529.29 | 2015-02-20 |  |  | 2018-03-31 |  |  |  | 1
20 | R202000100 | Construction Of 100 Bedded Civil Hospital Barwaha | Khargone | Badwaha | Health | DHFW | 862 | 732.7 | 408.38 | 2015-02-20 |  |  | 2018-03-31 |  |  |  | 1
20 | R202000101 | Construction Of 6-F, 16-G & 16 H Type Quarters At | Khargone | Badwaha | Health | DHFW | 426 | 362.1 | 32.59 | 2015-02-20 |  |  | 2018-03-31 |  |  |  | 1
20 | R202000102 | Construction Of 100 Bedded Civil Hospital Badnagar | Ujjain | Badnager | Health | DHFW | 1150 | 977.5 | 88.05 | 2015-02-20 |  |  | 2018-03-31 |  |  |  | 1
20 | R202000103 | Construction Of 6-F, 16-G & 16 H Type Quarters At | Ujjain | Badnager | Health | DHFW | 428 | 363.8 | 32.74 | 2015-02-20 |  |  | 2018-03-31 |  |  |  | 1
20 | R202000104 | Contruction Of 6-F, 16-G & 16 H Type Quarters At C | Sehore | Aastha | Health | DHFW | 428 | 363.8 | 363.8 | 2015-02-20 |  |  | 2018-03-31 |  |  |  | 1
20 | R202000105 | Upgradation Of Kailashnath Katju Civil Hospital W | Bhopal | Bhopal | Health | DHFW | 2436 | 2070.6 | 198.31 | 2015-02-20 |  |  | 2018-03-31 |  |  |  | 1
21 | P2016700000000000008 | Construction Of Building For I. T. I (Conventional) | Agar Malwa | Susner | School | TE&SD | 400 | 340 | 238.38 | 2016-09-14 |  |  | 2019-10-31 |  |  |  | 240
21 | P2016700000000000009 | Construction Of Building For I. T. I (Conventional) | Vidisha | NA | School | TE&SD | 400 | 340 | 225.58 | 2016-09-14 |  |  | 2019-10-31 |  |  |  | 240
21 | P2016700000000000010 | Construction Of Building For I. T. I (Conventional) | Sehore | Chakaldi | School | TE&SD | 400 | 340 | 195.46 | 2016-09-14 |  |  | 2019-10-31 |  |  |  | 240
21 | P2016700000000000011 | Construction Of Building For I. T. I (Conventional) | Hoshangabad | NA | School | TE&SD | 400 | 340 | 287.48 | 2016-09-14 |  |  | 2019-10-31 |  |  |  | 240
21 | P2016700000000000012 | Construction Of Building For I. T. I (Conventional) | Hoshangabad | Pipariya | School | TE&SD | 400 | 340 | 165.91 | 2016-09-14 |  |  | 2019-10-31 |  |  |  | 240
21 | P2016700000000000013 | Construction Of Building For I. T. I (Conventional) | Raisen | Mandideep | School | TE&SD | 400 | 340 | 236.82 | 2016-09-14 |  |  | 2019-10-31 |  |  |  | 240
21 | P2016700000000000014 | Construction Of Building For I. T. I (Conventional) | Betul | NA | School | TE&SD | 400 | 340 | 267.93 | 2016-09-14 |  |  | 2019-10-31 |  |  |  | 240
21 | P2016700000000000015 | Construction Of Building For I. T. I (Conventional) | Tikamgarh | Baldevgarh | School | TE&SD | 400 | 340 | 340 | 2016-09-14 |  |  | 2019-10-31 |  |  |  | 240
21 | P2016700000000000016 | Construction Of Building For I. T. I (Conventional) | Chattarpur | Badamalhera | School | TE&SD | 400 | 340 | 340 | 2016-09-14 |  |  | 2019-10-31 |  |  |  | 240
21 | P2016700000000000017 | Construction Of Building For I. T. I (Conventional) | Shivpuri | Pichore | School | TE&SD | 400 | 340 | 340 | 2016-09-14 |  |  | 2019-10-31 |  |  |  | 240
21 | P2016700000000000018 | Construction Of Building For I. T. I (Conventional) | Bhind | NA | School | TE&SD | 400 | 340 | 213.58 | 2016-09-14 |  |  | 2019-10-31 |  |  |  | 240
21 | P2016700000000000019 | Construction Of Building For I. T. I (Conventional) | Khargone | Kasravad | School | TE&SD | 400 | 340 | 319.04 | 2016-09-14 |  |  | 2019-10-31 |  |  |  | 240
21 | P2016700000000000020 | Construction Of Building For I. T. I (Conventional) | Ujjain | Mahidpur | School | TE&SD | 400 | 340 | 193.34 | 2016-09-14 |  |  | 2019-10-31 |  |  |  | 240
21 | P2016700000000000021 | Construction Of Building For I. T. I (Conventional) | Khargone | Karahi | School | TE&SD | 400 | 340 | 140.14 | 2016-09-14 |  |  | 2019-10-31 |  |  |  | 240
21 | P2016700000000000022 | Construction Of Building For I. T. I (Conventional) | Dewas | Kataphod | School | TE&SD | 400 | 340 | 229.94 | 2016-09-14 |  |  | 2019-10-31 |  |  |  | 240
21 | P2016700000000000023 | Construction Of Building For I. T. I (Conventional) | Ujjain | Women ITI | School | TE&SD | 400 | 340 | 195.44 | 2016-09-14 |  |  | 2019-10-31 |  |  |  | 240
21 | P2016700000000000024 | Construction Of Building For I. T. I (Conventional) | Khandwa | Khedikhalwa | School | TE&SD | 400 | 340 | 205.43 | 2016-09-14 |  |  | 2019-10-31 |  |  |  | 240
21 | P2016700000000000025 | Construction Of Building For I. T. I (Conventional) | Mandsaur | Garoth | School | TE&SD | 400 | 340 | 95.2 | 2016-09-14 |  |  | 2019-10-31 |  |  |  | 240
21 | P2016700000000000026 | Construction Of Building For I. T. I (Conventional) | Damoh | Patera | School | TE&SD | 400 | 340 | 250.93 | 2016-09-14 |  |  | 2019-10-31 |  |  |  | 240
21 | P2016700000000000027 | Construction Of Building For I. T. I (Conventional) | Damoh | Nohata | School | TE&SD | 400 | 340 | 239.08 | 2016-09-14 |  |  | 2019-10-31 |  |  |  | 240
21 | P2016700000000000028 | Construction Of Building For I. T. I (Conventional) | Sagar | Raheli | School | TE&SD | 400 | 340 | 229.93 | 2016-09-14 |  |  | 2019-10-31 |  |  |  | 240
21 | P2016700000000000029 | Construction Of Building For I. T. I (Conventional) | Jabalpur | Majhauli | School | TE&SD | 400 | 340 | 170.76 | 2016-09-14 |  |  | 2019-10-31 |  |  |  | 240
21 | P2016700000000000030 | Construction Of Building For I. T. I (Conventional) | Jabalpur | Patan | School | TE&SD | 400 | 340 | 256.51 | 2016-09-14 |  |  | 2019-10-31 |  |  |  | 240
21 | P2016700000000000031 | Construction Of Building For I. T. I (Conventional) | Chhindwara | Women ITI | School | TE&SD | 400 | 340 | 218.71 | 2016-09-14 |  |  | 2019-10-31 |  |  |  | 240
21 | P2016700000000000032 | Construction Of Building For I. T. I (Conventional) | Narsinghpur | NA | School | TE&SD | 400 | 340 | 235.53 | 2016-09-14 |  |  | 2019-10-31 |  |  |  | 240
21 | P2016700000000000033 | Construction Of Building For I. T. I (Conventional) | Narsinghpur | Gadarwada | School | TE&SD | 400 | 340 | 272.45 | 2016-09-14 |  |  | 2019-10-31 |  |  |  | 240
21 | P2016700000000000034 | Construction Of Building For I. T. I (Conventional) | Satna | Veersinghpur | School | TE&SD | 400 | 340 | 68 | 2016-09-14 |  |  | 2019-10-31 |  |  |  | 240
21 | P2016700000000000035 | Construction Of Building For I. T. I (Conventional) | Singrauli | Devsar | School | TE&SD | 400 | 340 | 159.24 | 2016-09-14 |  |  | 2019-10-31 |  |  |  | 240
21 | P2016700000000000036 | Construction Of Building For I. T. I (Conventional) | Singrauli | Bargawan | School | TE&SD | 400 | 340 | 269.42 | 2016-09-14 |  |  | 2019-10-31 |  |  |  | 240
21 | P2016700000000000037 | Construction Of Building For I. T. I (Conventional) | Rewa | NA | School | TE&SD | 400 | 340 | 193.17 | 2016-09-14 |  |  | 2019-10-31 |  |  |  | 240
21 | P2016700000000000039 | Mohanpura Major Multipurpose Irrigation Project | Rajgarh | Rajgarh | MIS | WRD | 118754.83 | 44151.73 | 32400.45 | 2015-10-21 |  |  | 2018-12-01 |  |  |  | 65000
21 | P2016700000000000062 | Antaraliya Jod To Kajlas Road | Agar (Shajapur) | Agar | Road | PWD | 388.32 | 310.66 | 85.51 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 5.2
21 | P2016700000000000063 | Tanodiya To Madkota Road | Agar (Shajapur) | Agar | Road | PWD | 2454.61 | 1963.69 | 552.62 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 20.94
21 | P2016700000000000064 | Birulbazar To Rai Amla Road | Betul | Multai | Road | PWD | 456.49 | 365.19 | 73.04 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 7
21 | P2016700000000000065 | Kumbhariya Jod To Mathini Road | Betul | Betul | Road | PWD | 144.47 | 115.58 | 62.75 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 2.2
21 | P2016700000000000066 | Simariyajoshi To Sontalai Road | Betul | Amla | Road | PWD | 169.21 | 135.37 | 66.63 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 2.4
21 | P2016700000000000067 | Upgrdation Of Road From Bilkhiria To Mahakankali Mandir | Bhopal | Fanda | Road | PWD | 605.85 | 484.68 | 96.94 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 4.5
21 | P2016700000000000068 | Chandla Bypass Road | Chattarpur | Lavkushnagar | Road | PWD | 1585.5 | 1268.4 | 253.68 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 9
21 | P2016700000000000069 | Chandla Hathoha Ajaygarh Road | Chattarpur | Chandla Ajaygarh | Road | PWD | 3468.51 | 2774.81 | 614.31 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 22.3
21 | P2016700000000000070 | Lavkushnagar Bypass Road | Chattarpur | Lavkushnagar | Road | PWD | 1717.48 | 1373.98 | 274.8 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 10
21 | P2016700000000000071 | Pipirya Nankar To Moti Nagar Road | Dewas | Khategaon | Road | PWD | 157.41 | 125.93 | 48.01 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 2
21 | P2016700000000000072 | Udaynagar (Sabalgarh Phata) To Kanad Road | Dewas | Bagli | Road | PWD | 1065.01 | 852.01 | 212.18 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 9.7
21 | P2016700000000000073 | Sandala Tilgara Road | Dhar | Badnawar | Road | PWD | 146.02 | 116.82 | 90.02 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 1.87
21 | P2016700000000000074 | Kusumkui Jhaklay Gadariya Harpalpur Hathnapur Road | Hoshangabad | Seoni Malwa | Road | PWD | 991.81 | 793.45 | 598.85 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 11
21 | P2016700000000000075 | Sikandari To Mohammadpur Londiya CC Road | Indore | Hatod | Road | PWD | 477.32 | 381.86 | 76.37 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 3
21 | P2016700000000000076 | Amgawan - Darouli - Keolari - Marha Road | Jabalpur | Sihora | Road | PWD | 302.36 | 241.89 | 56.38 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 3.55
21 | P2016700000000000077 | Karhaiya Kurna Tampal Road | Jabalpur | Bargi | Road | PWD | 208.76 | 167.01 | 143.21 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 2.55
21 | P2016700000000000078 | Mohankot To Morjhariya Via Semalkundia Road | Jhabua | Petlawad | Road | PWD | 454.56 | 363.65 | 238.48 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 6.2
21 | P2016700000000000079 | Gobaria Sangwada Upto Indore Ikshapur Highway | Khandwa | Pandhana | Road | PWD | 448.96 | 359.17 | 71.83 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 16.2
21 | P2016700000000000080 | Panjaria To Chhegaon Devi | Khandwa | Khandwa | Road | PWD | 670.5 | 536.4 | 145.2 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 8.5
21 | P2016700000000000081 | Katora To Bakawa Road | Khargone | Barwaha | Road | PWD | 425.47 | 340.38 | 221.66 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 5.4
21 | P2016700000000000082 | Pipri To Machalgaon Road | Khargone | Bhikangaon | Road | PWD | 336.55 | 269.24 | 53.85 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 4.7
21 | P2016700000000000083 | Asawati To Haripura Kurawan Ajaypur Road | Mandsaur | Garoth | Road | PWD | 1480.52 | 1184.42 | 336.63 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 12.7
21 | P2016700000000000084 | Badwan To Akya (Via Damnar) Road | Mandsaur | Mandsaur | Road | PWD | 841.84 | 673.47 | 164.69 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 13.6
21 | P2016700000000000085 | Guliyana To Ratikhedi (Via Nipniya Jogikheda) Road | Mandsaur | Mandsaur | Road | PWD | 737.65 | 590.12 | 293.35 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 11.5
21 | P2016700000000000086 | Munderi To Nahargarh Road | Mandsaur | Mandsaur | Road | PWD | 995.63 | 796.5 | 179.52 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 12.9
21 | P2016700000000000087 | Bohani To Rehli Road | Narsinghpur | Chanwarpatha | Road | PWD | 270.41 | 216.33 | 75.43 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 3.2
21 | P2016700000000000088 | Sukha To Jhiriyamata Road | Narsinghpur | Sainkheda | Road | PWD | 312.21 | 249.77 | 77.43 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 3.1
21 | P2016700000000000089 | Umariya To Piparha Road | Narsinghpur | Kareli | Road | PWD | 952.99 | 762.39 | 230.33 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 5.6
21 | P2016700000000000090 | Jhantia Govindpura Road (Via Saloda) | Neemuch | Jawad | Road | PWD | 271.88 | 217.5 | 217.5 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 3.6
21 | P2016700000000000091 | Moriya To Himmatkhedi Road | Ratlam | Alot | Road | PWD | 194.55 | 155.64 | 101.5 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 3
21 | P2016700000000000092 | Atariya To Bhitwa Road | Rewa | Rewa | Road | PWD | 228.23 | 182.58 | 36.52 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 2.7
21 | P2016700000000000093 | Padari Chiraiya Nalla To Dol Approach Road | Rewa | Sirmour | Road | PWD | 337.13 | 269.7 | 53.94 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 4
21 | P2016700000000000094 | Rajha Akauri Mauharia Road | Rewa | Gangeo | Road | PWD | 376.03 | 300.82 | 60.16 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 4
21 | P2016700000000000095 | Upgradation Of Mauganj Jail Approach Road | Rewa | Mauganj | Road | PWD | 440.29 | 352.23 | 70.45 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 6.7
21 | P2016700000000000096 | Mokalpur Chouraha To Madkhera Jagir Road | Sagar | Sagar | Road | PWD | 346.57 | 277.26 | 86.21 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 5.2
21 | P2016700000000000097 | Rakh Besli Road | Sagar | Banda | Road | PWD | 455.1 | 364.08 | 165 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 4
21 | P2016700000000000098 | Amarpatan Rampur Road | Satna | Rampur Baghelan and Amarpatan | Road | PWD | 3582 | 2865.6 | 573.12 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 25.6
21 | P2016700000000000099 | Delha Karaiya Karoundi Road | Satna | Maihar | Road | PWD | 398.9 | 319.12 | 100.59 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 4
21 | P2016700000000000100 | Burhar Jaitpur Road (Bhatiya Jaitpur) | Shahdol | Burhar | Road | PWD | 248.06 | 198.45 | 175 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 3
21 | P2016700000000000101 | Bardiyason Railway Gate To Palswad-Lalupura-Hanoti-Jhonkar-Jalalpura (AB Road) Road | Shajapur | Shajapur | Road | PWD | 1730.63 | 1384.5 | 588.99 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 19.7
21 | P2016700000000000102 | Tighra To Gorya Road Upto Rajashthan Border | Shivpuri | Pohari | Road | PWD | 201 | 160.8 | 32.16 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 2.7
21 | P2016700000000000103 | Jharda To Mahidpur Road Via Tarot-Kachariya-Katariya Khed-Barkheda Khurd-Sipawara-Sagwali-Tarnod-Karnawad-Kanakhedi | Ujjain | Mahidpur | Road | PWD | 1914.37 | 1531.5 | 306.3 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 25.45
21 | P2016700000000000104 | NH-86 Dhaturiya Haveli To Sorai Amachhar Chak- Dholkhedi (SH-19) Ring Road | Vidisha | Vidisha | Road | PWD | 2695.73 | 2156.58 | 449.7 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 11.5
21 | P2016700000000000221 | Sub Br Dhoriya Nalla | Balaghat | Katangi | Bridge | PWD | 635.98 | 708.82 | 337.96 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 160
21 | P2016700000000000222 | Sub Br Bah River | Bhopal | Berasia | Bridge | PWD | 980.34 | 632.23 | 432.96 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 180
21 | P2016700000000000223 | Sub Br Bah River In KM 5/4 & Nalla In KM 8/4 | Bhopal | Berasia | Bridge | PWD | 815.07 | 729.78 | 273.36 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 150
21 | P2016700000000000224 | Sub Br Narmada River | Dindori | Shahpur | Bridge | PWD | 730.42 | 1266.17 | 116.87 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 225
21 | P2016700000000000225 | H.L. Sub Br Gambhir River In 135 M | Indore | Hatod | Bridge | PWD | 688.83 | 508.78 | 527.34 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 135
21 | P2016700000000000226 | H.L Br Kshipra River In KM 5/2-8 | Ratlam | Alot | Bridge | PWD | 1338.41 | 563.27 | 430.3 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 480
21 | P2016700000000000227 | H.L. Br Bihar River | Rewa | Rewa | Bridge | PWD | 1582.71 | 584.34 | 995.03 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 100
21 | P2016700000000000228 | Sub Br Bewas River In KM 4/6-8 | Sagar |  | Bridge | PWD | 886.03 | 784.27 | 275.37 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 270
21 | P2016700000000000229 | Sub Br Satna River In KM 6/10 | Satna | Sohawal | Bridge | PWD | 790.29 | 551.06 | 237.86 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 147
21 | P2016700000000000230 | Sub Br Seep River | Sehore | Nusrullahganj | Bridge | PWD | 912.22 | 672.28 | 145.96 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 140
21 | P2016700000000000231 | H.L. Br Gopad River | Sidhi | Kusumi | Bridge | PWD | 840.35 | 1070.73 | 134.46 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 275
21 | P2016700000000000232 | Sub Br Saprar River | Tikamgarh | Jatara | Bridge | PWD | 654.95 | 652.06 | 349.04 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 195
21 | P2016700000000000233 | Sub Br Kshipra River | Ujjain | Mahidpur | Bridge | PWD | 704.09 | 523.96 | 112.65 | 2015-12-08 |  |  | 2019-01-31 |  |  |  | 150
21 | P2016700000000000270 | Narmada Malwa Gambhir Link Project - Phase Ii | Indore | Indore | MJP | NVDA | 109702 | 93099 | 27558.17 | 2016-01-15 |  |  | 2021-01-31 |  |  |  | 237000
22 | P2016700000000000690 | Bankpura GWSS | Rajgarh | Biora | MPJNM | RDWS | 13000 | 11050 | 2210 | 2016-08-22 |  |  | 2021-08-31 |  |  |  | 180250
22 | P2016700000000000691 | Badonkalan GWSS | Datia | Datia | MPJNM | RDWS | 6312.65 | 5365.75 | 1073.15 | 2016-08-22 |  |  | 2021-08-31 |  |  |  | 94065
22 | P2016700000000000730 | Anuppur - Jaithari Venkatnagar Road | Anuppur | Jaithari | PWD | Road | 4530.04 | 3579.81 | 910.93 | 2016-09-16 |  |  | 2019-10-31 |  |  |  | 40.6
22 | P2016700000000000731 | Katedhara Tirodi Khawasa Road | Balaghat | Katangi | PWD | Road | 3068.53 | 2454.82 | 490.96 | 2016-09-16 |  |  | 2019-10-31 |  |  |  | 23.21
22 | P2016700000000000732 | Phanda Tumda Jharkheda Road | Bhopal | Phanda | PWD | Road | 2573.01 | 2058.41 | 411.68 | 2016-09-16 |  |  | 2019-10-31 |  |  |  | 18.8
22 | P2016700000000000733 | Khajuri Sadak Dhamania Bakani Parwalia Road | Bhopal | Phanda | PWD | Road | 1929.78 | 1543.82 | 308.76 | 2016-09-16 |  |  | 2019-10-31 |  |  |  | 14.8
22 | P2016700000000000734 | Upgradation Of Dewas To Vijyaganj Mandi Road | Dewas | Dewas | PWD | Road | 4840.32 | 3731.38 | 746.28 | 2016-09-16 |  |  | 2019-10-31 |  |  |  | 30.6
22 | P2016700000000000735 | Jhukehi Kymore Bhatura Road | Katni | Vijayraghavgarh | PWD | Road | 5196.07 | 4156.86 | 831.37 | 2016-09-16 |  |  | 2019-10-31 |  |  |  | 27.64
22 | P2016700000000000736 | Mandsaur To Sanjit Road | Mandsaur | Mandsaur & Malhargarh | PWD | Road | 5949.66 | 3653.21 | 2096.95 | 2016-09-16 |  |  | 2019-10-31 |  |  |  | 32.9
22 | P2016700000000000737 | Ratlam - Dhanasuta Road | Ratlam | Ratlam | PWD | Road | 4600.8 | 3680.64 | 736.13 | 2016-09-16 |  |  | 2019-10-31 |  |  |  | 30
22 | P2016700000000000738 | Gourjhamar - Kesli - Tada -Searmau Road | Sagar & Raisen | Deori, Kesli & Silwani | PWD | Road | 7466.08 | 5654.63 | 2067.43 | 2016-09-16 |  |  | 2019-10-31 |  |  |  | 48.88
22 | P2016700000000000739 | Cheech To Kalwana Road | Sehore | Nasrullaganj | PWD | Road | 5507.51 | 4406.01 | 881.2 | 2016-09-16 |  |  | 2019-10-31 |  |  |  | 29.15
22 | P2016700000000000740 | Kahani Palari Road | Seoni | Ghasore, Dhanora & Keolari | PWD | Road | 7517.59 | 6014.07 | 1202.81 | 2016-09-16 |  |  | 2019-10-31 |  |  |  | 42.13
22 | P2016700000000000741 | Khawasa To Tirodi Road | Seoni | Kurai | PWD | Road | 3015.81 | 2412.65 | 482.53 | 2016-09-16 |  |  | 2019-10-31 |  |  |  | 19.52
22 | P2016700000000000742 | NH-86 Km 66 To Kuakhedi Gulabganj Andia Road | Vidisha | Gyaraspur | PWD | Road | 4577.42 | 3613.16 | 722.63 | 2016-09-16 |  |  | 2019-10-31 |  |  |  | 20.8
22 | P2016700000000001204 | Bridge Across Dokariya Nalla On Kochewahi - Botejhari Road | Balaghat | Waraseoni | PWD | Bridge | 562.84 | 450.27 | 90.04 | 2016-10-19 |  |  | 2019-12-01 |  |  |  | 165.32
22 | P2016700000000001205 | Bridge Across Tawa River On Sarni-Loniya Road | Betul | Ghodadongri | PWD | Bridge | 963.38 | 770.7 | 154.14 | 2016-10-19 |  |  | 2019-12-01 |  |  |  | 210
22 | P2016700000000001206 | Bridge Across Tapti River Jainabad Village - Rajghat Burhanpur | Burhanpur | Burhanpur | PWD | Bridge | 1307.22 | 1045.78 | 209.16 | 2016-10-19 |  |  | 2019-12-01 |  |  |  | 247
22 | P2016700000000001207 | Bridge Across Jam River - Sanwari Mohgalon Road | Chhindwara | Sausar | PWD | Bridge | 564.38 | 451.5 | 90.3 | 2016-10-19 |  |  | 2019-12-01 |  |  |  | 90
22 | P2016700000000001208 | Bridge Across Katni River Of Ganiyari-Ghinochi Road | Katni | Rithi | PWD | Bridge | 546.98 | 437.58 | 87.52 | 2016-10-19 |  |  | 2019-12-01 |  |  |  | 60
22 | P2016700000000001209 | Bridge Across Ghogra River - Bareli-Gaganwada Road | Raisen | Bareli | PWD | Bridge | 808.47 | 646.78 | 129.36 | 2016-10-19 |  |  | 2019-12-01 |  |  |  | 210
22 | P2016700000000001210 | Bridge Across Tenduni River - Mangrol-Bagalwada Road | Raisen | Bareli | PWD | Bridge | 1121.47 | 897.18 | 179.44 | 2016-10-19 |  |  | 2019-12-01 |  |  |  | 175
22 | P2016700000000001211 | Bridge Across Bais River - Dhokhedi Road | Vidisha | Vidisha | PWD | Bridge | 1401.89 | 1121.51 | 224.3 | 2016-10-19 |  |  | 2019-12-01 |  |  |  | 210
22 | P2016700000000001298 | Sidhaghat GWSS | Seoni | Dhanora | MPJNM | RDWS | 10104.31 | 8588.66 | 1717.73 | 2016-11-25 |  |  | 2019-12-31 |  |  |  | 117630
Formulas:
Expected Date of completion = DATE(YEAR([PSC_Dt])+3,MONTH([PSC_Dt])+1,DAY("1"))
Expected Date of completion = DATE(YEAR([PSC_Dt])+5,MONTH([PSC_Dt]),DAY("1"))